## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | SUPPRESS TRANSMISSION of COVID-19 AND SAVE LIVES IN JAMAICA | Overall Duration (months) | 8 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-06-01
MPTF Office Project Reference Number: | 121609 | Original End Date (dd.mm.yyyy) | 2021-01-31
Country | Jamaica | Current End date(dd.mm.yyyy) | 2021-01-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | PAHO/WHO; UNFPA | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health and Wellness; National Family Planning Board
Report Cleared By
o Name: | Shelly Trim
o Title: | Data and Results Reporting Officer
o Email address: | shelly.trim@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | PAHO remains embedded in the MOHW EOC and provides 24-hour technical support and guidance, including to the daily EOC briefing meetings. In collaboration with the Ministry of Health and Wellness (MOHW), the UNCT prepared the Strategic Preparedness and Response Plan with a corresponding budget and used to mobilize resources to support the national effort for COVID-19. During this period PAHO has provided guidelines and training at the national level and to all Health care workers on the pillars of the Response Plan. During this period, PAHO has procured and received PPEs through the WHO Global Supply Chain for distribution to the health sector. The organization is also working in collaboration with UNAIDS which has supported CSOs working with HIV/AIDS to respond to the needs of this community. PAHO has provided training of MOHW staff and procurement of essential items through targeted donations. Training and donations are just some of a wide range of interventions PAHO is engaged in to assist the MoHW in the COVID-19 response. Overall, since the onset of COVID-19 PAHO Jamaica office has actively assisted the MOHW to prepare and respond to the virus by: providing COVID-19 test kits and training in its use; providing PPE supplies for health care setting and CSOs; planning and coordination of the emergency response; facilitating training and capacity building programs; conducting COVID-19 briefing sessions for partners and stakeholders; providing risk communications materials and support; assisted with resource mobilization, case management, infection prevention and control and research. UNFPA implemented activities to ensure the continuity of essential, integrated sexual and reproductive health services. The results respond to the needs of vulnerable groups and persons living in poor and vulnerable communities for access to health services and medications for infections for COVID-19 as well as for sexual and reproductive products and services especially for women and girls. It also ensured continued access to family planning services reducing unwanted pregnancy in perilous conditions through the distribution and uptake of 16,000 doses of Depo Provera. Furthermore, it ensured continued access to safe maternity services (prenatal care, delivery care including emergency obstetric and new-born care, postnatal care including post- partum family planning) and ensured that SRH providers are equipped with PPEs. The funds maintained access to critical SRH services and information through an integrated risk communication and community engagement that included youth engagement. Messages focusing on COVID-19 and Gender-Based Violence; Pregnancy and After Delivery; Persons in the LGBTQI Community; Stigma and Discrimination; and Persons Living with HIV were developed. The digital products were used in an intense digital campaign via YouTube, Twitter and Facebook with approximately 228,055 being reached across the Caribbean, including Jamaica.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Public healthcare workers (women and men) assigned to communities
3.1 | Results: Outcome Level | Please include outcome level results achieved | Public healthcare workers (women and men) assigned to communities protected during COVID-19
3.2 | Results: Output Level | Please include output level results achieved | Infection Prevention and Control • PAHO supported key activities related to guarantee the safety of HCW and readiness of the country response to COVID-19, including provision of PPE for MOHW and CSOs, training on use of PPE and infection prevention and control practices as well material for communication. • PAHO also provided technical support on this area through webinar on varies Infection Prevention and Control (IPC) topics including administrative measures for IPC implementation, management of exposed HCW, rational use of PPE, reprocessing of respirators and IPC measures for non-conventional health settings. • Supporting the readiness of the COVID-19 PAHO implement the surveillance system, Go Data© to collection of data, including provision of tablets for field contact tracers. • Jamaica was trained by PAHO on molecular detection of COVID-19 early on the outbreak and PAHO provides laboratory supplies for test of COVID-19. PAHO is now supporting the expansion of testing capacity guiding the implementation of Antigen rapid test and providing test kits for Jamaica. • Provided technical guidance on Infection Prevention and Control during health care when COVID-19 is suspected. • Provided training on Infection Prevention and Control for all health care workers of Ministry of Health (MOHW) island wide and CSOs working in the area of HIV/AIDS . • Planning with the MOHW of a new round of sensitization and training for IPC in health care settings island wide. • UNFPA provided 16,000 doses of Depo Provera to the National Family Planning Board to ensure continued access to family planning commodities and services in order to reduce unwanted pregnancy • UNFPA implemented an integrated risk communication and community engagement campaign to maintain access to critical SRH services and information. Messages focused on COVID-19 and Gender-Based Violence; Pregnancy and After Delivery; Persons in the LGBTQI Community; Stigma and Discrimination; and Persons Living with HIV. The digital products were used in an intense digital campaign via YouTube, Twitter and Facebook and in Jamaica, with approximately 228,055 being reached, including Jamaica. • UNFPA provided PPEs to sexual and reproductive healthcare (SRH) providers to facilitate continued access to safe maternity services (prenatal care, delivery care including emergency obstetric and new-born care, postnatal care including post- partum family planning). Distribution took place islandwide through the South East Regional Health Authority, Southern Regional Health Authority, North East Regional Health Authority, and Western Regional Health Authority. The PPE items disributed were: Gowns - Isolation; Coveralls - Disposable; Surgical Respirators; Surgical Masks - Disposable; Goggles Panoramic. Regular Nose; Face Shields - Reusable; Gloves - Surgical. Long Cuff; Gloves - Examination; and Surgical Masks - Type IR. Disposable.
National Laboratory • Bolstered the testing capacity for SARS-CoV-2 with procurement and handing-over of extraction kits for the automated extractor at the National Public Health Laboratory. • Capacity building of the National Public Health Laboratory (NPHL) and the National Influenza Centre (NIC), to be able to conduct large scale testing when an outbreak begins. • Support provided to the National Influenza Centre in the development of the workflow to maximize efficiencies for COVID-19 laboratory testing in collaboration with the National Public Health Laboratory, MOHW. • Support provided to the National Public Health Laboratory, Jamaica to finalize its participation in the WHO WHO External Quality Assessment Project (EQAP) for the detection of SARS-CoV-2 by RT-PCR (2020). • Capacity building training sessions with staff from the national laboratories started on 13 and 14 February 2020. Training focused on molecular detection of SARS-COV 2 and results interpretation. At the completion of the training program, PAHO donated positive control, primers and probes for 300 samples, ensuring initial testing capabilities once SARS-CoV-2 reached Jamaica. A follow up virtual training course was facilitated by PAHO/WHO to train laboratory staff in the operation of the RT-PCR machine to detect SARS-CoV-2, an essential tool for rapid and effective testing.
Surveillance system • Support provided to the MOHW in the establishment of the Go.Data surveillance system© through comprehensive training programs in all related surveillance system areas, data analysis, capacity building of laboratory personnel, and the training in the transportation of infectious substances to effectively respond to outbreaks of respiratory disease. Furthermore, PAHO donated 25 Android tablets, with the contact tracing application Go.Data© installed, to MOHW to boost the capacity of COVID-19 surveillance and case investigation.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | • During a public health emergency, strategic planning is critical to ensure an effective response. A mainly reactive approach, rather than strategic, resulted in difficulties in the planning of the response since March up to September with current community transmission. Support was given to the MOHW for the development of the National response plan as well as capacity building in the use of estimation tools for planning the response. The tools for planning includes modeling of COVID-19 cases, estimations of Human Resources needs and hospital beds for the national response. • A key challenge for the expansion of the capacity of the health services is the availability of human resources for health, including nurses. There was significant investment in training on infection prevention and control and mental health and psychosocial support. • The chronic underfunding of the health system required significant efforts to expand the capacity to respond effectively to the COVID-19 Pandemic, as well as maintaining the access to essential health services. • Other challenges are the need for strengthening governance mechanisms for a whole-society and whole-government approach for Universal Health • There is the need to strengthen mechanisms for effective coordination, communication and linkages throughout the integrated health services network to address population health needs in the COVID-19 pandemic. • Significant challenges experienced with the procurement of PPEs and laboratory supplies due to the global shortage of these items and shipping restrictions. In addition to stockouts, significant price increases were another challenge experienced in procurement from local suppliers. • In the Risk Management Matrix, the following risk is noted: “Surge in the number of severe cases which places significant strain on the health care system.” This has proved to be a real risk. Limitations in the number of healthcare workers may result in exhaustion and burnout of workers and their reduced availability and capacity to perform. It is necessary to remain flexible and responsive and offer technical assistance where necessary. • Stigma and discrimination against healthcare workers has emerged as an issue and UNFPA addressed this issue in its integrated suite of risk communication and community engagement messages.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | A key anecdotal lesson learned is the importance of training healthcare workers in the prevention and mitigation of gender-based violence. The COVID-19 pandemic is not just a health matter but also a gendered phenomenon. Women perform a vital role in the fight against the outbreak – as first responders, health workers and professionals, community volunteers and care workers. They are often also disproportionately and adversely affected by the pandemic. Women are the vanguard of the response and endure a higher physical and emotional toll, as well as an increased risk of infection in the response. It is important to be even more attentive to sexual exploitation abuse of authority. COVID-19 has also caused an increase in stigma and discrimination against healthcare workers, the vast majority of whom are women. Particularly in times of crisis, women are still the most impacted by unpaid domestic and community care work. As a result of over-burdened health systems and school closures, the duty of care traditionally falls on women, who generally have a greater share of responsibility to care for sick family members, as well as children and the elderly. The outbreak has significantly affected women’s ability to secure their livelihoods. Employment and care services are impacted for women workers in general and especially for informal and domestic workers. The evidence demonstrates that quarantines significantly diminish economic and sustenance activities and unequally impact employment-generating sectors that are predominately female, such as tourism and trade. With regard to gender-based violence (GBV), even before the onset of the COVID-19 pandemic in Jamaica, the prevalence was worryingly high. The COVID-19 attributable empirical data on VAWG is difficult to ascertain but anecdotal reports suggest that the problem has likely become even worse since the pandemic started – the so-called “shadow pandemic” of VAWG. It has been noted that calls to helplines have increased multiple times and there has been a significant increase in reports of domestic violence and murders of women and girls. Gender-based violence (GBV), and intimate partner violence (IPV) in particular, are increasing in both prevalence and intensity. Prolonged quarantines, curfews and other movement restriction measures have led to increased reports of domestic violence due to forced cohabitation in confined residential quarters, no doubt worsened by the anxieties related to the economic and health consequences of the pandemic. UNFPA was able to make a significant contribution to gender equality and the empowerment of women and girls through the mutually reinforcing and collaborative linkages between the risk communication and community engagement component of the MPTF project and the Spotlight Initiative. Under Spotlight, support is being given to the development/update of GBV referral pathways and coordination system, including hotlines, shelters and psychosocial support to mitigate the impact of GBV among women and girls in all their diversity. The MPTF risk communication and community engagemet social media campaign included gender empowerment messages to increase access of women and girls to to GBV/VAWG support systems.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | • PAHO heightened its collaboration with MOHW to advance timely implementation of work plans for the COVID-19 response for USAID, US CDC, Global Affairs Canada, UK DFID, UN SG Multi-Partner Trust Fund, with on-going procurement. • PAHO provided the technical leadership for health for the COVID-19 response within the UNCT and the Government of Jamaica system. • Partnerships with the MOHW and other Ministries were strengthened in the preparation of the response to the COVID-19. • PAHO has strengthened partnerships with the Ministry of Local Government and Community Development, Ministry of Education, Information and Youth, Ministry of Science, Technology, Energy and Mining as well as the Ministry of Finance and Public Services, for planning the COVID-19 response in the different sectors of the society. • PAHO and UNAIDS has strengthened collaboration with CSOs working in the are of HIV/AIDS to support the community affected by HIV/AIDS • UNFPA brokered new and/or maintained robust stakeholder partnerships and engagement including with: o Ministry of Health and Wellness o National Family Planning Board o Bureau of Gender Affairs Jamaica o The Jamaica Family Planning Association – Famplan o Jamaica Network of Rural Women Producers o Jamaicans for Justice (JFJ) o WMW Jamaica o TransWave Jamaica o Jamaica Network of Seropositives
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The study, 'Coping with COVID 19, Health Risk Communication and vulnerable populations', explored the effect of health communcations on the elderly, mentally ill, physically challenged, deaf and blind members of the population and documented their lived experiences during the pandemic. There was access to large number of risk communication messaging by official health authorities during COVID-19 however less than 10% addressed the needs of the vulnerable poulations. Some reported that the messages at times caused them to be fearful and there was the loss of much of their usual support mechanisms including sources of income. Challenges to adhereing to the IPC measures among this population were also identifed. Based on the findings of this study a list of recommendations and a policy brief will be prepared and submitted to the MOHW and other national authorites for appropriate action.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Public healthcare workers (women and men) assigned to communities[1] protected during COVID 19 | Procurement of PPES for protection of public healthcare workers |  | Health Care Workers Surveillance Programme of the MOHW
Indicator: number of public healthcare workers infected with COVID-19
Baseline:0 confirmed cases of COVID-19 in the health workers
Planned Target :69 confirmed cases of COVID-19 in the health workers (as of 11 September, it is estimated to increase with the current surge of cases) | 319 health workers infected (12,8% positivity rate)
Output 3.1 Procurement and use of equipment to support ventilators | 100% healthcare workers with access to PPE: 10.000 FFP2/N95/KN95 for 6888 healthcare workers | Description of Personal Protective Equipment (PPE) and Quantities Delivered: Disposable Gown isolation. 2,022 Disposable Surgical Respirator FFP2/N95-mask. 10,000 Disposable Surgical Mask, type IIR. 10,000 Sterile Gloves. Surgical. 17,000.00 Gloves. Examination. 17,000.00 | MOHW Distribution plan on the number of PPE items distributed to SRH workers island wide.
Indicator 1.1.a % of targeted public healthcare workers (women and men) in communities7 with access to PPE
Baseline: 0% of targeted public healthcare workers (women and men) in communities with access to PPE
Planned Target: 100% of targeted public healthcare workers (women and men) in communities with access to PPE
Indicator 1.2 a:# women and men trained in effective use and disposal of PPE | 100% healthcare workers trained in effective use and disposal of PPEs (17,217 persons trained including 6888 healthcare workers). | The trainings and sensitization sessions received as at October 30, 2020 training/sensitization sessions reaching 17,217 persons. | PAHO training register; MOHW report on HCWs trained in use of PPEs
Baseline: 0 of targeted public healthcare workers (women and men) in communities with access to PPE
Planned Target: 100%of targeted public healthcare workers (women and men) in communities with access to PPE
Indicator: 2.3.b % of pregnant women and girls with continued access to antenatal care services |  | The percentage provided is the result of a self-assessment in consultation with the MOHW. There is no validated data for 2020 available. There is no data available on the antenatal care coverage by skilled birth attendants (%). There is only data available for the percentage of hospitals birth (97.6%) from 2016. There were significant efforts to strengthening capacity for antenatal care services, including hiring 1000 community health workers were hired to strengthen capacity for antenatal care services in the community. Training was provided, including care for pregnants infected with COVID/-19 according with the national guidelines established. | Self-assessment in consultation with the MOHW
Baseline: 0% of pregnant women with continued access to targeted antenatal care services
Planned Target: 100% of pregnant women with continued access to targeted antenatal care services | 100% pregnant women with continued access to antenatal care
Indicator 2.3.c: % of pregnant women and girls with continued access to Basic and Comprehensive Emergency Obstetric Care
Baseline: 0% of pregnant women with continued access to targeted Basic and Comprehensive Emergency Obstetric Cares
Planned Target: 100% of pregnant women with continued access to targeted Basic and Comprehensive Emergency Obstetric Care | 100% pregnant women with continued access to antenatal care
Indicator 4.1.a | Reached 228,055 from one hundred and fifty-two (152) new COVID-19 multimedia based products. These included audio podcasts, radio clips, a narrated dramatization, graphical leaflets, illustrated posters and infographics. |  | Social media analytics of Facebook and Twitter reach
Number of community members reached with messages to implement behaviors to protect against COVID-19
Baseline: 0 community members reached with messages to implement behaviors to protect against COVID-19
Planned Target: 30,000 community members reached with messages to implement behaviors to protect against COVID-19
Delivery of essential health services unrelated to COVID-19 – with emphasis on services related to NCDs (with emphasis on hypertension, diabetes and heart disease), sexual and reproductive health (SRH), pre- and post-natal care and for persons living with HIV and persons with disabilities | Mobile units are used to outreach most vulnerable groups, including women, girls, boys, and the elderly |  | Number of women and men - disaggregated by age - with access to health services through the mobile units
Indicator 2.1.a % of vulnerable women, men, girls, boys and the elderly needing essential health services who are able to access these services | Mobile units are used to outreach most vulnerable groups, including women, girls, boys, and the elderly
Baseline: 0% of vulnerable women, men, girls, boys and the elderly needing essential health services who are able to access these services
Planned Target :100% of vulnerable women, men, girls, boys and the elderly needing essential health services who are able to access these services
Output 2.1 Mobile units operationalized to provide essential health services in addition to COVID related services | 100% (3200 PHLIV able to access care from the total number of 3200 PLHIV in Jamaica( | The percentage presented is a self-assessment in consultation with the MOHW. There is currently no data on the total percentage of PHLIV with access. However, estimations revealed that HIV Testing is been affected due to COVID19. A survey conducted by PANCAP and PAHO showed that during 2020, facility-and community- based HIV testing services reduced in two-thirds (69%) of countries due to COVID-19. | Self-assessment in consultation with the MOHW
Indicator 2.1.a % of vulnerable women, men, girls, boys and the elderly needing essential health services who are able to access these services
Baseline:% PLHIV able to access care and retained in care during COVID 19 pandemic
Planned Target: 100 % PLHIV able to access care and retained in care during COVID 19 pandemic
Output 2.2 National Operations Centre is able to respond to requests related to essential health services for vulnerable groups, including women, girls, boys and the elderly
Indicator 2.2.a: # phone lines activated to accept calls related to essential health services8 | 21 Phone lines available to women, men and the elderly who require access to essential health services |  | Official report of the MOHW Jamaica
Baseline: No (0) phone lines available
Planned Target: 21 Phone lines available to women, men and the elderly who require access to essential health services
Indicator 2.2.b # staff trained to manage phonelines related to essential health services | 80 volunteers trained |  | Official report of the MOHW Jamaica
Baseline: 0 volunteers trained
Planned Target: 80 volunteers trained
Output 2.3 Chronic disease management adapted to address the COVID situation by maintaining supply chains for medications and needed supplies, with a reduction in provider encounters
Indicator 2.3.a: Medication available for vulnerable groups | Multi-month dispenser policy for ARV and other essential medicines implemented by MOHW. The activity impacts the 14.000 PLHIV who are on ART (UNAIDS, 2019)
Baseline: ARV and other essential medicines available for 6-month in stockpile and one month dispensing policy in place |  |  | Official report of the MOHW Jamaica
Planned Target: ARV and other essential medicines stockpile available for 1 year and multi month dispenser policy in place
Indicator 2.3.a: Medication available for vulnerable groups | Number of CSO keep their activities in support PLHIV. The activity impacts the 14.000 PLHIV who are on ART (UNAIDS, 2019) |  | Official report of the MOHW Jamaica
Baseline: CSO supporting delivery of care for PLHIV
Planned Target: CSO able to keep supporting of care for PLHIV
Output 2.4 Access to maternal healthcare maintained
Indicator 2.4.a: % of pregnant women and girls with continued access antenatal care services | Partial disruption of maternal healthcare | There is no available data from the MOHW on the percentage of disruption. The qualitative data provided is a self-assessment in consultatio n with the MOHW | Self-assessment in consultation with the MOHW
Baseline: % of disruption in antenatal care services
Planned Target: 0 % of disruption in antenatal care services
Indicator 2.4.b % of pregnant women and girls with continued access to Basic and Comprehensive Emergency Obstetric Care | Partial disruption of maternal healthcare | There is no available data from the MOHW on the percentage of disruption. The qualitative data provided is a self-assessment in consultatio n with the MOHW | Self-assessment in consultation with the MOHW
Baseline: % of disruption in emergency obstetric care
Planned Target :0% of disruption in antenatal care services
Enhanced case management of high-dependency patients in hospitals |  |  | Project evaluation and procurement records
Indicator :Enhanced case management of high-dependency patients in hospitals
Baseline:Number of fully operational ventilators with supporting equipment
Planned Target:Number of fully operational ventilators with supporting equipment
Output 3.1 Procurement and use of equipment to support ventilators | 28 ventilators with supporting equipment. | 28 ventilators donated by the European Union to the MOHW Jamaica. Supportive equipment was procured. | Equipment procured, distributed and effectively used by trained health professionals
Indicator 3.1.a: Number of ventilators with supporting equipment
Baseline:10 ventilators with supporting equipment
Planned Target: 28 ventilators with supporting equipment
Indicator 3.1.b Number of supporting equipment for effective use of ventilators | Supporting equipment for effective use of 28 ventilators | Equipment procured and technical support for reorganization of services provided to ensure the effective use of 28 ventilators. | Official report of the MOHW Jamaica
Baseline: Supporting equipment for effective use of 10 ventilators
Planned Target: Supporting equipment for effective use of 28 ventilators
Members of vulnerable communities are engaged and can play their part in the reduction of the spread of COVID-19 |  | The percentage of commities was estimated based in self-assessment in consultation with the MOHW | Project evaluation and procurement records
Indicator: percentage of public healthcare workers protected with PPEs and trained
Baseline:National risk communication and community plan for COVID-19 implemented | National risk communication and community plan for COVID-19 implemented
Planned Target :Percentage of communities informed and engaged in the response to COVID-19 | 100% communities informed and engaged in the response to COVID-19
Output 4.1 Community engagement for social and behaviour change implemented to ensure preventive community and individual health and hygiene practices in line with the national public health containment recommendations
Indicator 4.1.a. Number of community members reached with messages to implement behaviors to protect against COVID-19 | Reached 228,055 from one hundred and fifty-two (152) new COVID-19 multimedia based products. These included audio podcasts, radio clips, a narrated dramatization, graphical leaflets, illustrated posters and infographics. |  | Social media analytics from YouTube, Twitter and Facebook
Baseline: 0 community members reached with messages to implement behaviours to protect against and suppress COVID-19
Planned Target: 30000 community members reached with messages to implement behaviours to protect against and suppress COVID-19
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
PAHO/WHO and UNAIDS deliver vital PPE to support Jamaica’s vulnerable communities against COVID-19
Kingston, Jamaica, 26 Oct 2020: In a ceremony today, the Pan American Health Organisation (PAHO) and UNAIDS handed over vital personal protective equipment (PPE) to enable key community organisations to continue to provide essential support and services to some of Jamaica’s most vulnerable populations while protecting staff against COVID-19. Supplies including face shields, surgical masks, hand sanitisers, liquid soap and infrared thermometers were distributed to seven community organisations that address the needs of disadvantaged children and adolescents, people living with HIV, the transgender community and those requiring legal assistance. Relief packages were calculated to support each organisation and its staff for the next six months. Dr Bernadette Theodore-Gandi, PAHO/WHO Representative for Jamaica, Bermuda and the Cayman Islands, and Manoela Manova, UNAIDS Country Director for Jamaica commended the work of the community organisations as they handed over supplies to representatives from Eve for Life, Children First Agency, Jamaica AIDS Support for Life (JASL), the Jamaica Community of Women Living with HIV, Jamaicans for Justice, the Jamaica Network of Seropositives and Transwave. “Protecting the rights of the most vulnerable to access safe and equitable healthcare is at the core of PAHO’s work. We are pleased to be able to support these essential organisations so they can continue to provide life-saving services to those in need,” emphasised Dr Gandi. “Community and civil society organizations are among those providing essential services to the most affected, vulnerable and hard-to-reach populations. We are happy to provide PPE that will enable them to do this critical health and social work while keeping their staff and clients protected,” said Ms. Manova. COVID-19 has caused major disruptions in service delivery for many organisations including those that provide essential community support needs. The funding for the relief package was mobilised through the United Nations COVID-19Response and Recovery Multi-Partner Trust Fund (COVID-19 MPTF), which aims to address service disruptions to vulnerable communities. UN COVID-19 Response and Recovery Fund The United Nations (UN) COVID-19 Response and Recovery Multi-Partner Trust Fund (COVID-19 MPTF) is a UN inter-agency finance mechanism launched by the UN Secretary-General to support low- and middle- income programme countries in overcoming the health and development crisis caused by the COVID-19 pandemic. The Fund’s assistance targets those most vulnerable to economic hardship and social disruption. Built on the lessons learned from the Ebola Response Multi-Partner Trust Fund, the UN COVID-19 MPTF helps finance the three objectives of the UN Secretary-General’s Call for Solidarity, a plea for global action to stop the COVID-19 pandemic and the suffering it has caused. The Call’s objectives are to tackle the health emergency; focus on the social impact, and the economic response and recovery; and help countries recover better.
https://www.paho.org/en/news/26-10-2020-pahowho-and-unaids-deliver-vital-ppe-support-jamaicas-vulnerable-communities
PAHO Jamaica Delivers Vital Personal Protective Equipment to Assist Frontline Workers
https://www.paho.org/en/news/11-4-2020-paho-jamaica-delivers-vital-personal-protective-equipment-assist-frontline-workers
PAHO/WHO led partnership delivers 80,000 antigen rapid COVID-19 tests to boost Jamaica’s testing capacity
https://www.paho.org/en/news/26-10-2020-pahowho-led-partnership-delivers-80000-antigen-rapid-covid-19-tests-boost-jamaicas?utm_source=PAHO%2FWHO+JAM+Newsletter&utm_campaign=1011e6f6fd-EMAIL_CAMPAIGN_2020_06_17_09_37&utm_medium=email&utm_term=0_1a2f8b4b60-1011e6f6fd-
PAHO, USAID bolster Jamaica’s COVID-19 Response
https://www.paho.org/en/news/17-6-2020-paho-usaid-bolster-jamaicas-covid-19-response
Video on home isolation and quarantine
https://www.youtube.com/watch?v=Z7pRNjMWQLg
Video on staying healthy at home.
https://www.youtube.com/watch?v=Pj4Oep7ZI8g&feature=youtu.be
Video on Breastfeeding During COVID in Jamaica
https://www.youtube.com/watch?v=rEgco0QipvE&feature=youtu.be
Strengthening Health Systems & Services in Jamaica
https://www.paho.org/en/stories/strengthening-health-systems-services-jamaica
Video Violence against women and girls in COVID-19 Pandemic
https://youtu.be/EBLoYuTnC9o
Seth Broekman, Deputy Director, UNFPA Sub-Regional Office for the Caribbean, hands over personal protective equipment (PPE) to The Hon. Christopher Tufton, Minister of Health and Wellness of Jamaica. Supplying PPE to medical personnel delivering sexual and reproductive health (SRH) services in public health facilities, is critical to supporting the continuity of SRH services and choices during the COVID-19 pandemic.