## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protection of Women and Girls from Sexual and Gender Based Violence in the times of COVID-19 | Overall Duration (months) | 13 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 16.11.2020
MPTF Office Project Reference Number: | 124786 | Original End Date (dd.mm.yyyy) | 31.12.2021
Country | India | Current End date(dd.mm.yyyy) | 31.12.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNWOMEN, UNHCR, WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Line Ministries (MoWCD, MoE, MoHFW), Niti Ayog, the Judiciary, the Police, oversight mechanisms such as NCPCR, S/DCPCRs, CHILDLINE FOUNDATION, NIMHANS, academic institutions (such as Tata University), professional associations, NGOs/CSOs and youth platforms (NYKS, NCC and NSS), the one stop centers and counselling centers, helplines, etc.
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Within the first two months, UN agencies have managed to lay the solid foundation to ensure a successful roll-out of the program in 2021 including: put in place relevant coordination mechanisms, secure strategic partnerships, design and develop resource and campaign materials, ensure sufficient human resources and conduct planning and funding allocation to program locations (including Bihar, Chhattisgarh, Delhi, Hyderabad, Uttar Pradesh, Rajasthan and Madhya Pradesh). At the national level, a monthly inter-agency working group chaired by UNICEF with the participation of UNWOMEN, UNHCR and WHO was established to oversee the implementation of the program along with an inter-agency monitoring framework developed to ensure effective coordination. Through the joint program, UN agencies continue the strategic support to enhancing the capacity of frontline workers from all relevant sectors – child protection, health, education, law enforcement, etc. – in order to ensure the continuity of quality SGBV services delivered to women and girls during COVID-19. WHO and partners support in capacity building of frontline healthcare professionals to provide gender and age sensitive services to women and girl survivors of SGBV. UNICEF continues strengthening child protection systems in 17 States with an emphasis on front line respondents including CHIDLINE and the Police to ensure continuity of services. Based on its current model of community based mental health and psychosocial support (MHPSS), UNICEF and partners will continue expanding the model across states to better reach women and girls experiencing SGBV in the times of COVID-19. UN agencies have provided technical inputs to the long-term multi-sectoral action plan on MHPSS and will continue supporting the implementation by the Ministry of Health and Family Welfare and National Disaster Management Authority. For improved access to the justice system of women and girls at risk of or survivors GBV, a breakthrough agreement was reached by UNICEF with the National Police Academy to set up a National Child Protection Resource center to enhance police’s training, research and documentation on child protection and SGBV issues. Advocacy and close partnership with the Supreme Court leads to strategic support to the reform of the child protection systems and services and continuously bringing the attention to the agenda of violence against girls and boys, including gender-based violence. UN agencies continue planning for joint communication campaigns so that women and girls are aware of the risks of SGBV and harmful practices, and increasingly engaged in decision making processes related to COVID-19 response and recovery. 10-community consultations with different refugee communities (Afghan, Chin, Congolese, Somalis and Rohingya) were conducted by UNHCR to seek the inputs and discuss beneficiary identification criteria. Community reemphasized that having a source of income for women is essential to avert GBV related risks. 16 digital illustrations on intersectional identities on women and girls experiencing gender-based violence were developed by UNICEF and partners, which will be used further for the awareness generation campaigns and interventions under this program.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | During the 10 community consultations, approximately 200 direct beneficiaries were reached and directly 600 beneficiary were reached
3.1 | Results: Outcome Level | Please include outcome level results achieved | By December 2021, women and girls in India are protected from sexual and gender based violence and are empowered to use gender responsive and age sensitive essential services and recover from violence amidst the COVID19 pandemic (in progress)
3.2 | Results: Output Level | Please include output level results achieved | 1. Improved gender responsive and age sensitive protection and SGBV related multi-sectoral essential services are available for women and girlsand other groups at risk of and/or survivors of SGBV (in progress) 2. Women and girls and victims of SGBV have improved accesss to gender-sensitive justice systems (in progress) 3. Women and girls are aware of the risks of SGBV and harmful practices, and increasingly engaged in decision making processes related to COVID-19 response and recovery (in progress) 4. Vulnerable families of women and girls at risk of and/or survivors of SGBV/VAC have reduced their economic vulnerability and increased access to livelihood and income generation programs (in progress)
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | COVID-19 pandemic and related restrictions on mobility may affect outreach and on-ground implementation of programme, as well as pace of the project activities. To address that, UN agencies continue maintaining close partnerships with the government and implementing partners to expand the outreach of project interventions through innovative methods including virtual platforms. Inclusion of mixed methods of delivery of interventions, both in person where feasible, and online, building on the current experiences in mobilizing online platforms have been explored, especially with non-traditional partners such as the technology firms. Some challenges were identified when involving refugees and host communities especially about lack of access to basic financial services for refugees, which were addressed by partnering with local NGOs and local social enterprises. UN agencies continue leveraging existing institutional relationship and forge formal partnerships with the national and relevant state level government counterparts as well as implementing partners (via MoU and/or any forms of collaboration framework/agreement) to ensure the implementation of the program. Dynamic political context, including upcoming state elections and COVID-19 response, may further push back prioritizing and mainstreaming issues of Gender Equality and Women's Empowerment, particularly ending sexual and gender-based violence. To overcome that, UN agencies have been and continue focusing on the institutionalization of partnerships with key government agencies to ensure that programme activities are not affected by leadership change. Strategy of embedding consultants in Ministries by UN agencies has ensured consistent support to the Government on these substantive issues. Strategic alignment and inclusion of GBV as a core activity within the health sector response was helpful. Ensuring that GBV was included in strategic priorities of the organization like the UN Joint Response Plan, the socio-economic response framework and working with stakeholders through the national RG-7 (results group 7 for SDGs) was crucial in ensuring that the agenda was included and addressed. This has also contributed significantly to institutionalizing capacities on gender responsive governance, to mitigate risks accruing from changes in the larger political environment or churn at the individual level. Finally, the initiative will also rely on CSO partnerships to ensure adequate support and engagement with civil society. Increasing women and girl's agency and their access to economic resources can potentially lead to backlash and rejection from men and boys of principles of gender equality, leading to an increase of GBV. The programme has targeted interventions with men and boys in communities and other platforms to improve buy in for women and girl's leadership and reduce acceptance of gender based violence as a social norm. Alternatively, the programme will establish links with government departments and women's rights organizations to ensure economic and community focused interventions are complemented with access to referral services like counselling, shelter and child support where possible.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The COVID-19 pandemic has been an opportunity to bring visibility to sensitive issues such as violence against women and girls during the lockdown. Through the MPTF programme, UN agencies have been to contribute on this visibility by engaging in public fora, investing in evidence building, strengthening alliances with civil society organizations, and through collaborating with other sectors to ensure multidimensional nature of some SGBV risks. There is a need to build on this opportunity galvanizing attention from different stakeholders towards this critical agenda. The Pandemic also brought into focus the need for better digital communications due to the online mode of working. Frontline workers could not work to full capacity, physical access and support was rendered difficult and lack of online tools and connectivity, all hampered provision of essential GBV services. In the context of travel restriction and social distancing, technology and online platforms came in as prominent way to deliver capacity building sessions for partners in all fronts. By engaging with technology firms and digital platforms, the programme interventions would be able to reach out to a broader scope of target population despite the limited movement. COVID-19 response has brought along opportunities for leveraging resources, partnerships and joining forces to address UN’s priority agenda. UN agencies have been able to turn the opportunity of the MPTF call for COVID-19 response to leverage funding for regular systems strengthening interventions to address SGBV. Moreover, through the MPTF funded programme, the participating UN agencies managed to create the momentum for close collaboration among UN agencies, leaving the way for joining forces on boosting the agenda of SGBV.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UN agencies continues strengthening existing partnerships with the line Ministries (MoWCD, MoE, MoHFW), Niti Ayog, the Judiciary, the Police, oversight mechanisms such as NCPCR, S/DCPCRs, CHILDLINE FOUNDATION, NIMHANS, academic institutions (such as Tata University), professional associations, NGOs/CSOs and youth platforms (NYKS, NCC and NSS), the one stop centers and counselling centers, helplines, etc. to ensure interventions reach the most vulnerable children/community, especially in the hard-to-reach areas. In addition, COVID-19 context has created favorable conditions for exploring non-traditional partnerships, especially the private sector to bring in innovative and technology-based solutions to address SGBV in the unprecedented context. For example, NASSCOM Foundation’s support in digilisation of Childline’s case management system, technology firms to explore innovative digital platforms for women and girls at risks/survivors of SGBV for enhanced access to Artificial Intelligence (AI) based solutions, chatbots (Facebook, Websites, WhatsApp) for information dissemination, identifying and reporting, as well as referral to specialized services for women and girls experiencing SGBV. UN agencies continue strengthening the inter-agency coordination thanks to the MPTF funded joint programme and leveraging different platforms/networks to move the SGBV related agenda forward in a more systematic and coordinated way, which is critical especially in the times of COVID-19.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Not applicable
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Not applicable
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | NA | NA | Government and partners' reports, IMS
Indicator: a. Number of women and girls and other vulnerable groups at risk and or survivors of SGBV have improved access to effective gender based violence preventive and responsive services
Baseline: 260,000
Planned Target: 930,500
Indicator: b. Number of girls and boys, women that have increased their socio-economic empowerment and agency to be able to prevent and address SGBV
Baseline: 270,600
Planned Target: 1,200,000
Output 1 | NA | NA | Government and partners' reports, IMS
Indicator 1.1:Number of women and girls at risk and/or survivors of SGBV have access to SGBV case management and MHPSS services (Disaggregated by age, disability, ethnicity)
Baseline: 240,000
Planned Target: 800,000
Indicator 1.2:Number of frontline healthcare professionals, staff of OSC, child protection functionnairies have enhanced capacity on providing SGBV related services | NA | NA | Government and partners' reports, IMS
Baseline: 124,000
Planned Target: 248,000
Indicator 1.3: Number of women and girls at risks/survivors of SGBV have access to Artificial Intelligence (AI) based solutions (Disaggregated by age, disability, ethnicity)
Baseline: 0
Planned Target: 30,000
Output 2 | NA | NA | Government and partners' reports, IMS
Indicator 2.1:Number of women and girls at risk and /or survivors of sexual and gender-based violence received legal aid support (Disaggregated by age, disability, ethnicity)
Baseline: 0
Planned Target: 8,500
Indicator 2.2:Number of states with referral mechanisms and training schemes in place by the National Police Academy to prevent and respond to SGBV/VAC | NA | NA | Government and partners' reports, IMS
Baseline: 1
Planned Target: 8
Indicator 2.3: Number of officials from the law enforcement, security forces, CP functionnairies trained on cyber safety and security
Baseline: 200
Planned Target: 132,000
Output 3
Indicator 3.1: Number of local authorities, women's and community groups and women elected representatives benefit from participation-based comprehensive interventions to prevent and respond to SGBV | NA | NA | Government and partners' reports, IMS
Baseline: 157
Planned Target: 100,209
Indicator 3.2: Number of women, girls, boys, men reached with messages on SGBV prevention and response through community based outreach, media campaigns, including social media platforms | NA | NA
Baseline: 1,874,000
Planned Target: 2,662,000
Indicator 3.3: Number of girls and boys, male and female youth collectives actively participated in community led outreach interventions and movements on SGBV and VAC | NA | NA
Baseline: 250,000
Planned Target: 1,000,000
Output 4
Indicator 4.1:Number of women and girls at risk and/or survivors of SGBV benefit from social protection and livelihood programmes (Disaggregated by age, disability, ethnicity) | NA | NA | Government and partners' reports, IMS
Baseline: 20,600
Planned Target: 30,850
Indicator 4.2:Number of India's Flagship programmes on livelihoods that are gender sensitive | NA | NA
Baseline: 1
Planned Target: 3
Indicator 4.3: Number of states with Gender Action Plan, including responding to SGBV, developed and implemented | NA | NA
Baseline: 2
Planned Target: 4
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Not applicable as the programme has just started
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board