## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | COVID-19 and Resilience in Armenia: Mitigating the Socio-Economic Impact on Vulnerable People and Communities | Overall Duration (months) | 10 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-06-04
MPTF Office Project Reference Number: | 121956 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Armenia | Current End date(dd.mm.yyyy) | 2021-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP UNICEF UNFPA IOM | National counterparts (government, private, NGOs & others) and other International Organizations | UNIDO UNHCR FAO WFP Ministry of Labout and Social Affairs HayPost State Migration Service Social Security Service Armenain Association of Social Workers Armenian Statistical Committee Ministry of High-Tech Industry Ministry of Economy Nork Invormation Center State Employment Agency Investment Support Center Fund Nork Social Services Technology and Awareness Center National Institute of Labour and Social Research World Bank LIght Industry Export Consortium Ministry of Economy ACRA Credit Bureau Central Bank of Armenia
Report Cleared By
o Name: | Shombu Sharp
o Title: | UN Resodent Coordinator in Armenia
o Email address: | shombi.sharp@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The Project contributes significantly towards adressing the impcat of COVID-19 and supports the Government with multi-dimensional activities for beneficiaries and broad engagement of partners. For example, the Project provided cash assistance to 247 households of predominantly ethnic Armenian families displaced from Syria who have little or no employment opportunities due to lockdowns and an overall decrease of economic activities in the country. Support was provided to returned labour migrants to set-up small enterprises and to re-orient existing small businesses towards economic activities less affected by the COVID-19 pandemic with prospects for development beyond the crisis. Almost 15 communities in the migrant-sending regions of Armenia have been visited by IOM and around 156 persons have been registered with the project. Since the beginning of the COVID-19 pandemic, the government approved a number of socio-economic programmes to mitigate the impact, however, poor data availability and lack of needs assessments decreased the effectiveness of those programmes. To mitigate these shortcomings, the MPTF project supported the government with needs assessment, covering about 35,000 households and thus generating a comprehensive needs overview. The project also enabled the provision of the support, particularly in the area of mental health and psychosocial support to frontline workers. For example, 500 field professionals were trained and sensitized, as well as a child protection hotline was enhanced and became fully operational in the context of MHPSS and case management support. An innovative approach to address the challenge with testing services in the regions was introduced: “Mobile Healthcare Service” is being piloted including needs assessment, design of the mobile testing service, development of management system, capacity development of nurses, and finally, a upon completion of the pilot the roadmap will be published for the replication and scale up of the new service pilot. Together with social protection measures, the project targets economic assistance and resilience of SMEs. Within the reporting period the project supported 106 SMEs with various support mechanisms: 5 industrial companies with approximately 1000 employees in total, benefited from the production of medical uniforms and bed linens. They not only met the demand for the products, but also ensured economic stability of their employees. The other 101 SMEs received support funding for their entrepreneurial initiatives in various industries. With the rethinking of the reprioritization of economic industries, agriculture was identified as one of the top priorities. To support the government in this endeavour the project aims to generate three model scenarios for the development of Armenia’s agricultural and food sector. The model scenarios will inform the Ministry of Economy’s strategies and plans for agricultural development and will improve the targeting of current and new supporting packages for farmers and others engaged in the agriculture sector. The project also helped to financially support a group of elderly, thus, contributing to the government efforts in this area.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The purpose of the project is to support Armenian communities and persons who were severely impacted due to the pandemic, with particular inclusion of children, women, the elderly, and groups in vulnerable situations. All activities have been planned in line with the LNOB principle and based on the human-rights-based approach. A number of initiatives undertaken and ongoing aim at supporting the Government to better target its policies in response to the socio-economic impact of COVID-19, as well as economic recovery policy planning in agriculture, rural development, entrepreneurship, and strategically relevant light industries. In result, 4,712 persons directly benefitted from the project as of December 2020, of which 2,932 are children with disabilities (67% boys, 33% girls), 770 are older persons, 1,000 employees in light industries. To improve data availability, 8,000 families have participated in a rapid needs assessment by the Ministry of Labor and Social Affairs to better cater for their needs in the aftermath of COVID-19 and conflict. Direct beneficiaries also include 326 households, 5 industries in textile business and 101 SMEs. The indirect beneficiaries are the recipients of the state social benefits thanks to the new system in place, the social workers, household members, as well as business representatives in agriculture, entrepreneurship and light industries. An important achievement has been the support to the Government of Armenia in its efforts to prevent further spread of the novel coronavirus and enhance social protection, as well as local SMEs’ resilience in a post-epidemic context thereby paving the way to improved flexibility and sustainability of the light industries, while contributing to overall poverty reduction.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The disproportionate impact of COVID-19 on the most vulnerable and emerging vulnerable groups was mitigated through direct cash support to 3702 individual and 247 houswehold beneficiaries, prioritizing children with disabilities, older persons and displaced persons. Moreover, more than 30,000 persons (8,000 households) affected by COVID-19 and conflict were assessed through the rapid assessment undertaken by MoLSA and supported by the programme, including development of a dedicated platform for future enrolment of beneficiaries into social protection programmes. Further contamination has been considerably suppressed and poverty level was impacted to be decreased via enhanced local SMEs’ medical gear production capacities and their resilience in a post-epidemic context. The project largely contributes to a number of SERP monitoring framework global indicators: SERP Pillar 1: the establishment of Mobile Healthcare Service together with the training of the nurses contributes to monitoring indicators 1.2c Rapid training to provide essential MNCH services, 1.2g Establishing community-based health delivery points, 1.2h Ensuring supportive mechanisms, as well as 1.4 Number of community health workers receiving UN support to maintain essential services since COVID-19 disruptions, disaggregated by type of support. SERP Pillar 2: The project implementation contributes to monitoring indicators 2.5a, b and g on Financial aid packages, Cash for productivity / transfer programmes and Psychosocial support services. Through the programme 2,932 children with disabilities, 247 households with persons displaced from Syria, and 715 elderly age 75 and above living alone benefitted from the financial aid and cash support. For mental health and psychosocial support purposes 500 social service workforce professional have been sensitized and trained in case management to work in the situation of COVID-19. SERP Pillar 3: By providing support to 106 SMEs, the design of new financial scoring mechanism to mitigate the barriers for effective roll-out of the Government support package to MSMEs, as well as 3 scenarios being modelled in the agriculture sector for effective planning and targeting of COVID-19 recovery activities the project implementation is contributing to the delivery of indicators 3.2a and b on supporting private sector companies and formal and informal sector workers during and after the COVID-19 pandemic. SERP Pillar 4: Though the project has been drafted prior to the SEIA finalization in Armenia, the project implementation was largely informed and highly benefitted from the multi sector impact assessment. Additionally, IOM undertook individual vulnerability assessment to inform the identification of the most vulnerable labour migrants unable to leave for seasonal employment, and UNICEF considerably supported the development and launching of a rapid needs assessment covering more than 35,000 families affected by COVID-19. Hence, the project contributed to the delivery on indicators 4.1a,b and 4.2a, c, e on socio-economic impact assessments in response to the COVID-19 crisis informing the programmatic activities. SERP Pillar 5: Capacity development initiatives within the project, such as the capacitating of 500 social service workforce professionals, development of healthcare workers service guidance and their trainings, contribute to the delivery on indicators 5.2a and i on capacitating community based organizations to respond and mitigate the impact of the pandemic.
3.2 | Results: Output Level | Please include output level results achieved | • Opportunities for employment and entrepreneurship efforts have been supported and promoted for disadvantaged persons and MSMEs, including through improved access to technical assistance and digital innovation. • 1000 employees (95% women) were able to maintain their employment within local 5 companies producing medical supplies. • 5 companies enhanced their resilience by having production order for the Ministry of Health and improving their capacity of producing medical supplies. • 50 employees (100% women) were assisted in view of organizing medical gear production. • 2 PPE production value chains were assessed and tested. • 5 companies adopted the set medical gear standards. • A vertical cash top-up of 26,500 AMD per child – aligned with the childcare benefit value and food poverty line – was provided to 2,932 children with disabilities (67% boys, 33% girls) living in 2,797 families receiving family benefits countrywide to mitigate the socio-economic impacts of COVID-19. Based on the agreement between UNICEF and MoLSA, a dedicated Treasury account was opened for the Social Security Service under MoLSA, which was used for the transfer. An informational booklet on parenting at times of COVID-19 was also developed for pro bono distribution by Haypost. Due to escalation of hostilities in and around Nagorno Karabakh, the initiative was stalled, and instead, the booklets were provided as part of non-food item support to more than 4,000 women and children in refugee-like situation. • UNICEF and UNDP in collaboration with WFP, the World Bank and MoLSA, started development of a rapid assessment and beneficiary registration system primarily targeting families and children outside of existing social protection programmes and support packages, thus increasing the shock-responsiveness of the social protection system and improving the effectiveness and efficiency of MoLSA’s MIS systems. A questionnaire was developed with UNICEF support for initial collection of needs and expansion of social protection coverage by the National Institute for Labor and Social Research (targeting 35,000 households affected by COVID-19 and conflict), which is also being automatized by Nork Social Services Technology and Awareness Center for all social workers in the country. Two teams have been set up – IT and substantive – to draft the technical specification of the MIS system and business processes of family social assessment, including rapid assessment during emergencies and its linkages to the integrated single registry envisaged within the integrated social services reform. • The hotline of MoLSA was revamped through joint cooperation between UNICEF and UNDP. UNDP renovated the space, while UNICEF provided furniture and dedicated software, allowing for a smoother and more user-friendly services and quick expansion to address increased demands by beneficiaries during dual crises of COVID-19 and conflict. • UNICEF in cooperation with the Armenian Association of Social Workers developed materials and implemented training/coaching/mentoring of 500 social service workforce professionals and allied professionals from all regions of Armenia to increase their capacity of working in the situation of COVID19 and providing psychosocial support to the population in need. In the framework of the project professionals also created their own networks on the regional level and received support and guidance through the Helpline for Social Service Workforce professionals, established ealier in 2020 with UK CSSF financial support and sustained by the Armenian Association of Social Workers.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The COVID-19 pandemic has considerable socio-economic impact on Armenia and which has been very challenging for the government. In addition the conflict in and around Nagorno Karabakh put extra burden on the country, the government as well as the development community having to deal with compounded impact by two crises at the same time. The NK conflict was considered in the Risk Management Matrix of the project, but the likelihood of the escalation was underestimated, hence measures identified for risk mitigation turned out to be insufficient. The introduction of Martial Law had significant impact on all project interventions. During the period of the NK conflict and the martial law, it was extremely complicated to have regular interaction with the key government representatives, which resulted in the delay of the project implementation. In the aftermath of the statement on the cessation of the hostilities in November, a few cabinet members were replaced, which further delayed the implementation of a few planned activities. For IOM the movement restrictions during the escalation period were quite challenging as beneficiary identification is usually done via on-site visits and person -to -person meetings. Consequently a delay in the selection and timely registration processes resulted. Regarding the UNDP Mobile Healthcare Service Pilot, for instance, the Government was making amendments regarding the licensing of mobile health care services in the relevant Government decision. however, the decision on the amendment was postponed from October to November and started to be processed in late December: this decision is very important and fundamental for the Project team to ensure smooth piloting of the Mobile testing service,. Another challenge has been the need for rapid engagement with the government institutions on cash support modalities. Since there are systematic and programmatic requirements to be met both by the UN and by the Government, some activities took longer than planned. For example, the number of elderly and children with disabilities enrolled in the family benefit system identified as potential beneficiaries was bigger during the planning process, and during the three months of the project processing the beneficiary base got decreased, partially due to the severe cases of COVID-19 the elderly could not overcome. The extraordinary situation in Armenia pushed for further flexibility and agility of the implementation toolbox, and UN engagement got much appreciated both by the individual beneficiaries and by the Government.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The joint project was the first to be overall coordinated by the RC office, and it has been a great opportunity for UNCT Armenia and the RCO, to test the effectiveness of collaboration in this new format. Lessons learnt, both positive and negative, have two dimensions: operational/coordination and substance related. From the operational perspective it was very helpful to have a project tracker developed by the RCO, which is updated bi-weekly. The tracker contains information on the progress towards the project indicators, specific budget spending per activities and per agencies, identifies the focal points per activities, even if it is a joint activity, and include information on the communication initiatives. Bi-weekly progress meetings with the project team provide the team members insights about all the activities, thus creating the platform for the identification of interlinkages and leading towards joint project implementation. The willingness of the project team members to actively contribute to these meetings has been the cornerstone for collaboration and joint implementation. Lessons learned on the substantive dimension: • The opening of a Treasury account takes longer time (around 1-1,5 months), however, it is a better coordinated and more direct way of providing cash to vulnerable populations. • Work with the government within the project included provision of access of personalized information, which the government could not easily provide, if at all, due to the normative boundaries on the protection of personal information. Hence, data collection for monitoring and verification purposes has been and still continues to be a challenge.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNICEF worked with the National Institute of Labor and Social Research and Nork Social Services Technology and Awareness Center for the rollout of rapid needs assessment of COVID-19 and conflict affected families, including development of a questionnaire and a dedicated platform for social workers for data entry through tablets, thus easing data collection, analysis and policy-making. IOM has managed to build strong and successful partnerships with local community leaders in almost 15 communities of Armenia. This effective collaboration facilitated beneficiary identification, while outreach was quite challenging with the COVID-19 movement restrictions. Partnerships with UNHCR Operational Partners (both state entities and NGOs) have been strengthened and enhanced in exchanging information to ensure that duplication of efforts is avoided. UNHCR mobilized its operational partners particularly Armenian General Benevolent Union (AGBU), Aleppo Compatriotic Benevolent NGO, Armenian Red Cross Society (ARCS) to ensure timely and effective referrals of vulnerable households and that no vulnerable one individual were is left behind. Coordination with relevant state agencies, namely the Ministry of Labour and Social Affairs, the Migration Service and the Office for the High Commissioner for Diaspora Affairs was also undertaken to ensure information exchange and to avoid overlap. The partners have learned to operate online effectively and efficiently. UNIDO has successfully collaborated with the Ministry of Health to address the immediate PPE and other needs identified by the government partners. UNICEF and UNDP leveraged new partnerships with WFP and the World Bank, under the leadership of MoLSA, within the development of a rapid assessment system, which then grew into a family social needs assessment and social protection information management system. UN agencies are supporting the development of the terms of reference for the new system and business processes, while the World Bank will utilize its loan for the actual design of the system (SPAP II programme). This is unprecedented cooperation between the Government and development partners in the development of synchronized MIS systems and is fully aligned with the UN COVID-19 SERRP. In the framework of the project an innovative informational EmployeeProtect.am platform was launched, which aims to strengthen the system of the protection of labor rights in Armenia. The platform is managed by the Health and Labor Inspection Body of the Republic of Armenia. This platform was developed in partnership with the Armenian Lawyers' Association, which had previous experience in development of a similar platform for business protection. Additionally, in the framework of designing alternative scoring mechanisms, new partnerships were established with the Ministry of Economy, ACRA Credit Bureau and the Central Bank of Within Mobile Health Care component UNDP collaborates with the Amasia Health Center and local self-government bodies in Amasia and Arpi. They were engaged in needs assessment and co-design of the service.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | An individual vulnerability assessment has been conducted by IOM (female-headed HH, 3 or more children in the HH, unemployment, etc.) and procedures have been established to identify the most vulnerable labour migrants who were unable to leave for seasonal employment due to travel restrictions and were not able to cover their basic needs. A rapid needs assessment covering more than 35,000 families affected by COVID-19 and conflict is being conducted by the National Institute of Labour and Social Research with support from UNICEF, as well as partial support from the MPTF programme and pooled UNICEF emergency funding. Needs assessment of the enlarged municipalities Amasia and Arpi was conducted to pilot mobile health care service.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No major adjustment have been made to the outcome or the outputs. The only considerable adjustment in the project has been the no-cost extension for its implementation due the conflict in and around Nagorno- Karabakh leading to delay of activities.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Based on the high interest and need for Mobile Health Care Service in enlarged municipalities other than selected for the project purposes, mobile testing services will be upscaled within UNDP “Women and Youth for Innovative Local Development” project and will be established in one more enlarged municipality.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome: The disproportionate socio-economic impact of the COVID-19 pandemic on the most vulnerable people and businesses in Armenia is mitigated through access to adequate, inclusive and effective social and economic protection mechanisms.
Indicator 2.1a: Proportion of population covered by COVID-19 social protection programmes, by sex, age, vulnerability (related to SDG indicator 1.3.1) | 4202 direct beneficiaries; 35,000 target beneficiaries as households upon the completion of activities under indicator 2.1.1b; | More accurate data will be avalable upong the completion of the project. | ARMSTAT database and reports; GoA reports (sectoral and over-arching), project reports, and others
Baseline: 309,951 beneficiaries and 84,810 families for social support; 486,434 families beneficiaries for gas/utility subsidies
Planned Target: At least 10% increase in coverage of beneficiaries and families (with focus on emerging vulnerable groups outside of ongoing Government support programmes)
Indicator 2.1b: Proportion of population covered by COVID-19 economic assistance measures , by sex, age, vulnerability | 1000 beneficiaries from 5 SMEs; 101 SMEs and their employees | More accurate data will be avalable upong the completion of the project. | ArmStat, Government and Ministry of Economy reports, project reports
Baseline: 29,543 beneficiaries
Planned target: At least 10% increase in coverage of beneficiaries by economic assistance measures (focus on emerging groups)
Output 2.1.1. Rights- and evidence-based social protection measures, particularly cash transfers and services, are upgraded and their coverage expanded to minimize the exposure and vulnerability of disadvantaged groups to socio-economic impacts of COVID-19 | 2,932 children with disabilities 247 HHs with persons displaced from Syria 715 elderly age 75 and above living alone | The armed conflict in and around NK had an impact on the pro bono distribution of COVID awareness raising booklets for parents of CwDs by Haypost, considering the inability of the Ministry of Labour and Social Affair to provide lists of beneficiaires due to the martial law and overburdened system. The booklets were instead distributed as part of 4000 hygiene and dignity kits provided to affected families with children, including children with disabilities. Initially, 3,055 children with disabilities were planned for cash support, as identified by MoLSA as beneficiaires of family benefits, however, by the time the interventions was rolled out, the overall number of all children with disabilities living in families receiving family benefits, had decreased to 2,932 (67% boys, 33% girls; 2797 HHs nationwide). For equity purposes it was decided not to apply any discriminatory criteria for the celection of tghe elderly, thus, every person living alone and meeting the age criteria recived the one-time cash support. Due to data privacy issues, demographic information on the beneficiaries is not available at this point. | MoLSA reports and Government decisions, exchange of letters with Government partners, agreements with partners. UNHCR-Mission Armenia CBI committee documented decisions, list of bank transfers to the recipients.
Indicator 2.1.1a: Number of HHs/persons receiving direct cash transfers through JP response to COVID-19 (disaggregated by age, sex, vulnerability, location)
Baseline: 0
Planned Target: 3,500 children with disabilities; 220 HHs with persons displaced from Syria 300 women and older persons in vulnerable situations
Indicator 2.1.1b: Number of HHs/persons benefiting from new or additional social assistance measures provided by governments to respond to COVID-19 with JP support (disaggregated by age, sex, vulnerability, location, type (cash/services)) | Business case has been prepared, discussions are ongoing with MoLSA. MoLSA has drafted a concept note and timeline, which is pending internal approvals. Working group has been established and approved by the MoLSA, required experts have been hired, additional team members will be hired if necessary. MoLSA's hotline is being upgraded as well to ensure rapid and quality response to beneficiary needs, including a better software and conditions. This will help MoLSA to respond effectively to beneficiary querries during COVID-19 crisis, as well as as a result of escalation of the NK conflict. | 35,000 households are being targeted through pooled MPTF and UNICEF emergency funding for the needs assessment of COVID-19 and conflict affected families.For the reporting period, 8,000 families have been assessed, however, disaggregation will be available in the final report. Overall, the delay of the activity implementation is due to the escalation of the hostilities in Nagorno Karabakh in September November 2020. | ToR on the family needs assessment information platform, Order of the MoLSA Minister on establishing the working group, approving schedule and working procedures (N 6-Ա/1 dated January 19, 2021)
Baseline: 0
Planned Target: 7000 HHs/ 30,000 persons (from emerging vulnerable groups)
Indicator 2.1.1c: Number of social service workforce professionals/allied professionals who benefitted from capacity development activities (disaggregated by age and sex) | 500 SSW professionals trained on MHPSS and case management support. Child protection hotline enhanced and fully operational for provision of MHPSS and case management support. | The delay of the activity implementation is due to the escalation of the hostilities in Nagorno Karabakh in September November 2020. 500 social service workforce professionals have been sensitized on working in the situation of COVID-19 and on provision of MHPSS. | MoLSA reports, agreements with partners, training materials
Baseline: 0
Planned Target: 500 professionals
Indicator 2.1.1d: MoLSA procedures for collecting and analyzing COVID-19 related and LNOB (disaggregated by age, sex, vulnerability, location) data are developed. | Two servers have been purchsed for the Ministry of Labour and Social Affairs for unified data collection for Domestic Violence cases as well as for data development disaggregated by age, sex, vulnerability and location. Support of Rapid needs assessment platform developed together with UNICEF and Norq information analytical center is in progress. IT company has already been selected and the EmployeeProtect.am platform, which is aimed at reporting and protecting the employees’ rights, is in the process of development together with the Health and Labor inspection. In the framework of the project an innovative informational EmployeeProtect.am platform was launched, which aims to strengthen the system of the protection of labor rights in Armenia. Easy to navigate, the platform allows quick registration, acceptance, and examination of applications on violations of the rights of employees, which are then processed by the Health and Labor Inspection Body of the Republic of Armenia. This platform was developed in partnership with the Armenian Lawyers' Association, which had previous experience in development of a similar platform for business protection. The platform will be piloted for the next three months and improved based on the user feedback and operational efficiency. In parallel, a replicated model will be applied to mobile apps for IOS and Android systems. Inital mapping was implemented for Conducting Rapid Assessment and Mapping of Data and Process Gaps, the next step for detailed assessment is still in process. UNDP Mobile Testing Service Pilot:1) needs assessment and the codesign of the mobile testing service is completed. 2) procurement of the equipment for the pilot is in process; 3) the management system for the new service is in process (tablets are procured, Wi-Fi internet connection as well as the application development is in process), 4) capacity needs of the nurses to deliver the new service are identified and the training preparation in the process and 5) the roadmap for the new service pilot is in development process. | Due to increased number of calls as a result of COVID-19, the MoLSA Call Center is in the process of recruiting additional staff. Capacity buidling on psycho-social aspects with the help of psychologists will be implemented. A team of psychologists has already been selected and preliminary needs assessment of the current personnel is in process. UNDP Mobile Testing Service Pilot: Due to the conflict and second wave of the COVID-19 the launch of the pilot will start from February 2021 and the team will backstop and support Amasia medical center and the regional government to implement the pilot till end of 2021. | ToR for technical assistance team, LNOB data
Baseline: Few procedures in place, but data not synchronized and not comparable
Planned Target: Procedures in place, allowing for disaggregated data analysis, comparability and forecasting
Output 2.2.1. Employment creation and entrepreneurship efforts are supported and promoted for disadvantaged persons and MSMEs, including through improved access to financial and technical assistance and digital innovation. | 79 HHs with the labor migrants |  | Data from local communities, Project Reports
Indicator 2.2.1a: Number of female headed/male headed HHs/persons benefiting from economic support packages through JP response (disaggregated by age, sex, vulnerability, location)
Baseline: 0
Planned Target: 50 HHs with seasonal labour migrants 100 women and elderly persons in vulnerable situations
Indicator 2.2.1b: Number of businesses/ persons benefiting from financial and technical assistance through the JP (data collected disaggregated by age and sex) | 5 Industrial companies, 1000 employees 101 SMEs owned/managed by: unemployed women aged 50-63, abused women, disabled women, women with disabled children, single mothers, rural women, 63 and older women and men, persons having 63 and more aged family members | Initially, during the project preparation and approval stages, based on discussions with the representatives of the Ministry of Health, it was planned to involve 10 companies to produce: face masks, disposable medical shoes, medical uniforms and bed linen. Among these 10 companies: 2 were going to focus on production of medical uniforms, 3 companies were going to work on production of bed linen, 3 footwear companies were ready to get involved in production of medical disposable shoes and other two companies were going to set production of face masks. Planning and development of objectives were projected based on the initial project plan. Following the approval of the Project document, in July 2020 the project representatives had a meeting with the Ministry of Health to identify and finalize the types of PPE products needed, as anticipated by Project Document. At the meeting with the representatives of Ministry of Health , the Deputy Minister stressed out medical uniforms and bedlinen as a priority need in bigger quantities, informing of the recent supply of sufficient number of shoes and face masks. Eventually, the number of companies and employees to be engaged changed accordingly to meet the actual needs as requested. This accounts for the change in the number of companies directly involved in the production of the requested items. So the number of participating enterprises was reduced from 10 to 5, leaving out the face mask and footwear producers and keeping only the companies dealing with the production of medical bed linen and uniforms. Accordingly, the number of employees also decreased from 2 000 to 1 000. This change resulted in 50% decrease in our initial target . Despite the fact that the number of enterprises and employees involved decreased, the remaining five companies and 1 000 employees (95% are women) involved got the possibility to produce more items and ensure longer employability for their employees, thus more income for their families. | Ministry of Economy reports; Data from the beneficiary companies; Project reports
Baseline: 0
Planned Target: 10 industrial companies, including 2000 employees 100 MSMEs
Indicator 2.2.1c: Number of forecasting scenarios developed in agricultural sector for improved COVID-19 response planning and targeting (beneficiaries disaggregated by age and sex) | The development of the scenarios is planned for January-March 2021 | Due to the escalation of hostilities in Nagorno Karabakh and the risk of political instability, the project implementation was delayed. Currently, might pose risks to the project implementation. The natial expert has already been hired, the project has been launched. The team of international consultants has already been engaged and currently working closely with the FAO team; the necessary input data is already being transferred to the team for further analysis. Four expert interviews has already been conducted as part of the project. | Ministry of Economy reports, Reports with 3 scenarios
Baseline: 0
Planned Target: 3 forecasting scenarios
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
A UNHCR one-pager was published on UN Armenia website to raise public awareness on the emergency assistance for persons displaced from Syria to help them fight the economic challenges caused by COVID-19 pandemic. The pictorial document included figures at glance, the objective and scope of the assistance. The overview of its positive impact on vulnerable displaced persons, particularly women and children, single elderly and persons with specific needs was duly presented. Due to the escalation of the armed conflict around Nagorno-Karabakh, further communication activities covering the MPTF funding and the implemented project were put on hold.
http://www.un.am/en/news/1000
http://un.am/up/library/One-pager-UN%20COVID-19%20Response%20MPTF%20CBI-assistance%20UNHCR%2013%20October%20ENG.pdf
www.facebook.com/UnidoArmeniaLightIndustry
www.facebook.com/UnidoArmeniaLightIndustry
https://www.un.am/en/agency/UNIDO
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Press release on cash support to children with disabilities has been prepared and released https://www.unicef.org/armenia/en/press-releases/unicef-support-families-3055-children-disabilities-one-time-cash-plus-assistance https://www.unicef.org/armenia/%D5%A6%D5%A5%D5%AF%D5%B8%D6%82%D5%B5%D6%81%D5%B6%D5%A5%D6%80/%D5%AF%D5%B8%D6%80%D5%B8%D5%B6%D5%A1%D5%BE%D5%AB%D6%80%D5%B8%D6%82%D5%BD%E2%80%A4-%D5%AB%D5%9E%D5%B6%D5%B9-%D5%BA%D5%A5%D5%BF%D6%84-%D5%A7-%D5%AB%D5%B4%D5%A1%D5%B6%D5%A1%D5%B6-%D5%AE%D5%B6%D5%B8%D5%B2%D5%B6%D5%A5%D6%80%D5%A8 A sticker has been prepared for putting on furniture of MoLSA's hotline. Moreover, a plaquette will also be prepared together with UNDP, and a photo story will be developed on the hotline.
EmployeeProtect.am platform launch press release
https://iravaban.net/en/310598.html
http://un.am/en/news/1077
http://un.am/hy/news/1077
https://www.facebook.com/UNDPArmenia/posts/3582031761878067
The UNDP FB post has reached 2350 people (with no promotion)

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | COVID-19 and Resilience in Armenia: Mitigating the Socio-Economic Impact on Vulnerable People and Communities | Overall Duration (months) | 10 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-06-04
MPTF Office Project Reference Number: | 121956 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Armenia | Current End date(dd.mm.yyyy) | 2021-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP UNICEF UNFPA IOM | National counterparts (government, private, NGOs & others) and other International Organizations | UNIDO UNHCR FAO WFP Ministry of Labout and Social Affairs HayPost State Migration Service Social Security Service Armenain Association of Social Workers Armenian Statistical Committee Ministry of High-Tech Industry Ministry of Economy Nork Invormation Center State Employment Agency Investment Support Center Fund Nork Social Services Technology and Awareness Center National Institute of Labour and Social Research World Bank LIght Industry Export Consortium Ministry of Economy ACRA Credit Bureau Central Bank of Armenia
Report Cleared By
o Name: | Shombu Sharp
o Title: | UN Resodent Coordinator in Armenia
o Email address: | shombi.sharp@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The Project implementation significantly contributed addressing the impact of COVID-19 and supported the Government with multi-dimensional activities for beneficiaries and broad engagement of partners. The project overall aimed at mitigating the disproportionate socio-economic impact of the COVID-19 pandemic on the most vulnerable people and businesses in Armenia by providing them access to adequate, inclusive and effective social and economic protection mechanisms. As a result of the project implementation over 5067 persons and 3124 HHs directly benefitted from the project, of which 247 HHs with 813 persons displaced from Syria, 2797 HHs with 2932 children with disabilities and 722 elderly received cash support, 80 HHs of labour migrants received micro-grants for the set-up of small enterprises or re-profiling existing small businesses, and 500 Social Service Work professionals got trained on MHPSS and case management support. The number of indirect beneficiaries, excluding the HHs having benefitted from cash support, amounts to 29,000HHs, over 2000-3000 employees and 385 individuals targeted and benefitted from the economic support assistance - financial resources and business counselling. Among indirect beneficiaries are 1000 employees of 5 Industrial companies, over 2000 employees of 101 SMEs led by women, and 29,000 families that have been assessed through rapid needs assessment platform. Finally 106 businesses directly benefitted from financial support received through this project. The cash assistance provided to 247 HHs of predominantly ethnic Armenian families displaced from Syria was targeting HHs who had little or no employment opportunities due to lockdowns and an overall decrease of economic activities in the country. Support was provided to returned 80 HHs with labour migrants to set-up small enterprises and to re-orient existing small businesses towards economic activities less affected by the COVID-19 pandemic with prospects for development beyond the crisis. Almost 15 communities in the migrant-sending regions of Armenia have been visited by IOM and around 156 persons have been registered with the project. Since the beginning of the COVID-19 pandemic, the government approved a number of socio-economic programmes to mitigate the impact, however, poor data availability and lack of needs assessments decreased the effectiveness of those programmes. To mitigate these shortcomings, the MPTF project supported the government with needs assessment, covering about 29,000 HHs, and thus, generating a comprehensive needs overview. The project also enabled the provision of the support, particularly in the area of mental health and psychosocial support to frontline workers. For example, the abovementioned 500 field professionals were trained and sensitized, as well as a child protection hotline was enhanced and became fully operational in the context of MHPSS and case management support. An innovative approach to address the challenge with laboratory and instrumental services in the remote areas was introduced: “Mobile Laboratory and Instrumental Diagnostic and Sampling Service” was piloted including needs assessment, design of the mobile testing service, development of digital management system, capacity development of nurses, equipment of the medical center with missing and needed instruments and tools as well as the public awareness. The final model was validated with two department heads of the RA Ministry of Territorial Administration and Infrastructure and the RA Ministry of Health. Upon completion of the pilot the roadmap was to be published for the replication and scale up of the new service pilot. To provide technical assistance to the Ministry of Economy for improved planning and targeting of economic support packages, (re)design of the eligibility criteria, risk-scoring and scenario modelling to Micro, Small and Medium-sized Enterprises (MSMEs),14 scenarios were modelled for the agricultural sector for effective planning and targeting of COVID-19 support/recovery activities and Alternative Scoring Model was designed to improve access to finance for SMEs and Microenterprises which do not have credit history required by Financial Institutions for the provision of capital/debt. Machine Learning algorithms were applied to analyse non-financial information to calculate probability of default and alternative credit scores for micro and small enterprises which do not have credit records. Together with social protection measures, the project targets economic assistance and resilience of SMEs. Within the reporting period the project supported 106 SMEs with various support mechanisms: 5 industrial companies with approximately 1000 employees in total, benefited from the production of medical uniforms and bed linens. They not only met the demand for the products, but also ensured economic stability of their employees. The other 101 SMEs received support funding for their entrepreneurial initiatives in various industries. With the rethinking of the reprioritization of economic industries, agriculture was identified as one of the top priorities. To support the government in this endeavor the project aims to generate three model scenarios for the development of Armenia’s agricultural and food sector. The model scenarios will inform the Ministry of Economy’s strategies and plans for agricultural development and will improve the targeting of current and new supporting packages for farmers and others engaged in the agriculture sector.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | All the activities have been planned in line with the LNOB principle and based on the human-rights-based approach. A number of initiatives undertaken aimed at supporting the Government to better target its policies in response to the socio-economic impact of COVID-19, as well as economic recovery policy planning in agriculture, rural development, entrepreneurship, and strategically relevant light industries. In result, 6067 persons benefitted from the project as of of which 2,932 are children with disabilities (67% boys, 33% girls), 722 are older persons, 813 are persons displaced from Syria, 385 indirect beneficiaries in 80HHs of labour migrants, 500 are Social Service Work professionals and 1,000 are employees in light industries. To improve data availability, 29,000 families have participated in a rapid needs assessment by the Ministry of Labor and Social Affairs to better cater for their needs in the aftermath of COVID-19 and conflict. Beneficiaries also include overall 3124 HHs, 5 industries in textile business and 101 SMEs. The indirect beneficiaries are the recipients of the state social benefits thanks to the new system in place, the social workers, household members, as well as business representatives in agriculture, entrepreneurship and light industries.
3.1 | Results: Outcome Level | Please include outcome level results achieved | As the overall outcome of the project, the disproportionate impact of COVID-19 on the most vulnerable and emerging vulnerable groups was mitigated through direct cash support to individuals and housweholds, prioritizing children with disabilities, older persons and displaced persons. About 29,000 HHs were assessed through the rapid assessment undertaken by MoLSA and supported by the programme, including development of a dedicated platform for future enrolment of beneficiaries into social protection programmes. Further contamination has been considerably suppressed and poverty level was impacted to be decreased via enhanced local SMEs’ medical gear production capacities and their resilience in a post-epidemic context. The project contributed to a number of SERP monitoring framework global indicators: SERP Pillar 1: The establishment of Mobile Laboratory and Instrumental Diagnostic and Sampling Service together with the training of the nurses contributes to monitoring indicators 1.2c Rapid training to provide essential MNCH services, 1.2g Establishing community-based health delivery points, 1.2h Ensuring supportive mechanisms, as well as 1.4 Number of community health workers receiving UN support to maintain essential services since COVID-19 disruptions, disaggregated by type of support. SERP Pillar 2: The project implementation contributes to monitoring indicators 2.5a, 2.5b and 2.5g on Financial aid packages, Cash for productivity / transfer programmes and Psychosocial support services. Through the programme 2,932 children with disabilities, 247 HHs with persons displaced from Syria, and 722 elderly age 75 and above living alone benefitted from the financial aid and cash support. For mental health and psychosocial support purposes 500 social service workforce professional have been sensitized and trained in case management to work in the situation of COVID-19. SERP Pillar 3: By providing support to 106 SMEs, the design of new financial scoring mechanism to mitigate the barriers for effective roll-out of the Government support package to MSMEs, as well as 14 scenarios modelled in the agriculture sector for effective planning and targeting of COVID-19 recovery activities the project implementation contribute to the delivery of indicators 3.2a and 3.2b on supporting private sector companies and formal and informal sector workers during and after the COVID-19 pandemic. SERP Pillar 4: Though the project has been drafted prior to the SEIA finalization in Armenia, the project implementation was largely informed and highly benefitted from the multi sector impact assessment. Additionally, IOM undertook individual vulnerability assessment to inform the identification of the most vulnerable labour migrants unable to leave for seasonal employment, and UNICEF considerably supported the development and launching of a rapid needs assessment covering more than 29,000 families affected by COVID-19. Hence, the project contributed to the delivery on indicators 4.1a,b and 4.2a, 4.2c, 4.2e on socio-economic impact assessments in response to the COVID-19 crisis informing the programmatic activities. SERP Pillar 5: Capacity development initiatives within the project, such as the capacitating of 500 social service workforce professionals, development of healthcare workers service guidance and their trainings, contribute to the delivery on indicators 5.2a and 5.2i on capacitating community based organizations to respond and mitigate the impact of the pandemic.
3.2 | Results: Output Level | Please include output level results achieved | * 2,932 children with disabilities living in families receiving family benefits received one-time cash support of app. 55 USD per child. As per post-distribution monitoring, 88.3% of beneficiaries reported that the provided support had helped them significantly. Top five items for cash use were food, health services, hygiene supplies, shoes/clothes and utility expenses, proving once again the very vulnerable situation of these families. An informational booklet was also developed for families, which was disbursed pro bono by HayPost. Due to the escalation of the Nagorno Karabakh conflict, the distribution did not happen, rather the booklets were used as part of the distribution of hygiene and dignity kits to affected families (app. 4000). A post-distribution monitoring tool has been developed. * One-time cash assistance was prpovided to 247 vulnerable HHs displaced from Syria to cover increased basic needs in response to COVID19 crisis, as well as to 722 lonely elderly disbursed as part of regular family benefit payments. * Rapid assessment system was developed to be linked to the integrated management information system, that benefitted 29,000 families during the project lifetime, but intends to capture many more families in the future. Under MoLSA leadership, substantive working group has been established, IT working group has been established for development of the Rapid information management SP system. A review of business processes for family's social assessment was done, including during emergencies, with appropriate recommendations. MoLSA's hotline and hotline space have been upgraded to ensure rapid and quality response to beneficiary needs, including a better software and conditions. This will help MoLSA to respond effectively to beneficiary querries during COVID-19 crisis, as well as as a result of escalation of the Nagorno Karabakh conflict. * UNICEF in cooperation with the Armenian Association of Social Workers developed materials and implemented training/coaching/mentoring of 500 social service workforce professionals and allied professionals from all regions of Armenia to increase their capacity of working in the situation of COVID19 and providing psychosocial support to the population in need. In the framework of the project professionals also created their own networks on the regional level and received support and guidance through the Helpline for Social Service Workforce professionals, established ealier in 2020 with UK CSSF financial support and sustained by the Armenian Association of Social Workers. * Rapid assessment system, including beneficiary registration, has been designed and link to the integrated social services database. Two servers have been purchsed for MLSA for unified data collection for Domestic Violence cases as well as for data development disaggregated by age, sex, vulnerability and location. * 15 communities in the most migrant-sending regions of Armenia have been visited by IOM and around 156 HHs with returned labour migrants who were unable to resume their jobs due to the impact of COVID-19 have been registered with the project. The beneficiary HHs were thoroughly assessed in coordination with the MoLSA and with local community leaders and 80 HHs have been selected in the scope of the project for assistance to set up or adapt businesses. Through the project 83 workplaces have been created and, in total, 385 indirect beneficiaries were targeted and benefitted from the economic support assistance - financial resources and business counselling. The assistance was mainly delivered in Shirak region, which traditionally registers high level of labour emigration. Total grant amount provided in the region was approximately USD 100,000, while total amount disbursed is USD117,000. Almost 84 percent of the total assistance has been provided in livestock breeding, 9 percent in farming, 2.5 percent in greenhouse production. * 101 SMEs owned/managed by vulnerble groups have received grant support. * Scoring mechanisms have developed to improve access to finance for microbusinesses and unregistered entrepreneurs. The focus of the initiative has been the design of Alternative Scoring Model to improve access to finance for SMEs and Microenterprises which do not have credit history required by Financial Institutions to provide capital/debt. Further utilization the Alternative Scoring System requires capital and engagement of the Business Entity or Governmental Agency. * 14 scenarios were modelled for the agricultural sector for effective planning and targeting of COVID-19 support/recovery activities. 14 scenarious are modelled with the MAGNET (Modular Applied GeNeral Equilibrium Tool) model. * 5 industrial companies, including 1000 employees were supported for boosting local production of medical PPE production. benefiting from financial and technical assistance. 2623 sets of bedlinen, 2000 sets of medical uniform had beed supplied. The project made it possible to cover expressed needs in bed linen by 100 % and for medical uniforms by 75%. *Machine Learning based Alternative Scoring Model was developed for commercial banks, credit bureaus and development institutions able to provide additional scoring guidelines for credit and grant provision.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Armenia is one of the countries that COVID-19 has considerable socio-economic impact, which has been very challenging for the government. In addition to issues caused by the pandemic in September 2020 the unprecedented escalation of the hostilities in and around Nagorno Karabakh put extra burden on the government as well as the development community having to deal with compound crises at the same time. A new risk was added to be the breakout of war in and around Nagorno Karabakh. which had a significant impact on all project interventions due to announced martial law and aggravated by second wave of COVID-19. For most of the agencies and partner organizations the movement restrictions, especially during the conflict in and around NK represented a challenge as beneficiary identification is usually done via on-site visits and person -to -person meetings. Consequently, it resulted in slight delays in the beneficiary identification, timely registration, and applications processing. Within the framework of the project and considering the lack of data on potential beneficiaries from the state, UNHCR, through Mission Armenia NGO reached out to the most vulnerable persons in refugee-like situation from Syria. Considering the epidemiological situation, personal protective equipment was provided to the social workers to ensure their safe access to respective HHs. The process, including the needs assessment and provision of assistance was conducted as per respective SOPs on Cash-based Interventions, keeping UNHCR rules and regulations upheld. Regarding the UNDP Mobile Laboratory and Instrumental Diagnostic and Sampling Service Pilot, for instance, the Government was making amendments regarding the licensing of mobile health care services in the relevant Government decision. However, the decision on the amendment was postponed from October to November and started to be processed in late December. Another challenge has been the need for rapid engagement with the government institutions on cash support modalities. Since there are systematic and programmatic requirements to be met both by the UN and by the Government, some activities took longer than planned. For example, the number of elderly and children with disabilities enrolled in the family benefit system identified as potential beneficiaries was bigger during the planning process, and during the three months of the project processing the beneficiary base got decreased, partially due to the severe cases of COVID-19 the elderly could not overcome. The extraordinary situation in Armenia pushed for further flexibility and agility of the implementation toolbox, and UN engagement got much appreciated both by the individual beneficiaries and by the Government.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The joint project was the first to be overall coordinated by the RC office, and it has been a great opportunity for UNCT Armenia and the RCO, to test the effectiveness of collaboration in this new format. Lessons learnt, both positive and negative, have two dimensions: operational/coordination and substance related. From the operational perspective it was very helpful to have a project tracker developed by the RCO, which was being updated bi-weekly. The tracker contained information on the progress towards the project indicators, specific budget spending per activities and per agencies, identified the focal points per activities, e and included information on the communication initiatives. Bi-weekly progress meetings with the project team provided the team members insights about all the activities, thus creating the platform for the identification of interlinkages and leading towards joint project implementation. The willingness of the project team members to actively contribute to these meetings has been the cornerstone for collaboration and joint implementation. Our agencies learnt that opening of a Treasury account takes longer time than planned (around 1-1,5 months), at the same time, it is a better coordinated and more direct way of providing cash to vulnerable populations. Based on the high interest and need of Mobile Laboratory and Instrumental Diagnostic and Sampling Service we learnt that there is a need for upscaling the initiative, and within UNDP “Women and Youth for Innovative Local Development” project the service will be provided in one more enlarged municipality as well. Due to Nagorno Karabakh conflict and poliotical instability along with the economic decrease, the project team learnt that while planning the budget the possible significant changes in exchange rate should be taken into account.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNICEF worked with the National Institute of Labor and Social Research and Nork Social Services Technology and Awareness Center for the rollout of rapid needs assessment of COVID-19 and conflict affected families, including development of a questionnaire and a dedicated platform for social workers for data entry through tablets, thus easing data collection, analysis and policy-making. IOM has managed to build strong and successful partnerships with local community leaders in almost 15 communities of Armenia. This effective collaboration facilitated beneficiary identification, while outreach was quite challenging with the COVID-19 movement restrictions. Partnerships with UNHCR Operational Partners (both state entities and NGOs) have been strengthened and enhanced in exchanging information to ensure that duplication of efforts is avoided. UNHCR mobilized its operational partners particularly Armenian General Benevolent Union (AGBU), Aleppo Compatriotic Benevolent NGO, Armenian Red Cross Society (ARCS) to ensure timely and effective referrals of vulnerable HHs and that no vulnerable one individual were is left behind. Coordination with relevant state agencies, namely the Ministry of Labour and Social Affairs, the Migration Service and the Office for the High Commissioner for Diaspora Affairs was also undertaken to ensure information exchange and to avoid overlap. The partners have learned to operate online effectively and efficiently. UNIDO has successfully collaborated with the Ministry of Health to address the immediate PPE and other needs identified by the government partners. UNICEF and UNDP leveraged new partnerships with WFP and the World Bank, under the leadership of MoLSA, within the development of a rapid assessment system, which then grew into a family social needs assessment and social protection information management system. UN agencies are supporting the development of the terms of reference for the new system and business processes, while the World Bank will utilize its loan for the actual design of the system (SPAP II programme). This is unprecedented cooperation between the Government and development partners in the development of synchronized MIS systems and is fully aligned with the UN COVID-19 SERRP. In the framework of the project an innovative informational EmployeeProtect.am platform was launched, which aims to strengthen the system of the protection of labor rights in Armenia. The platform is managed by the Health and Labor Inspection Body of the Republic of Armenia. For the purpose of developing the platform, the UNDP has collaborated with the Armenian Lawyers' Association, which had previous experience in development of a similar platform for business protection. Additionally, in the framework of designing alternative scoring mechanisms, new partnerships were established with the Ministry of Economy, ACRA Credit Bureau and the Central Bank of Armenia. Within Mobile Laboratory and Instrumental Diagnostic and Sampling Service component UNDP collaborates with the Amasia Health Center and local self-government bodies in Amasia and Arpi. They were engaged in needs assessment and co-design of the service. The final model was validated with two department heads of the RA Ministry of Territorial Administration and Infrastructure and the RA Ministry of Health. UNDP established collaboration with private banks, credit scoring agency, Central Bank of Armenia and the Ministry of Economy of RA during design and stricturing of Alternative Scoring Model to create a platform for further implementation of the project by private and public stakeholders.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | In the scope of the post-distribution monitoring interviews, IOM has organized regular on-site visits and assessments with the project beneficiaries to ensure that operations have been proceeded effectively and the project had positive impact on beneficiary livelihoods. Interviews revealed that more than 90 per cent of project beneficiaries have increased their household income and improved livelihood. The most recent round of interviews indicated that the majority of the beneficiaries are committed to stay in the country and continue the micro-business activities. A rapid needs assessment covering more than 35,000 families affected by COVID-19 and conflict is being conducted by the National Institute of Labour and Social Research with support from UNICEF, as well as partial support from the MPTF programme and pooled UNICEF emergency funding. Needs assessment of the enlarged municipalities Amasia and Arpi was conducted to pilot Mobile Laboratory and Instrumental Diagnostic and Sampling Service service. The UNDP has conducted an assessment of COVID-19 response economic and social support packages provided to various groups of population, outlined the cases when the applications were refused, with outlining the issues and reasons for refusal (technical issues of the digital services, issues in the application, mismatch/lack of data), and prepared a draft report with key findings of the initial rapid assessment, issues, gaps and needs.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No major adjustment have been made to the outcome or the outputs. The only considerable adjustment in the project has been the no-cost extension for its implementation due the conflict in and around Nagorno- Karabakh leading to delay of activities.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome: The disproportionate socio-economic impact of the COVID-19 pandemic on the most vulnerable people and businesses in Armenia is mitigated through access to adequate, inclusive and effective social and economic protection mechanisms.
Indicator 2.1a: Proportion of population covered by COVID-19 social protection programmes, by sex, age, vulnerability (related to SDG indicator 1.3.1) | 5067 individuals and 3124 HHs as direct beneficiaries; 29,000HHs as indirect beneficiaries 385 indirect beneficiaries | The number of all children with disabilities in families receiving family benefits in the project proposal was mentioned to be 3055, however according to the Ministry of Labour and Social affairs data, it has decreased from 3,055 to 2,932. Only 722 lonely elderly have received one-time cash assistance as the rest of them have passed away during the period of payment and the remaining resources have been allocated to procurement of PPEs and food packages for another group of lonely elderly | ARMSTAT database and reports; GoA reports (sectoral and over-arching), project reports, and others
Baseline: 309,951 beneficiaries and 84,810 families for social support; 486,434 families beneficiaries for gas/utility subsidies
Planned Target: At least 10% increase in coverage of beneficiaries and families (with focus on emerging vulnerable groups outside of ongoing Government support programmes)
Indicator 2.1b: Proportion of population covered by COVID-19 economic assistance measures , by sex, age, vulnerability | 1000 beneficiaries from 5 SMEs; 101 SMEs and their employees 385 | More accurate data will be available upon the completion of the project. | ARMSTAT, Government and Ministry of Economy reports, project reports
Baseline: 29,543 beneficiaries
Planned target: At least 10% increase in coverage of beneficiaries by economic assistance measures (focus on emerging groups)
Output 2.1.1. Rights- and evidence-based social protection measures, particularly cash transfers and services, are upgraded and their coverage expanded to minimize the exposure and vulnerability of disadvantaged groups to socio-economic impacts of COVID-19
Indicator 2.1.1a: Number of HHs/persons receiving direct cash transfers through JP response to COVID-19 (disaggregated by age, sex, vulnerability, location) | 2,932 children with disabilities 247 HHs with 813 persons displaced from Syria 722 elderly age 75 and above living alone | The armed conflict in and around NK had an impact on the pro bono distribution of COVID awareness raising booklets for parents of CwDs by HayPost, considering the inability of the Ministry of Labour and Social Affair to provide lists of beneficiaries due to the martial law and overburdened system. The booklets were instead distributed as part of 4000 hygiene and dignity kits provided to affected families with children, including children with disabilities. Initially, 3,055 children with disabilities were planned for cash support, as identified by MoLSA as beneficiaries of family benefits, however, by the time the interventions was rolled out, the overall number of all children with disabilities living in families receiving family benefits, had decreased to 2,932 (67% boys, 33% girls; 2797 HHs nationwide). In the project 220 households with persons displaced from Syria were targeted to receive support under this project. Still, due to the planning and availability of resources 247 HHs became project beneficiaries. Only 722 lonely elderly have received one-time cash assistance as the rest of them have passed away during the period of payment and the remaining resources have been allocated to procurement of PPEs and food packages for another group of lonely elderly. | MoLSA reports and Government decisions, exchange of letters with Government partners, agreements with partners. UNHCR-Mission Armenia CBI committee documented decisions, list of bank transfers to the recipients.
Baseline: 0
Planned Target: 3,500 children with disabilities; 220 HHs with persons displaced from Syria 300 women and older persons in vulnerable situations
Indicator 2.1.1b: Number of HHs/persons benefiting from new or additional social assistance measures provided by governments to respond to COVID-19 with JP support (disaggregated by age, sex, vulnerability, location, type (cash/services)) | In collaboration with the Ministry of Labour and Social Affairs (MoLSA) together with the National Institute of Labour and Social Research a platform and software has has been put in place for a rapid needs assessment. The social workers are expected to conduct needs assessment of up to 35,000 families affected by COVID and conflict. A total of 29,000 families have been assessed. Substantive working group has been established, IT working group has been established for development of the Rapid information management SP system. Organization was hired to review business processes for family assessment system, including during emergencies. MoLSA's hotline and hotline space have been upgraded to ensure rapid and quality response to beneficiary needs, including a better software and conditions. In addition to physical and technical upgrade of the center, trainings were conducted on psycho-social, behavioral, communication and self-care aspects, which will help the operators better understand and respond to the core issues of the applicants. | The target of 7000 HHs with at least 30,000 persons has been reached since by the end of the project 29,000 families were assessed with the newly set-up Rapid Needs Assessment system. Due to increased number of calls as a result of COVID-19, the MoLSA Hotline is in the process of recruiting additional staff. For this purpose, the Hotline and hotline space upgrade was completed. Moreover, capacity buidling on psycho-social, self-care and behavioural aspects were conducted by a team of psychologists. | ToR on the family needs assessment information platform, Decree of the MoLSA Minister on establishing the working group, approving schedule and working procedures (N 6-Ա/1 dated January 19, 2021)
Baseline: 0
Planned Target: 7000 HHs/ 30,000 persons (from emerging vulnerable groups)
Indicator 2.1.1c: Number of social service workforce professionals/allied professionals who benefitted from capacity development activities (disaggregated by age and sex) | 500 SSW professionals trained on MHPSS and case management support. Child protection hotline enhanced and fully operational for provision of MHPSS and case management support. | UNICEF in cooperation with the Armenian Association of Social Workers developed materials and implemented training/coaching/mentoring of 500 social service workforce professionals and allied professionals (mostly women) from all regions of Armenia to increase their capacity of working in the situation of COVID19 and providing psychosocial support to the population in need. In the framework of the project professionals also created their own networks on the regional level and received support and guidance through the Helpline for Social Service Workforce professionals, established ealier in 2020 with UK CSSF financial support and sustained by the Armenian Association of Social Workers. | MoLSA reports, agreements with partners, training materials
Baseline: 0
Planned Target: 500 professionals
Indicator 2.1.1d: MoLSA procedures for collecting and analyzing COVID-19 related and LNOB (disaggregated by age, sex, vulnerability, location) data are developed. | Two servers have been purchased for the Ministry of Labour and Social Affairs for unified data collection for Domestic Violence cases as well as for data development disaggregated by age, sex, vulnerability and location. An assessment of COVID-19 response economic and social support packages provided to various groups of population was conducted. The report contains information on the cases when the applications were refused, with outlining the issues and reasons for refusal (technical issues of the digital services, issues in the application, mismatch/lack of data), and key findings of the initial rapid assessment, issues, gaps and needs. Support to Rapid needs assessment platform developed together with UNICEF and Norq information analytical center is in progress and will continue after the project ends, since it is part of a bigger initiative for creating a Unified system. Innovative informational EmployeeProtect.am platform was launched aiming to strengthen the system of the protection of labor rights in Armenia. The platform allows quick registration, acceptance, and examination of applications on violations of the rights of employees, which are then processed by the Health and Labor Inspection Body of the Republic of Armenia. The platform is available on mobile apps for IOS and Android systems. UNDP Mobile Laboratory and Instrumental Diagnostic and Sampling Service Pilot:1) needs assessment and the codesign of the mobile testing service is completed. 2) procurement of the equipment for the pilot is over; 3) digital management system for the new service is finalized, 4) capacity needs of the nurses to deliver the new service are identified and the trainings are in progress process (co-funded by other projects); 5) printing and visibility materials are developed; 6) validation/feedback meetings with the Ministry of Territorial Administration and Infrastructure and the Ministry of Health were conducted; and 7) the roadmap for the new service pilot is developed. | Due to increased number of calls as a result of COVID-19, the MoLSA Call Center is in the process of recruiting additional staff. For this purpose, the Call Center office renovation was completed. Moreover, capacity buidling on psycho-social, self-care and behavioural aspects with the help of psychologists has been implemented by a team of psychologists. UNDP Mobile Laboratory and Instrumental Diagnostic and Sampling Service pilot : Due to the conflict and second wave of the COVID-19 the launch of the pilot will start from March 2021 and the team will backstop and support Amasia medical center and the regional government to implement the pilot till end of 2021. | Due to increased number of calls as a result of COVID-19, the MoLSA Call Center is in the process of recruiting additional staff. For this purpose, the Call Center office renovation was completed. Moreover, capacity buidling on psycho-social, self-care and behavioural aspects with the help of psychologists has been implemented by a team of psychologists. UNDP Mobile Laboratory and Instrumental Diagnostic and Sampling Service Pilot: Due to the conflict and second wave of the COVID-19 the launch of the pilot will start from March 2021 and the team will backstop and support Amasia medical center and the regional government to implement the pilot till end of 2021.
Baseline: Few procedures in place, but data not synchronized and not comparable
Planned Target: Procedures in place, allowing for disaggregated data analysis, comparability and forecasting
Output 2.2.1. Employment creation and entrepreneurship efforts are supported and promoted for disadvantaged persons and MSMEs, including through improved access to financial and technical assistance and digital innovation.
Indicator 2.2.1a: Number of female headed/male headed HHs/persons benefiting from economic support packages through JP response (disaggregated by age, sex, vulnerability, location) | 80 HHs labour migrants have benefited from the project and received grant amounts. | There has been increase in the number of beneficiaries compared to the initial planning. | Data from local communities, Project Reports
Baseline: 0
Planned Target: 50 HHs with seasonal labour migrants 100 women and elderly persons in vulnerable situations
Indicator 2.2.1b: Number of businesses/ persons benefiting from financial and technical assistance through the JP (data collected disaggregated by age and sex) | 5 Industrial companies, 1000 employees 101 SMEs owned/managed by: unemployed women aged 50-63, abused women, disabled women, women with disabled children, single mothers, rural women, 63 and older women and men, persons having 63 and more aged family members, Alternative Scoring Model has been designed to improve access to finance for SMEs and Microenterprises which do not have credit history required by Financial Institutions to provide capital/debt. This can be used also to identify the eligible candidates for grants provided by development institutions. | Initially, during the project preparation and approval stages, based on discussions with the representatives of the Ministry of Health, it was planned to involve 10 companies to produce: face masks, disposable medical shoes, medical uniforms and bed linen. Among these 10 companies: 2 were going to focus on production of medical uniforms, 3 companies were going to work on production of bed linen, 3 footwear companies were ready to get involved in production of medical disposable shoes and other two companies were going to set production of face masks. Planning and development of objectives were projected based on the initial project plan. Following the approval of the Project document, in July 2020 the project representatives had a meeting with the Ministry of Health to identify and finalize the types of PPE products needed, as anticipated by Project Document. At the meeting with the representatives of Ministry of Health, the Deputy Minister stressed out medical uniforms and bedlinen as a priority need in bigger quantities, informing of the recent supply of sufficient number of shoes and face masks. Eventually, the number of companies and employees to be engaged changed accordingly to meet the actual needs as requested. This accounts for the change in the number of companies directly involved in the production of the requested items. So the number of participating enterprises was reduced from 10 to 5, leaving out the face mask and footwear producers and keeping only the companies dealing with the production of medical bed linen and uniforms. Accordingly, the number of employees also decreased from 2 000 to 1 000. This change resulted in 50% decrease in our initial target . Despite the fact that the number of enterprises and employees involved decreased, the remaining five companies and 1 000 employees (95% are women) involved got the possibility to produce more items and ensure longer employability for their employees, thus more income for their families. | Ministry of Economy reports; Data from the beneficiary companies; Project reports
Baseline: 0
Planned Target: 10 industrial companies, including 2000 employees 100 MSMEs
Indicator 2.2.1c: Number of forecasting scenarios developed in agricultural sector for improved COVID-19 response planning and targeting (beneficiaries disaggregated by age and sex) | 14 scenarios are modelled for the agricultural sector for effective planning and targeting of COVID-19 support/recovery activities. | Due to the escalation of hostilities in Nagorno Karabakh and the risk of political instability, the project implementation was delayed, however, it is now duly completed within the extended lifetime of the project, | Ministry of Economy reports, Reports with 14 scenarios (it was 3 scenarios in the initial projetc proposal).
Baseline: 0
Planned Target: 3 forecasting scenarios
Please include all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field | MEDIA COVERAGE
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Source: https://www.un.am/en/agency/UNIDO
Short movie describing the project concept, implementation process and outcomes
https://youtu.be/0-2jywcBarg
Media Coverage
1. www.facebook.com/UNArmenia/posts/4034591949933176
2. www.facebook.com/UnidoArmeniaLightIndustry/posts/2990589774503104
3. www.facebook.com/UNArmenia/posts/3737453749646999
4. www.facebook.com/UnidoArmeniaLightIndustry/posts/2924272907801458
5. www.facebook.com/UnidoArmeniaLightIndustry/posts/2909944675900948
6. https://twitter.com/UNIDOInnovation/status/1374044374380781571?s=20
7. https://twitter.com/armenia_unido/status/1333336959817805826?s=20
8. https://twitter.com/UNArmenia/status/1382305322468061192?s=20
Links to the photos depicting production processes and testimonial videos
https://drive.google.com/drive/folders/1jSumaVK5BzZfn9BDMGDRQQwtzvgThTZc?fbclid=IwAR3RB_q2GP6VWPoS-UWrfQnefIWelzgfcda6EEg0D7rJ5QPSs9QvGXoM4qA
https://drive.google.com/drive/folders/1W6NBfeVYRLRG3t-2ceFc5RuRb7sguGoe?fbclid=IwAR31f3MYJ58DO4s8O3keVsnmbDDxPFsBOg7zlbNEQKgHPssr-VkUUotJlNI | Source: www.facebook.com/UnidoArmeniaLightIndustry
Source: www.facebook.com/UnidoArmeniaLightIndustry