## Sheet1
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | UNFPA | UN Women | Total | Percent of budget for each output reserved for direct action on gender eqaulity (if any): | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs) | expenditure/ commitments in USD
OUTCOME 1: The needs and priorities of young men and women and provisions for youth inclusion are articulated in the peace agreement and post-conflict stabilization, relief and recovery plans
Output 1: | Young men and women are equipped to engage and participate actively in Track II dialogues, including in online dialogues.
Activity A1.a.1: | Conduct baseline assessment in six governorates | 35000 |  | 35000 | 50% | 100% |  | 35000
Activity A1.a.2: | Contextualize existing TOT gender-sensitivity and conflict-sensitivity training materials for political engagement of Yemeni youth and pilot traning materials in in one selected governorate |  | 35000 | 35000 | 50% | 100% |  | 35000
Activity A1.a.3: | Conduct TOT training of young men and women on UNSCR 2250 building their relevant skills in advocacy and communications, consensus building and facilitation skills while applying conflict-sensitive and gender-sensitive approaches | 60000 |  | 60000 | 50% | 100% |  | 60000
Activity A1.a.4: | TOT trainees cascade train young people in six governorates in Yemen | 40000 |  | 40000 |  | 100% |  | 40000
Activity A1.b.1: | Map, identify and establish agreements with existing internet cafes in targeted governorates |  | 35000 | 35000 | 50% | 100% |  | 35000
Activity A1.b.2: | Design, disseminate and analyse an online survey nationwide among young women and men about youth priorities in YPS topics , female-only time is made available to participants in internet cafes in the targeted governorates in support with the youth and advocacy consultant |  | 40000 | 40000 | 50% | 100% |  | 40000
Activity A1.b.3: | Activate dialogue fora in existing internet cafes in targeted governorates for a monthly moderated discussion on YPS issues |  | 20000 | 20000 | 50% | 100% |  | 20000
Activity A1.b.4: | Ensure that female-only time is made available to participants in internet cafes in the targeted governorates |  | 5000 | 5000 | 50% | 100% |  | 5000
Total Output 1 |  | 135000 | 135000 | 270000 | 50% |  |  | 270000
Output 2: | A national YPS dialogue structure including Government, UN and civil society is established with clear governance mechanisms and decision-making processes.
Activity A2.1: | Map youth-led CSOs, networks & initiatives at national & local levels in six selected governorates | 24000 |  | 24000 | 50% | 100% |  | 24000
Activity A2.1: | Conduct two workshops with youth leaders to define YPS Alliance governance and work-plan | 40000 |  | 40000 | 50% | 100% |  | 40000
Activity A2.3 : | Conduct six consultation meetings on participation, protection, prevention, partnership, release and reintegration taking into account the current humanitarian context of Yemen and the role of young people: three in the south, three in the north, and regional gatherings, building on lessons learned from the model of the Yemeni Women’s Pact for Peace and Security (YWP). | 100000 | 150000 | 250000 | 50% | 40% |  | 100000
Activity A2.4 : | Develop consultation paper results from the consultation meetings and data collected in the on-line survey about the above topics to advocate with strategic actors in the peace processes including Track I actors |  | 39900 | 39900 | 50% | 100% |  | 39900
Total Output 2 |  | 164000 | 189900 | 353900 | 50% |  |  | 203900
Output 3: | A collaboration between the national YPS dialogue process and youth-led CSOs is established to conduct joint advocacy and communications activities, engaging with additional Track II & III constituencies around inclusive peace.
Activity A3.1: | Develop advocacy & strategic communications strategy with clear mechanism for the alliance engagment with Track I & II & III actors |  | 30000 | 30000 | 50% | 0% |  | 0
Activity A3.2: | Develope YPS and YWP advocacy messages around peacebuilding at the community and national levels | 10000 |  | 10000 | 50% | 100% |  | 10000
Activity A3.3: | Implement advocacy and communications activities in cooperation with the YPS Alliance including dialougues meetings and community mobilization 6 targeted governorates | 110000 | 80000 | 190000 | 50% | 24.21% |  | 46000
Total Output 3 |  | 120000 | 110000 | 230000 | 50% |  |  | 56000
Output 4: | A strategic framework for UNSCR 2250 in Yemen is developed, reflecting the UNSCR 1325 model with the aim to foster political, programmatic, financial and technical support of YPS partners including government, UN agencies and Track I, II & III actors
Activity A4.1: | Produce situation report YPS and the context of stabilization, relief and recovery and identify gaps | 20000 |  | 20000 | 50% | 100% |  | 20000
Activity A4.2: | Establish a Youth Watch Commission consisting of experts from UN Women, UNFPA & young leaders to produce the YPS strategic framework | 50000 |  | 50000 | 50% | 23% |  | 11500
Activity A4.3: | Share project outputs and reports with the Secretary-General’s Progress Study Advisory Board for YPS and global partners, and follow-up feedback | 8000 |  | 8000 | 50% | 0% |  | 0
Activity A4.4: | Convene a regional consultative meeting with young people and relevant UN agencies (OSESGY, ILO, UNDP, OHCHR, etc) to validate the strategic framework | 50000 | 60000 | 110000 | 50% | 3% |  | 3300
Activity A4.5: | Establish youth- and women-led join monitoring mechanism for the implementation of the peace agreement | 20000 |  | 20000 | 50% | 0% |  | 0
Total Output 4 |  | 148000 | 60000 | 208000 | 50% |  |  | 34800
Total Programme |  | 567000 | 494900 | 1061900
Project personnel costs if not included in activities above | Project Manager (100%) | 54000 |  | 54000 |  | 90% |  | 48600
| Country Programme Manager (5%) |  | 19790 | 19790 |  | 0% |  | 0
| Programme Specialist (15%) Programme Specialist (15%) |  | 24250 | 24250 |  | 0% |  | 0
| 2 National UNVs (100%) | 30960 | 30960 | 61920 |  | 95% |  | 58824
Project operational costs if not included in activities above | Communications, miscellaneous | 20000 | 12576.6 | 32576.6 |  | 39% |  | 12704.874
| Travel | 12432.5 | 10000 | 22432.5 |  | 45% |  | 10094.625
| Equipment & furniture | 5000 | 5000 | 10000 |  | 50% |  | 5000
| Security | 10000 | 10000 | 20000 |  | 50% |  | 10000
Project M&E budget | M&E (including M&E visits, Endline assessment ) | 45000 |  | 45000
| Final Evaluation | 40000 |  | 40000
Audit |  | 10000 | 0 | 10000
Total DPMC |  | 227392.5 | 112576.6 | 339969.1 |  |  |  | 145223.499
SUB-TOTAL PROJECT BUDGET: |  | 794392.5 | 607476.6 | 1401869.1
Indirect support costs (7%): |  | 55607.475 | 42523.362 | 98130.837 |  | 58.68% |  | 57581.362
TOTAL PROJECT BUDGET: |  | 849999.975 | 649999.962 | 1499999.937
[6 empty] | Total expense/commitment |  | 767504.861
[6 empty] | Presentage |  | 51.17%
[6 empty] | Gender-responsive Budgeting: |  | 383752.4305