## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting lives of most vulnerable people during COVID-19 | Overall Duration (months) | 6 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 20.05.2020
MPTF Office Project Reference Number: | 121710 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | El Salvador | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNODC | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name: | Silvia Vides
o Title: | Partnership Officer
o Email address: | silvia.vides@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project aims to protect the most vulnerable populations like persons in prisions and reduce the number of patients in health centers during the pandemic, while maintaining access to treatment through home delivery of medicines and supplements. In one hand, the Project has been strengthening both the Ministry of Health (MINSAL) and the Office of Postal Services in El Salvador. MINSAL is implementing a project for the prevention of complications in patients with pre-existing comorbidities through home delivery of medicines because of the COVID-19 pandemic. It is dangerous for this population to be exposed to COVID-19, and even more, that they do not receive their medication. The delivery of the medicines is being done through the El Salvador´s Postal Office. The Postal Office is a first-line government institution and is the terrestrial logistics alternative to face the national emergency and supports the Ministry of Health to distribute the medicine kit. The postal staff is responsible for collecting, classifying, and distributing the material provided by the MINSAL. They mail men and women are the personnel who go to each vulnerable person’s home and delivery their medicine. The delivery of medicines requires special equipment and care. Some of the medications need to be at certain temperature. Here is where the MPTF project “Protecting Lives of the Most Vulnerable Population” has impact. The project has strengthened the alliance between MINSAL and the Postal Office by providing the right elements for the delivery of medicines. This include, refrigerators, coolers, thermometers, including protection wrapping paper and envelopes. Additionally, the project is strengthening the response of the Postal Service Office in their role of identifying women that have or are suffering violence at home. Considering their access to people in their homes for the delivery of medicines, they even have knowledge of the zones and areas where women that suffer violence can go and search for assistance. A campaign has been created with the Postal Service and with the Attorney General´s Office (PGR). This campaign consists on adding a postmark on all the mail received internationally and delivered nationally with a telephone number of the PGR. The PGR is one of the only two government institutions that delivers psychological, crisis and legal attention to women victims of violence. Through this campaign, 20 cell phones were given to the PGR in order to guarantee the delivery of assistance 24/7. Due to the amount of people and demand of the services required by the PGR, changes are being done in their institution in order to comply with biosafety measures to prevent COVID-19. Special cabins are under construction, that will provide a confidential but also a safe space to give assistance to the population seeking their services. In the other hand, with the support of the COVID-19 MPTF programme, 25 prisons were strengthened with medications y first-aid equipment to prevent COVID-19, included women prison. At least, 37190 (women 2789 and men 34401) of people in prisons and 1000 officers were received first-aid equipment. UNODC / UNAIDS / OHCHR supported the design and implementation of the COVID-19 contingency plan in prisons and strengthened the early diagnosis of COVID-19 and tuberculosis follow-up tests, as well as biosecurity measures for staff prisons, for people with HIV. By the end of 2020, 350 officers were trained (152 women, 198 men) on Mandela Rules, gender mainstreaming Bangkok Rules and Human Rights. A comprehensive specialized training syllabus has been drafted by UNODC / UNAIDS / OHCHR and adopted by the Penitentiary School from the General Directorate for Prisons (DGCP). The training syllabus meets the current training needs in human rights and biosecurity. This proposal presents an innovative approach not only to address the spread of the pandemic, but it has proved to be sustainable in the future. The project was very relevant in terms of responding to identified national priority needs relating to both inmates and staff within prison settings, and sustainable development goals in terms of combatting HIV/AIDs and other diseases. Promotion of human rights within prisons and other closed settings was prioritised. Its design and implementation was also relevant to reaching decision-makers and influencing strategic policy, practice and service delivery changes around inmate health and HIV/AIDS in prisons. The project supported the design and implementation of the COVID-19 contingency plan in prisons, to strengthen the early diagnosis of COVID-19 and tuberculosis follow-up tests, as well as biosecurity measures for staff prisons, for people with HIV, it is important to outline two strategic approaches: 1. First Aid and Medical Equipment donated: strengthen early diagnosis of COVID-19 and follow-up tests for tuberculosis, as well as biosafety measures for prisons staff, for persons with HIV, Tuberculosis and LGBTI population deprived of liberty and thus mitigate the impact of COVID 19 to reduce risks of contagion and spread of the virus. Prison staff and health care professionals working in prisons should be acknowledged as a workforce whose functions are essential to the response to the COVID-19 pandemic, and who must receive the necessary education, equipment and support. 2. Specialized Workshops: A comprehensive specialized training syllabus has been drafted and adopted by the Penitentiary School from the General Directorate for Prisons (DGCP). The syllabus will be replicated in 2021.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The direct beneficiaries of the project have been the 61,029 women and 29,117 men, that have chronic illness and have received in their homes their medication. Indirect beneficiaries have been the PGR and the Postal Office, which have improved their services with the equipment and procedures established through the project. In the prisons, the direct beneficiaries (officers trained and updated in biosecurity and international standards) Men: 198 Women: 152 Total: 350 Indirect Beneficiaries / Persons Deprived of liberty Women : 2,789 Men: 34,401 Total : 37,190
3.1 | Results: Outcome Level | Please include outcome level results achieved | • 32,613 Vulnerable popultation recieved their medicines on time through home delivery system. • 532 Women seeked assistance through the PGR call center • 99 Mail men and 51 women were trained in assisting women who are suffering violence • Improved care provided to vulnerable people suffering from other diseases during the COVID-19 emergency • Nº of people in prisons and officers beneficiaries. UNODC trained staff of the General Directorate of Prisons through 8 specialized workshops in human rights and biosafety and biosecurity approaches to restrain/contain and counter SARS-CoV-2/COVID-19. The main objective of the workshops was to expand the knowledge of all the staff in the field of human rights and the application of the Mandela and Bangkok rules, to mitigate the impact of COVID-19, reduce the spread of the virus, reduce the number of infections and knowing how to recognize warning signs and symptoms among prison staff, people deprived of liberty. In this way, visualize and protect the rights of people deprived of liberty with special needs and / or with chronic and infectious diseases (HIV and tuberculosis) without excluding the LGBTIQ population. Additionally, through the project the medical units have been strengthened (with special attention should be paid to women’s health issues, among other things, the prevention of the transmission of HIV to the child of pregnant and nursing mothers, and specialised reproductive health care) with the donation of medical supplies, reagents, tuberculosis test, medicine and personal protective equipment thus, improving the health care to vulnerable people.
3.2 | Results: Output Level | Please include output level results achieved | • 1 Campaign was launched to provide information for women victim of violence. • 13 PGR offices were strengthened with biosafety measures and equipment to better assist vulnerable population • 1 call center established, to assist women victims of gender violence. • Postal Services Office strengthen with equipment that guarantees a safe delivery of medications, as well as with the establishment of internal policy and protocols to assist and intervene in cases of women violence. • Facilitated the alliance among three government institutions working together for vulnerable population. • The strengthened prison system for COVID-19 pandemic prevention and containing UNODC gave technical assistance in the implementation of a COVID-19 contingency plan in prisons, strengthening early diagnosis of COVID-19 and follow-up tests for tuberculosis as well as biosafety measures for prisons staff, for persons with HIV, Tuberculosis and LGBTIQ population deprived of liberty and thus mitigating the impact of COVID 19 to reduce risks of contagion and spread of the virus. By the end of 2020, 62 officers from the dental-medical unit (29 women and 33 men) have been trained and updated in treatment of HIV and Tuberculosis.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The project encountered some challenges, especially in the initial months of implementation. Due to the mandatory quarantine, it has been difficult to supply all the equipment that the MINSAL requires for the home delivery of medicines. This has also happened with the biosafety supplies for the Attorney General´s Office. Suppliers and producers are requiring more days to give all the equipment. In order to catch up, process have been accelerated. Another challenge encountered has been the articulation among the MINSAL and the Postal Service Office. Usually these two institutions do not work together, and each one has different needs. However, a letter of agreement has been signed between to institutions for a better coordination. One of the challenges that the project has encountered regarding its beneficiaries are those related to pregnant women. Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project. During the implementation of the project, two hurricanes hit the Central American region. Even though El Salvador was not affected by the storms, the initial predictions were that it would. This caused for that the government institutions and its personnel, to focus in preparing for a new emergency. This caused a delay in the workshops give to the Postal Services and it required an adjustment in the curricula. However, 151 mail men and women participated and gain knowledge on how they can identify and assist women who are suffering from violence. Delayed in the procurement process due to the lack of supplies of medication or security equipment in the local market: This challenge has been overcome with the close support of the Procurement Office who has facilitated the registration of new vendors specialized in Protection Personal Equipment and Laboratory supplies.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | This project granted the possibility to work with a non-tradition actor such as the Postal Office. For the first time, this institution has been considered as a strategic partner in a UN project. The work that these men and women do, is extremely valuable, not only because of their roles, but because they know the communities and territories. They are able to reach places that are usually not accessible. The mail women and men are assigned to one area for years, which means that they are key actors, who know the community and it is important include them in projects and initiatives for the insight that they can bring. Due to their closeness to homes and families, they can identify different vulnerability profiles, such as women that are suffering from violence in their home. During the COVID-19 pandemic, this Office has not stopped working and providing services. Implementation of this project resulted in the sharing of valuable knowledge with the different actors reached. Key lessons learnt are: proper coordination of quality services can reach target beneficiaries and avoid duplication and built-in exit strategies should be a component of project design to avoid any issues with prison staff turnover. The syllabus designed for the General Directorate of Prisons its a comprehensive and sustainable approach. The main objective of this workshops was to expand the knowledge of all the staff in the field of human rights and the application of the Mandela and Bangkok rules, to mitigate the impact of COVID-19, reduce the spread of the virus, reduce the number of infections and knowing how to recognize warning signs and symptoms among prison staff, people deprived of liberty. In this way, visualize and protect the rights of people deprived of liberty with special needs and/or with chronic and infectious diseases (HIV and tuberculosis) without excluding the LGBTI population, so that they receive education and care with quality and warmth according to their health needs. At the end of the training, officers were trained and updated in the following: • Increased knowledge of international standards for the treatment of Prisoners (Tokyo Rules and Mandela Rules). • Reintegration and socialization measures for Persons Deprived of Liberty with an approach on gender and generational focus. • Increased knowledge in the establishment of Penitentiary Marks • Knowledge of the treatment guidelines for aspects related to the containment of the pandemic • Knowledge of the guidelines for prison conditions • Update in biosafety measures.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project has facilitated new alliances among government institutions. A nontraditional alliance has been between the PGR and the Postal Services. For the first time and through the postal seal, and with UNDP intervention, these institutions have collaborated together in a campaign to prevent women violence and to promote the access of the different services of assistance. With the PGR, new funds applications are being submitted to continue supporting this institution, specially the unit of family, through this project policies and biosafety devices will be installed in their offices. However, they require more assistance due to the demand that the institutions have received by the population. The project strongly supported the development of national networking, collaborations and partnerships. Coordination national levels increased through establishment of steering committees and technical working groups, training provided by multiple specialized institutions (such as Ministry of Health, National Tuberculosis and Respiratory Disease Program Unit and with the Follow-up committee to the Interinstitutional Cooperation Agreement for Health Care for Persons Deprived of Liberty) and improved collective planning between prison staff, prison health services and partners at operational levels. Additionally,UNODC / UNAIDS / OHCHR and the DGCP developed a valuable partnership in order to achieve the main objectives of this project. With this partnership this initiative complied with the regulations and guidelines established by the Government of El Salvador and the World Health Organization to combat COVID-19, as well as the application of the Mandela Rules and the Bangkok Rules.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | One of the challenges that the project has encountered regarding its beneficiaries are those related to pregnant women. Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Amount Committed Description $ 34,599.00 Medical Equipment $ 15,246.50 Personal Protective Equipment $ 48,995.00 Personal Protective Equipment $ 52,910.50 Medicine Purchase $ 1,205.10 Reagents & miscellaneous $ 36,886.00 KIT ZIEHL NEELSON Tuberculosis tests $ 189,842.10

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 36,313 (266 HIV+, 110 women and 156 men) | During the last trimester of 2020, the number of COVID cases fell, and people were picking up their medicines. The target established refered to all the people reached in one year. | MINSAL reports
Indicator: Number of vulnerable people who receive their medication on time, included STD/HIV-AIDS, disaggregated by sex, age, sexual diversity.
Baseline: 0
Planned Target: 77,000 people (34,000 women y 43,000 men)
Output 1.1: Home delivery (MED Express) system implemented | 36313 | There is a varience in the target since the agreement between MINSAL and the Mail Office, expired during the month of October 2020. Deliveries stopped for one month, however medicines were delivered again starting in November. | MINSAL reports
Indicator 1.1.1 a: Number of delivery medication carried out.
Baseline: 0
Planned Target: 61,029 Women & 29,117 Men | 420 (120 female & 300 male)
Indicator 1.1.1 b: Number of people receiving first-aid equipment, disaggregated by sex, sexual diversity and age. |  |  | MINSAL reports
Baseline: 0
Planned Target: 300
Indicator 1.1.1 c: Proportion of women of reproductive age (aged 15-49 years) with access to contraceptive methods | 0 | Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project. | MINSAL reports
Baseline: 0
Planned Target: 3,000
Indicator 1.1.1 d: Number of pregnant women receiving attention to their specific health needs | 0 | Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project. | MINSAL reports
Baseline: 0
Planned Target: 8,600
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2 | a. 25 prisons strengthened through the donation of medicine ($ 52,910.50 ), reagents for detection of Tuberculosis and personal protective equipment b. Over 1000 officers fully equipped with personal protective equipment and receiving first-aid equipment c. 350 officers trained on Mandela Rules, Bangkok Rules and Human Rights |  | No. of first-aid equipment to prevent COVID-19 delivered Nº the courses developed
Indicator 1.2.1: a. 25 prisons strengthened with medications y first-aid equipment to prevent COVID-19. b. Nº of people in prisons and officers receiving first-aid equipment c. Nº of people in prisons and officers trained on Mandela Rules, Bangkok Rules and Human Rights.
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://www.sv.undp.org/content/el_salvador/es/home/presscenter/articles/2020/12/modernas-cabinas-con-bioseguridad-para-atencion-de-audiencias-ju.html
https://twitter.com/pnudsv/status/1333567756197908480?s=21
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board