## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Mitigating the social-economic impact of COVID-19 in Viet Nam on the most vulnerable groups and supporting more resilient policies and systems | Overall Duration (months) | 8
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 18th May 2020
MPTF Office Project Reference Number: | 121617 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Vietnam | Current End date(dd.mm.yyyy) | 2020-12-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNFPA, UNDP, UNWOMEN | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health, Ministry of Agriculture and Rural Development, provincial Departments of Health, Selected existing community-led social enterprises; UNODC, UNAIDS, and Civil Society Organizations.
Report Cleared By
o Name: | Uzumma Erume
o Title: | RCO Economist
o Email address: | erume@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | With UNICEF’s support, a virtual planning workshop was organized with attendance of healthcare managers from the 4 heavily affected provinces of Ninh Thuan, Gia Lai, Kon Tum and Dien Bien. Key activities included trainings for healthcare workers; provision of health and nutrition services for pregnant women, mothers and their children; and provision of water, sanitation and hygiene (WASH) supplies to school, health centers and community. To date, 300 male and female front-line health workers (68 female) have been trained in the provision of integrated health and nutrition interventions. Most notably, approximately, 7,500 pregnant women received antenatal care (ANC) services including iron/ folic/micro-nutrient supplementation; 1,500 mothers and their newborns received post-natal care visits; 1,000 lactating women attended community-based communication sessions and have improved knowledge and skills in breastfeeding; and 4,500 children aged between 6-23 months received multiple micro-nutrient supplementations for prevention of anemia. Water, sanitation and hygiene (WASH) kits and upgrades were provided to 53 schools in Dien Bien, Gia Lai, Kon Tum and Ninh Thuan provinces, 41 bio-sand filtration models were demonstrated in these three communes and used for raising awareness and changing behaviors of the local people on applying effective and innovative ways to treat and store water safety at home. These WASH activities in schools and communities benefitted 21,300 children and 11,300 village people. UNDP provided direct unconditional transfers of 2.2 million VND (approx. US$100) each as well as personnel protective equipment (PPE) to support 600 household businesses (554 ethnic minority women and 46 ethnic minority men led) who are members of cooperatives and livelihoods groups in remote and mountainous rural communes of Ha Giang province. UNFPA supported the Department of Health in 8 vulnerable mountainous provinces (namely Ha Giang, Lai Chau, Bac Can, Son La, Hoa Binh, Cao Bang, Lao Cai and Thai Nguyen) and 3 provinces with a high concentration of migrant workers in industrial zones (Ninh Binh, Thai Binh and Long An) to strengthen capacities of local health system to respond to COVID-19 for ensuring the provision of sexual and reproductive health (SRH) services without disruptions. UNFPA also provided 12 fetus monitors for district hospitals in three mountainous provinces. In addition, UNFPA developed and piloted a smart phone application that enables users to arrange SRH appointments and attend online consultation with health providers, if they are not able to visit health facilities due to the COVID-19 or humanitarian crisis situations. It is estimated that the project support will benefit 210,400 visits for SRH services of which about 12,600 are for maternal health services. UNAIDS and UNODC jointly provided policy and technical support for the introduction of take-home dose methadone to facilitate greater access and adherence to methadone maintenance treatment (MMT) in the context of COVID-19. The pilot project will benefit 2,000 people who inject drugs (PWID) in three pilot provinces in the first year of implementation of 2021.UNAIDS also engaged in communication and advocacy action to deliver information on HIV and related healthcare for PLHIV in the context of COVID-19 through collaboration with the Southern Representative Office of VNP+ and the Sexual Health Promotion Clinic targeting MSM and transgender women in the North.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The main purpose of interventions is to support for continuing provision of essential health nutrition services at community level during the time of COVID-19 outbreak in 132 difficult and disadvantage communes of the four provinces of Dien Bien, Gia Lai, Kon Tum and Ninh Thuan. The direct beneficiaries included: - 7,500 pregnant women access to quality antenatal services and at least 1,500 new born women reached with postnatal home visited, and 1,000 lactating women joint local counselling club on health nutrition. (Indicator 2.1.1.c). - 4,500 children aged between 6-23 months (2,025 female, 2,475 male) reached with multiple micro-nutrient supplementations for prevention of anemia. (Indicator 2.1.1.d). - 8,700 parents/child care givers (1,305 male, 7.665 female) of children under 5 years old reached with communication messages. - 21,300 children in schools and community (9,585 female, 11,415 male) and 11,300 village people. (Indicator 2.1.1.e). Indirect beneficiaries included approximately: -150,000 village people in the project areas who benefited from an increased information on health, nutrition and prevention of the infection and transmission of a COVID-19 outbreak. - 600 household businesses/members of cooperatives and livelihoods groups benefited from unconditional transfers of 2.2 million VND (approx. US$100) each as well as personnel protective equipment. -554 ethnic minority women and 46 ethnic minority men in remote and mountainous rural communes of Ha Giang province who are the members of cooperatives and livelihoods groups in the fields of fabric weaving and sewing, agricultural production and tourism activities. The estimated indirect beneficiaries were 2,700 ethnic minority people in remote and mountainous rural communes of Ha Giang province. Based on monitoring by the project partner as well as household visits, beneficiaries mostly used the project direct transfers to purchase household essential supplies and to sustain and begin recovery of their business activities. - 600 ethnic minority women from 600 households received cash grant which ultimately benefited around 2,520 persons. - 800 ethnic minority people (600 women and 200 men) was raised awareness on violence against women in communications events. - 210,000 visits on SRH attended by project trained providers. - 12,600 women who are ethnic minority migrant workers received maternal health services. - 1,506 PLHIV and other key populations benefited from emergency HIV, STI and related health service support package, daily necessities package, cash transfer and social support. These emergency support packages were developed and delivered in collaboration with VNP+ and the Viet Nam Network of Self-help Groups of Sex Workers (VNSW). The support also included information sessions for sex workers on access to COVID-19 support schemes, social health insurance and available healthcare/HIV/STIs services. A total of 60,514 HIV key populations benefited from additional information and services. Specifically: (i) 564 male and female sex workers (SWs) received daily necessity support package, 142 received cash transfer together with information sessions; (ii) 800 MSM, PLHIV, SWs and PWUDs received health/HIV/STIs emergency services; (iii) 2,000 PWIDs to receive take-home dose methadone from the pilot project; (iv) 1,572 LGBTIQ community members and supporters received information on community initiatives for peer support during COVID-19 outbreak; (v) 57,714 HIV key populations were reached for additional information related to COVID-19, HIV, STIs and other health and social support services through online and in-person channels
3.1 | Results: Outcome Level | Please include outcome level results achieved | All interventions contributed to the program Outcome 1.2. that ensures most vulnerable people in targeted locations continue to access essential health care, nutrition, and WASH services during the pandemic, whilst key livelihood channels are supported before economic recovery begins. The interventions provided by UNICEF, UNFPA and UNODC supported the continuation of essential healthcare, nutrition and WASH services impacting pregnant and lactating women; children, and caregivers. UNODC in particular contributed to strengthening the Ministry of Public Security’s protocol for COVID-19 prevention and control in prisons by incorporating most update UNODC and WHO’s guidelines on COVID-19 preparedness and response in closed settings. Two interim guidelines were issued by the Ministry of Health to guide the provision Methadone Maintenance Therapy Service for people who inject drugs, in line with newest UNODC and WHO’s COVID-19 recommendations on harm reduction and drug treatment services during the pandemic. To date, due to lack of data it was not possible to report on the number of maternal and neonatal deaths in target locations (Outcome indicator 2.1a); and the percentage of CHCs reported contraceptives stock-out in last 6 months (Outcome indicator 2.2a). UNDP and UNWomen enabled 600 of the most vulnerable ethnic minority household businesses (who are members of cooperatives and livelihoods groups in remote and mountainous rural communes of Ha Giang) to maintain their key livelihood channels before economic recovery begins (Outcome indicator 2.3a).
3.2 | Results: Output Level | Please include output level results achieved | The interventions provided by UNICEF, UNFPA and UNODC led to the following output results for outputs 2.1.1; 2.1.2; 2.2.1 and 2.2.2: Pregnant women maintained access to quality antenatal and post-natal services at commune health clinic that included provision free of iron folic supplementation; children aged between 6-23 months reached with a specific intervention with multiple micro-nutrient supplementations for prevention of anemia; parents and child care givers reached with communication messages for improving information and knowledge on maternal and child health nutrition, and prevention of the infection and transmission of COVID-19; and school children having access to clean water during school time. With a purpose to mitigate negative impacts of the pandemic on Methadone Maintenance Therapy (MMT) service which is expanded to all 63 provinces, serving more than 53,000 thousand people who inject drugs (PWID) every day, UNODC provided technical inputs and advices to support Vietnam Authority of AIDS Control (VAAC/MOH) . The latest UNODC and WHO’s guidance on ensuring continuity and effectiveness of harm reduction and drug treatment services during the pandemic were translated and provided in timely manner for incorporation into national guidelines. 20,000 MMT patients in provinces affected by COVID-19 benefited from this intervention. During the same reporting period, UNODC and UNAIDS jointly provided support to VAAC for the introduction of take-home doses of methadone to facilitate greater access and adherence to MMT in the context of COVID-19. MOH has approved the take-home dose methadone pilot project, SOP and training manual, and organized provincial planning and training workshops, all with UN support, in late 2020. The pilot project will benefit 2,000 PWID in the first year of implementation of 2021 and inform national scale up in the coming years. The pandemic has exerted serious negative impacts on access to HIV harm reduction services among people who use drugs as results of social distancing, isolations or travel restrictions. During the second half of 2020, UNODC collaborated with MOH and Ho Chi Minh City University of Medicine and Pharmacy, jointly conducting 3 virtual training on Covid-19 and ham reduction for over 250 CSO members who are working with people who use drug and other populations infected and affected by HIV nationwide. As reported by the local partners, around 15,000 people who use drug have benefited from the UNODC-led trainings and materials support between July and December 2020. The interventions provided by UNDP and UNWomen led to the following output results for output 2.2.3: 600 household businesses who are members of cooperatives and livelihoods groups received additional cash transfers. The direct beneficiaries were 554 ethnic minority women and 46 ethnic minority men in remote and mountainous rural communes of Ha Giang province. 600 ethnic minority women from 600 poor households whose livelihoods were affected by the COVID-19 received USD100 cash grant. The cash grant ultimately benefited around 2,520 persons in the most vulnerable households Lao Cai province, with priority given to female headed households, households with pregnant or breast feeding women, households with children under 2 or older people above 65, and households with people living with a disability. - The cash was provided to the beneficiaries through a financial service providers - the Viet Nam Post Office. This ensured the professional, secure and transparent transfer of cash to recipients. The cash distributions organized at commune offices and during daytime which were convenient and accessible for beneficiaries. The cash was also delivered to households in case they were not able to travel to the distribution point. - The project targeted Bat Xat district which is one of the poorest areas in Lao Cai. It is home to 14 ethnic groups with the poverty rate is 15.09%, much higher than the average provincial poverty rate (8.46%) and average national poverty rate (4%). Ethnic minority women are among the groups that are potentially left behind due to their double vulnerability, being both woman and ethnic minority. - In this area, the main economic activity is agriculture and forestry. Due to limited agriculture land, mostly on terrace fields up on the mountains and a very cold winter, people’s livelihoods rely on a single summer rice crop which does not provide enough food and income for most families. As a result, many people have chosen to migrate to big cities or China to work. Due to the COVID-19, since February 2019, due to the social distancing policies and border closures, all of them had to return to their village and had no alternative jobs and incomes. Hundreds of households are at risk of falling back into poverty. - The cash grant has helped the most vulnerable people going through a difficult time. Households used the USD100 cash to buy rice and food for their family (100%), buy warm clothes (100%) and buy chickens and pigs to raise (50%). - Additionally, the pre-cash distribution showed that there is an increased in tense and violence against women and children in the family. Therefore, UN Women organized communication events on prevention of violence against women and children to increase the awareness of the community on this issue. The communication events were organized in combination with the cash distribution events, through stage-based methods, which attracted 800 people (600 women and 200 men).
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | There were challenges to ensuring timely procurement of supplies for COVID-19 responses. Fast track procurement was applied, saving between 15 and 30 days compared to open bidding, as in the case of WASH procurement by the National Centre for Rural Water and Sanitation (NCERWASS). However, the whole procurement process, from planning, approval and procurement to delivery still took more than two months. Long-term agreements with potential suppliers or pre-positioning of supplies would help to have supplies available within the shortest time and facilitate rapid response. Notwithstanding, open bidding needs to be encouraged wherever possible to ensure transparency and the best price. Government travel restriction, limited meetings/workshops and lockdown in some provinces negatively affected the implementation. Other issues which were more difficult to address directly include a new surge of COVID-19. For instance, the new wave of outbreak affected the organization of a national workshop by UNAIDS in collaboration with VAAC to review the emergency response to ensure undisrupted access to HIV services during the first outbreak. The workshop had to be postponed for two months and utilized a hybrid format of virtual and in-person participation but resulted in more inclusive and much greater attendance from health/HIV authorities at central and provincial levels as well as from HIV affected communities. Challenges related to social stigma and discrimination faced by HIV key populations are complex so constant dialogues were conducted with community leaders to know the needs for timely support is important. UNDP's initial discussions with provincial agencies and provincial Women's Union (implementation partner) indicated they were not confident to apply digital tools for direct transfers to beneficiaries due to unfamiliarity with the proposed approach and concerns over beneficiary capacity and digital access. UNDP arranged a briefing for provincial partners on digital options, visited a sample of beneficiary households and provided online training to provincial, district and commune personnel. As a result, with support from commune personnel all 600 beneficiaries could apply the online digital registration tool for the direct transfer. Regarding the risks noted in the Risk Management Matrix: 1. The prolonged pandemic has had significant impacts on the business activities and income of the beneficiaries supported by UNDP, particularly for businesses reliant on international tourism and cross-border trade with China. The support provided by the MPTF project has been vital during this period. 2. UNDP's activities were not affected by supply shortages. 3. UNDP's implementation was not impacted by social distancing measures; there were no outbreaks reported in the project locations during implementation. 4. Social distancing and lockdown introduced in 2020 caused delays in some training programmes. The Ministry of Health had to adapt the training programs to accommodate the situation so that they can organize the training courses (for instance, to reduce the number of trainers and select large training venue to keep safe distance between participants).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | COVID-19 highlighted the need for virtual approaches to learning and training. Due to COVID-19 travel restrictions and bans on social gatherings, traditional face-to-face training was impossible. At the same time, enhanced awareness, knowledge and skills on hygiene and infection prevention and control were more important than ever before. UNICEF therefore developed and conducted virtual training in these areas for essential workers in the health and education sectors. All courses achieved ratings of over 8.5/10 (from participant satisfaction surveys) and showed significant increases in knowledge between pre- and post-tests. Not only was the training appreciated, it enabled a broader, more inclusive and cost-effective reach to many more frontline workers. Such online training demonstrated great potential to be further utilized in routine programming. UNDP involved the national Social Assistance Department of the Ministry of Labor-Invalids and Social Affairs (MOLISA), who highly appreciated the opportunity to pilot digital registration and payment tools in remote communes with ethnic minority populations. A report on lessons learned has been prepared and will be applied by the Social Assistance Department as part of ongoing cooperation with UNDP on digitalization of national social assistance programmes including regular cash transfers to 3.1 million beneficiaries and emergency programmes such as COVID-19 social protection transfers that reached 14 million beneficiaries in 2020. Community-led initiatives for peer support during and post disease outbreaks proved to be very effective and essential for timely support for the most vulnerable and marginalised people in emergencies. This needs to be further promoted and supported by the UN and Governments. Fast track procurement mechanism could help shorten procurement process to bring vital equipment to prevent transmission of the Covid-19 and facilitate provision of SRH services without disruptions. Overall dissemination of key messages through local media system and social platforms such as Facebook and Zalo is a good way to reach a large amount of targeted population especially during the lockdown.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNICEF has established cooperation and partnership with the provincial health departments and the provincial CDC centres in 4 provinces of Dien Bien, Gia Lai, Kon Tum and Ninh Thuan. This has facilitated the timely planning and implementation of activities and leveraged additional financial support from local government authorities. The MPTF project built on and complemented ongoing ILO, UNICEF, UNFPA and UNDP support to MOLISA through the SDGF Joint Programme on Social Protection. Under the MPTF, UNDP worked with MOLISA to pilot digital tools and training for local personnel in areas considered to be some of the most challenging in the country. The MPTF thus contributed to accelerating digitization of management and service delivery of the national social protection system. UN Women partnered with Lao Cai Women's Union Lao Cai in implementing the project. The project also worked with the Lao Cai Post Office - a professional financial service provider who have a wide network at remote and mountainous areas in Lao Cai province. They are also contracted by the government to deliver cash for beneficiaries under the government social assistance programme. UNFPA found that during implementation the partnership between MOH, CCIHP (local CSO) and the private telecommunication provider had reduced administrative burdens to develop a smart-phone Apps to provide tele SRH services. As a result, for a short period of time, the smart phone App was designed and piloted in two provinces to bring benefits directly to the community. The interventions and support packages for HIV key affected populations were developed and implemented in close partnerships with the national authorities, community networks of people living with HIV and other HIV key affected populations, and UN agencies including UNODC and UNICEF. A national workshop was co-organized with US Government PEPFAR Programme (US President Emergency Plan for AIDS Relief) which is one of the largest donors for the national HIV response. COVID-19 helped create a new way of working including a timely meaningful dialogue, more flexible and more result-oriented approaches to protect lives among HIV key affected populations. The emergency response showed how an equal partnership and complementary roles and interventions between programme managers, service providers and service users can greatly improve programme’s effectiveness and efficiency. During the implementation, implementing partners leveraged additional funding from other donors to provide greater support for HIV key populations. For instance, the VNP+ Southern Representative Office provided additional funds from their “Helping Hands Charity Fund” to provide more inclusive emergency health/HIV support to project beneficiaries. The Sexual Health Promotion (SHP) Clinic matched MPTF funds and US CDC funds to provide more inclusive health/HIV/STI services for their MSM and TGW clients. Partnership with CSO and private sectors are vital to ensure timely provision of health care and GBV services for vulnerable populations during the pandemic.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNICEF conducted an online assessment on the impacts of the COVID-19 outbreak on routine health care services in 4 provinces supported by UNICEF. The findings showed that COVID-19 has had impacts on both delivery of health and nutrition services as well as on the communities’ health seeking behaviours. During the lock-down, the majority of commune health centers (CHCs) experienced disruption of services and decreases in numbers of visitors. The most heavily affected service is immunization, followed by group communications and child growth monitoring. The findings were used for planning and implementation of COVID-19 responses in the 4 provinces. UNDP and UN Women's rapid gender-sensitive assessment of COVID-19 socio-economic impacts conducted prior to the MPTF project confirmed that poor and vulnerable households, household businesses and micro-enterprises targeted by the MPTF project in Ha Giang and Lao Cai provinces, including ethnic minority women, faced disproportionate impacts due to COVID-19. https://www.vn.undp.org/content/vietnam/en/home/library/_covid-19-socio-economic-impact-on-vulnerable-households-and-ent.html Impact of Covid-19 to maternal and family planning in Vietnam (Technical Brief, UNFPA, 2020)
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No major adjustments
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The MPTF project in Ha Giang was implemented in a complementary manner with cash-for-work activities implemented by UNDP in partnership with the Ha Giang Women's Union, supported by the Government of Viet Nam in response to COVID-19. These activities supported different beneficiaries in similar locations (people losing employment due to COVID-19) and piloted the same digital payment tools.

## RBM-Final
Proposal Outcome: Most vulnerable people continue to access the essential health care and nutrition services amid Covid-19 epidemic, whilst key livelihood channels are supported before economic recovery begins | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome Indicator 2.1a: Number of maternal and neonatal deaths in target locations | No maternal death case in target areas reported by MCH/MOH | Due to lack of available data by the reporting time, proxy indicators are presented instead | MOH communication and report
Baseline: not available
Planned Target: No more than 10% increase in the absolute number of maternal deaths
Output 2.1.1: Vulnerable pregnant women (ie those in COVID-19 high risk locations, those residing in remote areas and migrant populations) provided with sexual and reproductive health services.
Indicator 2.1.1a: Level of implementing national guidelines for SRMNCH during the COVID-19 epidemic | Fully implemented throughout the whole country. |  | MOH report
Baseline: 0
Planned Target: Fully in use in 12 high risk locations, in target remote locations and migrant populations
Indicator 2.1.1.b: Percentage of health workers who have received additional training been trained in SRMNCH, appropriate use of PPE and IPC in the COVID-19 incidence context | 100% |  | MOH report
Baseline: 0
Planned Target: 100% (all the planned training courses were organized)
Output 2.1.2: Newborns, children (both boys and girls), and women have continued access to health, nutrition and water and hygienic sanitation (WASH) services especially emergency and life-saving services, adequate diets and to information on services and practices that improve their health and nutritional status.
| 12600 |  | Provincial IECD programme reports; MOH and UNICEF's monitoring reports
Indicator 2.1.1c. Number of pregnant and lactating women in selected provinces who continuously received a full package of pre- delivery, and post-natal care and multiple micro-nutrient supplementation in the context of COVID-19
Baseline: 1,120
Planned target: 10,000
Indicator 2.1.1d: Number of children under 5 years of ageold disaggregated by sex in selected provinces who continuously received essential health, nutrition and WASH services (immunization, post-natal visits for newborns, child grow monitoring, management of acute malnutrition, IYCF counseling and multiple micro-nutrient supplementations, and clean water) in the context of COVID-19 | 4,500 children 6-23 month of age (2,025 girl baby, 2,475 boy babies) reached mutiple micro-nutrient supplementation | The number of children targeted group at the beginning was over estimated | Provincial IECD programme reports and UNICEF's monitoring reports
Baseline: 3,150
Planned target: 5,000 children 6-23 months in 27 project communes
Indicator 2.1.1.e In the context of COVID-19, out of 22,500 children including children in schools, who have access to Infection Prevention and Control WASH package, of which at least 10,000 are girls | 21,500 school children (9,585 school girls, 11,415 boys) |  | Provincial IECD programme reports and UNICEF's monitoring reports
Baseline: n/a
Planned Target: 22,500
Outcome Indicator 2.2a: Percentage of CHCs reported contraceptives stock-out in last 6 months | No contraceptive stock-out at CHC in target areas reported by GOPFP/MOH | Due to lack of available data by the reporting time, proxy indicators are presented instead | MOH communication and report
Baseline:N/A
Planned target: Up to 20%
Output 2.2.1: Tele health mechanism is used to mitigate the impact of restricted movements by pregnant women in target locations
Indicator 2.2.1.a: Percentage of health facilities in the piloted areas able to provide telehealth services | 100% |  | CCIHP report
Baseline: 0
Planned Target: 70%
Output 2.2.2: Vulnerable key populations affected by HIV have continued access to HIV and STI prevention, harm reduction and other social support and referral services for mental health, stigma and discrimination, violence and substance use management.
Indicator 2.2.2a: Number of men and women people in prisons, compulsory education/reformatory centers reached and benefited from additional information and services with the assistance provided under the MPTF in the period of COVID-19. | 110000 |  | Ministry of Public Security's reports
Baseline:0
Planned Target: 100,000
Indicator 2.2.2b: Number of men and women people who use drugs (PWUD) reached and benefited from additional information and services with the assistance provided under the MPTF in the incidence period of COVID-19 | 35000 |  | Ministry of Health's reports
Baseline:0
Planned Target: 20,000
Indicator 2.2.2c: Number of key populations affected by HIV reached and benefited from additional information and services in the context of COVID-19 | A total of 60,514 HIV key populations benefited from additional information and services. |  | Workshop reports, activity reports from implementing partners
Baseline: 0
Planned Target: Total of 10,000 members of key populations reached and benefited from additional information & services
Outcome Indicator 2.3a: Number of poor households and micro-businesses, particularly those led and EM, that can maintain their livelihoods with the assistance provided under the MPTF. | 1200 (600 of each) |  | 1. Partner Reporting from Ha Giang Women's Union and Lao Cai Women's Union 2. Payment reporting from Viet Nam Post and Telecommunications (VNPT) 3. UNDP's household visits to some beneficiaries
Baseline:0
Planned Target:1,200
Output 2.3.1: A minimum of 1,200 poor households and micro-businesses, particularly those led by women and EM provided with additional cash transfers.
Indicator 2.3.1a:A Number of poor households and micro-businesses, particularly those led by women and ethnic minority, that receive additional cash transfer under the MPTF. | 1200 |  | 1. Partner Reporting from Ha Giang Women's Union and Lao Cai Women's Union. 2. Payment reporting from Viet Nam Post and Telecommunications (VNPT) 3. UNDP's household visits to some beneficiaries
Baseline: 0
Planned Target:1200
Please inlcude all three: Baseline, Planned Target and Achieved Targets
Outcome Indicator 2.1:

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://vietnam.un.org/en/102762-solidarity-time-covid-19-healthcare-people-most-affected-hiv
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board