## Work Plan
PBF SECRETARIAT Annual Workplan
Project Title: Strengthening the justice and security sector response to drug trafficking and transnational organized crime to reduce insecurity in Guinea-Bissau (2020-2021)
Resultats | Basline | Activity | 2020 |  |  |  | 2021 |  |  |  | 2019 |  | Responsible Party | Budegt Description | Budget 2020 |  |  | Budget 2021 |  |  | TOTAL
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | UNDP | UNODC | OIM | UNDP | UNODC | OIM
Outcome: Rule of Law and Security Institutions have sustainable capacity to effectively prevent, investigate and prosecute drug trafficking and transnational organized crime contributing to sustaining peace and development
Output 1.1: National security agencies and justice sectors have improved strategic and operational coordination capacity to prevent, investigate and prosecute drug trafficking and transnational organized crime. | [14 empty] | 40000 | 140000 | 40000 | 10000 | 35000 | 25000 | 290000
Indicator 1.1.1: A National Plan to fight DTOC is developed, endorsed and its implementation advanced | Baseline 1.1.1: Absence of an up-to-date integrated and inclusive National Plan to fight DTOC. Target 1.1.1: A National Plan is developed with all the national stakeholders including CSO, endorsed by the national authorities and implemented | A 1.1.1: Support the development and implementation of the National Strategic Plan to counter drug trafficking and transnational organized crime in close collaboration with regional and sub-regional organizations. | [10 empty] | UNODC | Local Consultant Int. Conslultant | 0 | 20000 | 0 | 0 | 10000 | 0 | 30000 | ` | bar: 2020 Q2 to 2021 Q3; 2019 Q1 to 2019 Q2
|  | A 1.1.2: Support the elaboration of an internal strategy to combat corruption and improve transparence within the rule of law institutions | [10 empty] | UNDP UNODC | Local Consultant Int. Conslultant | 30000 | 10000 | 0 | 0 |  | 0 | 40000 | bar: 2020 Q2 to 2021 Q3
Indicator 1.1.2: The legal framework relevant to DTOC is approved and in force | Baseline 1.1.2: Existing laws do not provide an efficient legislative framework to address DTOC Target 1.1.2: 1 law on anti-money laundering 1 law on witness protection are approved. The investigation law is revised; | A 1.1.3: Support the development and implementation of the National Strategic Plan to prevent and protect victims of human trafficking | U/IOM | U/IOM | IOM | IOM | IOM | IOM |  |  | x | x | UNODC OIM | Local Consultant Int. Conslultant | 0 | 10000 | 30000 | 0 | 0 | 20000 | 60000
|  | A 1.1.4: Provide legislative assistance for the review and development of a legal framework to tackle drug trafficking and transnational organized crime | [10 empty] | UNODC | Local Consultant Int. Conslultant | 0 | 35000 | 0 | 0 | 15000 | 0 | 50000 | bar: 2020 Q4 to 2021 Q3
Indicator 1.1.3: Cooperation mechanisms for security and justice are implemented or enhanced at national regional and international level | Baseline 1.1.3: National level: COSIPOL and TCU serve for coordination purpose but have not been active lately. - Regional level: AIRCOP, WACI, GIABA, ARIWNA platforms exist by Guinea-Bissau active participation is limited Target 1.1.4: 2 mechanisms are enhanced 1 at national level and 1 regional level 2 coordination meetings among donors are held and facilitated by the UN to share information on their assistance to rule of law and national security institutions on CDTOC | A 1.1.5: Facilitate discussion sessions with security and justice institutions, key countries (providers and receivers) and organizations to enhance regional cooperation on prevention, investigation and prosecution of drug trafficking and transnational organized crime | [10 empty] | UNODC | Learning Costs Travel | 0 | 15000 | 0 | 0 | 5000 | 0 | 20000 | bar: 2020 Q3; 2021 Q2
|  | A 1.1.6: Develop and enhance existing strategic and operational coordination mechanisms among security and justice sectors, including law enforcement agencies, and judiciary. | [10 empty] | UNODC | Learning Costs Travel | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | bar: 2020 Q1 to 2021 Q3; 2019 Q1 to 2019 Q2
|  | A 1.1.7: Support inter-agency exchange of information and operational coordination among law enforcement agencies and relevant stakeholders on prevention and investigation of transnational organized crime | [10 empty] | UNODC | Learning Costs Travel | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | bar: 2020 Q1 to 2021 Q3
|  | A 1.1.8:Advisory support to the Superior Council for Police and Internal Security Coordination (COSIPOL) as the strategic and operational coordination mechanism of Law enforcement agencies on DTOC that affects internal security of the country. | [10 empty] | UNODC | Learning Costs | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | bar: 2020 Q1 to 2021 Q3
|  | A 1.1.9: Advisory support to the Transnational Crime Unit (TCU) Management Board with oversight responsibility over this specialized Unit designated for criminal-intelligence gathering on DTOC | [10 empty] | UNODC | Learning Costs | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | bar: 2020 Q2
Indicator 1.1.4: Reliable national data on criminal offenses related to drug and human trafficking is available | Baseline 1.1.4: No centralized periodic data or analyses on DTOC is available Target 1.1.: Reliable data and information regarding DTOC are available and shared with relevant actors | A 1.1.10: Enhance capacities of the Ministry of Justice and relevant authorities to produce periodic analysis on data collected on drug and human trafficking |  | U | U/IOM | U/IOM | IOM | IOM | IOM |  | x | x | UNODC OIM | ITC Equip Wkshp | 0 | 10000 | 10000 | 0 | 5000 | 5000 | 30000
|  | A 1.1.11: Support the inspection services and external oversight mechanisms in rule of law institutions. | [10 empty] | UNDP | Travel | 10000 | 0 | 0 | 10000 | 0 | 0 | 20000 | bar: 2020 Q1 to 2021 Q4
Output 1.2: Security and justice sector institutions have improved capacity to effectively investigate, prosecute and adjudicate drug trafficking / transnational organized crime cases | [14 empty] | 325000 | 185000 | 20000 | 115000 | 128000 | 20000 | 793000
Indicator 1.2.1:Training curricula on DTOC are developed and implemented by LEAs | Baseline 1.2.1: Absence of training curricula on DTOC for LEAs Target 1.2.1: Training curricula on DTOC are developed and implemented for LEAs’ training sessions | A 1.2.1: Provide technical assistance to law enforcement agencies to develop training curricula on detection and investigation of drug trafficking and transnational organized crime, as well as on ethics and gender. | [10 empty] | UNODC | Local Consultant Int. Conslultant | 0 | 15000 | 0 | 0 | 15000 | 0 | 30000 | bar: 2020 Q4 to 2021 Q3; 2019 Q1 to 2019 Q2
|  | A 1.2.2: Deliver a Training of Trainers Programme to establish an inter-agency pool of national trainers on detection, investigation and prosecution of drug trafficking and transnational organized crime and provide on-site mentoring during the first cycle of national training delivery | [10 empty] | UNODC | Local Consultant Int. Conslultant Learning Cots Travel | 0 | 30000 | 0 | 0 | 20000 | 0 | 50000 | bar: 2021 Q1 to 2021 Q3
|  | A 1.2.3: Support through capacity building trainings, equipments the mandate implementation of specialized units to combat drug trafficking and transnational organized crime. | [10 empty] | UNDP UNODC | Travel Learning Costs | 25000 | 50000 | 0 | 15000 | 25000 | 0 | 115000 | bar: 2020 Q3 to 2020 Q4
Indicator 1.2.2: Number of drug couriers arrested, prosecuted, charged, judged and detained | Baseline 1.2.2: Limited ability to handle the prosecution of DTOC cases and sentenced couriers are granted suspended sentences. Target 1.2.2: Suspects on DTOC case are prosecuted, sentenced and convicted | A 1.2.4: Strengthening the capacity of the Drug Laboratory within the Judiciary Police to analyze a wider spectrum of narcotics | [10 empty] | UNODC | ITC Equip | 0 | 35000 | 0 | 0 | 15000 | 0 | 50000 | bar: 2020 Q2 to 2020 Q3; 2019 Q1
Indicator 1.2.3: The model police station is expanded | Baseline 1.2.3: There are only two model police stations within the country (in Bairro Militar in Bissau and in Buba in Quinara region). Target 1.2.3: 1 model police station is created in Gabu with involvement of community representatives, including women and youth | A. 1.2.5: Reinforce the security in Bafata detention facility to host the detainees condemn for DTOC cases | [10 empty] | UNDP | Construction ITC Equipement | 40000 | 0 | 0 | 10000 | 0 | 0 | 50000 | bar: 2020 Q1 to 2020 Q2
|  | A. 1.2.6: Support the replication of model police station in close coordination with local community | [10 empty] | UNDP | Construction | 185000 | 0 | 0 | 50000 | 0 | 0 | 235000 |  | 21050 | bar: 2020 Q1 to 2020 Q3
Indicator 1.2.4: Number of border posts refurbished and equipped, number of police officers trained on CDTOC, as well on passengers, documents and goods profiling | Baseline 1.2.4: There are only four refurbished border posts (Djegue, Pirada, Buruntuma and Cuntabane) Target 1.2.4: 4 additional border posts (Cambadju, Cacine, Suzana and Dungal) are refurbished and equipped The LEA staff affected in the border posts are trained, | A 1.2.7: Strengthen criminal investigations and border control services through refurbishment, capacity building and equipment |  |  | U | U/I | U/I | U/ I | U/I |  | X | X | UNDP UNODC OIM | Equipment Learning Costs Construction | 40000 | 25000 | 20000 | 40000 | 25000 | 20000 | 170000
|  | A 1.2.8: Provide technical advisory services and mentoring to the prosecutor’s office to improve its capacity to prosecute crimes related to drug trafficking and transnational organized crime | 2020 Q1: P; 2020 Q2: P; 2020 Q3: P/U; 2020 Q4: P/U; 2021 Q1: U | UNDP UNODC | Int. Consultant Local Consultant Travel | 15000 | 30000 | 0 |  | 28000 | 0 | 73000
|  | A 1.2.9:Extend the development of Case Management System on DTOC to the offices of the Prosecutor General and the courts | [10 empty] | UNDP | ITC Equipment | 20000 | 0 | 0 |  | 0 | 0 | 20000 | bar: 2020 Q1 to 2020 Q2
Output 1.3: Democratic governance and civilian oversight over the security practices and institutions responsible to combat drug trafficking and transnational organized crime is enhanced. | [14 empty] | 0 | 0 | 0 | 85000 | 65000 | 55000 | 205000
Indicator 1.3.1: Enhanced capacity amongst civil society partners to monitor, evaluate and report on results on CDTOC of the security and justice sectors | Baseline 1.3.1: Lack of information sharing and involvement of civil society and communities on the national threat posed by DTOC and response Target 1.3.1: 1 mapping of civil society organizations and key actors engaged in the CDTOC At least 1 community surveillance committee is created in 2 regions with involvement of women and youth At least 1 report on CDTOC is produced by CSOs | A 1.3.1: Convene a series of national consultation and trainings with all leading institutions to clarify the division of labor, mandate and responsibilities among security, justice and civil society actors. | [10 empty] | UNDP | Learning Costs | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | bar: 2020 Q1 to 2020 Q4; 2019 Q1 to 2019 Q2
|  | A 1.3.2: Provide advisory support and dedicated trainings to the new elected legislative, in particular the security, justice and defense committees, to exercise oversight over the security institutions | 2020 Q3: P; 2020 Q4: P/U; 2021 Q1: U; 2021 Q2: U; 2021 Q3: U | UNDP UNODC | Learning Costs |  |  |  | 20000 | 10000 | 0 | 30000
|  | A 1.3.3: Enhance and replicate existing community-oriented practices and networks with a focus on analysis the impact and enhance the response of the justice and security institutions to the needs of vulnerable groups, including women, men, boys and girls | [10 empty] | UNDP | Learning Costs |  | 0 | 0 | 20000 | 0 | 0 | 20000 | bar: 2020 Q3 to 2020 Q4
|  | A 1.3.4: Support to the National Drug Observatory to enhance coordination and cooperation between the Government and civil society in particular youth and women groups and act as a platform of Early Warning mechanism on DTOC | [10 empty] | UNODC | Learning Costs Travel | 0 |  | 0 | 0 | 30000 | 0 | 30000 | bar: 2020 Q3 to 2020 Q4
Indicator 1.3.2: A national communication campaign on the consequences of drug trafficking in the society is organized in consultation with civil society organizations, in particular youth and women groups | Baseline 1.3.2: Beside the political instrumentalism, there is no public debate on the consequence of drug trafficking in the society Target 1.3.2: 1 advocacy strategy on CDTOC The communities are aware of the real risk/ menace of drug trafficking on the social cohesion | A 1.3.5: Strengthen community and national awareness on the risk of drug trafficking and transnational organized crime through awareness raising campaigns engaging women, youth and volunteers’ networks and associations in all the country |  | P/I | P/I |  | P/U/ I | P/I |  |  | X | X | UNDP UNODC OIM | Learning Costs Communications Printing Travel |  |  |  | 25000 | 25000 | 25000 | 75000
|  | A 1.3.6: Support the creation of an early warning system based on existing vigilance committees and CSOs networks in the region for early detection and prevention of possible cases human trafficking | [10 empty] | OIM | Learning Costs Travel Equipment | 0 | 0 |  | 0 | 0 | 30000 | 30000 | bar: 2020 Q2 to 2021 Q2
Project Management | [14 empty] | 125000 | 98500 | 30000 | 200000 | 98500 | 30000 | 582000
Additional personnel costs | [12 empty] | UNDP UNODC OIM | NOB- Project Coordinator SB4 - Finance & Admin Assit UNODC Drug Control and Crime Prevention Officer | 75000 | 88500 | 20000 | 75000 | 88500 | 20000 | 367000 | bar: 2020 Q2 to 2020 Q4; 2021 Q2 to 2019 Q1
Additional Operational Costs | [12 empty] | UNDP UNODC OIM | Connectivity, Office Supplies, Printing, Fuel | 25000 | 10000 | 5000 | 25000 | 10000 | 5000 | 80000 | bar: 2020 Q1 to 2021 Q4; 2019 Q2
Monitoring &Communication budget | [12 empty] | UNDP UNODC OIM | Local Consultant Communications | 25000 | 0 | 5000 | 50000 |  | 5000 | 85000 | bar: 2020 Q1 to 2021 Q4; 2019 Q2
Budget for independent final evaluation | [12 empty] | UNDP UNODC OIM | Local Consultant Int. Conslultant |  |  |  | 50000 |  |  | 50000 | bar: 2021 Q2 to 2019 Q1
[14 empty] | Sub-Total | 490000 | 423500 | 90000 | 410000 | 326500 | 130000 | 1870000
[14 empty] | ISC 7% | 34300 | 29645 | 6300 | 28700 | 22855 | 9100 | 130900
[14 empty] | TOTAL | 524300 | 453145 | 96300 | 438700 | 349355 | 139100 | 2000900
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ongoing or as and when required
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ongoing or as and when required
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ongoing or as and when required

## Sheet1
2018 |  | Output 1.1 |  | Output 1.2 |  | Output 1.3
1. Staff and other personnel | 84000 |  | 84000 | #REF! | #REF! | #REF! | #REF!
2. Supplies, Commodities, Materials | 87500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3. Equipment, Vehicles, and Furniture (including Depreciation) | 76300 | #REF! | #REF! | #REF! | #REF! |  | #REF!
4. Contractual services (including M and E) | 89600 | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
5.Travel (including M and E) | 52500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6. Transfers and Grants to Counterparts | 105000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7. General Operating and other Direct Costs | 52500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! |  | #REF! |  | #REF!
2019
1. Staff and other personnel | 36000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2. Supplies, Commodities, Materials | 37500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3. Equipment, Vehicles, and Furniture (including Depreciation) | 32700 | #REF! | #REF! | #REF! | #REF! |  | #REF!
4. Contractual services (including M and E) | 38400 | #REF! | #REF! | #REF! | #REF! | 25000 | #REF!
5.Travel (including M and E) | 22500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6. Transfers and Grants to Counterparts | 45000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7. General Operating and other Direct Costs | 22500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! |  | #REF! |  | #REF!