## Work Plan
PBF SECRETARIAT Annual Workplan
Project Title: Political Stabilization and Reform through Confidence Building and Inclusive Dialogue (2020-2021)
Output | Baseline | Activity | 2020 |  |  |  | 2021 |  |  |  | 2019 |  | Responisble Party | Budegt Discription | Budget 2020 |  |  | Budget 2021 |  |  | TOTAL
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | UNDP | UNFPA | WFP | UNDP | UNFPA | WFP
Outcome 1: EFFECTIVE AND COORDINATED IN-COUNTRY CONFIDENCE BUILDING MEASURES, DIALOGUE AND MEDIATION INTERVENTIONS FROM ECOWAS, SRSG GOOD OFFICE, CIVIL SOCIETY AND OTHER KEY INTERNATIONAL ACTORS STRENGTHEN POLITICAL STABILIZATION IN GUINEA-BISSAU
Output 1.1: Support ECOWAS-led intervention efforts to foster effective inter-party and political leader dialogue | [14 empty] | 60000 | 30000 | 0 | 30000 | 0 | 0 | 120000 | 4200
Indicator 1.1.1: Intervention Strategy Developed | Baseline 1.1.1: 0 Target 1.1.1: 1 | A 1.1.1: Support the development of an intervention strategy to foster dialogue between political actors in Guinea-Bissau -identification of ECOWAS position - Recruit an expert in international negotiation techniques (mediation advisor) with competence in the geopolitical area to develop a strategy to support ECOWAS mediation - setting up of a virtual conference w/ stakeholders to form a multi-agency task force to elaborate an intervention strategy | [10 empty] | UNIOGBIS UNDP |  | 60000 |  |  | 30000 |  |  |  | 4200 | bar: 2020 Q2 to 2021 Q1; 2019 Q1 to 2019 Q2
Indicator 1.1.2: High level Forum held | Baseline 1.1.2: 0 Target 1.1.2:1 | A 1.1.2: Design and Facilitation of a High-level Forum - Support the multi-agency task-force to design and facilitate a High Level Forum, including confidence building measures amongst stakeholders | [10 empty] | UNFPA |  |  | 30000 | [5 empty] | 0 | bar: 2020 Q1 to 2019 Q2
Indicator 1.1.3: Crisis Management for High Level Actors held | Baseline 1.1.3: 0 Target 1.1.4: 1 | A 1.1.4:Support capacity building of high-level national actors | [12 empty] | 0 | [6 empty] | 0 | bar: 2020 Q4 to 2019 Q2
Output 1.2: Civil Society contributes activities effectively to Political Stabilization | [14 empty] | 39250 | 10000 | 0 | 39250 | 0 | 0 | 88500 | 2747.5
Indicator 1.2.1: Civil Society Crisis Strategy developed that diminished distrust among CSOs and enables them to contribute to stabilization | Baseline 1.2.1: 0 Target 1.2.1: Trust level changes | A 1.2.1: Convene a Civil Society Forum and working meetings to produce a Strategic Plan for Stabilization based on agreed strategies. -Develop a common understanding amongst CSO on key drivers of conflict and peacebuilding priorities (through bottom up dialogue) - Develop and support joint CSO initiatives, also through micro-grants, and recruittment of national consultants/facilitators, aimed at building confidence amongst stakeholders and promoting political dialogue during the coronavirus pandemic (such as the PUN's proposal to create a national pact for a national response to the pandemic, and create capacityes at the local level to participate in decision making related to measures to mitigate the pandemic) -Hold a CSO forum | [10 empty] | UNDP UNIOGBIS |  | 15000 |  |  | 15000 |  |  |  | 1050 | bar: 2020 Q3 to 2021 Q3; 2019 Q1 to 2019 Q2
Indicator 1.2.2: Crisis Management Training for Civil Society held | Baseline 1.2.2: 0 Target 1.2.2: 1 Workshop | A 1.2.2: Enable civil society capacity building in crisis management and conflict resolution skills and method. | [19 empty] | 0 | bar: 2020 Q1 to 2019 Q1
Indicator 1.2.3: Stabilizing Strategies implemented by CSO organizations | Baseline 1.2.3: OCNC negotiation of Stability Pact and Women’s Council Quiet Diplomacy effort Target 1.2.3: 3 CSO groups develop and implement a stabilization strategy in first 9 months of the project | A. 1.2.3: Support Civil Society Stabilizing Strategies - Support the implementation of sound proposals to mitigate the impacts of the pandemics in the findamental rigits of the people (air time, comms company, printing costs) | [10 empty] | UNDP UNIOGBIS |  | 14250 |  |  | 14250 |  |  |  | 997.5 | bar: 2020 Q2 to 2021 Q1
|  | A. 1.2.4: Conduct Baseline Mapping of Stakeholders - recruitment of consultants to conduct mapping (diferent actotrs would require different mapping methodologies) | [10 empty] | UNFPA UNDP | Local Consultant | 10000 | 10000 |  | 10000 |  |  |  | 700 | bar: 2020 Q2 to 2021 Q1
Output 1.3: Support the SRSG Good Offices role to build on and support coordination of dialogue initiatives and enable effective transition to the RC’s Office. | [14 empty] | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 1400
Indicator 1.3.1: # of advocacy meetings held with political parties in efforts to facilitate political agreement on key political disputed issues. | Baseline 1.3.1: 0 Target 1.3.1: 12 | A 1.3.1: Support Coordination of Stability Strategies - provide technical assistance to design an effective coordination strategy and workshops or dialogue forums, including meetings of the High Level Meeting on Reforms - Integrate the COVID-19 emergency situation in the coordination of the international community . Led by the UNRC with UNCT and UNIOGBIS components contribute based on respective portfolios. Setting up an Integrated COVID Response mechanisms for Data collection; Political, and CDTOC, HR, Gender analysis; Outreach; Political initiative for peacebuilding. To orient partners within a common framework, on both political and COVID prevention and crisis response. | [10 empty] | UNDP UNIOGBIS |  | 20000 | 0 | 0 |  | 0 | 0 | 20000 | 1400 | bar: 2020 Q1 to 2019 Q2
Outcome 2: SYSTEMIC REFORMS ADVANCED THROUGH INCLUSIVE PROCESSES (AS SITUPLATED IN THE ECOWAS ROADMAP AND CONAKRY AGREEMENT
Output 2.1: Systemic reforms drafted and approved with effective lobbying, implementation strategies designed, monitoring mechanism established and training and communication strategies undertaken | [14 empty] | 197391 | 20000 | 0 | 122609 | 0 | 0 | 340000 | 20677.1922
Indicator 2.1.1: Draft Reforms laws written with stakeholder input | Baseline 2.1.1: Current draft laws Target 2.1.1: Revised draft laws include stakeholder inputs | A 2.1.1: Support the Reform Unit within the Prime Minister’s Office and the ANPs ad-hoc Parliamentary Commissions and/or other bodies/mechanism created to advance systemic reforms, with specific focus on the three draft reform laws. - recruit experts that can support the process - facilitate knolwedge and best practices sharing | [10 empty] | UNIOGBIS UNDP |  | 50000 |  |  | 50000 |  |  |  | 16590 | bar: 2020 Q3 to 2021 Q3; 2019 Q1 to 2019 Q2
Indicator 2.1.2: National Consultation held on 3 draft law |  | A 2.1.2: Support the organization and facilitation of stakeholder consultations on draft political party, electoral laws and Constitution and their implementation. - organise meetings and conferences for consultation - Support the ad hoc Commission on the revision of the constitution and the commission on the electoral and political parties laws (organization of internal retreats and consultation process) - support CSOs to develop a road map, including measures to participate in official forums (such as the ad hoc commission on the reform of the constitution) - Recruit national consultants and the Faculty of Law to provide technical expertise during the consultation process | [10 empty] | UNIOGBIS UNDP |  | 50000 |  |  | 50000 |  |  |  | 1987.1922 | bar: 2020 Q3 to 2021 Q3; 2019 Q1
|  | A 2.1.3: Enable bottom up advocacy for the design and passage of the draft laws in parliament. - support CSO advocacy activities related to the implementation of the CSO's comon agenda (micro grants) | [10 empty] | UNIOGBIS UNDP |  | 30000 |  |  | 10000 | bar: 2020 Q3 to 2021 Q3
|  | A 2.1.4: Enable media communication and public education/dissemination efforts on reform laws based on a jointly developed Strategic Communication Plan - Recruit a communication specialist to support the elaboration of a joint strategic comm plan - workshop with journalists and CSO's communication officers - production of relevant material for dissemination | [10 empty] | UNIOGBIS UNDP |  | 17391 |  |  | 12609 | bar: 2020 Q3 to 2021 Q4
Indicator 2.1.5 # of regional consultations held to produce thematic reports and # of CSOs members of the Network involved in the organization of those consultation | Baseline 2.1.5: Regional consultations: 20 regional consultations organized with the participation of 4 CSOs Target 2.1.5: Community meetings: 30 regional consultations organized with the participation of 8 CSOs | A. 2.1.5: Support design, establishment and maintenance of a Civil Society Observatory for monitoring of the systemic reforms. - support the set-up of CS network (formalization, creation of a website to publish thematic reports, recomendationa and activities) - Support the network to procuce thematic reports (such as monitoring the implementation of the Emergency measures and their impact on the rights protected by the constitution) -Support regional monitoring activities - | [10 empty] | UNDP UNFPA |  | 50000 | 20000 | [5 empty] | 2100 | bar: 2020 Q1 to 2021 Q4
Output 2.2: CSO stakeholders, government officials and political party leaders supported, and capacities built to enable effective engagement on the three systemic reform processes | [14 empty] | 150000 | 0 | 125000 | 197782 | 0 | 0 | 472782
Indicator 2.2.1.1: Other sources of funding which contribute to the Academy | Baseline 2.2.1: 200,000 Target 2.2.1: 300,000 | A 2.2.1: Develop a replicable and contextualized Training Materials and provide tailored training to the different stakeholder groups that would be engaged in the three systemic national policy processes - set-up an academic board - elaboration of contents - contract of an anchoring institute - Grant to the GB national association of librarians to preserve, catalogue and organize physical and digital originals of public policy documents and studies produced since independance - in-person and online trainings - reach-out planning - elaboration of comm material | [10 empty] | UNDP WFP |  | 100000 |  | 125000 | 147782 | bar: 2020 Q2 to 2019 Q2
Indicator 2.2.1.2: Tailored training held for Stakeholder groups | Baseline 2.2.1.2: 0 Target 2.2.1.2: 5 | bar: 2019 Q1
Indicator 2.2.2: Regional Stakeholder Consultations held | Baseline 1.2.3: 0 Target 1.2.3: 3 regional consultations are inclusive by age and sex (combining 3 regions per consultation) | A. 2.2.2: Support the formation of local and regional advocacy structures - organise regional advocacy meetings - During the coronavirus pandemic, use regional structures to create a common vision and recommendations to mitigare the impacts of the pandemic in the livelohoods of the people. These regional structures can then be developed to hold consultations on regorms. | [10 empty] | UNDP |  | 50000 |  |  | 50000 | bar: 2020 Q1 to 2021 Q4
Output 2.3: Preparations and follow up actions for the National Conference Paths to Peace and Development supported | [14 empty] | 24000 | 0 | 0 | 66000 | 0 | 0 | 90000
Indicator 2.3.1: Diverse Delegates participate in National Conference | Baseline 2.3.1: Target 2.3.1: | A. 2.3.1: Engage Stakeholders and prepare them to participate in the National Conference - organise training workshop - develop and print material - Recruit a consultant to catalogue material from the INEP archive to the be used at the National Conference | [10 empty] | UNIOGBIS UNDP | wksp learning costs travel printing | 14000 |  |  | 6000 | bar: 2020 Q3 to 2021 Q1; 2019 Q1 to 2019 Q2
Indicator 2.3.2: Preparation completed, and model options defined | Baseline 2.2.1.2: 0 Target 2.2.1.2: 5 | A. 2.3.2: Help Prepare the OCNC to facilitate the National Conference - recruit 2 national consultants (one to assist in design and organization and one to examine possible mechanisms that can come out of the conference and draft legal corresponding legal texts) | [10 empty] | UNIOGBIS UNDP | Local Consultant | 10000 | bar: 2020 Q1 to 2019 Q1
|  | A. 2.3.3: Support the development and implementation of a Strategic Communication Plan about the conference. - contract national consultant - develop and oversee the production of material | [10 empty] | UNIOGBIS UNDP | Local Consultant |  |  |  | 20000 | bar: 2020 Q1 to 2021 Q4
Indicator 2.3.4.1: Inclusive and participatory Conference Held and model chosen | Baseline 1.2.3: 0 Target 1.2.3: # and kinds of stakeholder groups that attended the conference agree on a model | A. 2.3.4: Hold the National Conference. - securing of loctation - hold the national conference. | [10 empty] | UNIOGBIS UNDP | DSA WKSP LEARNING COSTS |  |  |  | 30000 | bar: 2020 Q3 to 2021 Q1
Indicator 2.3.4.2: Conference results are gender-sensitive | Baseline 1.2.3: 0 Target 1.2.3: At least 3 recommendation from the Conference address gender specific issues related to reconciliation | A. 2.3.5: Support post conference reporting and the development of a strategic action plan. - elaborate the report of the conf and its strategic action plan - print and disseminate material | [10 empty] | UNIOGBIS UNDP | Printing &Publication |  |  |  | 10000 | bar: 2020 Q3 to 2021 Q1
Project Management | [14 empty] | 295388.46 | 33300 | 22750 | 330388.46 | 33300 | 22750 | 737876.92
Additional personnel costs | [12 empty] | UNDP UNFPA WFP | P3- Project Coordinator SB4 - Finance & Admin Assit | 237000 | 27500 | 15000 | 237000 | 27500 | 15000 | 559000 | bar: 2020 Q1 to 2019 Q2
Additional Operational Costs | [12 empty] | UNDP UNFPA WFP | Connectivity, Office Supplies, Printing, Fuel | 28388.46 | 1800 | 3750 | 28388.46 | 1800 | 3750 | 67876.92 | bar: 2020 Q1 to 2019 Q2
Monitoring &Communication budget | [12 empty] | UNDP UNFPA WFP | Local Consultant Communications | 30000 | 4000 | 4000 | 30000 | 4000 | 4000 | 76000 | bar: 2020 Q1 to 2019 Q2
Budget for independent final evaluation | [12 empty] | UNDP | Local Consultant Int. Conslultant |  |  |  | 35000 |  |  | 35000 | bar: 2020 Q1 to 2019 Q2
[14 empty] | Sub-Total | 786029.46 | 93300 | 147750 | 786029.46 | 33300 | 22750 | 1869158.92
[14 empty] | ISC 7% | 55022.0622 | 6531 | 10342.5 | 55022.0622 | 2331 | 1592.5 | 130841.1244
[14 empty] | TOTAL | 841051.5222 | 99831 | 158092.5 | 841051.5222 | 35631 | 24342.5 | 2000000.0444

## Sheet1
2018 |  | Output 1.1 |  | Output 1.2 |  | Output 1.3
1. Staff and other personnel | 84000 |  | 84000 | #REF! | #REF! | #REF! | #REF!
2. Supplies, Commodities, Materials | 87500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3. Equipment, Vehicles, and Furniture (including Depreciation) | 76300 | #REF! | #REF! | #REF! | #REF! |  | #REF!
4. Contractual services (including M and E) | 89600 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.Travel (including M and E) | 52500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6. Transfers and Grants to Counterparts | 105000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7. General Operating and other Direct Costs | 52500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! |  | #REF! |  | #REF!
2019
1. Staff and other personnel | 36000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2. Supplies, Commodities, Materials | 37500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3. Equipment, Vehicles, and Furniture (including Depreciation) | 32700 | #REF! | #REF! | #REF! | #REF! |  | #REF!
4. Contractual services (including M and E) | 38400 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.Travel (including M and E) | 22500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6. Transfers and Grants to Counterparts | 45000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7. General Operating and other Direct Costs | 22500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! |  | #REF! |  | #REF!