## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Immediate response to sustainable economic reintegration of young women in Chile | Overall Duration (months) | 18
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: | MPTF_00209 | Original End Date (dd.mm.yyyy) | 30.06.2022
Country | Chile | Current End date(dd.mm.yyyy) | 30.06.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, ECLAC, ILO and FAO. | National counterparts (government, private, NGOs & others) and other International Organizations | The Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, the Ministry of Social Development and Family and their different services and programs (Chile Valora, Bolsa Nacional de Empleo, SENCE, Programa Mujeres Jefas de Hogar, Programa de 4 a 7, SERNAMEG, SENAMA), the Production Development Corporation (CORFO), the Ministry of Economy, the Export Promotion Bureau (ProChile), from the Ministry of Foreign Affairs and the Agriculture and the Livestock Development Institute (INDAP) from the Ministry of Agriculture. United Federation of Workers - CUT, the Confederation of Production and Trade - CPC. From the private sector, the WEPs Companies Network, the Global Compact Network, the Companies from the Gender Parity Initiative (IPG), and CPC. Local governments and the different services at a territorial level, in the Municipality of Renca in the Metropolitan Region and the Municipality of Padre Las Casas in the Araucanía Region. The Implementing partners are Innovacien and Fundación Emplea.
Report Cleared By
o Name: | Fabio Bertranou
o Title: | RC ai and ILO Director for the Southern Cone of Latin America
o Email address: | bertranou@ilo.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | This report provides information on the activities conducted during the implementation of the MPTF program in the first quarter of 2021 by the four United Nations agencies and the Office of the Resident Coordinator of the United Nations System in Chile. The initial stage of the project's implementation involved a series of coordination activities between the United Nations System agencies focused on the project's startup. Similarly, a work plan was created to divide and organize the different activities and leverage the installed capacity of each agency. Likewise, the locations in which the training and care services pilot programs will be applied were defined. These locations are highly representative of the target group (women from rural areas, indigenous women, young women, and migrants) and allow articulating the pilot program with previous initiatives that have been taking place in the community based on the conversations held with the Government of Chile. The communes selected are San Pedro de Atacama (Rural) in the northern area, Renca (Urban) in the Metropolitan Area of the central area of the country, and Padre Las Casas (Rural) in the Araucanía region in the south. This period is characterized by the launch of the project's products in which the creation of partnerships with different entities has been predominant. The project has been presented to institutions from the public and private sectors and to workers' organizations and employers, creating a willingness to collaborate to attain the outcomes proposed. These institutions have committed to cooperate with technical and financial resources that contribute to the progress of the project's outcomes. During the first stage of the project, a work team within the United Nations System agencies was established, and implementing institutions were hired for the agreed activities. Especially those institutions in charge of developing the project's web platforms. One of the most important outcomes of the period is launching the MujeresEmplea platform that has reached 2,120 users to date. The permanent involvement and support from strategic partners were also attained. These are the Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, the Ministry of Social Development and Family and their corresponding offices together with INDAP, the United Federation of Workers (CUT), the Confederation of Production and Trade (CPC), the Global Compact Network of Companies, and Pro Chile, an institution from the Ministry of Foreign Affairs that promotes Chilean goods and services in the world, the Production Development Corporation (CORFO) among others which through their authorities and officials participate in the different activities of the program and were also involved in the launching of the MujeresEmplea.org platform.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | During the first quarter of the project's implementation, only those participants who logged into the MujeresEmplea.org platform will be presented to provide information on the number of users who benefited from this information tool. Since its launching, 2,120 new users have been detected, and the site has reported more than 8,200 visits with an average interaction of 2 minutes per visit. In terms of the information on the cities in which users log into the platform. They are mainly from Santiago, with 63.3% of users, followed far by Antofagasta with 2.6% of users. In terms of log in devices, 77.8% of users log in through a smartphone, followed by 21.7% of computer log-ins, and only 0.5% of users do it through a tablet. Users land at the page mainly through a link from another website in 61.5% of the cases; it can be through another portal or a post on social media. 31.5% of users land directly at the website and 7% via a search engine. This indicator is an expression of the work conducted with different partners and associates to increase the reach of the MujeresEmplea platform.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1: Higher employability and economic opportunities to ensure the participation of women, especially young women, in the labor market. Progress The results obtained in this sense are directly related to the development and launching of the MujeresEmplea.org platform that currently has more than 100 job offers, training opportunities, and care services available to all women. The institutions involved in the platform have reported an increase in the number of users in their own platforms and programs. In the meantime, no progress has been made in the outcomes in terms of the women that have undergone training and then accessed the labor market. Outcome 2: Greater access to care services for women, especially for young women, focusing on the heads of the families to destroy the existing barriers for their participation in the labor market. Progress The outcomes achieved are mostly related to the involvement and connection of the different sectors and actors in the country and the different territories to design the care services pilot program at a community level and implement awareness-raising actions promoting joint responsibility in care work and other unpaid domestic chores. Meanwhile, no progress has been made in the outcomes of women who have undergone training and accessed care services. Regarding the global indicators of the United Nations System Plan for Economic Recovery in the Framework of the Pandemic (SERP Plan), the MPTF project contributes to the Third Pillar "Economic Response and Recovery" specifically in the promotion of decent, safe and sustainable labor for women, in supporting sustainable small companies led by women, and promoting entrepreneurship in women of rural areas. In terms of the MPTF and the global indicators, the following stand out: 1. Indicator 3.1: Reinforcement of employment policies and a proper regulatory environment for economic recovery and decent labor, especially in sectors where women are more exposed to COVID. Although the MPTF project is focused on creating a rapid response to the impact of the crisis generating actions that contribute to the labor insertion of women, especially young women, migrants, residents of rural areas, and members of indigenous communities, it also generates evidence to create policies that promote decent labor. Through the training pilot program that aims at providing training and labor insertion opportunities for women of the target population in STEM areas, the objective is to generate evidence that can be used in the future to create policies that promote decent labor in these sectors, also helping to close the digital gender gap. Moreover, the training and certification activities of women that belong to the caregivers' network move in line with the improvement of work conditions for women towards decent labor conditions. In addition, considering that one of the most frequent barriers in the participation of women in the workforce is their unpaid care and housework responsibilities, the actions with the public sector to design a strategy to coordinate the existing services at a community level and provide a fast implementation solution, are initiatives that, if successful, can be easily replicated and even set the basis to design a more integrated care services system. The articulated work with public institutions, especially the Ministry of Women and Gender Equity and the Ministry of Labor and Social Security, and the Ministry of Social Development, allows for socializing these experiences to move towards a workplace with more favorable conditions for women. 2. Indicator 3.2: Number of companies from the private sector and workers from the formal and informal sectors supported during and after the COVID-19 pandemic. In this global indicator, the MPTF project works with women entrepreneurs providing training opportunities in several areas. One of them is the incorporation of their businesses and facilitating their positioning as vendors for more demanding markets (large companies), promoting the growth of their businesses. In a second stage, with the involvement of ProChile, even reach international markets. Progress is being made by providing training to many women, giving them access to better work conditions and formal job opportunities in some cases. In this line, the certification process for caregivers will allow them to obtain certifications for their jobs and care services.
3.2 | Results: Output Level | Please include output level results achieved | Outcome 1.1 An integrated platform aimed at women's employability, connecting supply and demand. Progress Creation and startup of the "MujeresEmplea.org" platform (https://www.mujeresemplea.org/) that includes job offers, training and entrepreneurship opportunities, and care services. The MujeresEmplea.org platform was launched online on June 22, 2021. This event, hosted by UN Women, was attended by high authorities such as the Minister of Women and Gender Equity, the Undersecretary of Labor, the Resident Coordinator of the United Nations System in Chile, the Director of the ILO Office for the Southern Cone of Latin America, the FAO Representative in Chile, the Director of the Division for Gender Affairs of ECLAC, and the Coordinator of UN Women Chile along with more than 100 people. It is important to emphasize the inter-agency partnerships made to design and incorporate offers within the platform that made its implementation possible. Public, private, and civil society institutions have made an outstanding commitment to become part of this project. The platform was designed in a participative and inclusive manner with the different actors involved, and one of the first steps taken was to review the content that could be included in it. It is a user-friendly platform intended for women, compatible with all Internet browsers, and can be accessed via mobile devices (smartphones, tablets) and computers. To articulate and organize the existing offers intended to facilitate women's access into the labor market, a series of new offers have been posted on the website. These are updated according to their category and the creation of new partnerships. The contents are constantly being updated. It must be mentioned that every week the content is updated or that at least three new initiatives are included in the platform. 1. More than 15 online job portals (Bolsa Nacional de Empleo, Mujeres en Obra, Chiletrabajos, Trabajando.com, TrabajandoMujer, Empleos Públicos, Económicos de El Mercurio, Laborum, Somos Empleo, Publipega, Servicio Civil, Trabajos en Obra). 2. Two job fairs, one organized by SENCE and BNE and the second one by CUP (Corporation of Private Universities) that groups 11 universities in the entire country. 3. More than 17 portals on STEM skills training free of charge for women (Kolibri, INFOCAP, CORFO, Banco Estado, SERCOTEC, FOSIS, Microsoft, SENCE, Pymes en Línea, Relink, Tecnipro, OTEC Impulsa*, OTEC Universidad SEK*, OTEC Innovares*, OTEC Good Neighbors*, OTEC Expocursos*, Fundación Chile, Caja de Compensación Los Andes) - OTEC stands for Technical Training Institution. 4. Four institutions related to care services (Chile Atiende, Chile Crece Contigo, Esmiturno.cl, Instituto de Previsión Social.) 5. Information on offers from the State to improve employability, including a series of employment subsidies, information on women's labor subsidy, and the heads of the home program that promotes labor insertion, permanence, and career development opportunities for women with family responsibilities. 6. Four online courses portals from the United Nations Agencies in Chile (ILO, ECLAC, UN Women, and FAO.) A campaign to promote the platform has been created with the support of the United Nations Agencies involved in the Project and the various public and private institutions that are part of the project. The scope of the campaign includes more than 18 appearances in the written press, two television interviews, and posts on the agencies' social media accounts, as described in the following table. Table 1: Scope of Social Media Agency Social Media Posts Reach Interactions UN Women Chile Instagram 5 16,481 599 Instagram (Stories) 14 3,883 - Twitter 21 23,440 124 UN Women (Regional) Facebook 1 662 8 Facebook (Stories) 1 3,018 - Twitter 1 12,316 161 FAO Twitter 1 8,000 147 ILO Southern Cone Twitter 28 16,957 344 Total 72 84,757 1,383 Source: Own, based on social media reports. Secondly, the interconnection between Bolsa Nacional de Empleo (National Job Bank), a department of the Ministry of Labor and Social Security, and the MujeresEmplea.org platform was achieved. According to the reports from the platform, a large percentage of visitors come from a banner posted on BNE's (National Job Bank) website. BNE has committed to publishing the banner permanently every 15 days to create a more significant impact. In addition, the platform has been promoted through BNE's social media. The following table presents the results of the posts made during June. Table 2: Scope of Social Media - BNE Social Media Reach Interactions Instagram 285 295 Facebook 315 6 Twitter 333 14 LinkedIn 13,828 561 Total 14,761 876 Source: BNE social media report, July 2021. The Ministry of Labor and Social Security has agreed to apply filters to make offers targeted at women for the next stage. The filters will be used carefully to avoid discriminating or promoting possible existing gender biases, especially in the areas with a more prominent presence of men, to foster the incorporation of women into these sectors. Third, a partnership between CORFO (Production Development Corporation), ProChile (Governmental Institution in charge of promoting the offer of Chilean exportable goods and services), and the MPTF Project was made to bring together the demand of large Chilean companies and the supply of entrepreneur women, and also to offer training programs that promote women's entrepreneurship. With this in mind, the "Activa Empresarias" platform has been designed. This website is a meeting point for large businesses and women entrepreneurs. One of its future goals is to connect women entrepreneurs with international industries. Up to date, there are 11 trade associations and private companies that are part of the platform coming from the WEPs signatory Companies Network, IPG Companies Network, Global Compact, and CPC, and 50 profiles of women entrepreneurs that will offer their products and services coming from the networks of UN Women (Win-Win Program, Originarias, Tu Oportunidad), CORFO, ProChile, and other programs implemented by agencies. In the future, it is estimated to incorporate more large businesses and 600 entrepreneurs. Similarly, through this partnership with CORFO and ProChile, it was agreed to provide online training to women entrepreneurs to promote their businesses. These services will be implemented through Innovacien, the institution selected for this purpose. The "ActivaEmpresarias" platform continues adding more content. Its official launch is planned for August and will include the participation of government authorities (CORFO, ProChile), the private sector (WEPs Companies Networks, IPG, Global Compact, CPC), and the agencies involved. Meetings are held every week with CORFO and ProChile to develop and sustain this platform. Bilateral meetings are held with companies to incorporate them into the platform, and activities are established to continue adding companies and entrepreneurs to the website. Large companies that are part of the "Activa Empresarias" platform: Medtronic Grupo Bimbo Finning Microsoft Masisa Pfizer Scotiabank Essbio ABB Accenture Dell Source: UN Women MPTF Report. Regarding the socialization of the platform and the conduction of workshops, it has been determined that they will take place in the three priority regions of the project in partnership with their corresponding municipalities, in the framework of the implementation of the training and care services pilot program. These workshops are planned online and simultaneously with several institutions. They will allow to make improvements to the platform and obtain information on the experience of its female users. Outcome 1.2. Setting up a public and private partners network to promote sustainable employment plans for women, particularly for young women at a national and local level. Progress The first implementation period has been marked by the creation of partnerships with several private, public and civil society institutions. Meetings have been held with the Ministry of Women and Gender Equity and the Undersecretariat of Labor. In addition, bilateral meetings have also taken place periodically with the different services and programs from both ministries and the Ministry of Social Development and Family, establishing detailed work plans (Programa Mujeres Jefas de Hogar, Chile Valora, SENCE, Bolsa Nacional de Empleo, and SENAMA). On the other hand, and as mentioned before, strategic partnerships have been made with CORFO and ProChile. In contrast, during this implementation period, the communes that will be part of the pilot program have been selected, and meetings with two of the three selected municipalities, Padre Las Casas, in the Araucanía region and Renca in the Metropolitan region, have taken place. The meeting with the San Pedro de Atacama municipality in the region of Antofagasta is pending due to the recent elections that have implied changes in local authorities. In parallel to creating an Employers Network "on gender equality," an Action and Operation Protocol was developed to be taken into consideration by the companies engaged in this objective. The project has been presented, and meetings have been held with WEPs signatory companies, the Executive Secretary of the Global Compact Network, the Executive Secretary of the Gender Parity Initiative (IPG), and the General Manager of CPC. They all expressed their interest in being part of the project, and lines of action were established. Up to date, 11 companies have joined the Activa Empresarias platform. In addition, three companies from the technology sector and one from the mining sector offered posts for internships to women in the training pilot programs. Efforts are still being made to add more companies to this network and reach more agreements to create more labor insertion opportunities for women, especially for young women. All the partnerships made within the Second Chance Education Program's framework are being used to implement this initiative. An example is an agreement made with the European Southern Observatory (ESO) that offered internship posts in Chile's most traditionally men-led sector for women participating in the project. As part of the transformational recovery measures with gender equality, it has been detected that there is a need to promote inclusive digital transformation processes that incorporate the access of women to digital technologies (digital technology basket) and that also promote women's skills in the use of those technologies to break the socio-economic barriers that they face and improve their economic opportunities. The current context has shown that the effective development of activities such as online learning or remote work requires a high-speed Internet connection and the use of computers or tablets because smartphones can present limitations. The basic digital basket includes devices other than smartphones, such as laptops and tablets. Access to technology by itself does not lead to more economic and social opportunities. The importance that the basic basket has to also promote the use of technology and facilitate the development of an acceptable level of digital skills has been highlighted. The basic digital basket has to be an effective connectivity proposal. During the period, the necessary information to use as a basis to fund the basic basket has been collected, and an evaluation of the mechanisms that could be used for its implementation has been conducted. Outcome 1.3. Training pilot program implemented in technology, entrepreneurship, labor, and women's rights issues to improve women's employment, particularly young women in the labor market. Progress Considerable progress has been made in this product in a coordinated manner between the agencies in charge. A pilot program for training women in technology, labor rights, unionization, and entrepreneurship to improve their employability was designed. This pilot program is available to 400 women, and it is divided into three stages, where one of the first ones is training. For this stage, there is a curriculum with the contents that will be addressed during the process, and then women will enter an internships program in the companies. They will also have an individual mentoring period in parallel. The initial stage for this pilot program is in charge of Innovacien, responsible for the training sessions. The second stage is in charge of Fundación Emplea, who will be in charge of the mentorships and supporting women during the internships and later during their labor insertion. The United Federation of Workers, CUT, and the Confederation of Production and Trade, CPC, constituents of ILO, created their work plans to implement actions within the framework of the project. To implement the Start Your Own Business (SYB) methodology, ILO granted three scholarships to the institutions involved in the project: CORFO, the Municipality of Renca, and to NGO Innovacien so that an official from each institution could obtain training in that methodology. After obtaining their certification, these trainers will teach courses to women entrepreneurs to improve their opportunities and promote decent labor. The work plans of both implementing institutions have been developed, and they include details on the program's curriculum and processes. One of the main challenges during this stage is for the women participating in the program to have access to a computer or laptop to undergo the online training process and the internships since the STEM skills to be developed consider using programs that may be difficult to install on smartphones. In this context, it has been observed that many women do not own a computer or share it with other members of their families. Currently, arrangements are being made so that the companies offering internship positions can also provide access to computers. Similarly, regarding internships, a connectivity subsidy is being considered for the program participants to facilitate their online attendance, if needed by the company. In parallel, coordination with two of the mayors of the selected communes is already in place, and a meeting with the third mayor has been scheduled. The program has presented a slight delay due to the municipal elections of May, which has involved elected leaders taking office on June 28. The work started with the commune of Renca since its mayor was re-elected and because of the availability of his team to work on the project, which in turn has allowed to create a joint work plan for the upcoming months. Currently, there are 15 internship positions for women participating in the pilot program offered by the companies involved in it. The initiatives and programs currently applied by the United Nations System agencies in Chile have been connected with the project to offer its participants new opportunities. They have also been connected with the UN Women Tu Oportunidad and Originarias programs in which training sessions in employability and entrepreneurship are offered. Once the participants complete both programs, they will be able to sign up for the training sessions, mentorships, and paid internships provided by the MPTF project. Output 2.1 A strategy to coordinate existing public and private assistance services was created to facilitate the participation of women, specifically young women, in the labor market and business initiatives. Progress The progress made to facilitate access to care services is the creation of the pilot plan in which a strategy is being designed to apply it in the three communes selected for the program. Progress has been made in mapping and determining the care services that are currently provided in the territories. In this regard, it is essential to point out the difficulties presented by the health crisis and the measures imposed by the authorities in the development of this component. Movement restrictions and the reduced capacity of premises included in the Government's Paso a Paso Plan make it challenging to plan in-person activities due to the uncertainty of the pandemic. The Paso a Paso Plan comprises 4 phases, from lockdown to opening, which depend on a series of health factors that are difficult to predict, and each commune can be in a different phase according to its rates and the status of the pandemic. These phases change every week with a two or four-day notice before applying measures (https://www.gob.cl/pasoapaso/). In this sense, it is difficult to predict the behavior of the pandemic in the country and any possible upcoming waves. However, vaccination rates are favorable and have increased rapidly. In terms of partnerships, meetings have been scheduled with institutions that offer care services. The MujeresEmplea.org platform has included information on care services such as those provided by Chile Crece Contigo and Programa de 4 a 7, and information on financial assistance such as the maternity subsidy, the Basic Solidary Pension, and the Solidary Pension Fund Contributions. Finally, a portal with job offers exclusively for workers of the care services sector. In the same terms, connections have been established with the NODO Platform, a program led by United Nations in Chile, funded by the SDG Fund and that works together with SENAMA (National Service for Senior Citizens) and citizens, whose aim is to achieve the well-being of senior citizens through the use of information technology, incorporating the community aspect (https://plataformanodo.cl/). In addition, this project is conducted, among other communes, in Padre las Casas, allowing to connect care services for senior citizens in that territory. In addition, a series of meetings with SENAMA (National Service for Senior Citizens) have been scheduled to make them part of the care services pilot program. Progress has been made in the arrangements to incorporate all the services and branches in the mapping of the offer at a community level together with the Ministry of Women and Gender Equity, the Ministry of Labor and Social Security, and the Ministry of Social Development and Family. The caregivers' network has already arranged the certification of 300 caregivers from Chile Valora to professionalize their services and improve their conditions towards decent labor. In this context, 20 caregivers living in the communes where the pilot plan will be implemented have been identified. They will be part of the first group of certified women who currently perform these duties in public services without a certification that validates their competencies. Output 2.2 A greater level of awareness was developed to acknowledge and re-distribute unpaid housework and care work and promote co-responsibility between men and women, the State, the market, families, and the community. Progress In the first stage of implementation, an awareness-raising campaign on the shared responsibilities of care targeted at men, women, and young women is being designed to acknowledge and re-distribute unpaid housework and care work and promote the joint responsibility of the State, the market, families, and the communities. Visual material is being created to promote co-responsibility in care and positive masculinities. Also, arrangements are being made to involve the member companies of the Employers Network on Gender Equality in the promotion of assistance co-responsibility policies among workers as one of the central pillars to become part of this initiative. Workshops and participatory dialogues have been postponed for a later stage of the project until a closer relationship with the social organizations present in the territories selected for the pilot programs has been built. Regarding the technical assistance for the Time Use National Survey program, support is being provided regularly to the National Institute of Statistics (INE) to incorporate the module on the use of time within the National Employment Survey in Chile. This support is provided in on-going weekly work meetings between the ILO and the INE team. And finally, the technical assistance initiative for Municipalities will occur near the end of the care services program implementation. It will also consider incorporating the lessons learned and best practices to each municipality to strengthen its continuity at a community level.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The health crisis due to COVID-19 worldwide implies a series of ongoing challenges that have had to be overcome due to mobility restrictions, social distancing, the closing of schools, among other situations that create adverse conditions to conduct in-person activities. The pandemic has made it challenging to schedule the activities for the care services pilot program, where in-person attendance is vital. Socialization workshops have been agreed to take place online during this first stage. However, planning the activities has become difficult due to the volatility of health conditions and the new waves of COVID-19. Another obstacle is the Paso a Paso Plan implemented by the government to face the crisis with strict lockdowns, mobility restrictions, reduced capacity of premises, and changes according to the rates of each commune. Likewise, since the situation is so volatile in the country, the health protocols and initiatives at a community level are either precarious or inexistent. In several cases, in-person activities have migrated to an online modality without a proper plan in place, thus increasing the access gap in women with higher levels of vulnerability. Elections have also taken place in the country this year to choose, among others, local government authorities, which has delayed the work of the pilot program in the communes where new leaders have been elected. Nevertheless, after the authorities took office, coordination work started to conduct the activities. In addition, elections took place in the United Federation of Workers (CUT), which delayed the work plan's design process, however there is an institutional commitment to the project. Third, there has been a challenge to conduct training sessions for the women of the pilot program. This training plan includes activities that must be completed on a computer, and unfortunately, not all participants have one, and if they do many times, they have to share it with other members of their homes. In terms of connectivity, there is also a significant challenge to conduct training sessions and provide assistance because it is necessary to have a good Internet connection. At moments, there are signal problems, or families have limited resources due to the cost involved in Internet plans. Another obstacle that the pilot project has found in the online training sessions is the low availability of time and low concentration levels of the participants. The closing of schools and daycare centers has meant for them to take care of boys, girls, adolescents, and senior citizens while multitasking, which reduces their ability to focus on the content of the training sessions and often hinders their participation. The articulation of all actors has involved a thorough coordination work to carry out the program's activities, which has forced to postpone some launching dates and joint activities, among others. Furthermore, the need to articulate the services offered to women has been observed, either in training areas, job offers, and especially in care services institutions. The latter proves the need to articulate public sector institutions at a national, regional, and communal level to set the basis for the consolidation of a comprehensive support network.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The excellent articulation work between the institutions undertaken during this first semester has revealed a low articulation of public initiatives in the related topics. One of the practices considered innovative is the articulation and coordination between the different programs offered to women. These efforts involve the different public and private institutions in the framework of ongoing initiatives that need to be promoted or improved. The project is implemented very closely with the private sector, paying particular attention to companies to develop initiatives based on actual requirements. In terms of the lessons learned, a broad range of job offers, free training opportunities, and entrepreneurship in several public and private institutions has been identified. The need to gather all the information in one portal that allows collecting more data for women to quickly access a broad range of programs, training sessions, funds, and bids has also been detected. In this respect, the inclusion of filters has been promoted in different public and private institutions for offers primarily aimed at women, taking care of not reproducing gender biases and looking to incorporate women in predominantly men-led sectors, such as with Trabajando Mujeres, and initiative of Trabajando.com and Bolsa Nacional de Empleo. An excellent opportunity to improve the functionalities of the existing employment portals has been detected, promoting the use of filters for women to apply to jobs in traditionally men-led sectors. During the first semester of the implementation stage, it was observed that public and private institutions agree on the diagnosis made on the effects of the pandemic in women, specifically in terms of the delay in the participation of women in the workplace and the overload of house and care work. These conclusions have been translated into a willingness to collaborate in the activities of the program. The mentioned elements have led to an open and fluent collaboration from the institutions with the project.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The creation of strategic partnerships and networks is a vital part of the program. As mentioned before, significant progress has been made in the generation of these public and private networks. National and local governmental institutions and civil society organizations, including workers and employers' organizations. The project is implemented in association with the Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, the Ministry of Social Development and Family and their different services and programs (Chile Valora, Bolsa Nacional de Empleo, SENCE, Programa Mujeres Jefas de Hogar, Programa de 4 a 7, SERNAMEG, SENAMA). The project also includes the participation of other public institutions according to the activities implemented, such as the Production Development Corporation (CORFO), the Ministry of Economy, the Export Promotion Bureau (ProChile), from the Ministry of Foreign Affairs and the Agriculture and the Livestock Development Institute (INDAP) from the Ministry of Agriculture. Also, within the project's scope, a work plan for the constituents of the ILO (United Federation of Workers - CUT) and the Confederation of Production and Trade - CPC) is being implemented. Regarding the "Employers Network on gender equality," the project has the collaboration and commitment from the private sector, the WEPs Companies Network, the Global Compact Network, the Companies from the Gender Parity Initiative (IPG), and CPC. Similarly, to implement the pilot project, currently, it has the support and collaborative work of the corresponding local governments and the different services at a territorial level, especially in the Municipality of Renca in the Metropolitan Region and the Municipality of Padre Las Casas in the Araucanía Region.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Resources have been mobilized in the creation of partnerships to meet the goals of the program. The first corresponds to the commitment of Microsoft to fund a training program for women that participate in the training pilot program (400 women.) And the second is from Chile Valora, which has committed to certify women that are part of the Caregivers' Network (300) that will be created in the framework of the program.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 45.3% |  | INE Quarterly Report June 2021
Indicator: Women's Labor Participation (National): Women in the Work Force (Working+Looking for a Job)/Female Population in working age (National)
Baseline: 43.9%
Planned Target: 48%
Indicator: Women´s participation rate in Labor Market (Araucanía Region) | 36.6%
Baseline: 35.7%
Planned Target: 42.1%
Indicator: Women´s participation rate in Labor Market (Antofagasta Region) | 48.1%
Baseline: 44.6%
Planned Target: 49.8%
Indicator: Women´s participation rate in Labor Market (Metropolitan Region) | 50.09%
Baseline: 44.9%
Planned Target: 50.04%
Output 1.1 | 2120 | To date, it is not possible to identify the age and sex of the users of the platform. So the indicator is only de number of new users in the platform instead of number of Young Women - low income households registered/using the platform | Information collected from Google Analytics
Indicator 1.1.1: Number of users in the platform
Baseline: 0
Planned Target: 70,000
Output 1.2 | 0 |  | Partnership MoU signed and implemented
Indicator 1.2.1: Number of partnerships endorsed by RC and leading agency Reps.
Baseline: 0
Planned Target: 10
Output 1.3 | 0 |  | Reports of the training component of the platform.
Indicator 1.3.1: Number of young low income women trained in technological, labor and women`s right and entrepreneurship areas
Baseline: 0
Planned Target: 2000
Output 1.3 | 0 |  | Reports of the internships component of the platform.
Indicator 1.3.2: Number of young low income women with internships completed.
Baseline: 0
Planned Target: 400
Outcome 2 | 6 | The value of this indicator goes from 2,500 to 20, because in principle it corresponded to jobs in demand and offered on the platform. Now it corresponds to the number of care services included in the platform. It is closer to the reality of available and possible care services established in Chile. | Specific reports of care service cases posted in the platform
Indicator: Number of care service demand and supply posts in the platform
Baseline: 0
Planned Target: 25
Output 2.1 | 0 |  | Copy of agreements uploaded to project M&E reports
Indicator 2.1.1: Number of signed agreements between public and private care service initiatives and the project leading
Baseline: 0
Planned Target: 5
Output 2.2 | 0 |  | Verification and contrasting of project formulation components/parameters and Project M&E reports
Indicator 2.2.1:Number of components of the strategy implemented, including parameters related to campaigns, workshops, polls, and technical assistance delivered at local governments (municipalities and regions)
Baseline: 0
Planned Target: 1
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board