## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Mitigating socioeconomic impact of COVID19 on employment and income of own-account women workers in the informal economy | Overall Duration (months) | 13
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 30.11.2020
MPTF Office Project Reference Number:[2] | 124712 | Original End Date (dd.mm.yyyy) | 31.10.2021
Country | Bolivia (Plurinational State of) | Current End date(dd.mm.yyyy) | 31.12.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | ILO UNDP UNWOMEN | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Productive Development and Plural Economy (MDPyEP) Ministry of Labour, Employment and Social Welfare (MTEPS) Servicio Público de Empleo (SPE) Servicio Plurinacional de la Mujer y la Despatriarcalización (SEPMUD) Confederación de Empresarios Privados de Bolivia (CEPB) Global Compact in Bolivia Central Obrera Boliviana (COB) Inter-American Center for Knowledge Development in Vocational Training (CINTERFOR) CIF-OIT - International Training Centre: Technical Vocational Training Centers Microfinance Institutions Women's organizations Women's workers organisations
Report Cleared By
o Name: | Susana Sottoli
o Title: | UN Resident Coordinator in Bolivia
o Email address: | maria.sottoli@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Progress in Q1 has been achieved in spite of the second wave of the pandemic and beginning of JP activities over the holiday season. Recruitment of personnel within the RUNOs is underway and nearly finalized. It is expected that by February the JP will count on (two with the ILO; 2 with UNDP; and 1 with UN Women), which will ensure: (i) an optimal execution of the financial resources and achievement of the proposed goals; (ii) coordination for the implementation of the Joint Programme; (iii) follow-up and review of products and knowledge generated; and, (iv) coordination of events and activities, among others. In addition, the first study of the Joint Programme, which will produce the necessary knowledge and characterization of the women in the target group, in accordance with the concept note and its outcomes/outputs, is underway. Besides generating knowledge that will aid in the development of public policy, the study will serve to approach potential partners (particularly public institutions) and develop interests on the project and its results, thus enhancing the scalability potential of the Joint Programme. Lastly, given the lack of nationally recognised definitions of the formal and informal Bolivian economy, the partners of the Joint Programme have generated a conceptual framework that will support the measurement of the target population. This will be done by utilizing employment and socioeconomic variables from the Surveys undertaken by the National Institute of Statistics and the informality guidelines provided by the ILO.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | During the reporting period there were no direct meetings with the target population. However, during this period a process was carried out to generate a conceptual framework of criteria and definitions for the targeting of the intervention's participants. In the absence of clear definitions of official categories of the formal and informal sectors in the Bolivian labour market, socio-demographic and socio-economic variables were considered. Special emphasis was placed on employment, using the Continuous Employment Survey and the Household Survey as tools, in addition to statistical definitions provided by the ILO.
3.1 | Results: Outcome Level | Please include outcome level results achieved | No results were achieved at the outcome level during the reporting period.
3.2 | Results: Output Level | Please include output level results achieved | The JP has achieved progress at output level during Q1 reporting period. However, as work is ongoing and requires further engagement with national counterparts, this section outlines activities and progress attained thus far. Output 1.1 Evidence-based knowledge on the characterisation of own-account women workers in the informal economy, for the promotion of targeted public policies and programmes to address their needs in relation to formalization, social protection and co-responsibility for care, has been generated. During the reporting period, the first study of the Joint Programme that will serve in the characterisation of the target group, was started. The study is in accordance with the established criteria of the Joint Programme. Output 1.2. By the end of the Joint Programme, multi-stakeholder dialogue mechanisms with women's organisations, trade unions and the identified strategic governmental institutions, have been established at the regional and/or national level, to support the design of policies and programmes related to the transition to the formal economy of own-account women workers. No results were achieved for this output during the reporting period. Output 1.3. By the end of the Joint Programme, the capacities of governmental institutions and other stakeholders to design and implement policies and programmes related to the care economy, that will support the formalization of own-account women workers, will have been stregnthened." No results were achieved for this output during the reporting period. UN Women is working on identifying an Alliance Partner (grant) to support in the implementation of the activities foreseen for output 3.3. Output 2.1. Studies to identify the emerging and most dynamic sectors of the economy, for the generation of entrepreneurship and labour insertion of women during and after the COVID-19 crisis, have been elaborated. No results were achieved for this output during the reporting period. Output 2.2. Own-account women workers in the informal economy with strengthened capacities that favor their labour insertion and establishment of enterprises, through the transfer of methodologies and tools in entrepreneurship, digitalization, green economy, among others identified in product 2.1, in alliance with institutions of economic empowerment for women, technical and vocational training centers and the Public Employment Service. During the reporting period, the mapping of potential implementing partner institutions was initiated to identify recipients for an implementation of the ILO's women's entrepreneurship methodology "GET Ahead". This activity holds relevance for the JP as it will transfer capacities within national institutions to deliver training for women's economic empowerment. Output 3.1. Inclusive financial and non-financial products and services adapted to the specific needs of women in the target group, generated by the social innovation laboratories. With regard to the progress of outputs 3.1 and 3.2, the qualitative study on the economic autonomy of women owners and owners of micro and small enterprises in Bolivia has been completed, thus outlining the main characteristics that should be included in the financial and non-financial products to be encouraged. At the same time, a survey of information has been initiated to establish which financial products are currently offered by the financial system. Output 3.2. Measures that generate incentives for development finance institutions to design and/or adapt their financial product and services to the needs of own-account women, in alliance with the Bank of Productive Development (Banco de Desarrollo Productivo) and other private or public institutions of the financial sector. Progress for this output were reported in output 3.1. Output 3.3. Women from the target group will have benefited from a financial education programme that improves financial management skills and the sustainability of monetary resources. No results were achieved for this output during the reporting period. UN Women is working on identifying an Alliance Partner (grant) to support in the implementation of the activities foreseen for output 3.3.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | I. Initiation of the Joint Programme in the midst of an electoral process and the establishment of a new government The JP has started activities shortly after national elections. This could have implied significant delays due to the new government restructuring and the implementation of the Government's new development plan (PDES 2022-2025). This problem is been addressed by engaging in new conversations with the elected government to set a course of joint actions. II. Beginning of a second wave of the pandemic in Bolivia The second wave of the COVID-19 pandemic has hit Bolivia in late December and is expected to reach its peak in early February 2021. This has not only increased socioeconomic vulnerabilities for Bolivian women and men, and particularly accrued challenges for the JP's target population; but it has also increased safety and security risks for all JP parties (RUNOs, partners and stakeholders). In this regard, to mitigate risks for implementing partners all face-to-face meetings have been suspended. This has implied engaging with counterparts virutally to ensure commitment and ownership of the JP's activities. Thus far, and in spite of the spread of the pandemic, each RUNO has managed to engage with relevant government and civil society counterparts to discuss the official launch of the JP. This is expected to occur by mid-February.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | No policy, programmatic and/or operational lessons or findings from the programme were generated during the reporting period.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | I. Liaising with newly elected government and implementing partners During the reporting period, discussions were initiated with the Ministry of Productive Development, through its Vice-Ministry of Microenterprise, to share information on the Joint Programme and its scope, which is aligned with the Government's priorities, as stated by the authorities of this institution, which will allow an effective joint work during the implementation period. With the Productive Development Bank, the development of an Impact Monitoring System has been completed, which has the objective of measuring the impacts of credits to MSMEs aimed at mitigating the effects of COVID-19. This system has defined gender indicators, which seek to be the incentive to develop adequate financial products for self-employed women. UN Women is working on identifying an Alliance Partner (grant) to support the organization on its activities within the Joint Program, more specifically working towards these results: By the end of the Joint Program, the capacities of governmental institutions and other stakeholders to design and implement policies and program, related to the care economy, that will support the formalization of own-account women workers, will have been strengthened (Output 1.3). Women from the target group will have benefited from a financial education program that improves financial management skills and the sustainability of monetary resources (Output 3.3).
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNDP has carried out a Socioeconomic Impact Assessment Study on SMEs in Bolivia, which focused its analysis on the productive activities carried out in the economy and their effects on formal and informal employment. Additionally, a qualitative investigation was concluded on the economic autonomy of women owners and owners of micro and small businesses in Bolivia. This study has been carried out within the framework of the SEIA. ILO is currently validating the following studies which will enrich the context-setting activities and baseline generation for the JP: Study on the impact of COVID-19 on employment, informality and enterprises in Bolivia, with policy proposals, gender focus and emphasis on youth. Study on the challenges of social protection and evaluation of the different options to improve the coverage, benefits and sustainability of the system, particularly during COVID-19 and its impacts.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Major adjustments in strategies, targets, key outcomes and outputs did not take place during the reporting period.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | I. Recruitment of personnel for the Joint Programme UNDP has recruited two people who will be responsible for coordinating and executing UNDP-related actions of the Joint Programme, with special emphasis on Result 3 of the intervention, linked to generating access to financial and non-financial services. UN Women is in the process of hiring an International UNV who will be working with the coordination of the MPTF Programme from a gender perspective under the supervision of the Programme Management Specialist. It is expected that the person will join the team as of February 2021. ILO has launched recruitment process for two staff members that will lead the implementation of the JP: 1 NO-A for coordination of the JP and lead the ILO-led activities and 1 G-5 for administrative and financial management in topics related to labour market issues. Recruitment process is expected to finalize by end of Februrary 2021. The recruited personnel will be responsible for among other things: 1) Coordination of the implementation of the Joint Programme. 2) Follow-up and review of products and documents that may be developed in the framework of the implementation of the Joint Programme. 3) Coordination and organization of events and activities within the framework of the Joint Programme. 4) Development of policy documents, knowledge management, proposals, project documents, communication notes and others required in the framework of the implementation of the Joint Programme. 5) Technical, programmatic, and financial monitoring of program implementation. II. Movilización de recursos adicionales UN Women has mobilized 6.6 M USD for the strengthening of women's business capacity with the support of local gender responsive normative frameworks. This project will: 1.Promote the access of vulnerable women small business owners to productive resources, tools and technology to improve their income security and the continuity of their entrepreneurships. 2.Support municipal governments in the implementation of gender-sensitive public policies to increase women entrepreneurs economic opportunities and awareness of their rights. UNDP has mobilized 600.000 USD with the objective of providing women who have lost their jobs, or are in the middle of a layoff as result of the pandemic, through an intelligent platform focused on the worker that includes three main sections: i) Collection of profile data (AI recruitment assistant); ii) Virtual education market driven by peer-topeer mentoring for formal employment and self-employment; and iii) a job search platform. funds that seek to strengthen the results of this joint proposal.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1. By 2022, strategic govermental institutions have designed gender and social public policy proposals and programmes that promote the transition of own-account women workers from the informal to the formal economy, taking into account the care economy, in the cities and sectors identified by the programme.
Indicator 1: Number of public policies or programmes, developed in consultation and coordination with governments, employers, workers and civil society representatives, that promote the effective transition from the informal to the formal economy of own-account women workers, submitted to the government for their enactment and efficent implementation in the sectors and cities identified. | 0/2 | None
Baseline: 0
Planned Target: At least 2
Output 1.1 Evidence-based knowledge on the characterisation of own-account women workers in the informal economy, for the promotion of targeted public policies and programmes to address their needs in relation to formalization, social protection and co-responsibility for care, has been generated.
Indicator 1.1.1: Number of assessments and studies carried out in consultation with government, workers, employers and civil society representatives, to generate reliable and accurate evidence about the target group's situation, needs and characteristics. | 0/2 | None
Baseline: 0
Planned Target: At least 2
Output 1.2 By the end of the Joint Programme, multi-stakeholder dialogue mechanisms with women's organisations, trade unions and the identified strategic governmental institutions, have been established at the regional and/or national level, to support the design of policies and programmes related to the transition to the formal economy of own-account women workers.
Indicator 1.2.1: Number of agreements generated through the multi-stakeholder mechanism with women's organisations, trade unions, and the identified strategic governmental institutions, in order to promote the transition of own-account women workers from the informal to the formal economy. | 0/4 | None
Baseline: 0
Planned Target: At least 4
Output 1.3 By the end of the Joint Programme, the capacities of governmental institutions and other stakeholders to design and implement policies and programmes related to the care economy, that will support the formalization of own-account women workers, will have been stregnthened."
Indicator 1.3.a : Number of public policy proposals for social protection that identify an integral care system under a rights-based approach for own-account women workers, designed by the JP with effective and efficient standards. | 0/1 | None
Baseline: 0
Planned Target: 1
Indicator 1.3.b: Number of own-account women workers of the informal economy who participate in the dialogue spaces for the design and validation of the proposals for public policies and programmes focused on meeting their needs towards formalization, social protection and an integral care system under a rights-based approach. | 0/150 | None
Baseline: 0
Planned Target: 150
Indicator 1.3.c: % of own- acccount young women who participate in the dialogue spaces | 0/30% | None
Baseline: 0
Planned Target: 30%
Outcome 2. By 2022, own-account women workers in the informal sector (in the urban areas of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) will have the skills and abilities that will improve their employability and the generation of enterprises, so that they can access sources of decent work. "
Indicator 2.A. Percentage of own-account women workers identified by the assessment on their characterisation in the informal economy, with strengthened entrepreneurial skills, that have established their own formal business or have joined a formal associative venture through the JP's technical assistance. | 0/40% | None
Baseline: 0%
Planned Target: at least 40%
Indicator 2.B. Percentage of the trained (through 2.A) own-account women workers that have entered the formal labour market through the JP's technical assistance. | 0/30% | None
Baseline: 0%
Planned Target: at least 30%
Output 2.1 Studies to identify the emerging and most dynamic sectors of the economy, for the generation of entrepreneurship and labour insertion of women during and after the COVID-19 crisis, have been elaborated.
Indicator 2.1.1: Number of studies to identify dynamic and emerging sectors in Bolivia with their corresponding skills needs, that are conducive to generate labour market inclusion and the establishment of sustainable formal entrepreneurial enterprises and ventures. | 0/2 | None
Baseline: 0
Planned Target: At least 2
Output 2.2 Own-account women workers in the informal economy with strengthened capacities that favor their labour insertion and establishment of enterprises, through the transfer of methodologies and tools in entrepreneurship, digitalization, green economy, among others identified in product 2.1, in alliance with institutions of economic empowerment for women, technical and vocational training centers and the Public Employment Service.
Indicator 2.2.a: Number of own-account women workers in the target group that have effectively benefitted from entrepreneurship training at the end of the JP. | 0/170 | None
Baseline: 0
Planned Target: at least 170
Indicator 2.2.b: Number of own-account women workers in the target group that have effectively benefitted from skills development training to increase their employability at the end of the JP. | 0/170 | None
Baseline: 0
Planned Target: at least 170
Outcome 3. By 2022, own-account women workers (from the urban areas of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) will have access to financial and non-financial mechanisms adapted to their needs, which will contribute to their formalization."
Indicator 1: Number of own-account women workers (from the urban area of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) that reached access to inclusive and effective financial and non-financial mechanisms adapted to their needs | 0/85 | None
Baseline: NA
Planned Target: At least 85
Output 3.1 Inclusive financial and non-financial products and services adapted to the specific needs of women in the target group, generated by the social innovation laboratories
Indicator 3.1.2: Number of own-account women workers associated in ventures, that have been involved in the fast-prototyped mechanisms, have accessed agile financing for their jobs. | 0/80 | None
Baseline: 1
Planned Target: 80
Output 3.2 Measures that generate incentives for development finance institutions to design and/or adapt their financial product and services to the needs of own-account women, in alliance with the Bank of Productive Development (Banco de Desarrollo Productivo) and other private or public institutions of the financial sector.
Indicator 3.2.1: Number of development finance institutions and commercial banks that have designed and/or adapted financial products and services, adapted to the needs of own-account women workers, based on the incentives developed by the JP. | 0/2 | None
Baseline: NA
Planned Target: 2
Output 3.3 Women from the target group will have benefited from a financial education programme that improves financial management skills and the sustainability of monetary resources.
Indicator 3.3.a: Number of own-account women workers trained in financial management through the financial education program developed by the project. | 0/425 | None
Baseline: 0
Planned Target: 425
Indicator 3.3.b: % of own- acccount young women workers trained in financial management | 0/30% | None
Baseline: 0
Planned Target: 30%
Please inlcude all three: Baseline, Planned Target and Achieved Targets
_ftnref1

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
_ftn1
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
_ftnref1

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board