## Com. Project Delivery UNDP&IOM
Project Number: | 00121078 |  |  |  |  | Title: | Climate Security Project
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | Focus Countries
2019
|  | Q1 | Q2 | Q3 | Q4 |  |  | Dept ID | Budget Code & Description | Total Budget | Expenses As of 30th September , 2021. | Balance Budget
Outcome 1: Country and Regional capacity established and strengthed to address their climate security priorities.
Output 1.1 | Dedicated catalytic local capacity in 3 CANNCC Atoll Nations driving country level project mplementation, dialogue, analysis and direction on critical climate security issues.
Activity 1.1.1 | Building local Capacity by identifying and recruiting country focal points as country ordinators in Tuvalu, Kiribati and RMI |  |  |  |  | UNDP | Kiribati | B0413 | 71400- SC Costs | 37500 | 15990.98 | 21509.02
[6 empty] | UNDP | Tuvalu | B0437 | 71400 - SC Costs | 46000 | 15606.01 | 30393.99
[6 empty] | IOM | RMI | B0415 | 71400 - SC Costs | 100000 | 10324.75 | 89675.25
Activity 1.1.2 | Identify implementation priorities and approach to climate security profiling |  |  |  |  | UNDP | Kiribati | B0413 | 75700 - Learning Costs | 14998 | 2025.17 | 12972.83
[6 empty] | UNDP | Tuvalu | B0437 | 75700 - Learning Costs | 34001 | 2321.46 | 31679.54
[6 empty] | IOM | RMI | B0415 |  | 0
Activity 1.1.3 | Establish long term cross governmental capacity for climate security coordination |  |  |  |  | UNDP | Kiribati | B0413 | 71600 - Travel | 20000 |  | 20000
[6 empty] | UNDP | Tuvalu | B0437 | 71600 - Travel | 20000 |  | 20000
[6 empty] | IOM | RMI | B0415 | 71600 - Travel | 20000 |  | 20000
OUTPUT TOTAL 1.1 | [9 empty] | 292499 | 46268.37 | 246230.63
Output 1.2 | Dedicated facility established to provide high-level dedicated policy advce to atoll nations on climate secuirty on an on demand basis.
Activity 1.2.1 | Provide current support and establish a more permanent support to the Chair of CANCC in form of an advisor and strengthen partnership mechanisms with the UN. |  |  |  |  | UNDP | Kiribati | B0413 | 71200- International Consultant | 51666 |  | 51666
[9 empty] | 71600-Travel | 3334 |  | 3334
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - International Consultant | 66666 |  | 66666
[9 empty] | 71600 -Travel | 3334 |  | 3334
[6 empty] | UNDP | RMI | B0415 | 71200 - International Consultant | 66666 |  | 66666
[9 empty] | 71600 - Travel | 13334 |  | 13334
OUTPUT TOTAL 1.2 | [9 empty] | 205000 | 0 | 205000
Output 1.3 | Co-ordination capacity strengtheened in the Pacific Islands Forum to support the developing regional understanding of climate security and feeding into the Boe Declaration Action Plan
Activity 1.3.1 | Strenthen capacity of Pacific Islands Forum (PIFS) to manage regionally focused activities of the project, foster collaboration amongst key stakeholders in the region, provide support to the country co-ordiantors and feed into releant reporting and decifiosn making processes linkrf to the Boe Declaration and relevant regional and international fora |  |  |  |  | UNDP | Kiribati | B0413 | 71200- International Consultant | 30000 |  | 30000
[9 empty] | 71600 - Travel | 5000 |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 71200- International Consultant | 30000 |  | 30000
[9 empty] | 71600 - Travel | 5000 |  | 5000
[6 empty] | UNDP | RMI | B0415 | 71200- International Consultant | 30000 |  | 30000
[9 empty] | 71600 - Travel | 5000 |  | 5000
OUTPUT TOTAL 1.3 | [9 empty] | 105000 | 0 | 105000
Total Outcome 1 (excluding GMS) | [9 empty] | 602499 | 46268.37 | 556230.63
GMS Costs Apportioned to Outcome 1 | [5 empty] | UNDP |  |  | 75100-GMS | 42174.93 | 3108.85 | 39066.08
TOTAL OUTCOME 1 INCLUDING GMS | [9 empty] | 644673.93 | 49377.22 | 595296.71
Outcome 2: Strengthen ability of key stakeholders in Pacific countries to understand, articulate and mitigate security threats of climate change with a particular focus to atoll nations.
Output 2.1 | 3 country specific Climate Security Profiles developed to identify critical climate security issues as the basis of action ,resource mobilization and advocacy in Kiribati, RMI and Tuvalu, building on the existing assessments.
Acitivity 2.1.1 | Conduct consultation on objectives, focus and purpose of Climate Security Profiles |  |  |  |  | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 10000 |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 10000 |  | 10000
Activity 2.1.2 | Identify gaps in relevant information availability and sources relating to Climate Security in the 3 Pacific Nations |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 5000 |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 5000 |  | 5000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 5000 |  | 5000
Activity 2.1.3 | Design methodology/approach to develop National Climate Security Profiles drawing on the UN Conceptual Approach for Climate Related Security Measurements |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 11000 |  | 11000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 11000 |  | 11000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 11000 |  | 11000
Activity 2.1.4 | Develop 3 National Climate Security Profiles (CSP) - one for each Atoll country . |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 10000 |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 50000 |  | 50000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 50000 |  | 50000
Activity 2.1.5 | Identify and recommend policy and management frameworks (e.g. National Security Policies , Climate Change Profiles) |  |  |  |  | UNDP | Kiribati | B0413 | n/a | 0 | 0 | 0
[6 empty] | UNDP | Tuvalu | B0437 | n/a | 0 | 0 | 0
[6 empty] | IOM | RMI | B0415 | n/a | 0 | 0 | 0
OUTPUT TOTAL 2.1 | [9 empty] | 178000 | 0 | 178000
Output 2.2 | Country focused consultative process and outreach arrangements established in Tuvalu and RMI that help to inform, validate and address and respond to climate change security risks overtime.
Activity 2.2.1 | Building on existing mechanisms to design and reach agreement on country specific collaborative arrangements to support ongoing inclusive dialogue and decision-making processes. (Two meetings in each country, at the beginning and ending of the project. |  |  |  |  | UNDP | Tuvalu | B0437 | 71200- Contractual Service / Consultant | 18000 |  | 18000
[9 empty] | 75700 - Learning Costs / Supplies | 6000 |  | 6000
[9 empty] | 71600 - Travel | 15000 |  | 15000
0
[6 empty] | IOM | RMI | B0415 | 71200- Contractual Service / Consultant | 18000 |  | 18000
[9 empty] | 71600 - Travel | 15000 | 3582.5 | 11417.5
[9 empty] | 75700 - Learning Costs / Supplies | 6000 | 3045.62 | 2954.38
Activity 2.2.2 | Undertake inclusive dialogue and outreach in the relevant focus countries . (eg. country wide inception discussions; thematic focused dialogue and outreach; other innovative ways to engage unique perspectives including diaspora) |  |  |  |  | UNDP | Tuvalu | B0437 | 75700 - Learning Costs / Supplies | 20000 |  | 20000
[9 empty] | 71600 - Travel | 40000 |  | 40000
[6 empty] | UNDP | Kiribati | B0413 | 75700- Learning Costs | 10000 | 2661.33 | 7338.67
[9 empty] | Travel | 15000 | 8985.57 | 6014.43
[6 empty] | IOM | RMI | B0415 | 75700 - Learning Costs | 30000 | 7064.99 | 22935.01
[9 empty] | 71600 - Travel | 30000 |  | 30000
Activity 2.2.3 | Build capacities of local NGO's, CSO, women, youth and community organizationsto effectively engage in the climate change security risk discourse. |  |  |  |  | UNDP | Tuvalu | B0437 | 72600- Grants | 40000 |  | 40000
[6 empty] | IOM | RMI | B0415 | 75700 - Learning Costs | 40000 | 8135.36 | 31864.64
OUTPUT TOTAL 2.2 | [9 empty] | 303000 | 33475.37 | 269524.63
Output 2.3 | Pilot at least 3 initiatives that address an identified climate secuirty priority at country or the community level
Activity 2.3.1 | Establish a criteria and process for the selection of the pilot projects to respond to climate change secuirty related risks, drawing on country level, regional and international expertise on peacebuidling and conflict prevention as well as updated the plans in place. |  |  |  |  | UNDP | Kiribati | B0413 | n/a
[6 empty] | UNDP | Tuvalu | B0437 | n/a
[6 empty] | IOM | RMI | B0415 | n/a
Activity 2.3.2 | Develop and implement at least 3 pilot interventions, at least 1 relevant to each country of Tuvalu, RMI and Kiribati |  |  |  |  | UNDP | Kiribati | B0413 | 72300 - Materials & Goods | 350000 |  | 350000
[9 empty] | 75700 - Learning Costs | 17500 |  | 17500
[6 empty] | UNDP | Tuvalu | B0437 | 72300 - Materials & Goods | 100000 |  | 100000
[9 empty] | 75700 - Learning Costs | 20000 |  | 20000
[6 empty] | IOM | RMI | B0415 | 72600 - Grants | 110000 |  | 110000
OUTPUT TOTAL 2.3 | [9 empty] | 597500 | 0 | 597500
Output 2.4 | Establish a Pacific Climate Security network (PCSN)
Activity 2.4.1 | Review existing relevant formal and informal coordination mechanisms to establish network partnerships and engage in face to face periodic meetings with all stakeholders |  |  |  |  | IOM | RMI | B0415 | 71600- Travel | 23000 |  | 23000
[9 empty] | 75700 - Learning Costs / Supplies | 2000 |  | 2000
Activity 2.4.2 | Develop deep dive assessments on at least one climate fragility issues (issues to be recommended by Pacific Climate Security Network) |  |  |  |  | IOM | RMI | B0415 | 72100 - Contractual Services | 50000 |  | 50000
Activity 2.4.3 | Convene at least one regional dialogue on climate fragility issues with a focus on issues most relevant to Atoll Nations |  |  |  |  | IOM | RMI | B0415 | 71600- Travel | 40000 |  | 40000
[9 empty] | 75700 - Learning Costs / Supplies | 10000 | 115.76 | 9884.24
OUTPUT TOTAL 2.4 | [9 empty] | 125000 | 115.76 | 124884.24
Output 2.5 | A Pacific Climate Security Assessment prepaed and presented, drawing on and feeding back into the UN Conceptual Approach to Climate Related Secuirty Risk Assessments
Activity 2.5.1 | Engagement in dialogue with vulneable groups in communities. |  |  |  |  | UNDP | Kiribati | B0413 | 75700- Learning Costs | 7000 |  | 7000
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Contractual Services | 5000 |  | 5000
[9 empty] | 75700 - Learning Costs / Supplies | 2000 |  | 2000
[6 empty] | UNDP | RMI | B0415 | 75700 - Learning Costs | 7000 |  | 7000
Activity 2.5.2 | Engage leading experts (particularly from Atoll Nations) to support the translation of the global UN Conceptual Approach |  |  |  |  | UNDP | Kiribati | B0413 | 74200- Translation Costs | 10000 |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 74200- Translation Costs | 10000 |  | 10000
[6 empty] | UNDP | RMI | B0415 | 74200- Translation Costs | 10000 |  | 10000
Activity 2.5.3 | Present outcome framework and any associated comprehensive assessments (see output 1.4.ii below) to the Forum Officials Sub-committee on Regional Security |  |  |  |  | UNDP | [5 empty] | 0
Activity 2.5.4 | Identify opportunities to ensure a strengthened regional understanding of climate security is integrated into UN reporting and analysis on the global issue |  |  |  |  | UNDP | [5 empty] | 0
OUTPUT TOTAL 2.5 | [9 empty] | 51000 | 0 | 51000
Total Outcome 2 (excluding GMS) | [9 empty] | 1254500 | 33591.13 | 1220908.87
GMS Costs Apportioned to Outcome 2 | [5 empty] | UNDP |  |  | 75100-GMS | 87815 | 2252.03 | 85562.97
TOTAL OUTCOME 2 INCLUDING GMS | [9 empty] | 1342315 | 35843.16 | 1306471.84
Outcome 3: Atoll Nations and Pacific Island Countries to have stronger targeted advocacy in global for a combating climate change and addressing the root cause of these security threats.
Output 3.1 | Greater awareness and reflection of positions on climate fragility and security for Pacific SIDS and low-lying Atoll Nations in relevant fora.
Acitivity 3.1.1 | Develop agreed country level impactful advocacy strategies associated with the Country Climate Security Profiles |  |  |  |  | UNDP | Kiribati | B0413 | 71300- Local Consultant / Contratual Service - Videographer | 10000 | 3776.62 | 6223.38
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Local Consultant / Contratual Service - Videographer | 10000 |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71300- Local Consultant / Contratual Service - Videographer | 10000 |  | 10000
Activity 3.1.2 | Develop an agreed joint Regional Advocacy Strategy for targeting key fora and events |  |  |  |  | UNDP | Kiribati | B0413 | 71300- Local Consultant / Contratual Service | 3333 |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Local Consultant / Contratual Service | 3333 |  | 3333
[6 empty] | UNDP | RMI | B0415 | 71300- Local Consultant / Contratual Service | 3333 |  | 3333
Acivity 3.1.3 | Support the CANCC to convene and build consensus on their priority climate security challenges |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 9667 |  | 9667
[9 empty] | 75700 - Learning Costs / Supplies | 4000 |  | 4000
[9 empty] | 72400- Comm Equipment | 13000 |  | 13000
[9 empty] | 71300 - Local Consultant / Contractual Service | 3333 |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 9667 |  | 9667
[9 empty] | 75700 - Learning Costs / Supplies | 4000 | 741.37 | 3258.63
[9 empty] | 72400 - Comm Equipment | 13000 |  | 13000
[9 empty] | 71300 - Local Consultant / Contractual Service | 3333 |  | 3333
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 9666 |  | 9666
[9 empty] | 72400 - Comm Equipment | 13000 |  | 13000
[9 empty] | 75700 - Learning Costs / Supplies | 4002 |  | 4002
[9 empty] | 71300 - Local Consultant / Contractual Service | 3335 |  | 3335
Activity 3.1.4 | Design and develop communication products from the Pacific |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 1884 | 1591 | 293
[9 empty] | 72500 - Communications / Supplies | 4004 |  | 4004
[9 empty] | 71500 - UNV | 31001 | 11916.92 | 19084.08
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 1885 | 1636 | 249
[9 empty] | 72500 - Communications / Supplies | 2998 |  | 2998
[9 empty] | 71500 - UNV | 31000 | 11674.78 | 19325.22
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 1883 | 1603.94 | 279.06
[9 empty] | 72500 - Communications / Supplies | 3000 |  | 3000
[9 empty] | 71500 - UNV | 31000 | 13391.15 | 17608.85
Activity 3.1.5 | Support CANCC members and stakeholders to attend key reional events to promote greater awareness of their climate security challenges |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 15000 |  | 15000
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 15000 |  | 15000
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 15000 |  | 15000
OUTPUT TOTAL 3.1 | [9 empty] | 283657 | 46331.78 | 237325.22
Output 3.2 | Identification, moblization and co-ordination of resources fro addressing the unique climate security challlenges of the focus countries.
Activity 3.2.1 | Develop resource opportunity strategies with consultations between Atoll , Pacific Countries and donors for development of climate Security Profiles for focused countries |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 11667 |  | 11667
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 11667 |  | 11667
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 11667 |  | 11667
Activity 3.2.2 | Support government to negotiate the inclusion of he unique climate security considerations of the Pacific in relevance to climate finance, development finance and security finance fora. |  |  |  |  | UNDP | Kiribati | B0413 | 72100- Contractual Services | 15000 |  | 15000
[6 empty] | UNDP | Tuvalu | B0437 | 72100- Contractual Services | 15000 |  | 15000
[6 empty] | UNDP | RMI | B0415 | 72100- Contractual Services | 15000 |  | 15000
OUTPUT TOTAL 3.2 | [9 empty] | 80001 | 0 | 80001
Total Outcome 3 (excluding GMS) | [9 empty] | 363658 | 46331.78 | 317326.22
GMS Costs Apportioned to Outcome 3 | [5 empty] | UNDP |  |  | 75100-GMS | 25456.06 | 2993.26 | 22462.8
TOTAL OUTCOME 3 INCLUDING GMS | [9 empty] | 389114.06 | 49325.04 | 339789.02
Outcome 4: PROJECT MANAGEMENT COSTS
Output 4.1 | Project Management Unit (PMU)
Activity 4.1.1 | Salary for Technical Staff - Professional Technical Staff |  |  |  |  | UNDP | Kiribati | B0413 | 61300 - NP Staff | 151169 | 104530.21 | 46638.79
[6 empty] | UNDP | Tuvalu | B0437 | 61300 - NP Staff | 163831 | 29400.66 | 134430.34
[6 empty] | IOM | RMI | B0415 | 61300 - Staff | 97000 | 31819.99 | 65180.01
[6 empty] | UNDP | RMI | B0415 | 61300 - NP Staff | 55000 | 43666.68 | 11333.32
Activity 4.1.2 | Salary of Technical Staff- Finance & Admin |  |  |  |  | UNDP | Kiribati | B0413 | 71400- SC Staff | 24495 | 13652.72 | 10842.28
[6 empty] | UNDP | Tuvalu | B0437 | 71400- SC Staff | 11836 | 6343.38 | 5492.62
[6 empty] | UNDP | RMI | B0415 | 71400- SC Staff | 23669 | 8466.65 | 15202.35
Activity 4.1.3 | Conduct face to face meetings and monitoring of activites implementation in countries - PMU Travel |  |  |  |  | UNDP | Kiribati | B0413 | 71600-Travel | 11000 | 494.14 | 10505.86
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 12000 |  | 12000
[6 empty] | UNDP | RMI | B0415 | 71600 - Travel | 12000 |  | 12000
Activity 4.1.4 | General Expenses including direct project costs, bills and stationery |  |  |  |  | UNDP | Kiribati | B0413 | 72500- Supplies | 13335 | 4520.31 | 8814.69
[6 empty] | UNDP | Tuvalu | B0437 | 72500- Supplies | 13335 | 1004.99 | 12330.01
[6 empty] | UNDP | RMI | B0415 | 72500- Supplies | 13330 | 1605.49 | 11724.51
Activity 4.1.5 | Computer & Equipment |  |  |  |  | UNDP | Kiribati | B0413 | 72200 - Office Equipment | 5000 | 4999.73 | 0.27
[6 empty] | UNDP | Tuvalu | B0437 | 72200- Office Equipment | 5000 | 5000 | 0
[6 empty] | UNDP | RMI | B0415 | 72200- Office Equipment | 5000 | 1429.45 | 3570.55
Activity 4.1.6 | Safety & Security Clearances |  |  |  |  | UNDP | Kiribati | B0413 | 63500 - Security | 1000 |  | 1000
[6 empty] | UNDP | Tuvalu | B0437 | 63501 - Security | 1000 |  | 1000
[6 empty] | UNDP | RMI | B0415 | 63502 - Security | 1000 |  | 1000
OUTPUT TOTAL 4.1 | [9 empty] | 620000 | 256934.4 | 363065.6
Output 4.2 | Monitoring & Evaluation
Activity 4.2.1 | Conduct a Inception workshop to familiarize all stakeholders on the project objectives and Climate Security |  |  |  |  | UNDP | Kiribati | B0413 | 75700- Learning Costs - Inception Workshop | 3333 | 451.95 | 2881.05
[6 empty] | UNDP | Tuvalu | B0437 | 75700- Learning Costs - Inception Workshop | 3333 | 2195.84 | 1137.16
[6 empty] | UNDP | RMI | B0415 | 75700- Learning Costs - Inception Workshop | 3334 | 666.94 | 2667.06
Activity 4.2.2 | Conduct mid term evaluation to measure progress of project |  |  |  |  | UNDP | Kiribati | B0413 | 71200-International Consultant | 10000 |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200-International Consultant | 10000 |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200-International Consultant | 10000 |  | 10000
Activity 4.2.3 | Conduct a knowledge exchange forum to identify the Pacific nations needs in terms of Climate Security and existing data platforms. |  |  |  |  | UNDP | Kiribati | B0413 | 71600 -Travel | 11666.58 |  | 11666.58
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  | 8333
[6 empty] | UNDP | Tuvalu | B0437 | 71600 -Travel | 11666.58 |  | 11666.58
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  | 8333
[6 empty] | UNDP | RMI | B0415 | 71600 -Travel | 11667.05 |  | 11667.05
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  | 8333
Activity 4.2.4 | Independent Final Evaluation |  |  |  |  | UNDP | Kiribati | B0413 | 71200-International Consultant | 10000 |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200-International Consultant | 10000 |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200-International Consultant | 10000 |  | 10000
OUTPUT TOTAL 4.2 | [9 empty] | 149997.21 | 3314.73 | 146682.48
Total Outcome 4 (excluding GMS) | [9 empty] | 769997.21 | 260249.13 | 509748.08
GMS Costs Apportioned to Outcome 4 | [5 empty] | UNDP |  |  | 75100-GMS | 53899.8047 | 16411.52 | 37488.2847
TOTAL OUTCOME 4 INCLUDING GMS | [9 empty] | 823897.0147 | 276660.65 | 547236.3647
Workplan Total | [9 empty] | 3200000.0047 | 411206.07 | 2788793.9347
0.1285
WORKPLAN
[7 empty] | Kiribati | Tuvalu | RMI - UNDP | RMI- IOM
[6 empty] | First Tranch | 682770 | 651491.57 | 343746.74 | 402500
[6 empty] | GMS @7% | 47793.9 | 45604.4099 | 24062.2718 | 28175
[6 empty] | Total | 730563.9 | 697095.9799 | 367809.0118 | 430675
[6 empty] | 2nd Tranch | 293114.6 | 283393 | 145139 | 188500
[6 empty] | GMS @7% | 20518.022 | 19837.51 | 10159.73 | 13195
[6 empty] | Total | 313632.622 | 303230.51 | 155298.73 | 201695
[6 empty] | TOTALS AWP | 1044196.522 | 1000326.4899 | 523107 | 632370
[6 empty] | Total Funding | 1044196.49 | 1000326.49 | 523107.02 | 632370
[6 empty] | Unprogrammed | -0.032 | 0.0001 | 0 | 0
Performance-Based Tranche Breakdown
[7 empty] | Recipient Organization 1 | Recipient Organization 4 | Tranche %
[7 empty] | UNDP- Kiribati | IOM-RMI
[6 empty] | First Tranche | 730937.54 | 442659 | 70%
[6 empty] | Second Tranche | 313258.95 | 189711 | 30%
[6 empty] | Third Tranche (as required) | $ - | $ -
[6 empty] | Total | 1044196.49 | 632370 | 100%

## Delivery Status UNDP
Project Number: | 00121078 |  |  |  |  | Title: | Climate Security Project
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | Focus Countries
2019
|  | Q1 | Q2 | Q3 | Q4 |  |  | Dept ID | Budget Code & Description | Total Budget | Expenses As of 30th September , 2021. | Commitments as of 30th September, 2021. | Balance Budget
Outcome 1: Country and Regional capacity established and strengthed to address their climate security priorities.
Output 1.1 | Dedicated catalytic local capacity in 3 CANNCC Atoll Nations driving country level project mplementation, dialogue, analysis and direction on critical climate security issues.
Activity 1.1.1 | Building local Capacity by identifying and recruiting country focal points as country ordinators in Tuvalu, Kiribati and RMI |  |  |  |  | UNDP | Kiribati | B0413 | 71400- SC Costs | 37500 | 15990.98 |  | 21509.02
[6 empty] | UNDP | Tuvalu | B0437 | 71400 - SC Costs | 46000 | 15606.01 |  | 30393.99
[6 empty] | IOM | RMI | B0415 | 71400 - SC Costs |  |  |  | 0
Activity 1.1.2 | Identify implementation priorities and approach to climate security profiling |  |  |  |  | UNDP | Kiribati | B0413 | 75700 - Learning Costs | 14998 | 2025.17 |  | 12972.83
[6 empty] | UNDP | Tuvalu | B0437 | 75700 - Learning Costs | 34001 | 2321.46 |  | 31679.54
[6 empty] | IOM | RMI | B0415 |  | 0
Activity 1.1.3 | Establish long term cross governmental capacity for climate security coordination |  |  |  |  | UNDP | Kiribati | B0413 | 71600 - Travel | 20000 |  |  | 20000
[6 empty] | UNDP | Tuvalu | B0437 | 71600 - Travel | 20000 |  |  | 20000
[6 empty] | IOM | RMI | B0415 | 71600 - Travel |  |  |  | 20000
OUTPUT TOTAL 1.1 | [9 empty] | 172499 | 35943.62 |  | 156555.38
Output 1.2 | Dedicated facility established to provide high-level dedicated policy advce to atoll nations on climate secuirty on an on demand basis.
Activity 1.2.1 | Provide current support and establish a more permanent support to the Chair of CANCC in form of an advisor and strengthen partnership mechanisms with the UN. |  |  |  |  | UNDP | Kiribati | B0413 | 71200- International Consultant | 51666 |  |  | 51666
[9 empty] | 71600-Travel | 3334 |  |  | 3334
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - International Consultant | 66666 |  |  | 66666
[9 empty] | 71600 -Travel | 3334 |  |  | 3334
[6 empty] | UNDP | RMI | B0415 | 71200 - International Consultant | 66666 |  |  | 66666
[9 empty] | 71600 - Travel | 13334 |  |  | 13334
OUTPUT TOTAL 1.2 | [9 empty] | 205000 | 0 |  | 205000
Output 1.3 | Co-ordination capacity strengtheened in the Pacific Islands Forum to support the developing regional understanding of climate security and feeding into the Boe Declaration Action Plan
Activity 1.3.1 | Strenthen capacity of Pacific Islands Forum (PIFS) to manage regionally focused activities of the project, foster collaboration amongst key stakeholders in the region, provide support to the country co-ordiantors and feed into releant reporting and decifiosn making processes linkrf to the Boe Declaration and relevant regional and international fora |  |  |  |  | UNDP | Kiribati | B0413 | 71200- International Consultant | 30000 |  |  | 30000
[9 empty] | 71600 - Travel | 5000 |  |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 71200- International Consultant | 30000 |  |  | 30000
[9 empty] | 71600 - Travel | 5000 |  |  | 5000
[6 empty] | UNDP | RMI | B0415 | 71200- International Consultant | 30000 |  |  | 30000
[9 empty] | 71600 - Travel | 5000 |  |  | 5000
OUTPUT TOTAL 1.3 | [9 empty] | 105000 | 0 |  | 105000
Total Outcome 1 (excluding GMS) | [9 empty] | 482499 | 35943.62 |  | 466555.38
GMS Costs Apportioned to Outcome 1 | [5 empty] | UNDP |  |  | 75100-GMS | 33774.93 | 2386.1 |  | 32658.8766
TOTAL OUTCOME 1 INCLUDING GMS | [9 empty] | 516273.93 | 38329.72 |  | 499214.2566
Outcome 2: Strengthen ability of key stakeholders in Pacific countries to understand, articulate and mitigate security threats of climate change with a particular focus to atoll nations.
Output 2.1 | 3 country specific Climate Security Profiles developed to identify critical climate security issues as the basis of action ,resource mobilization and advocacy in Kiribati, RMI and Tuvalu, building on the existing assessments.
Acitivity 2.1.1 | Conduct consultation on objectives, focus and purpose of Climate Security Profiles |  |  |  |  | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 10000 |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 10000 |  |  | 10000
Activity 2.1.2 | Identify gaps in relevant information availability and sources relating to Climate Security in the 3 Pacific Nations |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 5000 |  |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 5000 |  |  | 5000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 5000 |  |  | 5000
Activity 2.1.3 | Design methodology/approach to develop National Climate Security Profiles drawing on the UN Conceptual Approach for Climate Related Security Measurements |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 11000 |  |  | 11000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 11000 |  |  | 11000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 11000 |  |  | 11000
Activity 2.1.4 | Develop 3 National Climate Security Profiles (CSP) - one for each Atoll country . |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 10000 |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 50000 |  |  | 50000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 50000 |  |  | 50000
Activity 2.1.5 | Identify and recommend policy and management frameworks (e.g. National Security Policies , Climate Change Profiles) |  |  |  |  | UNDP | Kiribati | B0413 | n/a | 0 | 0 |  | 0
[6 empty] | UNDP | Tuvalu | B0437 | n/a | 0 | 0 |  | 0
[6 empty] | IOM | RMI | B0415 | n/a | 0 | 0 |  | 0
OUTPUT TOTAL 2.1 | [9 empty] | 178000 | 0 |  | 178000
Output 2.2 | Country focused consultative process and outreach arrangements established in Tuvalu and RMI that help to inform, validate and address and respond to climate change security risks overtime.
Activity 2.2.1 | Building on existing mechanisms to design and reach agreement on country specific collaborative arrangements to support ongoing inclusive dialogue and decision-making processes. (Two meetings in each country, at the beginning and ending of the project. |  |  |  |  | UNDP | Tuvalu | B0437 | 71200- Contractual Service / Consultant | 18000 |  |  | 18000
[9 empty] | 75700 - Learning Costs / Supplies | 6000 |  |  | 6000
[9 empty] | 71600 - Travel | 15000 |  |  | 15000
0
[6 empty] | IOM | RMI | B0415 | 71200- Contractual Service / Consultant |  |  |  | 0
[9 empty] | 71600 - Travel |  |  |  | 0
0
Activity 2.2.2 | Undertake inclusive dialogue and outreach in the relevant focus countries . (eg. country wide inception discussions; thematic focused dialogue and outreach; other innovative ways to engage unique perspectives including diaspora) |  |  |  |  | UNDP | Tuvalu | B0437 | 75700 - Learning Costs / Supplies | 20000 |  |  | 20000
[9 empty] | 71600 - Travel | 40000 |  |  | 40000
[6 empty] | UNDP | Kiribati | B0413 | 75700- Learning Costs | 10000 | 2661.33 |  | 7338.67
[9 empty] | Travel | 15000 | 8985.57 |  | 6014.43
[6 empty] | IOM | RMI | B0415 | 72600- Grants |  |  |  | 0
[9 empty] | 71600 - Travel |  |  |  | 0
Activity 2.2.3 | Build capacities of local NGO's, CSO, women, youth and community organizationsto effectively engage in the climate change security risk discourse. |  |  |  |  | UNDP | Tuvalu | B0437 | 72600- Grants | 40000 |  |  | 40000
[6 empty] | IOM | RMI | B0415 | 72600- Grants |  |  |  | 0
OUTPUT TOTAL 2.2 | [9 empty] | 164000 | 11646.9 |  | 152353.1
Output 2.3 | Pilot at least 3 initiatives that address an identified climate secuirty priority at country or the community level
Activity 2.3.1 | Establish a criteria and process for the selection of the pilot projects to respond to climate change secuirty related risks, drawing on country level, regional and international expertise on peacebuidling and conflict prevention as well as updated the plans in place. |  |  |  |  | UNDP | Kiribati | B0413 | n/a
[6 empty] | UNDP | Tuvalu | B0437 | n/a
[6 empty] | IOM | RMI | B0415 | n/a
Activity 2.3.2 | Develop and implement at least 3 pilot interventions, at least 1 relevant to each country of Tuvalu, RMI and Kiribati |  |  |  |  | UNDP | Kiribati | B0413 | 72300 - Materials & Goods | 350000 |  |  | 350000
[9 empty] | 75700 - Learning Costs | 17500 |  |  | 17500
[6 empty] | UNDP | Tuvalu | B0437 | 72300 - Materials & Goods | 100000 |  |  | 100000
[9 empty] | 75700 - Learning Costs | 20000 |  |  | 20000
[6 empty] | IOM | RMI | B0415 | 72600 - Grants |  |  |  | 0
OUTPUT TOTAL 2.3 | [9 empty] | 487500 | 0 |  | 487500
Output 2.4 | Establish a Pacific Climate Security network (PCSN)
Activity 2.4.1 | Review existing relevant formal and informal coordination mechanisms to establish network partnerships and engage in face to face periodic meetings with all stakeholders |  |  |  |  | IOM | RMI | B0415 | 71600- Travel |  |  |  | 0
[9 empty] | 75700 - Learning Costs / Supplies |  |  |  | 0
Activity 2.4.2 | Develop deep dive assessments on at least one climate fragility issues (issues to be recommended by Pacific Climate Security Network) |  |  |  |  | IOM | RMI | B0415 | 72100 - Contractual Services |  |  |  | 0
Activity 2.4.3 | Convene at least one regional dialogue on climate fragility issues with a focus on issues most relevant to Atoll Nations |  |  |  |  | IOM | RMI | B0415 | 71600- Travel |  |  |  | 0
[9 empty] | 75700 - Learning Costs / Supplies |  |  |  | 0
OUTPUT TOTAL 2.4 | [9 empty] | 0 | 0 |  | 0
Output 2.5 | A Pacific Climate Security Assessment prepaed and presented, drawing on and feeding back into the UN Conceptual Approach to Climate Related Secuirty Risk Assessments
Activity 2.5.1 | Engagement in dialogue with vulneable groups in communities. |  |  |  |  | UNDP | Kiribati | B0413 | 75700- Learning Costs | 7000 |  |  | 7000
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Contractual Services | 5000 |  |  | 5000
[9 empty] | 75700 - Learning Costs / Supplies | 2000 |  |  | 2000
[6 empty] | UNDP | RMI | B0415 | 75700 - Learning Costs | 7000 |  |  | 7000
Activity 2.5.2 | Engage leading experts (particularly from Atoll Nations) to support the translation of the global UN Conceptual Approach |  |  |  |  | UNDP | Kiribati | B0413 | 74200- Translation Costs | 10000 |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 74200- Translation Costs | 10000 |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 74200- Translation Costs | 10000 |  |  | 10000
Activity 2.5.3 | Present outcome framework and any associated comprehensive assessments (see output 1.4.ii below) to the Forum Officials Sub-committee on Regional Security |  |  |  |  | UNDP | [6 empty] | 0
Activity 2.5.4 | Identify opportunities to ensure a strengthened regional understanding of climate security is integrated into UN reporting and analysis on the global issue |  |  |  |  | UNDP | [6 empty] | 0
OUTPUT TOTAL 2.5 | [9 empty] | 51000 | 0 |  | 51000
Total Outcome 2 (excluding GMS) | [9 empty] | 880500 | 11646.9 |  | 868853.1
GMS Costs Apportioned to Outcome 2 | [5 empty] | UNDP |  |  | 75100-GMS | 61635 | 715.97 |  | 60819.717
TOTAL OUTCOME 2 INCLUDING GMS | [9 empty] | 942135 | 12362.87 |  | 929672.817
Outcome 3: Atoll Nations and Pacific Island Countries to have stronger targeted advocacy in global for a combating climate change and addressing the root cause of these security threats.
Output 3.1 | Greater awareness and reflection of positions on climate fragility and security for Pacific SIDS and low-lying Atoll Nations in relevant fora.
Acitivity 3.1.1 | Develop agreed country level impactful advocacy strategies associated with the Country Climate Security Profiles |  |  |  |  | UNDP | Kiribati | B0413 | 71300- Local Consultant / Contratual Service - Videographer | 10000 | 3776.62 |  | 6223.38
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Local Consultant / Contratual Service - Videographer | 10000 |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71300- Local Consultant / Contratual Service - Videographer | 10000 |  |  | 10000
Activity 3.1.2 | Develop an agreed joint Regional Advocacy Strategy for targeting key fora and events |  |  |  |  | UNDP | Kiribati | B0413 | 71300- Local Consultant / Contratual Service | 3333 |  |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Local Consultant / Contratual Service | 3333 |  |  | 3333
[6 empty] | UNDP | RMI | B0415 | 71300- Local Consultant / Contratual Service | 3333 |  |  | 3333
Acivity 3.1.3 | Support the CANCC to convene and build consensus on their priority climate security challenges |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 9667 |  |  | 9667
[9 empty] | 75700 - Learning Costs / Supplies | 4000 |  |  | 4000
[9 empty] | 72400- Comm Equipment | 13000 |  |  | 13000
[9 empty] | 71300 - Local Consultant / Contractual Service | 3333 |  |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 9667 |  |  | 9667
[9 empty] | 75700 - Learning Costs / Supplies | 4000 | 741.37 |  | 3258.63
[9 empty] | 72400 - Comm Equipment | 13000 |  |  | 13000
[9 empty] | 71300 - Local Consultant / Contractual Service | 3333 |  |  | 3333
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 9666 |  |  | 9666
[9 empty] | 72400 - Comm Equipment | 13000 |  |  | 13000
[9 empty] | 75700 - Learning Costs / Supplies | 4002 |  |  | 4002
[9 empty] | 71300 - Local Consultant / Contractual Service | 3335 |  |  | 3335
Activity 3.1.4 | Design and develop communication products from the Pacific |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 1884 | 1591 |  | 293
[9 empty] | 72500 - Communications / Supplies | 4004 |  |  | 4004
[9 empty] | 71500 - UNV | 31001 | 11916.92 |  | 19084.08
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 1885 | 1636 |  | 249
[9 empty] | 72500 - Communications / Supplies | 2998 |  |  | 2998
[9 empty] | 71500 - UNV | 31000 | 11674.78 |  | 19325.22
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 1883 | 1603.94 |  | 279.06
[9 empty] | 72500 - Communications / Supplies | 3000 |  |  | 3000
[9 empty] | 71500 - UNV | 31000 | 13391.15 |  | 17608.85
Activity 3.1.5 | Support CANCC members and stakeholders to attend key reional events to promote greater awareness of their climate security challenges |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 15000 |  |  | 15000
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 15000 |  |  | 15000
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 15000 |  |  | 15000
OUTPUT TOTAL 3.1 | [9 empty] | 283657 | 46331.78 | 0 | 237325.22
Output 3.2 | Identification, moblization and co-ordination of resources fro addressing the unique climate security challlenges of the focus countries.
Activity 3.2.1 | Develop resource opportunity strategies with consultations between Atoll , Pacific Countries and donors for development of climate Security Profiles for focused countries |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 11667 |  |  | 11667
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 11667 |  |  | 11667
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 11667 |  |  | 11667
Activity 3.2.2 | Support government to negotiate the inclusion of he unique climate security considerations of the Pacific in relevance to climate finance, development finance and security finance fora. |  |  |  |  | UNDP | Kiribati | B0413 | 72100- Contractual Services | 15000 |  |  | 15000
[6 empty] | UNDP | Tuvalu | B0437 | 72100- Contractual Services | 15000 |  |  | 15000
[6 empty] | UNDP | RMI | B0415 | 72100- Contractual Services | 15000 |  |  | 15000
OUTPUT TOTAL 3.2 | [9 empty] | 80001 | 0 |  | 80001
Total Outcome 3 (excluding GMS) | [9 empty] | 363658 | 46331.78 |  | 317326.22
GMS Costs Apportioned to Outcome 3 | [5 empty] | UNDP |  |  | 75100-GMS | 25456.06 | 2993.26 |  | 22212.8354
TOTAL OUTCOME 3 INCLUDING GMS | [9 empty] | 389114.06 | 49325.04 |  | 339539.0554
Outcome 4: PROJECT MANAGEMENT COSTS
Output 4.1 | Project Management Unit (PMU)
Activity 4.1.1 | Salary for Technical Staff - Professional Technical Staff |  |  |  |  | UNDP | Kiribati | B0413 | 61300 - NP Staff | 151169 | 104530.21 |  | 46638.79
[6 empty] | UNDP | Tuvalu | B0437 | 61300 - NP Staff | 163831 | 29400.66 |  | 134430.34
[6 empty] | IOM | RMI | B0415 | 61300 - Staff |  |  |  | 0
[6 empty] | UNDP | RMI | B0415 | 61300 - NP Staff | 55000 | 43666.68 |  | 11333.32
Activity 4.1.2 | Salary of Technical Staff- Finance & Admin |  |  |  |  | UNDP | Kiribati | B0413 | 71400- SC Staff | 24495 | 13652.72 |  | 10842.28
[6 empty] | UNDP | Tuvalu | B0437 | 71400- SC Staff | 11836 | 6343.38 |  | 5492.62
[6 empty] | UNDP | RMI | B0415 | 71400- SC Staff | 23669 | 8466.65 |  | 15202.35
Activity 4.1.3 | Conduct face to face meetings and monitoring of activites implementation in countries - PMU Travel |  |  |  |  | UNDP | Kiribati | B0413 | 71600-Travel | 11000 | 494.14 |  | 10505.86
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 12000 |  |  | 12000
[6 empty] | UNDP | RMI | B0415 | 71600 - Travel | 12000 |  |  | 12000
Activity 4.1.4 | General Expenses including direct project costs, bills and stationery |  |  |  |  | UNDP | Kiribati | B0413 | 72500- Supplies | 13335 | 1690.31 |  | 11644.69
[6 empty] | UNDP | Tuvalu | B0437 | 72500- Supplies | 13335 | 787.99 |  | 12547.01
[6 empty] | UNDP | RMI | B0415 | 72500- Supplies | 13330 | 1605.49 |  | 11724.51
Activity 4.1.5 | Computer & Equipment |  |  |  |  | UNDP | Kiribati | B0413 | 72200 - Office Equipment | 5000 | 7829.73 |  | -2829.73
[6 empty] | UNDP | Tuvalu | B0437 | 72200- Office Equipment | 5000 | 5216.51 |  | -216.51
[6 empty] | UNDP | RMI | B0415 | 72200- Office Equipment | 5000 | 1429.45 |  | 3570.55
Activity 4.1.6 | Safety & Security Clearances |  |  |  |  | UNDP | Kiribati | B0413 | 63500 - Security | 1000 |  |  | 1000
[6 empty] | UNDP | Tuvalu | B0437 | 63501 - Security | 1000 |  |  | 1000
[6 empty] | UNDP | RMI | B0415 | 63502 - Security | 1000 |  |  | 1000
OUTPUT TOTAL 4.1 | [9 empty] | 523000 | 225113.92 |  | 297886.08
Output 4.2 | Monitoring & Evaluation
Activity 4.2.1 | Conduct a Inception workshop to familiarize all stakeholders on the project objectives and Climate Security |  |  |  |  | UNDP | Kiribati | B0413 | 75700- Learning Costs - Inception Workshop | 3333 | 451.95 |  | 2881.05
[6 empty] | UNDP | Tuvalu | B0437 | 75700- Learning Costs - Inception Workshop | 3333 | 2195.84 |  | 1137.16
[6 empty] | UNDP | RMI | B0415 | 75700- Learning Costs - Inception Workshop | 3334 | 666.94 |  | 2667.06
Activity 4.2.2 | Conduct mid term evaluation to measure progress of project |  |  |  |  | UNDP | Kiribati | B0413 | 71200-International Consultant | 10000 |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200-International Consultant | 10000 |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200-International Consultant | 10000 |  |  | 10000
Activity 4.2.3 | Conduct a knowledge exchange forum to identify the Pacific nations needs in terms of Climate Security and existing data platforms. |  |  |  |  | UNDP | Kiribati | B0413 | 71600 -Travel | 11666.58 |  |  | 11666.58
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  |  | 8333
[6 empty] | UNDP | Tuvalu | B0437 | 71600 -Travel | 11666.58 |  |  | 11666.58
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  |  | 8333
[6 empty] | UNDP | RMI | B0415 | 71600 -Travel | 11667.05 |  |  | 11667.05
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  |  | 8333
Activity 4.2.4 | Independent Final Evaluation |  |  |  |  | UNDP | Kiribati | B0413 | 71200-International Consultant | 10000 |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200-International Consultant | 10000 |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200-International Consultant | 10000 |  |  | 10000
OUTPUT TOTAL 4.2 | [9 empty] | 149997.21 | 3314.73 |  | 146682.48
Total Outcome 4 (excluding GMS) | [9 empty] | 672997.21 | 228428.65 |  | 444568.56
GMS Costs Apportioned to Outcome 4 | [5 empty] | UNDP |  |  | 75100-GMS | 47109.8047 | 14184.12 |  | 31119.7992
TOTAL OUTCOME 4 INCLUDING GMS | [9 empty] | 720107.0147 | 242612.77 |  | 475688.3592
Workplan Total | [9 empty] | 2567630.0047 | 342630.4 |  | 2224999.6047
WORKPLAN
[7 empty] | Kiribati | Tuvalu | RMI - UNDP | RMI- IOM
[6 empty] | First Tranch | 682770 | 651491.57 | 343746.74 | 402500
[6 empty] | GMS @7% | 47793.9 | 45604.4099 | 24062.2718 | 28175
[6 empty] | Total | 730563.9 | 697095.9799 | 367809.0118 | 430675
[6 empty] | 2nd Tranch | 293114.6 | 283393 | 145139 | 188500
[6 empty] | GMS @7% | 20518.022 | 19837.51 | 10159.73 | 13195
[6 empty] | Total | 313632.622 | 303230.51 | 155298.73 | 201695
[6 empty] | TOTALS AWP | 1044196.522 | 1000326.4899 | 523107 | 632370
[6 empty] | Total Funding | 1044196.49 | 1000326.49 | 523107.02 | 632370
[6 empty] | Unprogrammed | -0.032 | 0.0001 | 0 | 0
Performance-Based Tranche Breakdown
[7 empty] | Recipient Organization 1 | Recipient Organization 4 | Tranche %
[7 empty] | UNDP- Kiribati | IOM-RMI
[6 empty] | First Tranche | 730937.54 | 442659 | 70%
[6 empty] | Second Tranche | 313258.95 | 189711 | 30%
[6 empty] | Third Tranche (as required) | $ - | $ -
[6 empty] | Total | 1044196.49 | 632370 | 100%

## Delivery Status IOM
Project Number: | 00121078 | [10 empty] | Title: | Climate Security Project
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | TIMEFRAME | [5 empty] | RESPONSIBLE PARTY | Focus Countries | BUDGET
|  |  | 2019 |  |  |  | 2021 |  |  | 2022
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | Fund Code | Donor Code | Dept ID | Budget Code & Description | Tranche 1 (USD) | Tranch 2 (USD)
Outcome 1: Country and Regional capacity established and strengthed to address their climate security priorities. | [19 empty] | TOTAL BUDGET | EXPENSES TILL September 30 th 2021 | BALANCE
Output 1.1 | Dedicated catalytic local capacity in 3 CANNCC Atoll Nations driving country level project mplementation, dialogue, analysis and direction on critical climate security issues.
Activity 1.1.1 | Building local Capacity by identifying and recruiting country focal points as country ordinators in Tuvalu, Kiribati and RMI | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 | bar: 2021 Q2 to 2022 Q2
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 71400 - SC Costs | 67500 | 32500 | 100000 | 10324.75 | bar: 2021 Q2 to 2022 Q2
Activity 1.1.2 | Identify implementation priorities and approach to climate security profiling | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 |  |  | 0 | bar: 2019 Q1 to 2021 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 |  |  | 0
[12 empty] | IOM | RMI | 11363 | 30000 | B0415
Activity 1.1.3 | Establish long term cross governmental capacity for climate security coordination | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 71600 - Travel | 10000 | 10000 | 20000
OUTPUT TOTAL 1.1 | [17 empty] | 77500 | 42500
Output 1.2 | Dedicated facility established to provide high-level dedicated policy advce to atoll nations on climate secuirty on an on demand basis.
Activity 1.2.1 | Provide current support and establish a more permanent support to the Chair of CANCC in form of an advisor and strengthen partnership mechanisms with the UN. | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 1.2 | [17 empty] | 0 | 0
Output 1.3 | Co-ordination capacity strengtheened in the Pacific Islands Forum to support the developing regional understanding of climate security and feeding into the Boe Declaration Action Plan
Activity 1.3.1 | Strenthen capacity of Pacific Islands Forum (PIFS) to manage regionally focused activities of the project, foster collaboration amongst key stakeholders in the region, provide support to the country co-ordiantors and feed into releant reporting and decifiosn making processes linkrf to the Boe Declaration and relevant regional and international fora | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 1.3 | [17 empty] | 0 | 0
Total Outcome 1 (excluding GMS) | [17 empty] | 77500 | 42500
GMS Costs Apportioned to Outcome 1 | [11 empty] | UNDP |  | 11363 | 30000 |  | 75100-GMS | 5425 | 2975 | bar: 2019 Q1 to 2022 Q2
TOTAL OUTCOME 1 INCLUDING GMS | [17 empty] | 82925 | 45475
Outcome 2: Strengthen ability of key stakeholders in Pacific countries to understand, articulate and mitigate security threats of climate change with a particular focus to atoll nations.
Output 2.1 | 3 country specific Climate Security Profiles developed to identify critical climate security issues as the basis of action ,resource mobilization and advocacy in Kiribati, RMI and Tuvalu, building on the existing assessments.
Acitivity 2.1.1 | Conduct consultation on objectives, focus and purpose of Climate Security Profiles | [10 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 | bar: 2021 Q2
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 2.1.2 | Identify gaps in relevant information availability and sources relating to Climate Security in the 3 Pacific Nations | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2021 Q3
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 2.1.3 | Design methodology/approach to develop National Climate Security Profiles drawing on the UN Conceptual Approach for Climate Related Security Measurements | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2021 Q3
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 2.1.4 | Develop 3 National Climate Security Profiles (CSP) - one for each Atoll country . | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q3 to 2022 Q1
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 2.1.5 | Identify and recommend policy and management frameworks (e.g. National Security Policies , Climate Change Profiles) | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q3 to 2022 Q1
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | IOM | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 2.1 | [17 empty] | 0 | 0
Output 2.2 | Country focused consultative process and outreach arrangements established in Tuvalu and RMI that help to inform, validate and address and respond to climate change security risks overtime.
Activity 2.2.1 | Building on existing mechanisms to design and reach agreement on country specific collaborative arrangements to support ongoing inclusive dialogue and decision-making processes. (Two meetings in each country, at the beginning and ending of the project. | [10 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 |  |  | 0 | bar: 2021 Q2 to 2021 Q3
0
[12 empty] | UNDP | Kiribati | 11363 | 30000 | B0413
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 71200- Contractual Service / Consultant | 18000 | 0 | 18000
[17 empty] | 71600 - Travel | 15000 |  | 15000 | 3582.5
[17 empty] | 75700 - Learning Costs / Supplies | 6000 | 0 | 6000 | 3045.62
Activity 2.2.2 | Undertake inclusive dialogue and outreach in the relevant focus countries . (eg. country wide inception discussions; thematic focused dialogue and outreach; other innovative ways to engage unique perspectives including diaspora) | [10 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 |  |  | 0 | bar: 2021 Q2 to 2021 Q3
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 75700 - Learning Costs / Supplies | 30000 | 0 | 30000 | 7064.99
[17 empty] | 71600 - Travel | 30000 |  | 30000
Activity 2.2.3 | Build capacities of local NGO's, CSO, women, youth and community organizationsto effectively engage in the climate change security risk discourse. | [10 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 | bar: 2021 Q2 to 2022 Q1
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 75700 - Learning Costs / Supplies | 30000 | 10000 | 40000 | 8135.36
OUTPUT TOTAL 2.2 | [17 empty] | 129000 | 10000
Output 2.3 | Pilot at least 3 initiatives that address an identified climate secuirty priority at country or the community level
Activity 2.3.1 | Establish a criteria and process for the selection of the pilot projects to respond to climate change secuirty related risks, drawing on country level, regional and international expertise on peacebuidling and conflict prevention as well as updated the plans in place. | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | n/a | 0 | 0 | bar: 2021 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437 | n/a | 0 | 0
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | n/a | 0 | 0
Activity 2.3.2 | Develop and implement at least 3 pilot interventions, at least 1 relevant to each country of Tuvalu, RMI and Kiribati | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2022 Q1
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 72600 - Grants | 90000 | 20000 | 110000
OUTPUT TOTAL 2.3 | [17 empty] | 90000 | 20000
Output 2.4 | Establish a Pacific Climate Security network (PCSN)
Activity 2.4.1 | Review existing relevant formal and informal coordination mechanisms to establish network partnerships and engage in face to face periodic meetings with all stakeholders | [10 empty] | IOM | RMI | 11363 | 30000 | B0415 | 71600- Travel | 15000 | 8000 | 23000 | bar: 2021 Q2; 2022 Q1
[17 empty] | 75700 - Learning Costs / Supplies | 1000 | 1000 | 2000
Activity 2.4.2 | Develop deep dive assessments on at least one climate fragility issues (issues to be recommended by Pacific Climate Security Network) | [10 empty] | IOM | RMI | 11363 | 30000 | B0415 | 72100 - Contractual Services | 40000 | 10000 | 50000 | bar: 2021 Q4 to 2022 Q1
Activity 2.4.3 | Convene at least one regional dialogue on climate fragility issues with a focus on issues most relevant to Atoll Nations | [10 empty] | IOM | RMI | 11363 | 30000 | B0415 | 71600- Travel |  | 40000 | 40000 | bar: 2022 Q1
[17 empty] | 75700 - Learning Costs / Supplies |  | 10000 | 10000 | 115.76
OUTPUT TOTAL 2.4 | [17 empty] | 56000 | 69000
Output 2.5 | A Pacific Climate Security Assessment prepaed and presented, drawing on and feeding back into the UN Conceptual Approach to Climate Related Secuirty Risk Assessments
Activity 2.5.1 | Engagement in dialogue with vulneable groups in communities. | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q3 to 2021 Q4
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 2.5.2 | Engage leading experts (particularly from Atoll Nations) to support the translation of the global UN Conceptual Approach | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2021 Q4
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 2.5.3 | Present outcome framework and any associated comprehensive assessments (see output 1.4.ii below) to the Forum Officials Sub-committee on Regional Security | [10 empty] | UNDP | bar: 2021 Q3 to 2021 Q4
Activity 2.5.4 | Identify opportunities to ensure a strengthened regional understanding of climate security is integrated into UN reporting and analysis on the global issue | [10 empty] | UNDP | bar: 2021 Q2 to 2022 Q2
OUTPUT TOTAL 2.5 | [17 empty] | 0 | 0
Total Outcome 2 (excluding GMS) | [17 empty] | 275000 | 99000
GMS Costs Apportioned to Outcome 2 | [11 empty] | UNDP |  | 11363 | 30000 |  | 75100-GMS | 19250 | 6930 | bar: 2019 Q1 to 2022 Q2
TOTAL OUTCOME 2 INCLUDING GMS | [17 empty] | 294250 | 105930
Outcome 3: Atoll Nations and Pacific Island Countries to have stronger targeted advocacy in global for a combating climate change and addressing the root cause of these security threats.
Output 3.1 | Greater awareness and reflection of positions on climate fragility and security for Pacific SIDS and low-lying Atoll Nations in relevant fora.
Acitivity 3.1.1 | Develop agreed country level impactful advocacy strategies associated with the Country Climate Security Profiles | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q3 to 2021 Q4
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 3.1.2 | Develop an agreed joint Regional Advocacy Strategy for targeting key fora and events | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2022 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Acivity 3.1.3 | Support the CANCC to convene and build consensus on their priority climate security challenges | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2021 Q4
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 3.1.4 | Design and develop communication products from the Pacific | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 3.1.5 | Support CANCC members and stakeholders to attend key reional events to promote greater awareness of their climate security challenges | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2022 Q1
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 3.1 | [17 empty] | 0 | 0
Output 3.2 | Identification, moblization and co-ordination of resources fro addressing the unique climate security challlenges of the focus countries.
Activity 3.2.1 | Develop resource opportunity strategies with consultations between Atoll , Pacific Countries and donors for development of climate Security Profiles for focused countries | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2022 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 3.2.2 | Support government to negotiate the inclusion of he unique climate security considerations of the Pacific in relevance to climate finance, development finance and security finance fora. | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2022 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 3.2 | [17 empty] | 0 | 0
Total Outcome 3 (excluding GMS) | [17 empty] | 0 | 0
GMS Costs Apportioned to Outcome 3 | [11 empty] | UNDP |  | 11363 | 30000 |  | 75100-GMS | 0 | 0 | bar: 2019 Q1 to 2022 Q2
TOTAL OUTCOME 3 INCLUDING GMS | [17 empty] | 0 | 0
Outcome 4: PROJECT MANAGEMENT COSTS
Output 4.1 | Project Management Unit (PMU)
Activity 4.1.1 | Salary for Technical Staff - Professional Technical Staff | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | IOM | RMI | 11363 | 30000 | B0415 | 61100 - Staff | 50000 | 47000 | 97000 | 31819.99
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.1.2 | Salary of Technical Staff- Finance & Admin | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.1.3 | Conduct face to face meetings and monitoring of activites implementation in countries - PMU Travel | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q3 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.1.4 | General Expenses including direct project costs, bills and stationery | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.1.5 | Computer & Equipment | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.1.6 | Safety & Security Clearances | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 4.1 | [17 empty] | 50000 | 47000
Output 4.2 | Monitoring & Evaluation
Activity 4.2.1 | Conduct a Inception workshop to familiarize all stakeholders on the project objectives and Climate Security | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2019 Q1
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.2.2 | Conduct mid term evaluation to measure progress of project | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q4
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.2.3 | Conduct a knowledge exchange forum to identify the Pacific nations needs in terms of Climate Security and existing data platforms. | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2021 Q2 to 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
Activity 4.2.4 | Independent Final Evaluation | [10 empty] | UNDP | Kiribati | 11363 | 30000 | B0413 | bar: 2022 Q2
[12 empty] | UNDP | Tuvalu | 11363 | 30000 | B0437
[12 empty] | UNDP | RMI | 11363 | 30000 | B0415
OUTPUT TOTAL 4.2 | [17 empty] | 0 | 0
Total Outcome 4 (excluding GMS) | [17 empty] | 50000 | 47000
GMS Costs Apportioned to Outcome 4 | [11 empty] | UNDP |  | 11363 | 30000 |  | 75100-GMS | 3500 | 3290 | bar: 2019 Q1 to 2022 Q2
TOTAL OUTCOME 4 INCLUDING GMS | [17 empty] | 53500 | 50290
Workplan Total | [17 empty] | 430675 | 201695 | 591000 | 64088.97 | 526911.03
[19 empty] | GMS @7% | 41370 | 4486.21 | 36883.79
[20 empty] | 632370 | 68575.18 | 563794.82
WORKPLAN
[13 empty] | Kiribati | Tuvalu | RMI - UNDP | RMI- IOM
[12 empty] | First Tranch | 682770 | 651491.57 | 343746.74 | 402500
[12 empty] | GMS @7% | 47793.9 | 45604.4099 | 24062.2718 | 28175
[12 empty] | Total | 730563.9 | 697095.9799 | 367809.0118 | 430675
[12 empty] | 2nd Tranch | 293114.6 | 283393 | 145139 | 188500
[12 empty] | GMS @7% | 20518.022 | 19837.51 | 10159.73 | 13195
[12 empty] | Total | 313632.622 | 303230.51 | 155298.73 | 201695
[12 empty] | TOTALS AWP | 1044196.522 | 1000326.4899 | 523107.7418 | 632370
[12 empty] | Total Funding | 1044196.49 | 1000326.49 | 523107.02 | 632370
[12 empty] | Unprogrammed | -0.032 | 0.0001 | 0 | 0
Performance-Based Tranche Breakdown
[13 empty] | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Tranche %
[13 empty] | UNDP- Kiribati | UNDP- Tuvalu | UNDP- RMI | IOM-RMI
[12 empty] | First Tranche | 730937.54 | 700228.54 | 366174.92 | 442659 | 70%
[12 empty] | Second Tranche | 313258.95 | 300097.95 | 156932.11 | 189711 | 30%
[12 empty] | Third Tranche (as required) | $ - | $ - | $ - | $ -
[12 empty] | Total | 1044196.49 | 1000326.49 | 523107.02 | 632370 | 100%
Note on U73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This budget line was for previously categorized as Supplies
Note on U76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This budget line was originally Supplies - 20,000 and Travel-10,000

## Budgets Working Sheet
Annual Workplan January 2021- June 2022 (Climate Security Project)
Project Number: | 00121078 |  |  |  |  | Title: | Climate Security Project
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | Focus Countries
2019
|  | Q1 | Q2 | Q3 | Q4 |  |  | Dept ID | Budget Code & Description | Total Budget | Expence To Date | Balance
Outcome 1: Country and Regional capacity established and strengthed to address their climate security priorities.
Output 1.1 | Dedicated catalytic local capacity in 3 CANNCC Atoll Nations driving country level project mplementation, dialogue, analysis and direction on critical climate security issues. | [12 empty] | kiribati | tuvalu | RMI- UN | RMI-IOM
Activity 1.1.1 | Building local Capacity by identifying and recruiting country focal points as country ordinators in Tuvalu, Kiribati and RMI |  |  |  |  | UNDP | Kiribati | B0413 | 71400- SC Costs | 37500 |  |  |  | 37500
[6 empty] | UNDP | Tuvalu | B0437 | 71400 - SC Costs | 46000 |  |  |  |  | 46000
[6 empty] | IOM | RMI | B0415 | 71400 - SC Costs | 100000 | [6 empty] | 100000
Activity 1.1.2 | Identify implementation priorities and approach to climate security profiling |  |  |  |  | UNDP | Kiribati | B0413 | 75700 - Learning Costs | 14998 |  |  |  | 14998
[6 empty] | UNDP | Tuvalu | B0437 | 75700 - Learning Costs | 34001 |  |  |  |  | 34001
[6 empty] | IOM | RMI | B0415 |  | 0
Activity 1.1.3 | Establish long term cross governmental capacity for climate security coordination |  |  |  |  | UNDP | Kiribati | B0413 | 71600 - Travel | 20000 |  |  |  | 20000
[6 empty] | UNDP | Tuvalu | B0437 | 71600 - Travel | 20000 |  |  |  |  | 20000 |  | 20000
[6 empty] | IOM | RMI | B0415 | 71600 - Travel | 20000
OUTPUT TOTAL 1.1 | [9 empty] | 292499 | 0 | 0
Output 1.2 | Dedicated facility established to provide high-level dedicated policy advce to atoll nations on climate secuirty on an on demand basis.
Activity 1.2.1 | Provide current support and establish a more permanent support to the Chair of CANCC in form of an advisor and strengthen partnership mechanisms with the UN. |  |  |  |  | UNDP | Kiribati | B0413 | 71200- International Consultant | 51666 |  |  |  | 51666
[9 empty] | 71600-Travel | 3334 |  |  |  | 3334
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - International Consultant | 66666 |  |  |  |  | 66666
[9 empty] | 71600 -Travel | 3334 |  |  |  |  | 3334
[6 empty] | UNDP | RMI | B0415 | 71200 - International Consultant | 66666 | [5 empty] | 66666
[9 empty] | 71600 - Travel | 13334 | [5 empty] | 13334
OUTPUT TOTAL 1.2 | [9 empty] | 205000 | 0 | 0
Output 1.3 | Co-ordination capacity strengtheened in the Pacific Islands Forum to support the developing regional understanding of climate security and feeding into the Boe Declaration Action Plan
Activity 1.3.1 | Strenthen capacity of Pacific Islands Forum (PIFS) to manage regionally focused activities of the project, foster collaboration amongst key stakeholders in the region, provide support to the country co-ordiantors and feed into releant reporting and decifiosn making processes linkrf to the Boe Declaration and relevant regional and international fora |  |  |  |  | UNDP | Kiribati | B0413 | 71200- International Consultant | 30000 |  |  |  | 30000
[9 empty] | 71600 - Travel | 5000 |  |  |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 71200- International Consultant | 30000 |  |  |  |  | 30000
[9 empty] | 71600 - Travel | 5000 |  |  |  |  | 5000
[6 empty] | UNDP | RMI | B0415 | 71200- International Consultant | 30000 | [5 empty] | 30000
[9 empty] | 71600 - Travel | 5000 | [5 empty] | 5000
OUTPUT TOTAL 1.3 | [9 empty] | 105000 | 0 | 0
Total Outcome 1 (excluding GMS) | [9 empty] | 602499 | 0 | 0
GMS Costs Apportioned to Outcome 1 | [5 empty] | UNDP |  |  | 75100-GMS | 42174.93 | 0 | 0
TOTAL OUTCOME 1 INCLUDING GMS | [9 empty] | 644673.93 | 0 | 0
Outcome 2: Strengthen ability of key stakeholders in Pacific countries to understand, articulate and mitigate security threats of climate change with a particular focus to atoll nations.
Output 2.1 | 3 country specific Climate Security Profiles developed to identify critical climate security issues as the basis of action ,resource mobilization and advocacy in Kiribati, RMI and Tuvalu, building on the existing assessments.
Acitivity 2.1.1 | Conduct consultation on objectives, focus and purpose of Climate Security Profiles |  |  |  |  | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 10000 |  |  |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 10000 | [5 empty] | 10000
Activity 2.1.2 | Identify gaps in relevant information availability and sources relating to Climate Security in the 3 Pacific Nations |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 5000 |  |  |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 5000 |  |  |  |  | 5000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 5000 | [5 empty] | 5000
Activity 2.1.3 | Design methodology/approach to develop National Climate Security Profiles drawing on the UN Conceptual Approach for Climate Related Security Measurements |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 11000 |  |  |  | 11000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 11000 |  |  |  |  | 11000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 11000 | [5 empty] | 11000
Activity 2.1.4 | Develop 3 National Climate Security Profiles (CSP) - one for each Atoll country . |  |  |  |  | UNDP | Kiribati | B0413 | 71200 - Contractual Service / International Consultant | 10000 |  |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200 - Contractual Service / International Consultant | 50000 |  |  |  |  | 50000
[6 empty] | UNDP | RMI | B0415 | 71200 - Contractual Service / International Consultant | 50000 | [5 empty] | 50000
Activity 2.1.5 | Identify and recommend policy and management frameworks (e.g. National Security Policies , Climate Change Profiles) |  |  |  |  | UNDP | Kiribati | B0413 | n/a | 0 | 0 | 0
[6 empty] | UNDP | Tuvalu | B0437 | n/a | 0 | 0 | 0
[6 empty] | IOM | RMI | B0415 | n/a | 0 | 0 | 0
OUTPUT TOTAL 2.1 | [9 empty] | 178000 | 0 | 0
Output 2.2 | Country focused consultative process and outreach arrangements established in Tuvalu and RMI that help to inform, validate and address and respond to climate change security risks overtime.
Activity 2.2.1 | Building on existing mechanisms to design and reach agreement on country specific collaborative arrangements to support ongoing inclusive dialogue and decision-making processes. (Two meetings in each country, at the beginning and ending of the project. |  |  |  |  | UNDP | Tuvalu | B0437 | 71200- Contractual Service / Consultant | 18000 |  |  |  |  | 18000
[9 empty] | 75700 - Learning Costs / Supplies | 6000 |  |  |  |  | 6000
[9 empty] | 71600 - Travel | 15000 |  |  |  |  | 15000
0
[6 empty] | IOM | RMI | B0415 | 71200- Contractual Service / Consultant | 18000 | [6 empty] | 18000
[9 empty] | 71600 - Travel | 15000 | [6 empty] | 15000
[10 empty] | 6000 | [6 empty] | 6000
Activity 2.2.2 | Undertake inclusive dialogue and outreach in the relevant focus countries . (eg. country wide inception discussions; thematic focused dialogue and outreach; other innovative ways to engage unique perspectives including diaspora) |  |  |  |  | UNDP | Tuvalu | B0437 | 75700 - Learning Costs / Supplies | 20000 |  |  |  |  | 20000
[9 empty] | 71600 - Travel | 40000 |  |  |  |  | 40000
[6 empty] | UNDP | Kiribati | B0413 | 75700- Learning Costs | 10000 |  |  |  | 10000
[9 empty] | Travel | 15000 |  |  |  | 15000
[6 empty] | IOM | RMI | B0415 | 72600- Grants | 30000 | [6 empty] | 30000
[9 empty] | 71600 - Travel | 30000 | [6 empty] | 30000
Activity 2.2.3 | Build capacities of local NGO's, CSO, women, youth and community organizationsto effectively engage in the climate change security risk discourse. |  |  |  |  | UNDP | Tuvalu | B0437 | 72600- Grants | 40000 |  |  |  |  | 40000
[6 empty] | IOM | RMI | B0415 | 72600- Grants | 40000 | [6 empty] | 40000
OUTPUT TOTAL 2.2 | [9 empty] | 303000 | 0 | 0
Output 2.3 | Pilot at least 3 initiatives that address an identified climate secuirty priority at country or the community level
Activity 2.3.1 | Establish a criteria and process for the selection of the pilot projects to respond to climate change secuirty related risks, drawing on country level, regional and international expertise on peacebuidling and conflict prevention as well as updated the plans in place. |  |  |  |  | UNDP | Kiribati | B0413 | n/a
[6 empty] | UNDP | Tuvalu | B0437 | n/a
[6 empty] | IOM | RMI | B0415 | n/a
Activity 2.3.2 | Develop and implement at least 3 pilot interventions, at least 1 relevant to each country of Tuvalu, RMI and Kiribati |  |  |  |  | UNDP | Kiribati | B0413 | 72300 - Materials & Goods | 350000 |  |  |  | 350000
[9 empty] | 75700 - Learning Costs | 17500 |  |  |  | 17500
[6 empty] | UNDP | Tuvalu | B0437 | 72300 - Materials & Goods | 100000 |  |  |  |  | 100000
[9 empty] | 75700 - Learning Costs | 20000 |  |  |  |  | 20000
[6 empty] | IOM | RMI | B0415 | 72600 - Grants | 110000 | [6 empty] | 110000
OUTPUT TOTAL 2.3 | [9 empty] | 597500 | 0 | 0
Output 2.4 | Establish a Pacific Climate Security network (PCSN)
Activity 2.4.1 | Review existing relevant formal and informal coordination mechanisms to establish network partnerships and engage in face to face periodic meetings with all stakeholders |  |  |  |  | IOM | RMI | B0415 | 71600- Travel | 23000 | [6 empty] | 23000
[9 empty] | 75700 - Learning Costs / Supplies | 2000 | [6 empty] | 2000
Activity 2.4.2 | Develop deep dive assessments on at least one climate fragility issues (issues to be recommended by Pacific Climate Security Network) |  |  |  |  | IOM | RMI | B0415 | 72100 - Contractual Services | 50000 | [6 empty] | 50000
Activity 2.4.3 | Convene at least one regional dialogue on climate fragility issues with a focus on issues most relevant to Atoll Nations |  |  |  |  | IOM | RMI | B0415 | 71600- Travel | 40000 | [6 empty] | 40000
[9 empty] | 75700 - Learning Costs / Supplies | 10000 | [6 empty] | 10000
OUTPUT TOTAL 2.4 | [9 empty] | 125000 | 0 | 0
Output 2.5 | A Pacific Climate Security Assessment prepaed and presented, drawing on and feeding back into the UN Conceptual Approach to Climate Related Secuirty Risk Assessments
Activity 2.5.1 | Engagement in dialogue with vulneable groups in communities. |  |  |  |  | UNDP | Kiribati | B0413 | 75700- Learning Costs | 7000 |  |  |  | 7000
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Contractual Services | 5000 |  |  |  |  | 5000
[9 empty] | 75700 - Learning Costs / Supplies | 2000 |  |  |  |  | 2000
[6 empty] | UNDP | RMI | B0415 | 75700 - Learning Costs | 7000 | [5 empty] | 7000
Activity 2.5.2 | Engage leading experts (particularly from Atoll Nations) to support the translation of the global UN Conceptual Approach |  |  |  |  | UNDP | Kiribati | B0413 | 74200- Translation Costs | 10000 |  |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 74200- Translation Costs | 10000 |  |  |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 74200- Translation Costs | 10000 | [5 empty] | 10000
Activity 2.5.3 | Present outcome framework and any associated comprehensive assessments (see output 1.4.ii below) to the Forum Officials Sub-committee on Regional Security |  |  |  |  | UNDP
Activity 2.5.4 | Identify opportunities to ensure a strengthened regional understanding of climate security is integrated into UN reporting and analysis on the global issue |  |  |  |  | UNDP
OUTPUT TOTAL 2.5 | [9 empty] | 51000 | 0 | 0
Total Outcome 2 (excluding GMS) | [9 empty] | 1254500 | 0 | 0
GMS Costs Apportioned to Outcome 2 | [5 empty] | UNDP |  |  | 75100-GMS | 87815 | 0 | 0
TOTAL OUTCOME 2 INCLUDING GMS | [9 empty] | 1342315 | 0 | 0
Outcome 3: Atoll Nations and Pacific Island Countries to have stronger targeted advocacy in global for a combating climate change and addressing the root cause of these security threats.
Output 3.1 | Greater awareness and reflection of positions on climate fragility and security for Pacific SIDS and low-lying Atoll Nations in relevant fora.
Acitivity 3.1.1 | Develop agreed country level impactful advocacy strategies associated with the Country Climate Security Profiles |  |  |  |  | UNDP | Kiribati | B0413 | 71300- Local Consultant / Contratual Service - Videographer | 10000 |  |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Local Consultant / Contratual Service - Videographer | 10000 |  |  |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71300- Local Consultant / Contratual Service - Videographer | 10000 | [5 empty] | 10000
Activity 3.1.2 | Develop an agreed joint Regional Advocacy Strategy for targeting key fora and events |  |  |  |  | UNDP | Kiribati | B0413 | 71300- Local Consultant / Contratual Service | 3333 |  |  |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 71300- Local Consultant / Contratual Service | 3333 |  |  |  |  | 3333
[6 empty] | UNDP | RMI | B0415 | 71300- Local Consultant / Contratual Service | 3333 | [5 empty] | 3333
Acivity 3.1.3 | Support the CANCC to convene and build consensus on their priority climate security challenges |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 9667 |  |  |  | 9667
[9 empty] | 75700 - Learning Costs / Supplies | 4000 |  |  |  | 4000
[9 empty] | 72400- Comm Equipment | 13000 |  |  |  | 13000
[9 empty] | 71300 - Local Consultant / Contractual Service | 3333 |  |  |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 9667 |  |  |  |  | 9667
[9 empty] | 75700 - Learning Costs / Supplies | 4000 |  |  |  |  | 4000
[9 empty] | 72400 - Comm Equipment | 13000 |  |  |  |  | 13000
[9 empty] | 71300 - Local Consultant / Contractual Service | 3333 |  |  |  |  | 3333
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 9666 | [5 empty] | 9666
[9 empty] | 72400 - Comm Equipment | 13000 | [5 empty] | 13000
[9 empty] | 75700 - Learning Costs / Supplies | 4002 | [5 empty] | 4002
[9 empty] | 71300 - Local Consultant / Contractual Service | 3335 | [5 empty] | 3335
Activity 3.1.4 | Design and develop communication products from the Pacific |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 1884 |  |  |  | 1884
[9 empty] | 72500 - Communications / Supplies | 4004 |  |  |  | 4004
[9 empty] | 71500 - UNV | 31001 |  |  |  | 31001
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 1885 |  |  |  |  | 1885
[9 empty] | 72500 - Communications / Supplies | 2998 |  |  |  |  | 2998
[9 empty] | 71500 - UNV | 31000 |  |  |  |  | 31000
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 1883 | [5 empty] | 1883
[9 empty] | 72500 - Communications / Supplies | 3000 | [5 empty] | 3000
[9 empty] | 71500 - UNV | 31000 | [5 empty] | 31000
Activity 3.1.5 | Support CANCC members and stakeholders to attend key reional events to promote greater awareness of their climate security challenges |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 15000 |  |  |  | 15000
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 15000 |  |  |  |  | 15000
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 15000 | [5 empty] | 15000
OUTPUT TOTAL 3.1 | [9 empty] | 283657 | 0 | 0
Output 3.2 | Identification, moblization and co-ordination of resources fro addressing the unique climate security challlenges of the focus countries.
Activity 3.2.1 | Develop resource opportunity strategies with consultations between Atoll , Pacific Countries and donors for development of climate Security Profiles for focused countries |  |  |  |  | UNDP | Kiribati | B0413 | 71600- Travel | 11667 |  |  |  | 11667
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 11667 |  |  |  |  | 11667
[6 empty] | UNDP | RMI | B0415 | 71600- Travel | 11667 | [5 empty] | 11667
Activity 3.2.2 | Support government to negotiate the inclusion of he unique climate security considerations of the Pacific in relevance to climate finance, development finance and security finance fora. |  |  |  |  | UNDP | Kiribati | B0413 | 72100- Contractual Services | 15000 |  |  |  | 15000
[6 empty] | UNDP | Tuvalu | B0437 | 72100- Contractual Services | 15000 |  |  |  |  | 15000
[6 empty] | UNDP | RMI | B0415 | 72100- Contractual Services | 15000 | [5 empty] | 15000
OUTPUT TOTAL 3.2 | [9 empty] | 80001 | 0 | 0
Total Outcome 3 (excluding GMS) | [9 empty] | 363658 | 0 | 0
GMS Costs Apportioned to Outcome 3 | [5 empty] | UNDP |  |  | 75100-GMS | 25456.06 | 0 | 0
TOTAL OUTCOME 3 INCLUDING GMS | [9 empty] | 389114.06 | 0 | 0
Outcome 4: PROJECT MANAGEMENT COSTS
Output 4.1 | Project Management Unit (PMU)
Activity 4.1.1 | Salary for Technical Staff - Professional Technical Staff |  |  |  |  | UNDP | Kiribati | B0413 | 61300 - NP Staff | 151169 |  |  |  | 151169
[6 empty] | UNDP | Tuvalu | B0437 | 61300 - NP Staff | 163831 |  |  |  |  | 163831
[6 empty] | IOM | RMI | B0415 | 61300 - Staff | 97000 | [6 empty] | 97000
[6 empty] | UNDP | RMI | B0415 | 61300 - NP Staff | 55000 | [5 empty] | 55000
Activity 4.1.2 | Salary of Technical Staff- Finance & Admin |  |  |  |  | UNDP | Kiribati | B0413 | 71400- SC Staff | 24495 |  |  |  | 24495
[6 empty] | UNDP | Tuvalu | B0437 | 71400- SC Staff | 11836 |  |  |  |  | 11836
[6 empty] | UNDP | RMI | B0415 | 71400- SC Staff | 23669 | [5 empty] | 23669
Activity 4.1.3 | Conduct face to face meetings and monitoring of activites implementation in countries - PMU Travel |  |  |  |  | UNDP | Kiribati | B0413 | 71600-Travel | 11000 |  |  |  | 11000
[6 empty] | UNDP | Tuvalu | B0437 | 71600- Travel | 12000 |  |  |  |  | 12000
[6 empty] | UNDP | RMI | B0415 | 71600 - Travel | 12000 | [5 empty] | 12000
Activity 4.1.4 | General Expenses including direct project costs, bills and stationery |  |  |  |  | UNDP | Kiribati | B0413 | 72500- Supplies | 13335 |  |  |  | 13335
[6 empty] | UNDP | Tuvalu | B0437 | 72500- Supplies | 13335 |  |  |  |  | 13335
[6 empty] | UNDP | RMI | B0415 | 72500- Supplies | 13330 | [5 empty] | 13330
Activity 4.1.5 | Computer & Equipment |  |  |  |  | UNDP | Kiribati | B0413 | 72200 - Office Equipment | 5000 |  |  |  | 5000
[6 empty] | UNDP | Tuvalu | B0437 | 72200- Office Equipment | 5000 |  |  |  |  | 5000
[6 empty] | UNDP | RMI | B0415 | 72200- Office Equipment | 5000 | [5 empty] | 5000
Activity 4.1.6 | Safety & Security Clearances |  |  |  |  | UNDP | Kiribati | B0413 | 63500 - Security | 1000 |  |  |  | 1000
[6 empty] | UNDP | Tuvalu | B0437 | 63501 - Security | 1000 |  |  |  |  | 1000
[6 empty] | UNDP | RMI | B0415 | 63502 - Security | 1000 | [5 empty] | 1000
OUTPUT TOTAL 4.1 | [9 empty] | 620000
Output 4.2 | Monitoring & Evaluation
Activity 4.2.1 | Conduct a Inception workshop to familiarize all stakeholders on the project objectives and Climate Security |  |  |  |  | UNDP | Kiribati | B0413 | 75700- Learning Costs - Inception Workshop | 3333 |  |  |  | 3333
[6 empty] | UNDP | Tuvalu | B0437 | 75700- Learning Costs - Inception Workshop | 3333 |  |  |  |  | 3333
[6 empty] | UNDP | RMI | B0415 | 75700- Learning Costs - Inception Workshop | 3334 | [5 empty] | 3334
Activity 4.2.2 | Conduct mid term evaluation to measure progress of project |  |  |  |  | UNDP | Kiribati | B0413 | 71200-International Consultant | 10000 |  |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200-International Consultant | 10000 |  |  |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200-International Consultant | 10000 | [5 empty] | 10000
Activity 4.2.3 | Conduct a knowledge exchange forum to identify the Pacific nations needs in terms of Climate Security and existing data platforms. |  |  |  |  | UNDP | Kiribati | B0413 | 71600 -Travel | 11666.58 |  |  |  | 11666.58
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  |  |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  |  |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  |  |  | 8333
[6 empty] | UNDP | Tuvalu | B0437 | 71600 -Travel | 11666.58 |  |  |  |  | 11666.58
[9 empty] | 75700- Learning Costs / Supplies | 3333 |  |  |  |  | 3333
[9 empty] | 71200 - Contractual Service | 3333 |  |  |  |  | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 |  |  |  |  | 8333
[6 empty] | UNDP | RMI | B0415 | 71600 -Travel | 11667.05 | [5 empty] | 11667.05
[9 empty] | 75700- Learning Costs / Supplies | 3333 | [5 empty] | 3333
[9 empty] | 71200 - Contractual Service | 3333 | [5 empty] | 3333
[9 empty] | 71300 - Local Consultant- M& E / Contractual Service | 8333 | [5 empty] | 8333
Activity 4.2.4 | Independent Final Evaluation |  |  |  |  | UNDP | Kiribati | B0413 | 71200-International Consultant | 10000 |  |  |  | 10000
[6 empty] | UNDP | Tuvalu | B0437 | 71200-International Consultant | 10000 |  |  |  |  | 10000
[6 empty] | UNDP | RMI | B0415 | 71200-International Consultant | 10000 | [5 empty] | 10000
OUTPUT TOTAL 4.2 | [9 empty] | 149997.21 | 0 | 0
Total Outcome 4 (excluding GMS) | [9 empty] | 769997.21 | 0 | 0
GMS Costs Apportioned to Outcome 4 | [5 empty] | UNDP |  |  | 75100-GMS | 53899.8047 | 0 | 0 |  | 975884.58 | 934884.58 | 488885.05 | 591000
TOTAL OUTCOME 4 INCLUDING GMS | [9 empty] | 823897.0147 | 0 | 0 | GMS | 68311.9206 | 65441.9206 | 34221.9535 | 41370
Workplan Total | [9 empty] | 3200000.0047 | 0 | 0 |  | 1044196.5006 | 1000326.5006 | 523107.0035 | 632370
WORKPLAN
[7 empty] | Kiribati | Tuvalu | RMI - UNDP | RMI- IOM
[6 empty] | First Tranch | 682770 | 651491.57 | 343746.74 | 402500
[6 empty] | GMS @7% | 47793.9 | 45604.4099 | 24062.2718 | 28175
[6 empty] | Total | 730563.9 | 697095.9799 | 367809.0118 | 430675
[6 empty] | 2nd Tranch | 293114.6 | 283393 | 145139 | 188500
[6 empty] | GMS @7% | 20518.022 | 19837.51 | 10159.73 | 13195
[6 empty] | Total | 313632.622 | 303230.51 | 155298.73 | 201695
[6 empty] | TOTALS AWP | 1044196.522 | 1000326.4899 | 523107 | 632370
[6 empty] | Total Funding | 1044196.49 | 1000326.49 | 523107.02 | 632370
[6 empty] | Unprogrammed | -0.032 | 0.0001 | 0 | 0
Performance-Based Tranche Breakdown
[7 empty] | Recipient Organization 1 | Recipient Organization 4 | Tranche %
[7 empty] | UNDP- Kiribati | IOM-RMI
[6 empty] | First Tranche | 730937.54 | 442659 | 70%
[6 empty] | Second Tranche | 313258.95 | 189711 | 30%
[6 empty] | Third Tranche (as required) | $ - | $ -
[6 empty] | Total | 1044196.49 | 632370 | 100%