## Joint_Workplan_SPB
Joint Annual Workplan for Phase 2
PBF Project: Sustaining Peace in Bougainville
Outcome/ Output number | Outcome/ output/ activity formulation: | Implementing Agency (RUNO) | Activty Budget in 2020 | Activty Budget in 2021 | Total Activity Budget (Post-referendum project) | Total Activity Budget (Sustaining Peace) | 2020 | [5 empty] | 2021
Outcome 1: Enhenced political dialogue between the two Governments and the two Parliaments ensures decisions around BPA implementation and (post) referendum are progressed jointly. | [6 empty] | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
Output 1.1: The two parliaments make joint decisions on the BPA and referendum processes, including on the post-referendum period in close consultations with women and youth focused civil society organisations.
Activity 1.1.1: | Number of consultation meetings of the Post Referendum Joint Ministerial Consultations Preparation Team | UNDP (through Post-referendum project) | 100000 | 100000 | 200000
Sub-activity 1.1.1.1. Technical and logistical support to the office of the ABG Chief Secretary and the Department of Post Referendum Dialogue and Department of Community Development for coordination of post-referendum planning with national government. | bar: 2021 May; 2021 Jul; 2021 Sept; 2021 Nov
Activity 1.1.2: | External Moderator contracted and providing support when required | UNDP (through Post-referendum project) |  | 220000 | 220000
Activity 1.1.3: | Comparative Transition, Legal and Constitutional expertise | UNDP (through Post-referendum project) |  | 114500 | 114500 | bar: 2021 Nov to 2021 Dec
| Sub-activity 1.1.3.1. Conduct Legal and Consitutional expertise for National Parliamentary ratification process of the Referendum Outcome (pending advance of post-referendum consultation process and requesst of Government partners) | UNDP (through Post-referendum project)
Activity 1.1.4: | National Parliament ratification process agreed and disseminated | UNDP (through Post-referendum project) |  | 25000 | 25000
Sub-activity 1.1.4.1. Assist media departments of ABG and GoPNG in disemminating joint key messages on post-referendum and ratification process. | bar: 2021 Jul; 2021 Sept; 2021 Nov
Output 1.2: Key government institutions with responsibilities for BPA implementation and coordination between the two governments are enabled to implement their functions effectively.
Activity 1.2.1: | Joint Post-Referendum Secretariat fully equipped to perform its functions | UNDP (through Post-referendum project) |  |  | 110000
Activity 1.2.2: | Induction programmes designed for new Members of the House of Representatives | UNDP
| Sub-activity 1.2.2.1. Contract National Liason Officer, who will act as a focal point in any communicataion with NCOBA, ABG and key Government stakeholders | UNDP | bar: 2021 March to 2021 May
| Sub-activity 1.2.2.2. Conduct awareness raising sessions to Members of the House of Representatives on BPA and post-referendum process | UNDP | bar: 2021 Aug; 2021 Oct
Activity 1.2.3: | Key government institutions with responsibilities for BPA implementation and coordination are enabled to implement their functions effectively | UNDP (through SPB) | 10000 | 30000 |  | 40000 | bar: 2021 March to 2021 Apr
Sub-Activity 1.2.3.1. Provision of office equipment, communication equipment, for Joint Secretariat to function | bar: 2021 March to 2021 Apr
Output 1.3: Bougainville youth, women, veterans and church leaders are supported to provide inputs into the post-referendum consultations and conduct post-referendum dialogues within their associations.
Activity 1.3.1: | Key networks (Women, Youth, Churches) are supported to participate in the post referendum process | UNDP, UNFPA, UN Women (through SPB) | 80000 | 80000 |  | 160000 | bar: 2021 June to 2021 Aug
| Convene coordination meeting between women leaders from CG, Churches, CSOs and Women MPs to identify priority issues for women to present to Post Referendum working committee and vice versa | UNW |  | 70000 |  | 70000 | bar: 2021 June to 2021 Aug
| Convene coordination meeting to create space for youth particiation in the post referendum dialogue and awerenes | UNFPA |  | 50000 |  | 50000 | bar: 2021 Apr to 2021 Dec
TOTAL $ FOR OUTCOME 1: |  |  |  |  | 669500 | 200000
OUTCOME 2: Increased dialogue and awareness on the BPA, referendum, and postreferendum issues, ensuring that both the population in and outside of Bougainville is informed and feels included in the process
Output 2.1: Innovative community-led dialogues about the BPA and a peaceful future for Bougainville are facilitated throughout the island;
Activity 2.1.1 | The Post Referendum Secretariat drafts joint messages on the post-referendum process and facilitates their dissemination. | UNDP | 20000 | 40000 | 60000 | bar: 2021 May; 2021 Jul; 2021 Sept; 2021 Nov
Sub-activity 2.1.1.1. Assist in developping joint messages on ratification process through contracting Media and Communications Consultant | bar: 2021 March; 2021 May; 2021 Jul; 2021 Sept
Sub-activity 2.1.1.2. Assist media departments of ABG and GoPNG in disemminating joint key messages on post-referendum process. | bar: 2021 March; 2021 May; 2021 Jul; 2021 Sept
Activity 2.1.2 | Community led dialogues about the post-referendum process and a peaceful future for Bougainville | UNDP, UNW, UNFPA | 80000 | 80000 |  | 160000 | bar: 2021 Feb to 2021 Dec
| Youth Community led dialogues about the post-referendum process and a peaceful future for Bougainville | UNFPA |  | 50000 |  | 50000 | bar: 2021 Feb to 2021 Dec
| Sub-activity 2.1.2.1. Develop community facilitator awareness materials and capacity building to support targeted communities’ dialogues on post referendum story | UNDP (through IP PACSIA) | bar: 2021 March; 2021 May; 2021 Jul; 2021 Sept; 2021 Nov
| Sub-activitiy: Conduct sensitization workshop on post-Referendum processes with women leaders from the Community Government, church leaders and CSOs | UNW |  | 70000 |  | 70000 | bar: 2021 March; 2021 May; 2021 Jul to 2021 Nov
| Sub-activity 2.1.2.2. Conduct community dialogues in targeted communities to increase awareness on post referendum story | UNDP (through IP PACSIA) | bar: 2021 March; 2021 May; 2021 Jul; 2021 Sept; 2021 Nov
Output 2.2: District level “town hall” dialogues led by both governments, including the CoChairs of the Post Referendum Joint Ministerial Consultations Preparation Team to inform and receive feedback from the population across Bougainville and mainland PNG* during the post referendum period
Activity 2.2.1: | BPA dialogue and post referendum awareness raising by national and ABG leaders and key actors within Bougainville and for Bougainvillean’s living outside of Bougainville | UNDP (through IP PACSIA) | 60000 | 90000 |  | 150000
Activity 2.2.2: | Awareness Adverts aired across Papua New Guinea on the post-referendum process | UNDP | 32185 | 70000 | 102185
Activity 2.2.3 | Media Training on Post-Referendum Process | UNDP |  | 20000 | 20000
Sub-activity 2.2.3.1. Conduct trainings to ABG and GoPNG media departmetns and journalists on conflict sensitive post referendum reporting in Bougainville and ratification process | bar: 2021 Aug; 2021 Oct
Activity 2.2.4 | Awareness sessions conducted on the post-referendum process in the National Parliament and the BHoR | UNDP | bar: 2021 June to 2021 Jul
| Technical and logistical support to Joint Town Halls connecting communities in the 13 districts with local and national political leadership | UNDP |  | 20000 |  | 20000 | bar: 2021 June to 2021 Jul
Activity 2.2.5 | Monitoring Perception Survey | UNDP |  | 50000 | 50000
TOTAL $ FOR OUTCOME 2: |  |  |  |  | 232185 | 310000
Outcome 3: Strengthened unification of outlier communities into the peace architecture and post-referendum dialogue
Activity 3.1.1: | Peace interventions to build confidence and encourage participation in post-referendum process by outlier factions | UNDP, UNW, UNFPA | 85000 | 80000 |  | 170000 | bar: 2021 March to 2021 Dec
| Youth based Peace interventions to build confidence and encourage participation in post-referendum process by outlier factions | UNFPA |  | 30000 |  | 30000 | bar: 2021 March to 2021 Dec
| Design quick impact through bottom up dialogue to support peaceful inclusion of outlier groups | UNDP |  | 20000 |  | 20000 | bar: 2021 March to 2021 Dec
Activity 3.1.2: | Human Rights Forum agree plan and with the BHOR Human Rights and Gender Committee monitor Human Rights | UNDP | 25000 | 25000 |  | 50000
Activity 3.1.3: | Key ABG and GoPNG institutions are supported to host Socio-Economic and Investment Summit | UNDP |  | 40000 |  | 40000 | bar: 2021 Jul to 2021 Sept
TOTAL $ FOR OUTCOME 3: | [5 empty] | 280000
All
Evaluation cost |  |  |  | 40000 |  | 40000
Operations |  |  | 112026 | 112026 | 168039 | 56013
Personnel
Project Manager (iUNV) |  |  | 82052 | 82052 | 124185 | 39919
National Liaison Officer (SB5) |  |  | 55626 | 55626 | 111252
Operations analyst (SB4) |  |  | 45626 | 45626 | 69055 | 22197
Admin associate (SB3) |  |  | 22279 | 22279 | 44558
Driver (SB2) |  |  | 13257 | 13257 | 20064 | 6450
Personnel sub total |  |  |  |  | 369114 | 68566
M&E and Communications |  |  | 36582 | 36582 |  | 73165
DPC |  |  | 18291 | 18292 |  | 36583
SUB-TOTAL PROJECT BUDGET: |  |  |  |  | 1,548,586 | 934579
Indirect support costs (7%): |  |  |  |  | 123887 | 65421
TOTAL PROJECT BUDGET: |  |  |  |  | 1,672,473 | 1000000
Note on C61: Salary Pro-Forma Cost for One Year $367,827: Project Manager (NOB) - 100% - $58,000 Project Officer - Buka (SB4) - 100% - $46,202 Project Officer - Buka (SB4) - 100% - $46,202 M&E Officer - (SB4/SC8) - 50% - $ 23,101 Receptionist - Buka (SB2) - 100% - $ 18,528 Operations Analyst Buka - (SB4) - 100% - $46,202 Driver Arawa - (SB1) - 100% - $ 12,539 Driver Buka - (SB1) - 100% - $ 12,539 Project Associate Arawa - (SB3) - 100% - $ 34,514 Operations Manager Buka - (NOC) - 100% - $ 70,000 For 24 months $735,654 ($367,827 x 2)
Note on C62: Operational Cost for Bougainville Office for one year $190,271 Buka Office Electricity $6,000 Buka Office Internet (Primary) $33,000.00 Buka Office Internet (Secondary) $29,000.00 Buka Office Rental $49,000.00 Arawa Office Rental $41,706 Arawa Office Internet (Secondary $5,800 Arawa Office Internet (Primary) $14,000 Project Vehicle Maintainces $4,500.00 Arawa Office Electricity $1,895 Fuel - Arawa $2,527 Fuel - Buka $2,843 Operational Cost for 24 months: $380,542 ($190,271 x 2)