## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual (hidden)
Programme Title & Project Number |  | Programme Duration
Programme Title: | Integrating WASH, Nutrition, MNH interventions for COVID-19 Response in Western Province, Papua New Guinea | Overall Duration (months) | 10
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 20.05.2020
MPTF Office Project Reference Number: | 00121672 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Papua New Guinea | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IOM, UNFPA and UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Western Provincial Government, Western Provincial Health Authority, North Fly District Government, World Vision, National Department of Health; Evangelical Church PNG, Catholic Church Health Services: Diocese of Daru and Kiunga
Report Cleared By
o Name: | Gianluca Rampolla
o Title: | Resident Coordinator
o Email address: | rampolla@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual (hidden)
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The United Nations in Papua New Guinea has successfully implemented the COVID-19 response project that targets WaSH, Nutrition and Maternal and Newborn Health in the Western Province of Papua New Guinea. As a result of this joint intervention: lives of mothers and newborns were saved through trained health professionals and increased supplies and equipment for Maternal and Newborn Health; lives of children with Severe Acute Malnutrition (SAM) were saved through availability of treatment services; and health and hygiene in eight targeted locations improved through Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE). Under the nutrition programme, a cumulative total of 17,402 individuals (direct beneficiaries) were reached with various nutrition services against a project target of 11,700 people (please find breakdown in section 2 here under). In addition, the nutrition component reached 5,915 indirect beneficiaries (male 2,574 and female 3,341) with COVID-19 related messaging while 1,767 children with moderate acute malnutrition were also treated. Further, the project enhanced the technical capacities of 62 Village Health Volunteers (VHVs) and 43 health care workers (51% females) who were trained in nutrition with the skills attained applied in the routine provision of nutrition services. The nutrition component of the programme was implemented in partnership with Catholic Church Health Services (CCHS). This partnership was instrumental in building the capacity of the nutrition programme and in the achievement of results. Seven target communities benefitted from the Maternal and Newborn Health (MNH) interventions. A total of 32 health workers from seven health facilities and 50 Village Health Volunteers (VHVs) linked to these facilities, were trained on Safe motherhood and Emergency obstetric and newborn care in COVID-19. As a result, 6,610 community members were informed of the associated risks and dangers of COVID-19 during pregnancy, the importance of delivery in a health facility, newborn care, and family planning. The capacity of health facilities and service providers to provide quality MNH services was strengthened to aid the safe delivery of mothers and newborns particularly in situations of lockdowns and restricted movements. A total of 829 pregnant and nursing mothers were referred to and received antenatal, maternity and postnatal care at health facilities. Also, 104 newborns were delivered and provided with neonatal care during the reporting period. WASH site assessments for eight locations (schools and host communities) in North Fly district of Western Province, targeting 7,123 beneficiaries were completed and complementary. Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE) sessions were conducted. Bahasa language RCCE was also delivered to 149 Indonesian refugees. While tangible results under this joint intervention is already visible, some of the activities under the MNH and WASH components have experienced delays due to disruption in the global supply chains which has also affected procurement from both local and international markets. A no-cost extension was approved and all pending activities will be completed within the extended timeline of 31 March 2021. One of the key lessons learnt was in the area of partnership: engaging with CSOs, and mobilizing and using community volunteers is an efficient strategy in delivering emergency response services in hard-to-reach/inaccessible communities.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | For the nutrition component: • Direct beneficiaries: - Children aged 6-59 months: 9,469 (52% female) - Women: 3,993 • Indirect beneficiaries: - Community members: 5,915 (56% female) - Children under five years treated of moderate acute malnutrition: 1,767 For the Maternal and Newborn Health component: • Direct beneficiaries: - 50 Village Health Volunteers and 32 Health Care Workers - Seven Health facilities and communities 6610 Community members - 829 pregnant and post-partum women - 104 newborns For the WASH component: • Direct beneficiaries: - 2,211 (933 M, 1218 F)
3.1 | Results: Outcome Level | Please include outcome level results achieved | As a result of this joint UN intervention in the Western Province of Papua New Guinea: lives of mothers and newborns were saved through trained health professionals and increased supplies and equipment for Maternal and Newborn Health; lives of children with Severe Acute Malnutrition (SAM) were saved as a result of enhanced nutrition status folllowing availability of treatment services; and health and hygiene in eight target locations improved through Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE). Towards achieving the project outcome, the nutrition component focused on providing critical and lifesaving services for the care of children with SAM. A total of 172 out of the 215 children (45% female) admitted were cured, thereby exceeding the planned target of 150 children. This is a notable achievement because if left untreated, SAM results in an increased risk of death of up to 12 times (Olofin et al 2013), compared to non-malnourished children, while 12 per cent of overall childhood mortality is attributable to wasting (Lancet 2013). Additionally, the project provided other promotive and preventive interventions that included micronutrient supplementation and nutrition education. These interventions are critical in enhancing the attainment of optimal nutrition status among individuals in the immediate and long term. The Maternal and Newborn Health (MNH) component focused on safe deliveries through antenatal and postnatal care in the seven target locations, towards increased deliveries in a health facility. The proportion of births delivered in a health facility increased to 64 per cent against the planned target of 62 per cent. The capacity building interventions for health workers, improved health facilities and services, and awareness creation among communities on the importance of delivery in a health facility, newborn care, and family planning have helped in the achievement of this outcome. A total of 829 pregnant and nursing mothers were referred to and received antenatal, maternity and postnatal care at health facilities. Also, 104 newborns were delivered and provided with neonatal care during the reporting period. Furthermore, because of Athe WASH interventions, eight remote border communities in Western Province will have access to safe and reliable water sources for improved health and hygiene by the end of February 2021. A total of 7,123 individuals will have benefitted against the planned target of 5,000 individuals. There is an enhanced level of awareness among communities which is the result of the complementary Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE) that were conducted in the eight target communities.
3.2 | Results: Output Level | Please include output level results achieved | The Nutrition component fully achieved and exceeded the expected project results: • A total of 172 (45% female) children were admitted, treated and cured of Severe Acute Malnutrition (SAM) against a target of 150 (Indicator 1. 1.1). • 9,469 children aged 6-59 months (52% female) received Vitamin A supplementation against a target of 1,500 people (Indicator 1.1.2.a). • A total of 3,725 (male 1,951 and female 1,774) children under five years received Micronutrient Powder supplementation against a target of 1,500 (Indicator 1.1.2.b). • 3,272 (male 1,492 and female 1,780) caregivers of children aged 0-23 months received Infant and Young Child Feeding (IYCF) counselling against a project target of 1,500 (Indicator 1.2.1). • A total of 215 (male 118 and female 97) children were admitted and treated of SAM against a target of 150 Indicator 1.2.2). • A total of 3,993 pregnant and lactating women received nutrition education against a target of 2,000 people (Output 1.2.1.c). • 5,915 (male 2,574 and female 3,341) community members have been reached with COVID-19 related messaging against a target of 1,000 (Output 1.2.1.d) (Indirect) The nutrition education activity aimed at improving the awareness of and enhancing care giver knowledge on appropriate childcare and feeding practices. To this end, a total of 7,265 caregivers comprised of mostly mothers of children aged 6 – 23 months were reached with counselling on appropriate child feeding practices. The caregivers gained specific skills and knowledge on maternal and child nutrition and are expected to apply this in caring for their children. Sub optimal child feeding practices especially during the complementary feeding period is a key driver of undernutrition among children within this age cohort. The project enhanced the technical capacities of 62 Village Health Volunteers (VHVs) and 43 health care workers (51% females) who were trained on three broad areas of nutrition, including treatment of SAM, micronutrient supplementation as well as on support and promotion of appropriate child feeding. Additionally, 5,915 individuals in the target geographical area were reached with COVID-19 related messages specifically focused on infection prevention and control. Under the Maternal and Newborn Health (MNH) component, the following results were achieved in the seven target communities: • 829 pregnant and postpartum women received antenatal and postnatal care at health facilities and through home visits. • 104 newborns were delivered and provided with neonatal care. • 62 healthcare providers whose capacities were built to provide quality Maternity and neonatal care with adequate IPC measures. • 6610 community members were reached with information on COVID-19, danger signs in pregnancy, the importance of delivery in a health facility, newborn care, and family planning. • Emergency transport system established for prompt transport of pregnant, postpartum women and newborn for advanced care. The resultant skills from the training provided to health workers were immediately put to use in saving a woman from death who had delivered three weeks before the training and was bleeding but could not get to the hospital immediately because of transport restrictions. The trained health worker applied the non-pneumatic antishock garment, and the heart failure and shock the woman experienced was reversed. Another trained health worker prevented the death of a mother and her triplets through the administration of Magnesium Sulphate injection: a skill she had just acquired during the training. Also, the capacity of health facilities and service providers to provide quality MNH services was strengthened through the provision of 400 clean Reproductive Health Delivery kits, six Anti-shock Garments and Mannequins to the six project health facilities and the VHVs, to aid the safe delivery of mothers and newborns particularly in situations of lockdowns and restricted movements. A basket fund has been established for emergency transport of mothers and newborns from rural communities/facilities to the Rumginae referral hospital that is managed by the Rumginae referral hospital management. The renovation of the Matkomnae Sub health centre and Rumginae Rural hospital has been completed to facilitate respectful maternity care services. Under the WASH component, a needs assessment identified 25 target sites (six health centres/posts, 12 schools and seven other sites) in eight villages for WaSH infrastructure rehabilitation and upgrade. The project activities are ongoing and will be completed by the end of January 2021. This will benefit 1,203 households including 7,123 individuals. The Participatory Health & Hygiene Education and Risk Communication and Community Engagement awareness raising programs have led to improved hygiene practices thereby, mitigating the spread of COVID-19.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) |  Considering that nutrition service delivery is relatively new within the health care system in PNG, there is limited technical capacity for implementation at both central and local levels. To address this, UNICEF partnered with the CCHS that runs most health facilities in the target geographical area to lead implementation at the local level. To ensure the ownership of implementation and results, as well as seamless integration into the project area, consultations were held involving the National Department of Health (NDoH) and the Western Provincial Health Authority (WPHA), CCHS and UNICEF. The partnership was able to deliver on the project and achieved beyond the programmatic targets.  For the UNFPA-implemented MNH component, COVID-19 movement restrictions and total lockdown in the project target province slowed down the implementation of activities. In addition, the difficult terrain and inaccessibility by road also posed challenges in timely implementation of the project. To ensure timely implementation of activities, high-level engagement with the National Department of Health, the Provincial and District Health administrators for travel restriction exemptions was deployed while adhering to COVID-19 measures. Project staff were also deployed additional days ahead of start of implementation of activities to avoid implementation delays.  For the WASH component, the main challenge was accessibility in reaching the project sites. Two remote inland communities originally targeted along the Alice river could not be reached as river waters levels fell too low to navigate owing to lack of rain and were otherwise inaccessible by alternative land routes. Given this reality, IOM identified two other villages in the same local government administration with similar needs that were accessible to include in the project delivery. Limited access to and availability of stocks and supplies that were on backorder from the local vendors delayed procurement of supplies needed to complete WASH infrastructure projects in planned timeframes. To minimize delays, IOM procured some items from Port Moresby and delivered them by airfreight. Furthermore, mobilizing community involvement for site preparation was another challenge as communities were expecting to be paid for participating in their own community development. Through support and engagement of church and government partners, communities began to embrace ownership over the positive community development aspects of project initiatives and now embrace their role in both planning and participating in efforts to improve WaSH infrastructure and maintenance.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | - Partnerships with civil society organizations (CSOs) are effective in programme delivery and in the achievement of set targets in the area of nutrition. The collaboration between UNICEF and CCHS in Kiunga was the key driver in the timely roll out of nutrition services and in the achievement of programmatic targets and results. - The engagement of Village Health Volunteers (VHVs) in nutrition promotion and community mobilization is effective in achieving scale. This was exemplified in the project whereby VHVs were trained and deployed to provide nutrition promotion messaging as well as IPC awareness raising on COVID-19 through home visits and other community engagement approaches. - There must be consistent advocacy with Government and engagement with private partners for the provision of emergency transport for mothers and babies in situations when transport restrictions are necessary including in pandemics if maternal and newborn deaths are to be avoided. - Expanding access to information and services to the rural, disadvantaged, and hard to reach communities and not just to the urban population is critical in mitigating community spread of COVID-19 and reducing maternal and newborn mortality.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | - Partnerships with civil society organizations (CSOs): This has proven to be effective in programme delivery and in the achievement of set targets across the three project components as IOM, UNICEF and UNFPA had all partnered with the Church Groups. Under the nutrition component, the new collaboration between UNICEF and CCHS in Kiunga was the key driver in the timely roll out of nutrition services and in the achievement of programmatic targets and results. This partnership can be an opportunity to catalyze future nutrition work in geographic areas where there are service gaps. In addition, strong working relationship and partnerships were ensured between UNICEF and NDoH at central level and WPHA, as well as with other UN agencies involved in the implementation of the project. UNICEF provided its implementing partners with technical support during trainings and field level implementation, Information, Education and Communication materials as well as monitoring to enable them deliver on the project activities. For the WASH component, IOM partnered with the Church groups that were instrumental in facilitating access for project staff and local government officials to remote communities and to overcome community reservations, misunderstandings and apprehensions around COVID-19, that were addressed in RCCE. Church group partners familiarity with target communities helped to overcome engagement challenges and ultimately led to joint collaboration between project staff, church representatives and local government on RCCE and PHHE practices, particularly with regard to promoting the government’s “new normal” guidance around social distancing, wearing of masks, washing of hands with soap and water, etc. The Catholic church also assisted with logistical support to the Provincial Disaster Office and project staff through providing free storage space for COVID-19 relief items. UNFPA developed partnerships with the Church groups in North Fly District to ensure continued provision of MNH services despite lockdowns and movement restrictions. - Partnership with private organizations: The MNH programme has catalyzed a strong partnership with the OK Tedi Mining company and Digicel Telecom company in facilitating emergency transport for mothers and newborns from border communities and health facilities to the referral obstetric hospital in Rumginae. The basket fund under the MNH Project is used to provide funding for fueling of the OK Tedi chopper, and Digicel procured ambulance. The OK Tedi Mining also partnered with IOM on the WASH component whereby, it provided the local government with free airlift of supplies into remote locations; especially in relation to supporting Western Papuan refugees accommodated in Western Province. - Partnership with local authorities: Vibrant partnerships were created with the Provincial Government, Health Authority and North Fly District Health Office. This led to smooth travel approvals for project staff even in the midst of lockdowns and strict movements in the province, as the activities were deemed essential, lifesaving and critical by the Government.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNICEF participated in multi-agency assessment of the situation of Indonesian refugees in Western Province who have settled in the same geographic area as the project. The findings informed recommendations on key actions to support the 149 refugees. UNICEF provided technical assistance in the assessment of nutrition needs of the refugees as well as in the development of a food basket. The assessment formed the foundation for advocacy and solicitation of support to address the needs of the refugees. The food basket is being used by the Food and Agricultural Organization to provide a balanced food ration to the refugees. Participating in the same assessment, IOM made recommendations for relocation site planning, constructed WASH facilities (6 pit latrines, 6 shower blocks, 4 water taps and installed three flood lights (supported by UNHCR funds)
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | As indicated in the project’s midterm report under the nutrition component, the implementation strategy was changed due to the capacity limitations faced by the WPHA to implement. This was mitigated by engaging CCHS to strengthen service delivery.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Additional resources were mobilized under UNFPA's Emergency Fund through the Asia pacific Regional Office. A project officer located within the project communities was engaged to manage project activities. The additional funding was used to complement i) the capacity building of maternity and sexual and reproductive health service providers in the province through facilitating remote learning by providing tablets with Safe Delivery Applications and Solar chargers and projectors; ii) building the capacities of these service providers on Clinical Management of Rape and Minimum Initial Service Package for SRH and GBV in emergencies and iii) addressing gender-based violence issues in the project area including health / clinical response to GBV and provision of Dignity Kits to women of reproductive age in the communities served. IOM coordinated with donor of existing DRR programme to allocate pre positioned soap to supplement water buckets distributed to 149 refugees in complement to PHHE efforts.

## RBM-Annual (hidden)
OUTCOME: Western Province Border communities that are most vulnerable/left behind and at-risk of the COVID-19 outbreak in PNG continue to have to access critical, life-saving services to ensure progress towards the achievement of sustainable development priorities/goals remains on track | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Indicator:1.1a Number of children aged 6-59 months with severe acute malnutrition who were admitted for treatment and cured (SDG Target 2.2)
Baseline: 0
Planned Target: 150 | 172 |  | Administrative data
Indicator: 1.1b Proportion of births delivered in a health facility (SDG Target 3.1)
Baseline: 58%
Planned Target: 62% | 64% |  | Post-assistance monitoring
Indicator: 1.1c Number of people from vulnerable communities who have improved access to, and are utilizing, safe drinking water sources and sanitation facilities (SDG Target 6.2)
Baseline: 0
Planned Target: 5000 | 7123 | 8x sites selected, they are Kungim, Yenkanae, Matkomnai, Yogi, Dome, Rumginae, Sinamre & St. Gabriel Tec. Secondary School with the population more than the target inclusive of the host communities and the intended beneficaries | Internal report- (Field activity reports and field monitoring reports) yet to published online. WASH cluster sitrep
Output 1.1.1: Government, service providers and community stakeholders continue to implement critical basic WASH, nutrition and MNH services according to standards at all times in border communities, that are not covered by the national/sub-national COVID-19 response and reach vulnerable and disadvantaged border communities, specifically women and girls of reproductive age (duty bearers)
Indicator 1.1.1a: Number of children aged 6-59 months who received: (a) Vitamin A supplements (b) Multiple Micronutrient Powder
Baseline: a:0; b: 0
Planned Target: a:1500; b: 1500 | a: 9469; b: 3725 |  | Administrative data
Indicator 1.1.1b: Number of pregnant and postpartum women who received antenatal and postnatal care at health facilities and through home visits
Baseline: 0
Planned Target: 700 | 829 |  | Facility, home visits and monitoring reports
Indicator 1.1.1c: Number of Healthcare providers whose capacities are built to provide quality Maternity and neonatal care with adequate IPC measures
Baseline: 0
Planned Target: 50 | 62 |  | Training and monitoring reports
Indicator 1.1.1d: Emergency transport system established for prompt transport of pregnant, postpartum women and newborn for advanced care
Baseline: No
Planned Target: Yes | Yes |  | Monitoring reports
Indicator 1.1.1e: Number of people with increased access to installed and/or rehabilitated water points
Baseline: 0
Planned Target: 5000 | ongoing
Indicator 1.1.1f: Number of households with increased access to installed and/or rehabilitated pit latrines
Baseline: 0
Planned Target: 200 | ongoing
Indicator 1.1.1g: Number of water point minders to ensure quality and functioning is maintained
Baseline: 0
Planned Target: 20 | ongoing
Output 1.2.1: Caregivers, family members, women of reproductive age, and communities have improved knowledge of improved feeding/nutrition, WASH, and maternal and newborn caring practices and to seek quality services, especially in groups that are the most vulnerable and disadvantaged
Indicator 1.2.1a: Number of primary caregivers of children aged 0-23 months who received IYCF counselling through facilities and community platforms
Baseline: 0
Planned Target: 1500 | 3272 |  | Administrative data
Indicator 1.2.1b: Number of children aged 6-59 months with severe acute malnutrition who are admitted for treatment
Baseline: 0
Planned Target: 200 | 215 |  | Administrative data
Indicator 1.2.1c: Number of pregnant and lactating women receiving nutrition education including infant and young child feeding practices
Baseline: 0
Planned Target: 2000 | 3993 |  | Administrative data
Indicator 1.2.1d: Number of adolescents receiving nutrition education
Baseline: 0
Planned Target: 1000 | 5915 |  | Administrative data
Indicator 1.2.1e: Number of community members provided with information on pregnancy, delivery and COVID-19 infection prevention
Baseline: 0 | 6610
Planned Target: 6000
Indicator 1.2.1f: Number of people reached with PHHE/RCCE Awareness
Baseline: 0 | 2111 (993M; 1218F)
Planned Target: 5000 |  | Full target to be achieved by end of Jan 2021 | Internal report: field activity report and field monitoring report, yet to be published
Indicator 1.2.1g: Number of community members participating in functioning water user committees (gender parity)
Baseline: 0
Planned Target: 60 | ongoing
Indicator 1.2.1h: Number of households receiving WASH supplies (soap and water containers or budgets with lids)
Baseline: 0
Planned Target: 1000 | Ongoing
Please inlcude all three: Baseline, Planned Target and Achieved Targets

## Communication-Annual (hidden)
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
https://papuanewguinea.un.org/en/89078-we-are-just-sweating-unfpa-funds-renovation-maternity-ward-matkomnai-western-province
https://twitter.com/UNFPA_PNG/status/1349882763327926274
https://www.facebook.com/UNFPAPNG/posts/3395325763923464
https://www.instagram.com/p/CKC9v7rB2Sc/
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final (hidden)
Programme Title & Project Number |  | Programme Duration
Programme Title: | Integrating WASH, Nutrition, MNH interventions for COVID-19 Response in Western Province, Papua New Guinea | Overall Duration (months) | 10
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 20.05.2020
MPTF Office Project Reference Number: | 00121672 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Papua New Guinea | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IOM, UNFPA and UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Western Provincial Government, Western Provincial Health Authority, North Fly District Government, World Vision, National Department of Health; Evangelical Church PNG, Catholic Church Health Services: Diocese of Daru and Kiunga
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Response
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The United Nations in Papua New Guinea has successfully closed its COVID-19 response project that supported the provision of services in WaSH, Nutrition and Maternal and Newborn Health in the Western Province of Papua New Guinea. This joint UN intervention in the Western Province of Papua New Guinea contributed to lives of mothers and newborns saved through improved access to and availability of trained health professionals and increased supplies and equipment for Maternal and Newborn Health; lives of children with Severe Acute Malnutrition (SAM) saved as a result of enhanced nutrition status following availability of treatment services; and health and hygiene in eight target locations improved through Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE). While tangible results under this joint intervention are already visible, some of the activities under the MNH and WASH components have experienced delays due to disruption in the global supply chains which has also affected procurement from both local and international markets. An approved no-cost extension of the project to 31st March 2021, allowed the project to complete all it intended to do. The project identified partnership: engaging with Civil Society Organisation (CSOs), and engagement of community volunteers as efficient strategies in delivering emergency response services in hard-to-reach/inaccessible communities. Under the nutrition programme, a cumulative total of 17,402 individuals (direct beneficiaries) were reached with various nutrition services against a project target of 11,700 people (please find breakdown in section 2 here under). In addition, the nutrition component reached 5,915 indirect beneficiaries (male 2,574 and female 3,341) with COVID-19 related messaging while 1,767 children with moderate acute malnutrition were also treated. Further, the project enhanced the technical capacities of 62 Village Health Volunteers (VHVs) and 43 health care workers (51% females) who were trained in nutrition with the skills attained applied in the provision of nutrition services. The nutrition component of the programme was implemented in partnership with Catholic Church Health Services (CCHS). This partnership was instrumental in building capacities of health care workers around nutrition and in the achievement of results. Seven target communities benefitted from the Maternal and Newborn Health (MNH) interventions. A total of 32 health workers from seven health facilities and 50 Village Health Volunteers (VHVs) linked to these facilities, were trained on Safe motherhood and Emergency obstetric and newborn care in COVID-19. As a result, 6,610 community members were informed of the associated risks and dangers of COVID-19 during pregnancy, the importance of delivery in a health facility, newborn care, and family planning. The capacity of health facilities and service providers to provide quality MNH services was strengthened to aid the safe delivery of mothers and newborns particularly in situations of lockdowns and restricted movements. A total of 829 pregnant and nursing mothers were referred to and received antenatal, maternity, and postnatal care at health facilities. Also, 104 newborns were delivered and provided with neonatal care during the reporting period. WASH site assessments for eight locations (schools and host communities) in North Fly district of Western Province, targeting 7,123 beneficiaries were completed. Participatory Health and Hygiene Education (PHHE) awareness raising, and Risk Communication and Community Engagement (RCCE) sessions were conducted. Bahasa language RCCE was also delivered to 149 Indonesian refugees. A total of 6,243 individuals (3,722 M and 2,521 F) now have improved access to clean and safe drinking water. This was achieved through installing new rain-fed water supply systems and rehabilitating existing systems such as the 50,000L water reservoir at St. Gabriel Technical Secondary School and water bore well at Rumginae Rural Hospital under the project. These interventions in identified health facilities, schools and local communities are providing safe drinking water to in-patients and health care staff; school children, teachers, and non-teaching staff; and community members from 7 locations. The project equipped 61 individuals (51M and 10F) who are members of the Water User Committees (WUCs) from the 8 target locations with skills and knowledge on water point management to ensure proper usage and functioning water points. The WUCs played a key role in mobilizing local community members during the installation of water points. Also, 20 pump minders (16M and 4F) from the 8 locations received on-site demonstrations on water supply system repair and maintenance, and were supplied basic tools (screwdriver set, hacksaw frame, multi-grip plier and tape measure) to enable them to carry out maintenance and basic repair works of the newly installed and rehabilitated water points. Establishing WUCs and pump minders, including equipping them with knowledge and basic tools help guarantee sustainability of the water points. Improved access to sanitation for a total 9,080 individuals (4,681 M and Female 4,399 F) from 8 target locations was achieved through installing new gender-segregated Ventilated Improved Pit (VIP) latrines (22) in six locations and rehabilitating existing gender-segregated Septic Tank latrines (10) in two locations. The dilapidated gender-segregated latrines at the Kiunga airport, which serves as one of the primary entry points to Western Province, were rehabilitated to improve health and hygiene standards for airport staff and arriving/departing travellers. Handwashing stations (19) were installed at communal and strategic locations across the 8 target locations and at Kiunga airport to complement the water supply and sanitation interventions, promoting personal health and hygiene including protecting people from the spread of COVID-19, as well as other viruses and bacteria. A total of 1,203 households (approximately 8,060 [individuals (4,148 M and 3,912 F]) received water containers and soap across the 8 locations. Also WASH NFIs were delivered to target schools and health facilities. This included Wheelie Bins (25), Dust Bins (14), Hand gloves (24), Rubber boots (24), 5L anti-septic cleaning detergents (20), mops (33), mop buckets (33) and multipurpose brooms with heavy duty bristles (33). Participatory Health and Hygiene (PHHE) and Risk Communication and Community Engagement (RCCE) awareness was conducted in several locations including those targeted under the project. The project utilized print media that were developed by the PNG National Department of Health and WHO in conducting PHHE and RCCE reaching 7,056 individuals (3,237 M and 3,819 F). Solar lighting was installed in seven locations as a protection measure, especially for women and girls, when accessing the latrines during the dark. A monitoring visit to Kungim health facility found out that the solar power system installed through this project is also used as back-up power for the small fridge used to store vaccines. As part of the UN’s COVID-19 response in Western Province, the project supplied collapsible water containers (120), two-man tents (30) and sleeping bags (30) to the PNG Defence Force Forward Operating Base responsible for monitoring points of entry along PNG’s Western Border. Bahasa language RCCE was also delivered to 149 Indonesian refugees.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | For the nutrition component: • Direct beneficiaries: - Children aged 6-59 months: 9,469 (52% female) - Women: 3,993 • Indirect beneficiaries: - Community members: 5,915 (56% female) - Children under five years treated of moderate acute malnutrition: 1,767 Cumulatively, a total of 17,402 direct beneficiaries were reached with various nutrition services against a cumulative programme target of 11,700 people. A further 7,862 indirect beneficiaries were reached by the project and comprised of; 1,767 children with moderate acute malnutrition who were treated through the project, noting that this is not captured in the project results framework whereas, 5,915 (male 2,574 and female 3,341) community members were reached with COVID-19 related messaging. For the Maternal and Newborn Health component: • Direct beneficiaries: - 50 Village Health Volunteers and 32 Health Care Workers - Seven Health facilities and 6,610 ccommunity members - 829 pregnant and post-partum women - 104 newborns For the WASH component: • Direct beneficiaries: - 6,243 individuals (3,722 M and 2,521 F) with improved access to clean and safe drinking water. - 9,080 individuals (4,681 M and 4,399 F) with improved access to decent sanitation. - 20 individuals (16M and 4F): Water Point Minders. - 7,056 individuals (3,237 M and 3,819 F) reached through PHHE and RCCE awareness. - 61 individuals (51M and 10F) equipped with skills and knowledge on Water Point Maintenance. -1,203 households (approximately 8,060 [individuals (4,148 M and 3,912 F]) received soaps and water containers. • Indirect beneficiaries: - 21,9013 individuals who access the identified health facilities through referrals. - At least 2,400 individuals (travellers) on a monthly basis that use Kiunga airport.
3.1 | Results: Outcome Level | Please include outcome level results achieved | As a result of this joint UN intervention in the Western Province of Papua New Guinea: lives of mothers and newborns were saved through trained health professionals and increased supplies and equipment for Maternal and Newborn Health; lives of children with Severe Acute Malnutrition (SAM) were saved as a result of enhanced nutrition status following availability of treatment services; and health and hygiene in eight target locations improved through Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE). Towards achieving the project outcome, the nutrition component focused on providing critical and lifesaving services for the care of children with SAM. A total of 172 out of the 215 children (45% female) admitted were cured, thereby exceeding the planned target of 150 children. This is a notable achievement because if left untreated, SAM results in an increased risk of death of up to 12 times (Olofin et al 2013), compared to non-malnourished children, while 12 per cent of overall childhood mortality is attributable to wasting (Lancet 2013). Additionally, the project provided other promotive and preventive interventions that included micronutrient supplementation and nutrition education. These interventions are critical in enhancing the attainment of optimal nutrition status among individuals in the immediate and long term. The Maternal and Newborn Health (MNH) component focused on safe deliveries through antenatal and postnatal care in the seven target locations, towards increased deliveries in a health facility. The proportion of births delivered in a health facility increased to 64 per cent against the planned target of 62 per cent. The capacity building interventions for health workers, improved health facilities and services, and awareness creation among communities on the importance of delivery in a health facility, newborn care, and family planning have helped in the achievement of this outcome. A total of 829 pregnant and nursing mothers were referred to and received antenatal, maternity, and postnatal care at health facilities. Also, 104 newborns were delivered and provided with neonatal care during the reporting period. As a result of the WASH interventions, a total of 6,243 and 9,080 individuals have improved access to clean and safe drinking water supply and decent sanitation respectively, improving the health status of the beneficiaries and mitigating the negative impacts of COVID-19. There is an enhanced level of awareness among communities on COVID-19 mitigation and safe hygiene practices as a result of the complementary Participatory Health and Hygiene Education (PHHE) awareness raising and Risk Communication and Community Engagement (RCCE) that were conducted in the eight target locations. Installing solar lighting has improved the safety, especially of women and girls, when accessing the latrines during the dark.
3.2 | Results: Output Level | Please include output level results achieved | The Nutrition component fully achieved and exceeded the expected project results: • A total of 172 (45% female) children were admitted, treated, and cured of Severe Acute Malnutrition (SAM) against a target of 150 (Indicator 1. 1.1). • 9,469 children aged 6-59 months (52% female) received Vitamin A supplementation against a target of 1,500 people (Indicator 1.1.2.a). • A total of 3,725 (male 1,951 and female 1,774) children under five years received Micronutrient Powder supplementation against a target of 1,500 (Indicator 1.1.2.b). • 3,272 (male 1,492 and female 1,780) caregivers of children aged 0-23 months received Infant and Young Child Feeding (IYCF) counselling against a project target of 1,500 (Indicator 1.2.1). • A total of 215 (male 118 and female 97) children were admitted and treated of SAM against a target of 150 Indicator 1.2.2). • A total of 3,993 pregnant and lactating women received nutrition education against a target of 2,000 people (Output 1.2.1.c). • 5,915 (male 2,574 and female 3,341) community members have been reached with COVID-19 related messaging against a target of 1,000 (Output 1.2.1.d) (Indirect) The nutrition education activity aimed at improving the awareness of and enhancing care giver knowledge on appropriate childcare and feeding practices. To this end, a total of 7,265 caregivers comprised of mostly mothers of children aged 6 – 23 months were reached with counselling on appropriate child feeding practices. The caregivers gained specific skills and knowledge on maternal and child nutrition and are expected to apply this in caring for their children. Sub optimal child feeding practices especially during the complementary feeding period is a key driver of undernutrition among children within this age cohort. The project enhanced the technical capacities of 62 Village Health Volunteers (VHVs) and 43 health care workers (51% females) who were trained on three broad areas of nutrition, including treatment of SAM, micronutrient supplementation as well as on support and promotion of appropriate child feeding. Additionally, 5,915 individuals in the target geographical area were reached with COVID-19 related messages specifically focused on infection prevention and control. Under the Maternal and Newborn Health (MNH) component, the following results were achieved in the seven target communities: • 829 pregnant and postpartum women received antenatal and postnatal care at health facilities and through home visits. • 104 newborns were delivered and provided with neonatal care. • 62 healthcare providers whose capacities were built to provide quality Maternity and neonatal care with adequate IPC measures. • 6,610 community members were reached with information on COVID-19, danger signs in pregnancy, the importance of delivery in a health facility, newborn care, and family planning. • Emergency transport system established for prompt transport of pregnant, postpartum women and newborn for advanced care. The resultant skills from the training provided to health workers were immediately put to use in saving a woman from death who had delivered three weeks before the training and was bleeding but could not get to the hospital immediately because of transport restrictions. The trained health worker applied the non-pneumatic antishock garment, and the heart failure and shock the woman experienced was reversed. Another trained health worker prevented the death of a mother and her triplets through the administration of Magnesium Sulphate injection: a skill she had just acquired during the training. Also, the capacity of health facilities and service providers to provide quality MNH services was strengthened through the provision of 400 clean Reproductive Health Delivery kits, six Anti-shock Garments and Mannequins to the six project health facilities and the VHVs, to aid the safe delivery of mothers and newborns particularly in situations of lockdowns and restricted movements. A basket fund has been established for emergency transport of mothers and newborns from rural communities/facilities to the Rumginae referral hospital that is managed by the Rumginae referral hospital management. The renovation of the Matkomnae Sub health centre and Rumginae Rural hospital has been completed to facilitate respectful maternity care services. Following a needs assessment identifying 25 target sites (six health centres/posts, 12 schools and seven other sites) in eight villages for WaSH infrastructure rehabilitation and upgrade, the WASH component achieved the following results: • A total of 6,243 individuals (3,722 M and 2,521 F) now have improved access to clean and safe drinking water against a target of 5,000 individuals. • 9,080 individuals (4,681 M and Female 4,399 F) now have improved access to decent sanitation against a target of 872 individuals. • 20 individuals (16M and 4F): Water Point Minder against a target of 20 individuals • 7,056 individuals (3,237 M and 3,819 F) with PHHE and RCCE awareness against a target of 5,000 individuals • 61 individuals (51M and 10F) were equipped with skills and knowledge on Water Point Maintenance against a target of 60 individuals •1,203 households (approximately 8,060 [individuals (4,148 M and 3,912 F]) received soaps and water containers against a target of 1,000 households (approximately 4,800 individuals) The Participatory Health & Hygiene Education and Risk Communication and Community Engagement awareness raising programs have led to improved hygiene practices thereby, mitigating the spread of COVID-19.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Ø Considering that nutrition service delivery is relatively new within the health care system in PNG, there is limited technical capacity for implementation at both central and local levels. To address this, UNICEF partnered with the CCHS that runs most health facilities in the target geographical area to lead implementation at the local level. To ensure the ownership of implementation and results, as well as seamless integration into the project area, consultations were held involving the National Department of Health (NDoH) and the Western Provincial Health Authority (WPHA), CCHS and UNICEF. The partnership was able to deliver on the project and achieved beyond the programmatic targets. Ø For the UNFPA-implemented MNH component, COVID-19 movement restrictions and total lockdown in the project target province slowed down the implementation of activities. In addition, the difficult terrain and inaccessibility by road also posed challenges in timely implementation of the project. To ensure timely implementation of activities, high-level engagement with the National Department of Health, the Provincial and District Health administrators for travel restriction exemptions was deployed while adhering to COVID-19 measures. Project staff were also deployed additional days ahead of start of implementation of activities to avoid implementation delays. Ø For the WASH component, the main challenge was accessibility in reaching the project locations. Two remote inland communities originally targeted along the Alice river could not be reached as river waters levels fell too low to navigate owing to lack of rain and were otherwise inaccessible by alternative land routes. Given this reality, IOM identified two other villages in the same local government administration with similar needs that were accessible to include in the project delivery. Limited access to and availability of stocks and supplies that were on backorder from the local vendors delayed procurement of supplies needed to complete WASH infrastructure projects in planned timeframes. To minimize delays, IOM procured some items from Port Moresby and delivered them by airfreight. Furthermore, mobilizing community involvement for site preparation was another challenge as communities were expecting to be paid for participating in their own community development. At one of the target locations, Kungim, installation of the water point was delayed because of nil stock of power cables from the service provider. To address this, the project paid for the cables on back-order to ensure the completion of the project. Through support and engagement of church and government partners, communities began to embrace ownership over the positive community development aspects of project initiatives and now embrace their role in both planning and participating in efforts to improve WASH infrastructure and maintenance.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Ø Partnerships with civil society organizations (CSOs) are effective in programme delivery and in the achievement of set targets in the area of nutrition. The collaboration between UNICEF and CCHS in Kiunga was the key driver in the timely roll out of nutrition services and in the achievement of programmatic targets and results. Ø The engagement of Village Health Volunteers (VHVs) in nutrition promotion and community mobilization is effective in achieving scale. This was exemplified in the project whereby VHVs were trained and deployed to provide nutrition promotion messaging as well as IPC awareness raising on COVID-19 through home visits and other community engagement approaches. Ø There must be consistent advocacy with Government and engagement with private partners for the provision of emergency transport for mothers and babies in situations when transport restrictions are necessary including in pandemics if maternal and newborn deaths are to be avoided. Ø Expanding access to information and services to the rural, disadvantaged, and hard to reach communities and not just to the urban population is critical in mitigating community spread of COVID-19 and reducing maternal and newborn mortality.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Ø Partnerships with civil society organizations (CSOs): This has proven to be effective in programme delivery and in the achievement of set targets across the three project components as IOM, UNICEF and UNFPA had all partnered with the Church Groups. Under the nutrition component, the new collaboration between UNICEF and CCHS in Kiunga was the key driver in the timely roll out of nutrition services and in the achievement of programmatic targets and results. This partnership can be an opportunity to catalyze future nutrition work in geographic areas where there are service gaps. In addition, strong working relationship and partnerships were ensured between UNICEF and NDoH at central level and WPHA, as well as with other UN agencies involved in the implementation of the project. UNICEF provided its implementing partners with technical support during trainings and field level implementation, Information, Education and Communication materials as well as monitoring to enable them deliver on the project activities. For the WASH component, IOM partnered with the Church groups that were instrumental in facilitating access for project staff and local government officials to remote communities and to overcome community reservations, misunderstandings and apprehensions around COVID-19, that were addressed in RCCE. Church group partners familiarity with target communities helped to overcome engagement challenges and ultimately led to joint collaboration between project staff, church representatives and local government on RCCE and PHHE practices, particularly with regard to promoting the government’s “new normal” guidance around social distancing, wearing of masks, washing of hands with soap and water, etc. The Catholic church also assisted with logistical support to the Provincial Disaster Office and project staff through providing free storage space for COVID-19 relief items. UNFPA developed partnerships with the Church groups in North Fly District to ensure continued provision of MNH services despite lockdowns and movement restrictions. Ø Partnership with private organizations: The MNH programme has catalyzed a strong partnership with the OK Tedi Mining company and Digicel Telecom company in facilitating emergency transport for mothers and newborns from border communities and health facilities to the referral obstetric hospital in Rumginae. The basket fund under the MNH Project is used to provide funding for fuelling of the OK Tedi chopper, and Digicel procured ambulance. The OK Tedi Mining also partnered with IOM on the WASH component whereby, it provided the local government with free airlift of supplies into remote locations; especially in relation to supporting Western Papuan refugees accommodated in Western Province. Ø Partnership with local authorities: Vibrant partnerships were created with the Provincial Government, Health Authority and North Fly District Health Office. This led to smooth travel approvals for project staff even in the midst of lockdowns and strict movements in the province, as the activities were deemed essential, lifesaving and critical by the Government.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNICEF participated in multi-agency assessment of the situation of Indonesian refugees in Western Province who have settled in the same geographic area as the project. The findings informed recommendations on key actions to support the 149 refugees. UNICEF provided technical assistance in the assessment of nutrition needs of the refugees as well as in the development of a food basket. The assessment formed the foundation for advocacy and solicitation of support to address the needs of the refugees. The food basket is being used by the Food and Agricultural Organization to provide a balanced food ration to the refugees. Participating in the same assessment, IOM made recommendations for relocation site planning, constructed WASH facilities (6 pit latrines, 6 shower blocks, 4 water taps and installed three flood lights (supported by UNHCR funds).
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | As indicated in the project’s midterm report under the nutrition component, the implementation strategy was changed due to the capacity limitations faced by the WPHA to implement. This was mitigated by engaging CCHS to strengthen service delivery.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Additional resources were mobilized under UNFPA's Emergency Fund through the Asia pacific Regional Office. A project officer located within the project communities was engaged to manage project activities. The additional funding was used to complement i) the capacity building of maternity and sexual and reproductive health service providers in the province through facilitating remote learning by providing tablets with Safe Delivery Applications and Solar chargers and projectors; ii) building the capacities of these service providers on Clinical Management of Rape and Minimum Initial Service Package for SRH and GBV in emergencies and iii) addressing gender-based violence issues in the project area including health / clinical response to GBV and provision of Dignity Kits to women of reproductive age in the communities served. IOM coordinated with donor of existing DRR programme to allocate prepositioned soap to supplement water buckets distributed to 149 refugees in complement to PHHE efforts.

## RBM-Final
Indicators |  | Achieved Indicator Targets - Annual | Achieved Indicator Targets - Final | Reasons for Variance with Planned Target (if any) | Source of Verification
OUTCOME: Western Province Border communities that are most vulnerable/left behind and at-risk of the COVID-19 outbreak in PNG continue to have to access critical, life-saving services to ensure progress towards the achievement of sustainable development priorities/goals remains on track
Indicator:1.1a
Number of children aged 6-59 months with severe acute malnutrition who were admitted for treatment and cured (SDG Target 2.2)
Baseline: | 0
Planned Target: | 150 | 172 | 172 | Target achieved in 2020 | Administrative data
Indicator: 1.1b
Proportion of births delivered in a health facility (SDG Target 3.1)
Baseline: | 58%
Planned Target: | 62% | 64% | 64% | Target achieved in 2020 | Post-assistance monitoring
Indicator: 1.1c
Number of people from vulnerable communities who have improved access to, and are utilizing, safe drinking water sources and sanitation facilities (SDG Target 6.2)
Baseline: | 0
Planned Target: | 5000 | 7123 | 6,243 individuals (M=3,722; F=2,521) | Over 13,366 people from 7 beneficiary locations i.e.., Yenkanae, Matkomnai, Iogi, Dome, Rumginae, Sinmrae & St. Gabriel Technical Secondary School now have improved access to and are utilizing safe drinking WaSH | Internal report- (Field activity reports and field monitoring reports) yet to published online. WASH cluster sitrep
Output 1.1.1: Government, service providers and community stakeholders continue to implement critical basic WASH, nutrition and MNH services according to standards at all times in border communities, that are not covered by the national/sub-national COVID-19 response and reach vulnerable and disadvantaged border communities, specifically women and girls of reproductive age (duty bearers)
Indicator 1.1.1a: Number of children aged 6-59 months who received:
(a) Vitamin A supplements
(b) Multiple Micronutrient Powder
Baseline: | a: 0; b: 0
Planned Target: | a:1500; b: 1500 | a: 9469; b: 3725 | a: 9469; b: 3725 | Target achieved in 2020 | Administrative data
Indicator 1.1.1b: Number of pregnant and postpartum women who received antenatal and postnatal care at health facilities and through home visits
Baseline: | 0
Planned Target: | 700 | 829 | 829 | Target achieved in 2020 | Facility, home visits and monitoring reports
Indicator 1.1.1c: Number of Healthcare providers whose capacities are built to provide quality Maternity and neonatal care with adequate IPC measures
Baseline: | 0
Planned Target: | 50 | 62 | 62 | Target achieved in 2020 | Training and monitoring reports
Indicator 1.1.1d: Emergency transport system established for prompt transport of pregnant, postpartum women and newborn for advanced care
Baseline: | No
Planned Target: | Yes | Yes | Yes | Target achieved in 2020 | Monitoring reports
Indicator 1.1.1e: Number of people with increased access to installed and/or rehabilitated water points
Baseline: | 0
Planned Target: | 5000 | ongoing | 6,243 individuals (M=3,722; F=2,521) | Target achieved at end of project | Field Activity and Monitoring Reports
Indicator 1.1.1f: Number of households with increased access to installed and/or rehabilitated pit latrines
Baseline: | 0
Planned Target: | 200 | ongoing | 9,080 individuals (M=4,681; F= 4,399) | Target achieved at end of project. Field WASH assessments identified Health facilities and Schools that were in critical need of sanitation and these facilities were targeted under the project. | Field Activity and Monitoring Reports
Indicator 1.1.1g: Number of water point minders to ensure quality and functioning is maintained
Baseline: | 0
Planned Target: | 20 | ongoing | 20 | Target achieved at end of project | Field Activity Report
Output 1.2.1: Caregivers, family members, women of reproductive age, and communities have improved knowledge of improved feeding/nutrition, WASH, and maternal and newborn caring practices and to seek quality services, especially in groups that are the most vulnerable and disadvantaged
Indicator 1.2.1a: Number of primary caregivers of children aged 0-23 months who received IYCF counselling through facilities and community platforms
Baseline: | 0
Planned Target: | 1500 | 3272 |  | Target achieved in 2020 | Administrative data
Indicator 1.2.1b: Number of children aged 6-59 months with severe acute malnutrition who are admitted for treatment
Baseline: | 0
Planned Target: | 200 | 215 |  | Target achieved in 2020 | Administrative data
Indicator 1.2.1c: Number of pregnant and lactating women receiving nutrition education including infant and young child feeding practices
Baseline: | 0
Planned Target: | 2000 | 3993 |  | Target achieved in 2020 | Administrative data
Indicator 1.2.1d: Number of adolescents receiving nutrition education
Baseline: | 0
Planned Target: | 1000 | 5915 |  | Target achieved in 2020 | Administrative data
Indicator 1.2.1e: Number of community members provided with information on pregnancy, delivery, and COVID-19 infection prevention
Baseline: | 0
Planned Target: | 6000 | 6610 |  | Target achieved in 2020
Indicator 1.2.1f: Number of people reached with PHHE/RCCE Awareness
Baseline: | 0
Planned Target: | 5000 | 2112 (993M; 1218F) | 7,056 individuals (M=3,237; F= 3,819) | Target achieved at end of project | Field Activity Report
Indicator 1.2.1g: Number of community members participating in functioning water user committees (gender parity)
Baseline: | 0
Planned Target: | 60 | ongoing | 61 (M=51; F= 10) | Target achieved at end of project | Field Activity Report
Indicator 1.2.1h: Number of households receiving WASH supplies (soap and water containers or budgets with lids)
Baseline: | 0
Planned Target: | 1000 | Ongoing | 1,203 households | Target achieved at end of project. The intervention was informed by field missions and identified people in need of WASH support. | Field Activity and Monitoring Reports
Please include all three: Baseline, Planned Target, and Achieved Targets

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
https://www.looppng.com/png-news/kiunga-airport-receives-improved-sanitation-amidst-surge-covid-19-cases-99041?fbclid=IwAR3brxjv5rBchZhd9FgtQRZcKeO09yxlVKGoSD5Oggr-cdtvcF3GAJOphTU
https://papuanewguinea.un.org/en/124540-iom-supports-rehabilitation-safe-drinking-water-supply-system-st-gabriel-technical-secondary?fbclid=IwAR3OmLcsRJM73fVF53f_eJ2uBrp9Wjn7shWQphdy1jrVSGrgsHSEVdiXPS8
https://papuanewguinea.un.org/en/111446-minds-every-person-along-alice-river-need-road-accessibility-delivering-development-western?fbclid=IwAR32EYJl9nvlNSNpl7O2Gy2Ne3GQ17bQKTNoHNOMh9_dHAG60g3VW8EF0-Y
UNFPA Supports the Renovation of Labour and Post Natal Wards
UNFPA supports the Transportation of People to Health Centers
UNFPA Supports the Renovation of Labour and Post Natal Wards (Launch Promo)
Matkomnai photos
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
IOM installing clean and safe drinking water supply system.
© Thomas Mek/ IOM
Latrine rehabilitation works with the support of IOM.
© Philip Nere/ IOM
IOM delivering WASH NFIs © Philip Nere/ IOM
Old sanitation facility before rehabilitation by IOM.
© Philip Nere/ IOM
Beneficiaries wash hands at the newly installed water point. © Philip Nere/ IOM
IOM delivering PHHE and RCCE in Western province
© Philip Nere/ IOM
Local community members installing VIP latrine in one of the target locations. © IOM/ Philip Nere
Rehabilitation of the water reservoir. © IOM/ Philip Nere