## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Immediate UN Response for coherent safeguarding the livelihoods of people made most vulnerable by COVID-19 in Nepal | Overall Duration (months) | 7
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 21.05.2020
MPTF Office Project Reference Number: | 121738 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Nepal | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | International Labour Organization (ILO) International Organization for Migration (IOM) United Nations Development Programme (UNDP) United Nations Educational, Scientific and Cultural Organization (UNESCO) | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Labour, Employment and Social Security (MoLESS); Ministry of Education, Science and Technology (MoEST); Ministry of Industry, Commerce and Supplies (MoICS), Nepal Tourism Board (NTB), Province and Local Governments, Infrastructure Development Offices (IDOs); Employment Service Centers (ESCs), The Council for Technical Education and Vocational Training (CTEVT)-certified training institutes and trainers, Sanothimi Technical School, Community Learning Centers, Partner NGOs
Report Cleared By
o Name: | Sara Beysolow Nyanti
o Title: | Resident Coordinator
o Email address: | sara.nyanti@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Since its initiation in June 2020, the Immediate UN Response for coherent safeguarding the livelihoods of people made most vulnerable by COVID-19 in Nepal Project (‘Project’ hereafter) has contributed to mitigating the socio-economic impacts of COVID-19 and safeguarded livelihoods of Nepalis made most vulnerable by the crisis. The project has directly benefitted a total of 2,812 beneficiaries, out of which 1,411 (50.2%) were women and at least 1,799 (64%) were from marginalized groups, including 1,000 Janajati (indigenous ethnic groups) (35.6%) and 786 (26%) Dalits. With this, the project has well exceeded the anticipated targets. Contributing to Global SERF Indicator 3.2, the project has complement and addressed gaps in the Government of Nepal’s recovery programme. First, the project has complemented the government's strategy to provide employment to vulnerable groups through for example regular maintenance of rural road networks or cash for work in the tourism sector. Second, it has targetted traditionally vulnerable groups whose vulnerabilities have been further compounded by COVID-19 measures. It has built on tested project interventions but modifying the targeting and implementation methods to the COVID-19 circumstances and its foreseen consequences. Implementing complementary initiatives for information and awareness-raising has been a health necessity, but has also been undertaken to clarify and address the high prevalence of rumours and misinformation concerning COVID-19. The UN agencies implementing the project recognize that addressing the socio-economic impacts of COVID-19 requires new solutions. Nevertheless, given the importance of providing immediate support to the most vulnerable and marginalized people and groups, the Project has also built on existing good practices, interventions and methods of working, making necessary adaptations to the current context. Thus, the Project has built on a range of scalable, tested interventions and existing programmes/projects relevant to different target populations. These interventions have been adjusted to meet the needs arising from the new context, with some new methodologies and methods of working. The project, in many cases, also made use of existing public sector systems for more rapid implementation and future scalability. The four implementing UN agencies in Nepal included the International Labour Organization (ILO), the International Organization for Migration (IOM), the United Nations Development Programme (UNDP) and the United Nations Educational, Scientific and Cultural Organization (UNESCO). ILO provided support to rural road maintenance work. IOM provided immediate cash assistance and recovery support to vulnerable migrant workers. UNDP supported entrepreneurship development and job creation for the most vulnerable groups, as well as short-term employment in the hard-hit tourism sector. UNESCO supported the most vulnerable groups in vocational and skills trainings. Implementation of the project during the COVID-19 pandemic presented multiple logistical and health-related challenges, including related to restrictions on travels and large gatherings. However, with an increased number of virtual meetings with implementing partners and key stakeholders, increased number of training opportunities, each with fewer participants, and strict health and safety protocols in place, the participating UN agencies successfully and timely implemented all project components. The strong partnerships between UN agencies and government agencies at all three levels, and civil society organizations significantly contributed to the success.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The project reached a total of 2,812 direct beneficiaries, out of which 1,411 (50.2%) were women and at least 1,799 (64%) were from marginalized groups, including 1,000 Janajati (indigenous ethnic groups) (35.6%) and 786 (26%) Dalits. The beneficiaries included 737 (26.2%) youth (aged 18-29), 1,401 (49.8%) persons agead 30 – 44, and 424 (15.1%) persons agead 45 or above. The below tables provides further details on the numbers and shares of beneficiaries for different project components.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Since its initiation in June 2020, the Immediate UN Response for coherent safeguarding the livelihoods of people made most vulnerable by COVID-19 in Nepal Project (‘Project’ hereafter) has contributed to mitigating the socio-economic impacts of COVID-19 and safeguarded livelihoods of Nepalis made most vulnerable by the crisis. In sum, the project has directly benefitted a total of 2,812 beneficiaries, out of which 1,411 (50.2%) were women and at least 1,799 (64%) were from marginalized groups, including 1,000 Janajati (indigenous ethnic groups) (35.6%) and 786 (26%) Dalits. The beneficiaries included 737 (26.2%) youth (aged 18-29), 1,401 (49.8%) persons agead 30 – 44, and 424 (15.1%) persons agead 45 or above. The project has well exceeded the outcome indicator targets for which data is already available. The number of project beneficiaries who were employed and have earned at the least the national minimum wage (Nrs. 13,500 ≈ US$ 115) for three months reached a total of 2,562 (1,230 women – 48%; and 1,588 from disadvantaged groups – 62%; 22.9% youth), compared to the original target of 1,030 persons. This has significantly contributed to mitigating the negative socio-economic impact of the COVID-19 crisis for the project beneficiaries and their families by providing urgent relief, in particular to returning migrants, women and the most vulnerable groups, including workers in the hard hit tourism sector. The employment generated through the project also contributed to counter local economic shocks, aid in initial recovery efforts, develop vital local infrastructure through road and tourist site maintenance, and offer avenues to sustainable livelihood opportunities. Similarly, the employment rate after two months of completing vocational and skills training to 244 direct project beneficiaries provided by the Council for Technical Education and Vocational Training (CTEVT), with support from UNESCO, was estimated at 58% as of 31 December 2020, compared to the original target of 50%. Initial results show that the employment rate is relatively high for the participants in trainings on construction work, masonry, electrification, plumbing, off-seasonal vegetable farming and animal health worker trades. For the employment of remaining training participants, the respective local governments have demonstrated their commitments to ensure provision of employment by exploring local opportunities. UNESCO will also continue to do necessary follow-up in the first trimester of 2021 under its regular programming.
3.2 | Results: Output Level | Please include output level results achieved | As a result of the project support, informal workers and returnee migrants in project areas have more sustainable income sources. This is a result of the project support provided by UNDP and IOM to create a total of 1,036 enterprises (510 women-led – 49.2%; 57.6% by disadvantaged groups; 29% by youth) new enterprises and businesses at the local level through dedicated trainings and start-up financial support, exceeding the original target of 1,000 (33% women-led). Furthermore, the project ensured that a total of 2,812 persons (1,426 women, 50.7%) participated in activities implemented to boost employment and income at the local level. Among them, at least 1,322 (47%) were from marginalized groups, including 836 Janajati (indigenous ethnic groups) (29.7%) and 486 (17.2%) Dalits. Employment and income generating activities included a wide range of locally suitable options, ranging from organic farming to rural road maintenance and covered all of Nepal’s seven provinces. Among these, immediate cash support of approximately USD 115 (NPR 13,500) was distributed to 250 (72.4% women, 79.2% disadvantaged groups; 37.6% youth) vulnerable returnee migrants through different NGOs shelters in Kathmandu Valley, Bagmati Province. Of the total number of returnee migrants supported, 35 % were undocumented, 23 % irregular and 42 % were in a stranded condition. The cash support was provided to support their further travels to home districts from Kathmandu, as well as for immediate food, accommodation and personal hygiene needs before and after they reached their intended destinations. Recovery assistance of USD 350 per person (equal to three months of minimum salary) was piloted with 410 (40% women, 64% disadvantaged groups, 34.9% youth) returnee migrants made increasingly vulnerable due to the COVID-19 pandemic in three municipalities of Province 1. The support was directed towards initiation of self-employment and entrepreneurship among the beneficiaries, and included orientations to the beneficiaires of different support schemes, financial literacy trainings, entrepreneurship development trainings, opening of bank accounts and provision of collateral free, low-interest loans from commercial banks, which some participants have already benefitted from. In addition, an employer mapping was conducted to identify small-, medium- and large scale enterprises in Province 1 which required additional employees in various capacities. The mapping highlighted the skills required by the enterprises aiming to incentivise returnee migrants to join local businesses, including machine operators, general workers, cooks, agricultural workers and health workers. The demand for workers in the domestic enterprises seems lower due to the COVID-19 pandemic as a number of industries and enterprises have been either shut down or are reducing their productions. The mapping also highlighted that many employers noted a reluctance to recruit returnee migrant workers due to skill gaps and high salary demands. Further, a total of 244 persons (49.6% women, 60% from excluded groups, 64.3% youth) have completed different technical and vocational trainings provided by UNESCO. These included training related to off-season vegetable farming, electricians, cooking, tailoring, animal health, plumbing, embroidery, masonry, mushroom farming, dry food production, carpentry, and mobile phone repairing. The employment rate after two months of completing the trainings was estimated at 58% as of 31 December 2020, compared to the original target of 50%. The project also supported trainings and establishment of 626 micro-enterprises (346 women-led; 53.3% by disadvantaged groups; 25.1% by youth), which has created a total of 1,129 jobs, following support provided by UNDP in partnership with the District Micro-Enterprises Group Association (DMEGA) in Karnali and Sudurpaschim Provinces. Additionally, UNDP support to vulnerable workers in the tourism sector resulted in the creation of 250 (87 women) short-term employment opportunities in waste management, cleaning and maintenance of trekking trails and other important tourism sites in Province 1, Province 2 and Gandaki Province. The rural road maintenance work carried out by the ILO generated 529 (338 women – 63.9%; 404 from disadvantaged groups – 76.3%; and 41 youth – 7.8%) short-term employment opportunities for road maintenance workers in Province 2 and Lumbini Province. In addition to providing immediate livelihoods support and income generation, this component also contributed to improve all-weather accessibility of rural roads in the project areas, as well as enhanced capacity of the provincial Ministries of Physical Infrastructure Development and Infrastructure Development Offices related to occupational health and safety and performance related wage payment systems.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The GoN, as well as district and local governments, enforced multiple complete or partial lockdowns, prohibitory orders, and restrictions on mobility and large gatherings to slow the spread of COVID-19 during the project period. This resulted in multiple challenges encountered during project implementation. Travels to project municipalities, for coordination with local governments, beneficiary selection, monitoring of implementation, and communications support has been limited since the project start. To address this, the UN agencies relied heavily on local implementing partners, Field Offices and local coordinators and mobilizers, all strictly following established government protocols. The UN agencies also held regular virtual meetings with project stakeholders, including implementing partners and local governments, to provide support and guidance, regularly track implementation, and discuss challenges and needs to safely and effectively implement the project with due consideration for varying local contexts. Additionally, project components were implemented in a phased approach, with initial implementation prioritized in areas with lower prevalence of COVID-19. Implementation of the project during the COVID-19 pandemic also presented health risks, and risk of stigma and anxiety among project beneficiaries, trainers, implementing partners and UN staff. To mitigate these challenges, the participating UN agencies developed and implemented strict health protocols to be followed by all partners and beneficiaries, in line with GoN and WHO guidelines. This included provision of personal protective equipment (PPE) and other relevant safety materials, as well as ensuring regular disinfection of surface areas, physical distancing and other relevant sanitation and safety measures to ensure clean and safe training/working environments. The project also supported awareness raising and counselling for participants. To the extent possible, the UN agencies increased the number of training opportunities, thereby providing the training in small groups. Furthermore, the lengthy lockdowns had severe implications on Nepal’s economy, with many enterprises and offices fully or partially closed for several months. This resulted in challenges for the project implementation, in terms of, for example, mapping of potential future employment opportunities and opening of bank accounts for project beneficiaries. While these issues were resolved, the initiatives took significantly longer time to complete as compared to during normal times. Throughout the implementation, the UN agencies have noted a lack of coordinated COVID-19 crisis response at the local level. Although resources are available and can be leveraged, lack of coordination and communication between various stakeholders has made the response more complicated and less effective, especially in terms of identifying and reaching those most in need of urgent support. To mitigate this challenge, the UN agencies have engaged in regular dialogue with the local governments and other key stakeholders, including NGOs, private sector actors, financial institutions, for example in support of entrepreneurship and job creation. Coordination with local governments has also been important in beneficiary selection, to ensure that the project reach the most vulnerable and severely affected people and groups. Coordination with labour unions for support to vulnerable workers in the tourism sector, facilitated by the Nepal Tourism Board, was also vital to ensure ownership and support of the project.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The evolving and unpredictable COVID-19 context forced the implementing UN agencies to remain flexible and open to learning and changes in the project implementation. Among the key learnings is the need for coordination support to local governments in developing and implementing comprehensive and sustainable job creation and livelihoods support plans, with focus on the most vulnerable and marginalized groups and utilization of local resources and assets. Given the large number of Nepali domestic and foreign migrants returning from their work destinations, the local governments must also consider the sustainable and inclusive reintegration of returnee migrants in the local economies and societies. In the current context, it has also proven even more essential to ensure community ownership and participation and to enhance collaboration and partnerships with non-government actors, including NGOs, the private sector and development agencies for a coordinated response to COVID-19. Coordination between all levels of government and non-state actors has also been vital to ensure contextually relevant response initiatives. Strengthened partnerships will also support the continuation of project initiatives as local level resources, organisations and companies can build on good practices implemented. In addition, given the need to provide immediate support, it has proven fruitful during project planning and implementation to build on existing initiatives, such as ongoing entrepreneurship support and rural road maintenance. Project partners and beneficiaries have also expressed the need for further sustained support, in particular focusing on the livelihoods of the most vulnerable and marginalized groups, as the socio-economic impacts of the COVID-19 crisis will be pro-longed. For example, based on the initial learnings, the short-term vocational trainings provided have been instrumental to establish showcase initiatives for sustainable livelihood development of vulnerable people with alternative solutions for local employability and entrepreneurship. Here, the project has demonstrated its significance in reducing the negative socio-economic impacts of COVID-19, particularly for women and marginalized people. Initial result indicated that the short term vocational skills trainings are not only a game changer for improved livelihoods of beneficiaries, but also contributory in fulfilling skills requirements at the local level.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Throughout project implementation, the UN agencies have further strengthened existing partnerships with the federal GoN, including key agencies such as the Ministry of Labour, Employment and Social Security (MoLESS), Ministry of Physical Infrastructure and Transport (MoPIT), Ministry of Industry, Commerce and Supplies (MoICS), Ministry of Education, Science and Technology (MoEST), the CTEVT, and the Nepal Tourism Board (NTB). Initiation of the partnership with NTB has led to further discussions on establishing a partnership between NTB and UNDP for long-term sustainable revival of Nepal’s tourism sector. Further, the UN agencies have strengthened partnerships with the provincial and local governments in the project areas, including relevant provincial level ministries. In close coordination with the partnering local governments, the UN agencies are exploring opportunities for further employment of trained project beneficiaries, beyond the end of the project, for example through the nation-wide, Government-run Prime Minister’s Employment Programme and other local employment opportunities. Partnerships have also been established with private sector actors and banks to facilitate access to bank accounts, provide financial literacy trainings and collateral-free loans, and guarantees to buy products produced by the newly trained entrepreneurs. Throughout project implementation, the UN agencies have worked closely with a number of partner NGOs, all in coordination with the respective local governments and groups representing the most vulnerable and marginalized groups, including returnee migrants and women’s groups and networks. Similarly, the project has partnered with the District Micro Entrepreneurship Group Association of Nepal (D-MEGA) in Karnali and Sudurpaschim Provinces, building on ongoing programming implemented jointly between the GoN and UN. These partnerships have contributed to strengthening institutional synergies among key stakeholders supporting the COVID-19 response at the local level, as well as long-term sustainability of the initiatives. The activities under this project are in line with and have informed the priorities of the UN Framework for Responding to the Socio-Economic Impacts of COVID-19 in Nepal, in particular under Pillar 3: Economic Response and Recovery. The Framework will guide the UN’s socio-economic response efforts, initially for an 18-months period (until December 2021). The Framework, as well as the MPTF-funded project, is directly in line with the GoN’s COVID-19 socio-economic response priorities, with a heavy emphasis on job creation, green recovery and skills development of the most vulnerable and marginalized groups, including returnee migrants, women and youth.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Not yet applicable as evaluations of the project components have not yet been undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | As highlighted in previous sections, adjustments of implementation timelines were made necessary to adapt to the evolving COVID-19 crisis in Nepal. While these provided challenges in terms of timely implementation, they did not result in any major adjustments in terms of targets, outcomes or outputs. As a result of local demand and availability of resources, due to lower-than-expected expenditure on monitoring missions and miscellaneous, additional project activities were implemented by UNESCO at the final stage of the project: Employment trade fairs: Utilizing the available project budget, trade fairs were organized at nine local venues in project implementation areas to inform relevant stakeholders and potential future employers about the availability of trained human resources in their locality. Beyond project beneficiaries and implementing partners, the trade fairs were attended by local government officials, local employers, corporate houses, bankers, and community members in the respective areas. Local governments played a key role in designing and implementing the trade fairs, further adding to local ownership. Although it is too early to assess the long-term impacts, this may result in positive change at the outcome level by contributing to contributing to the creation of employment opportunities beyond the project period. 2. Relief material distribution: Beyond the planned support, safety materials, including thermal guns, face masks, sanitizer, soap, towels, and buckets with taps for handwashing were distributed by UNESCO to the training centers at the inception. At the end of the trainings, UNESCO also distributed relief packages (including rice-25 kg, lentils-3 kg, cooking oil-5 litres, and 12 pieces of soap) to the training participants. With this support, 244 people directly, and 1380 family members of the trainees indirectly benefited from immediate relief support. The original target number (250) of people to be provided with short-term employment for the workforce who lost their jobs in the tourism sector was achieved. With the high demand for support at the local level, some of the municipalities in which the project was implemented are continuing with the programme with their own resources after the end to the project period. While this does not necessitate any adjustments in the project strategies or targets, it further adds to the sustainability of the intervention.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources have been mobilized from external partners. However, following repurposing of existing programming budgets, the project benefited from substantial support from the implementing UN agencies’ available human resources and already ongoing programming. ILO repurposed its regular budget to add USD 30,000 to the Project in order to cover the cost of Occupational Safety and Health (OSH) equipment for the 529 maintenance workers and six project engineers. ILO also mobilised government engineers from MoPIT in training the road maintenance workers and monitor the maintenance work. IOM utilized the presence and contact of the Migrant Resource Center to reach the vulnerable migrants and for their screening. Similarly, IOM build on its MoU with Rural Enterprise Remittance Program (RERP) of Ministry of Industry, Commerce and Supplies and its Migrants Resources Centers to execute the program which created synergies in the project implementation. The beneficiaries benefitted from the RERP existing supply chains and market access. UNDP utilized existing programming and staff in support of micro-entrepreneurs, including through the MEDPA programme and partnerships with D-MEGA’s in the project districts. Further, UNDP strengthened its partnership with the Nepal Tourism Board to provide immediate short-term employment support to affected workers in the tourism sector. Similarly, UNESCO engaged existing programming staff in project implementation and utilized its existing partnership with the CTEVT to support effective project implementation.
Compilation and breakdown of beneficiaries
|  |  |  | Agency | Type of support | Total direct beneficiaries | Women (No.) | Women (%) | Men (No.) | Men (%) | Janajati (No.) | Janajati (%) | Dalit No.) | Dalit (%) | Madhesi | Muslim | 18-29 | 18-29 (%) | 30 - 44 | 30-44 (%) | 45 + | 45+ (%)
|  |  |  | IOM | Cash support | 250 | 181 | 72.4% | 69 | 27.6% | 173 | 69.2% | 25 | 10% | 4 | 0 | 94 | 37.6% | 156 | 62.4% | 0 | 0%
[5 empty] | Recovery Assistance | 410 | 164 | 40% | 246 | 60% | 197 | 48% | 62 | 15.1% | 3 | 1 | 143 | 34.9% | 230 | 56.1% | 37 | 9%
|  |  |  | UNESCO | TVET | 244 | 121 | 49.6% | 123 | 50.4% | 107 | 43.9% | 39 | 16% | 40 | 2 | 157 | 64.3% | 74 | 30.3% | 13 | 5.3%
|  |  |  | UNDP | Micro Enterprises | 626 | 346 | 55.3% | 280 | 44.7% | 138 | 22% | 196 | 31.3% |  |  | 157 | 25.1% | 343 | 54.8% | 126 | 20.1%
[5 empty] | Jobs provided through MEs | 1129 | 520 | 47.4% | 609 | 39.7% | 248 | 22% | 370 | 32.8% |  |  | 302 | 26.7% | 613 | 54.3% | 214 | 19%
[5 empty] | Tourism | 250 | 87 | 34.8% | 163 | 65.2% | 134 | 53.6% | 37 | 14.8% |  |  |  | 0% |  | 0% |  | 0%
|  |  |  | ILO | Road construction | 529 | 338 | 63.9% | 191 | 36.1% | 141 | 26.7% | 253 | 47.8% | 270 | 10 | 41 | 7.8% | 328 | 62% | 160 | 30.2%
[6 empty] | 2812 | 1411 | 50.2% | 1401 | 49.8% | 1000 | 35.6% | 786 | 28% | 317 | 13 | 737 | 26.2% | 1401 | 49.8% | 424 | 15.1%

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: Socio-economic impact mitigated and livelihoods safeguarded for Nepalis made most vulnerable by COVID-19 measures |  | N/A | Partners' progress reports (ILO, IOM, UNDP, UNESCO)
Indicator2.1a: Number of households of which at least 33% are female headed households whose financial capital is not depleted by more than 30% (disaggregated by number of female / male headed households)
Baseline: 0 | Data not yet available
Planned Target: At least 80%
Indicator 2.1b: Number of persons, of which at least 33% women, who are employed and have earned at least the national minimum wage (Nrs. 13500 ≈ US$ 115) for three work months by sex, age and ethnic group
Baseline: 0 | 2,562 (48% women; 62% from disadvantaged groups; 643 youth - 22.9%)
Planned target: 1,030
Indicator 2.1c: Employment rate after two months of completing CTEVT training, disaggregated by gender, vulnerability and ethnicity | 58%
Baseline: 0
Planned target: At least 50%
| 1,036 (510 - 49.2% women led; 597 by disadvantaged groups - 57.6%; 300 by youth - 29%) | N/A | Partners' progress reports (IOM, UNDP)
Output 2.1.1 Informal workers and returnee migrants including women have more sustainable income sources
Indicator 2.1.1a: Number of enterprises/ businesses created at local level (disaggregated by type of MSME ownership-male/female), of which at least 33% are run by women
Baseline: 0
Planned Target: 1,000
| 2,812 (1,411 women - 50.2%; 1,626 from disadvantaged groups - 57.8%; 737 youth - 26.2% | N/A | Partners' progress reports (ILO, IOM, UNDP)
Indicator 2.1.1b: Number of people (by age, sex, ethnicity) who participated in activities implemented to boost employment and income, with at least 33% women
Baseline: 0
Planned Target: 1,400
Output 2.2.1 Informal workers, including women, have new skills | 244 (121 women - 49.6% women; 148 from disadvantaged groups - 60.6%; 157 youth - 64.3%) | N/A | Partners' progress reports (UNESCO)
Indicator 2.2.1a Number of persons, including at least 33% women, who completed a CTEVT certificate (disaggregated by sex and other vulnerability factors)
Baseline: 0
Planned Target: 200 (At least 33% women and 40% from disadvantaged communities)
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Prestige and income increased by skill training Jayshankar Yadav belongs to small and poor family. He lives in Janakpur-17, Dhanusha and was a daily wage labour. He already had difficulty to manage his family; COVID-19 further exacerbated the situation and he was under huge stress about how to run family. He had high interest in getting trained as a building electrician, however, considering the financial crisis his family was going through, he was unable to take the training. Due to his high interest, he learnt a few basics from here and there and also used to repair the electrical equipment. Jayshankar was extremely happy to hear about the news of free building electrician training to be provided by UNESCO. After his selection, even the trainer said that he is one of the passionate learner, never missed his classes, and was always an inquisitive one during the practical sessions. Right after two months of training, he had an opportunity to do the house-wiring of two building in Janakpur, with payment of NPR 15000.00, and NPR 18000.00. He was happy to share the news with the trainer and his participant friend. However, he also said that he did not have the tools required to do the job. As he was determined, he was supported and thus, he completed his first job by borrowing some tools from the training and other from his friend. After his first income, he bought some tools. The work opportunity, and the OJT training has helped build his self-confident. He says that training is very useful to individuals like him, as they get certified and people, market trust them; which increases their credibility and provide them further opportunities to earn. Jayshankar now says "People now respect me as a technician and I am proud of my skill". He aims of becoming a renowned building contractor in this market in future.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board