## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Unlocking Cambodian Women’s Potential through Fiscal Space Creation | Overall Duration (months) | 12
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-01-01
MPTF Office Project Reference Number: | 124823 | Original End Date (dd.mm.yyyy) | 2021-12-30
Country | Cambodia | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNCDF UNDP IOM | National counterparts (government, private, NGOs & others) and other International Organizations | MEF CGCC BOC PFIs
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Although the project is within its very early phases of implementation some quick win activities have been implemented that have yielded results. The following summarizes the activities and results to date; (i) organization and implementation of an international dialogue on credit guarantees to support the formulation process of the policy and legal framework for the establishment of the Credit Guarantee Corporation of Cambodia (CGCC), (ii) support to finalize CGCC legal framework and policy, (iii) establishment of the CGCC as a legal entity to support the governments COVID recovery strategy, (iv) support CGCC to develop the operationalization road map to enable credit guarantees to be issued Q2 2021, (v) facilitation of partnership development (Moody's and CGCC) and the introduction of risk management unit and policy and (vi) procurement of IC missions. The key result delivered to date is the legal establishment of the CGCC, the formal government approval of the CGCC policy framework and critical partnership development between the government, neighboring countries CG organizations and the private sector.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Underpinned by the LNOB principle, the objective of the programme is to support the women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement. To do so, the programme will support the RGC to introduce policy and innovative financial solutions in the form of credit guarantee scheme, which has never existed in the country before COVID-19, to provide low-cost and reliable financing to M/SME businesses. It is anticapated that 1000 MSMEs will benefit from from the CG via acceess to new finacial prodcuts being made avalable by the PFIs.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1 - Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement (on-going - 2/12 outputs complete)
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 - Consolidated Review Paper issued to MEF for CGCC Framework COMPLETE Output 1.2 - New regulatory framework for CGCC establishment for CGCC COMPLETE Output 2.4 - Pilot Credit Guarantees - Operationalization Support Ongoing Output 3.1 - Data and Performance Monitoring of CGCC early performance report - Strategic partnership development for the introduction of a risk management system (Moody’s)
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The RIF will be subject to review and ammendment as the speed of the operationalizing CGCC is over-taking the previuolsy designed MPTF intervention. More demand based inputs are emerging from the government as they rapdily develop the CGCC and their first guarantees as a policy priorty for COVID Impact (ie to free up capitial so that existing companies can maintain productove capacity and retain their workforce through partial salary payments - a form of shared extension of the social protection system.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The rapid establishment of the CGCC has been accelerated through the development and consultation of a policy framework that was initially shared and amended by private sector and neighboring countries CGCCs. These professional and peer reviews that bring in best international practice has been a key development driver for CGCC. The project is also bringing in professional solutions to support the CGCC in terms of risk management (Moody's) and capacity building via partnering and arranging staff embeddment with Thai Credit Gurantee as opposed to developing in-house solutions, thus optimizining the projct budget, implemnetation and providning industry standard professional solutions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | From its outset the project has taken a partnership approach to support establishment of the CGCC. This included initial meetings with the development banks (ADB and WB) to establish the division of labor related to the operationalization of the CGCC. This feature will support both the ADB and WB to provide operational capital to the CGCC to compliment the US$ 200 million allocated through the national budget. New partnerships have been forged with the private sector especially in terms of risk management systems with Moody’s analytics and operational support and institutional capacity building support through partnership with Thailand Credit Guarantee
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Investment requirement analysis for Cambodia to retain pre COVID trajectories and regain lost GDP
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Revisons to be made Q2 2021 based on results of survey works
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources mobilized todate

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 0 | on going | CGCC Portfollio
Indicator: Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement
Baseline:0
Planned Target:CGCC Operational 1 min of credit guarantee issued 2021
Output 1.1 support the policy design and the operational roll-out of the credit guarantee facility, which targets the marginalized groups from the first phase of the RGC’s support, particularly the women owned M/SMEs in informal sector. | Consolidated review paper issued | none work completed | Project files / email
Indicator 1.1: Consolidated Review Paper issued to MEF for CGCC Framework (CDF)
Baseline:0
Planned Target: 1
Indicator 1.2: new regulatory framework for CGCC (CDF / UNDP) | CGCC Framework and Law passed, CGCC established under law | none - work completed | CGCC Framwork
Baseline:0
Planned Target:Approved framework and sub decree
Indicator 1.3: Comparative study on how the investment into women owned M/SMEs and/or informal sector could trigger positive ripple effects in Cambodia’s economy (Know Prod) - (UNDP) | Planned Q2
Baseline: 0 |  |  | UNDP Web Site
Planned Target:1
Indicator 1.4: Guidelines for the selection criteria to prioritize the under-supported groups for 1st phase of support, particularly the women owned M/SMEs in informal sector (CDF / UNDP) |  | To revisit Q2 with CCGG
Baseline:0 |  |  | CGCC SOP
Planned Target: SOP
Indicator 1.5: Policy brief - Using fintech to increase women's access to business finance (CDF) | Planned Q3
Baseline:1
Planned Target: Policy Brief |  |  | UNCDF Web Portal
Output 2: Quick action research on women’s economic empowerment (WEE), employment, poverty alleviation and reducing inequality aspects of the credit guarantee scheme
Baseline:0 |  |  | UNDP Web Portal
Planned Target: 1 report
Indicator 2.1: Review paper - existing CGS in the M/SMEs sector in other countries to identify best practices in respect of WEE (Know Prod) - CDF / UNDP
Baseline:0 | ongoing 2021 Q3 | Publication and blogs | UNDCF UNDP web Portals
Planned Target: Knowledge Product CGS and WEE
Indicator 2.2: Rapid survey reach of CGCC to women businesses by sector and geo location (UNDP)
Baseline:0 | Planned Q3/Q4 |  | Survey report
Planned Target: 2 Surveys and research report
Indicator 2.3: Research Paper - gender-specific barriers women face and the gendered impact of COVID-19 from the perspective of WEE. (IOM)
Baseline:0 | on going
Planned Target:1 Publication |  |  | RCO and IOM website
Indicator 2.4: Survey female economic migrants impacted by COVID-19 and lost livelihoods (IOM)
Baseline:0 | on going
Planned Target: 1 Survey and Findings Report Published
Output 3: pilot the credit guarantee schemes with selected women owned M/SMEs (CDF) |  | to review to match fund operations
Indicator 3.1: Pilot Guarantee Roll Out - early impact assessment
Baseline:0 |  | To review scope with CGCC
Planned Target: Short narrative report Beneficaries unknown to be defined through PFI portfollios
Indicator 3.2: Data and Performance Monitoring of CGCC early performance report (UNDP)
Baseline:0 |  | To review and phase to launch of CGCC
Planned Target:1 CG Perfromance Report
Indicator 3.3: Women Business CGCC User Group meetings (UNDP)
Baseline:0 |  | To review and phase to launch of CGCC
Planned Target: 2 Meetings and 2 Blogs
Indicator 3.4: digital platform for accessing information on job opportunities for economic migrant workers, e linking with provincial job centres and women owned M/SMEs (IOM/IFAD)
Baseline:0
Planned Target:(IOM to fill)
Indicator 3.5: Raise awareness rasining events and publications on accessing financing and employment opportunities (IOM)
Baseline:0
Planned Target:2 Blogs, 2 migrant journeys |  | on going | IOM website
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This study should be conducted before the roll out of Phase 1 of CGCC
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I don't understand this. Reply: we have started to work on a joint paper to be completed 2021 Q3 typo on date
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This survey can be conducted after the 1st rollout of CGS by CGCC.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | The UN COVID-19 Response and Recovery Multi Partner Trust Fund. | Overall Duration (months) | 12 Months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 31.12.2021
Country | CAMBODIA | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNCDF UNDP IOM | National counterparts (government, private, NGOs & others) and other International Organizations | MEF CGCC
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 0 | on going | CGCC Portfollio
Indicator: Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement
Baseline:0
Planned Target:CGCC Operational 1 min of credit guarantee issued 2021
Output 1.1 support the policy design and the operational roll-out of the credit guarantee facility, which targets the marginalized groups from the first phase of the RGC’s support, particularly the women owned M/SMEs in informal sector. | Consolidated review paper issued | none work completed | Project files / email
Indicator 1.1: Consolidated Review Paper issued to MEF for CGCC Framework (CDF)
Baseline:0
Planned Target: 1
Indicator 1.2: new regulatory framework for CGCC (CDF / UNDP) | CGCC Framework and Law passed, CGCC established under law | none - work completed | CGCC Framwork
Baseline:0
Planned Target:Approved framework and sub decree
Indicator 1.3: Comparative study on how the investment into women owned M/SMEs and/or informal sector could trigger positive ripple effects in Cambodia’s economy (Know Prod) - (UNDP) | Planned Q2
Baseline: 0 |  |  | UNDP Web Site
Planned Target:1
Indicator 1.4: Guidelines for the selection criteria to prioritize the under-supported groups for 1st phase of support, particularly the women owned M/SMEs in informal sector (CDF / UNDP) |  | To revisit Q2 with CCGG
Baseline:0 |  |  | CGCC SOP
Planned Target: SOP
Indicator 1.5: Policy brief - Using fintech to increase women's access to business finance (CDF) | Planned Q3
Baseline:1
Planned Target: Policy Brief |  |  | UNCDF Web Portal
Output 2: Quick action research on women’s economic empowerment (WEE), employment, poverty alleviation and reducing inequality aspects of the credit guarantee scheme
Baseline:0 |  |  | UNDP Web Portal
Planned Target: 1 report
Indicator 2.1: Review paper - existing CGS in the M/SMEs sector in other countries to identify best practices in respect of WEE (Know Prod) - CDF / UNDP
Baseline:0 | ongoing 2021 Q3 | Publication and blogs | UNDCF UNDP web Portals
Planned Target: Knowledge Product CGS and WEE
Indicator 2.2: Rapid survey reach of CGCC to women businesses by sector and geo location (UNDP)
Baseline:0 | Planned Q3/Q4 |  | Survey report
Planned Target: 2 Surveys and research report
Indicator 2.3: Research Paper - gender-specific barriers women face and the gendered impact of COVID-19 from the perspective of WEE. (IOM)
Baseline:0 | on going
Planned Target:1 Publication |  |  | RCO and IOM website
Indicator 2.4: Survey female economic migrants impacted by COVID-19 and lost livelihoods (IOM)
Baseline:0 | on going
Planned Target: 1 Survey and Findings Report Published
Output 3: pilot the credit guarantee schemes with selected women owned M/SMEs (CDF) |  | to review to match fund operations
Indicator 3.1: Pilot Guarantee Roll Out - early impact assessment
Baseline:0 |  | To review scope with CGCC
Planned Target: Short narrative report Beneficaries unknown to be defined through PFI portfollios
Indicator 3.2: Data and Performance Monitoring of CGCC early performance report (UNDP)
Baseline:0 |  | To review and phase to launch of CGCC
Planned Target:1 CG Perfromance Report
Indicator 3.3: Women Business CGCC User Group meetings (UNDP)
Baseline:0 |  | To review and phase to launch of CGCC
Planned Target: 2 Meetings and 2 Blogs
Indicator 3.4: digital platform for accessing information on job opportunities for economic migrant workers, e linking with provincial job centres and women owned M/SMEs (IOM/IFAD)
Baseline:0
Planned Target:(IOM to fill)
Indicator 3.5: Raise awareness rasining events and publications on accessing financing and employment opportunities (IOM)
Baseline:0
Planned Target:2 Blogs, 2 migrant journeys |  | on going | IOM website
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This study should be conducted before the roll out of Phase 1 of CGCC
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I don't understand this. Reply: we have started to work on a joint paper to be completed 2021 Q3 typo on date
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This survey can be conducted after the 1st rollout of CGS by CGCC.

## Communication-Final
1. Impact Stories from the Field | 1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx | Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Find MHPSS story in the below link: https://www.who.int/cambodia/news/feature-stories/detail/who-rgc-and-partners-join-forces-to-offer-mental-health-support-to-migrant-workers-and-vulnerable-groups | Find MHPSS story in the below link: https://www.who.int/cambodia/news/feature-stories/detail/who-rgc-and-partners-join-forces-to-offer-mental-health-support-to-migrant-workers-and-vulnerable-groups
UNICEF has developed a video on social worker during COVID-19 experience: https://youtu.be/JgedKX1G5K4
2. Upload here: Communications and Visibility (OPTIONAL) | 2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941 | Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words) | Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries. | To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media. | Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation. | Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board. | Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board | See - Fund's Trello Board