## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Enhancing the Preparedness & Response Plan for COVID19 in Tokelau | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-06-01
MPTF Office Project Reference Number: | 121674 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Tokelau | Current End date(dd.mm.yyyy) | 2021-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNFPA | National counterparts (government, private, NGOs & others) and other International Organizations | Office of the Ongoing Government of Tokelau (OCOG), Department of Health
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UNDP has completed activities in relation to the COVID19 MPTF funding
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UNFPA received a no cost extension approval to 31 March 2021

## Narrative-Annual
# | Questions | Guidance to respondents | Responses | UNDP | UNFPA
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Tokelau is a small Pacific country with a total land area of only 12 square kilometers, and a population of 1,647 people (2019 estimate). The country is a group of three atolls (Atafu, Fakaofo, Nukunonu) in the South Pacific Ocean, about one-half of the way from Hawaii to New Zealand. As of today, Tokelau remains COVID19 free and support from MPTF has enabled them to stay this way. The project objective was to enhance preparedness for/containment of any potential COVID-19 cases by contributing to the following focal areas: 1. Each atoll to have fully operational quarantine and hospital isolation centres; and 2. Build capacity of homes to take on any probable overflow from hospital isolation. 3. Enhance national capacity to mainstream gender-sensitive protection activities and continuity of essential sexual and reproductive health (SRH) information and services in the national preparedness plan and response. During the implementation phase from June - December 2020, the following collective key activities and results were achieved through UNDP and UNFPA: 1. All three atolls have fully refurbished and operational quarantine centers and isolation rooms. Equipped with healthcare capabilities and airconditioning units. As a result of the fully functional facilities, the Tokelau Government have been able to safely quarantine 104 repatriates from Samoa, New Zealand, Fiji and Australia. 2. As part of strengthening the national capacities in response to COVID19, trainings were successfully delivered for 20 health care workers and 51 beneficiaries (4 adolesecents, 15 youth, 32 adults) on areas including sexual and reproductive health services, family planning, Minimum Initial Service Package and COVID19 case management 3. In terms of national awareness, public workshops and information materials were disseminated to all atolls and weekly programmes broadcasted on radio and social media platforms to continuously inform the public on COVID19 developments in Tokelau. 4. On the socio-economic level, hygiene and dignity kits were distributed to the public reaching 1000 people for personal protection and prevention control 5. SEIA survey for Tokelau has been completed with the report in development. The results will inform the SERP for Tokelau and collective interventions by the Samoa UN Multi Country Office. 6. Procurement and supply of 300 dignity kits (supply in progress) and 1,716 items (procured and supplied) of Personal Protective Equipment (PPE) for Tokelau to protect the hygiene needs of women and girls and to protect health workers to aid delivery of essential services in the event of COVID-19 outbreak in the country. A no-cost extension was granted to UNFPA until 31 March 2021 to complete implementation of all activities. During the period of the no-cost extension, implementation will focus on supplies and last mile distribution of procured commodities (PPEs and Dignity Kits) and COVID-19 SRH risk communication and community engagement in Tokelau. | Since the MPTF interim reporting period in September 2020, the UNDP MPTF COVID19 Response Proejct for Tokelau has now completed its implementation, and was operationally closed on the 31st December 2020. At the completion of implementation, All the three (3) Atolls (Fakaofo, Nukunonu, and Atafu) have completed the Refurbishment of their Quarantine Centres and are fully operational now. The Centres have a total number of 39 available furnished rooms equipped with beds, fans, and appliances (Atafu – 8 Single Rooms & 3 Family Rooms, Fakaofo – 6 Single Rooms & 2 Family Rooms, Nukunonu – 6 Single Rooms, 2 Family Rooms, 1 Staff Room) inclusive of 11 Isolations rooms/units (4 Atafu, 3 Fakaofo, and 4 Nukunonu) that are equipped with healthcare capabilities and as well as air conditioning units, to ensure a conducive environment that is best suited to isolate any suspected COVID19 cases. Each Atolls also have additional structures that have been repurposed with quarantine capacities to support the centers in the event of an influx of repatriates. As a result, between the inception of the project in June 2020 up to its completion in December, in spite of the existing COVID19 Restrictions, the Tokelau Government were able to safely facilitate the returning and quarantining of a total number of 104 repatriates from Samoa, New Zealand, Australia, and Fiji; and Tokelau remains COVID19 free (33 arrived on the 9th Dec, 38 arrived on the 27th Dec, and 33 arrived on 06th Jan 2021) Furthermore, as part of strengthening the National Capacities in response to COVID19, capacity building and trainings were successfully delivered for Health Care workers, where 20 health workers were trained on handling and case management any suspected COVID19 cases and operating in Quarantine Centers and Isolation Wards. In terms of National Awareness and Communication, public workshops and information materials were disseminated to all the atolls with information on COVID19 preparedness and response and weekly programmes were broadcasted on radio and social media platforms to continuously inform the public on the COVID19 developments in Tokelau and the progress of its preparatory and response efforts. On the socio-economic level, hygiene and dignity kits including PPEs were distributed to the public reaching 1000 people for personal protection and prevention control. UNDP in close collaboration with Office of the Council and the Tokelau Statistics Office were able successfully complete the COVID19 Socio-Economic Impact Assessment Survey of Tokelau. This support included the procurement of Consultant to support the Tokelau Statistics Office in carrying out the survey that targeted 300 Households which is 20% of the total population and 30 businesses to gauge the magnitude of the COVID19 impacts on Tokelau. The findings of this survey are now informing the Socio-Economic Impact Assessment (SEIA) Report for Tokelau which UNDP is currently developing and would in turn inform the Socio-Economic Response Plan (SERP) for Tokelau and the collective response by the UN Country Office. | The main aim of UNFPA’s implementation in the COVID-19 MPTF project for Tokelau is to enhance Tokelau’s systems and capacities to prepare and respond to the COVID-19 pandemic through activities strengthening healthcare operational capacities to ensure continuity of essential Sexual and Reproductive Health (SRH services). These activities include ensuring availability of Personal Protective Equipment (PPEs) and supplies to foster continuity of essential Sexual and Reproductive Health Services, ensuring availability of dignity kits for the protection needs of women and girls in Tokelau, building the capacity of health workers on Minimum Initial Service Package to deliver essential Sexual and Reproductive Health and Rights (SRHR) services during the pandemic, providing COVID-19 SRH risk communication and community engagement in Tokelau and providing technical assistance to integrate gender-responsive questions into the planned Socio-economic Impact Assessment Survey for Tokelau. Through this COVID-19 MPTF grant, UNFPA and its implementing partner – Department of Health Tokelau reached 51 direct beneficiaries including 4 adolescent aged 10-19 years, 15 youth (20-24 years) and 32 adults with life-saving sexual and reproductive health services such as family planning, antenatal care and obstetrics and new-born care services and capacity building for health workers to improve service delivery and ensure continuity of services between July 2020 to December 2020. The results achieved so far were facilitated by training of 14 health workers on the Minimum Initial Service Package (MISP) for essential SRH services in emergencies. The training covered 56 per cent of Tokelau’s health workforce and approximately 93 per cent of the SRH workforce, across all three atolls and health facilities in Tokelau. In addition, UNFPA procured 300 dignity kits and 1,716 items of Personal Protective Equipment (PPE) for Tokelau to protect the hygiene needs of women and girls and to protect health workers to aid delivery of essential services in the event of COVID-19 outbreak in the country. UNFPA also provided technical assistance to the recently completed SEIA in Tokelau. Overall, the project has directly served a total of 4 adolescents (10-19 years) – female (3) and male (1); 15 Youth (20-24 years) – female (12) and male (3); and 32 adults (25 years and above) – female (28) and male (4) during the period of implementation. Of the total grant available through UNFPA of 69, 950 USD, budget utilisation till date is approximately 50, 283 USD (72 per cent) representing expenditures, and commitments currently under payment processing. A no-cost extension was granted until 31 March 2021 to complete implementation of all activities. During the period of the no-cost extension, implementation will focus on supplies and last mile distribution of procured commodities (PPEs and Dignity Kits) and COVID-19 SRH risk communication and community engagement in Tokelau.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The main purpose of the project was to enhanced the systems and the capacities of Tokelau at the National level to prepare, respond, and recover from the impacts of COVID19 Pandemic. In terms of beneficiairies, the refurbishments of the quarantine centers on the 3 Atolls have directly benefited the 104 repatirates thave have successfully completed their quarantining process, the 20 health workers that were trained but indirectly benefited the whole population of 1,647 as Tokelau remains COVID free to date. With regards to the multimedia awareness campaign and the socio-economic impact assessment survey, it has directly benefitied the whole populate in terms of access to information, and access to socio-economic assistance via the response plans informed by the SEIA works. A total of 51 direct beneficiaries were reached during the implementation period comprising of 37 adolescents and adults reached with SRH services and 14 health care workers. Of the 51 direct beneficiaries, 42 females and 9 males. A total of 4 adolescents (10-19 years) – Female (3) and Male (1) benefitted directly; 15 Youth (20-24 years) – female (12) and male (3); and 32 adults (25 years and above) – Female (28) and male (4) | The main purpose of the project was to enhanced the systems and the capacities of Tokelau at the National level to prepare, respond, and recover from the impacts of COVID19 Pandemic. In terms of beneficiairies, the refurbishments of the quarantine centers on the 3 Atolls have directly benefited the 104 repatirates thave have successfully completed their quarantining process, the 20 health workers that were trained but indirectly benefited the whole population of 1,647 as Tokelau remains COVID free to date. With regards to the multimedia awareness campaign and the socio-economic impact assessment survey, it has directly benefitied the whole populate in terms of access to information, and access to socio-economic assistance via the response plans informed by the SEIA works. | The project’s main aim is to enhance Tokelau’s systems and capacities to prepare and respond to the COVID-19 pandemic through strengthening of healthcare operational capacities to ensure continuity of essential Sexual and Reproductive Health (SRH services) and implementation of COVID-19 SRH risk communication and awareness programmes for target groups – women of reproductive age group, adolescents and youth. A total of 51 direct beneficiaries were reached during the implementation period comprising of 37 adolescents and adults reached with SRH services and 14 health care workers. Of the 51 direct beneficiaries, 42 females and 9 males. A total of 4 adolescents (10-19 years) – Female (3) and Male (1) benefitted directly; 15 Youth (20-24 years) – female (12) and male (3); and 32 adults (25 years and above) – Female (28) and male (4)
3.1 | Results: Outcome Level | Please include outcome level results achieved | The national capacity of Tokelau to effectively prepare, response, and recover from COVID19 and other communicable disease was enhanced through specific training provided as well equipped with facilities and supplies for emergencies. Tokelau remains COVID free to date and also evident in the number of repatriates that have safely returned and undergone the quarantine process. Increased utilisation of essential SRH services has been linked to capacity building of health workers. A 50 per cent increase in the number of Family Planning clients served with information and services was noted in the last quarter of implementation when compared to the quarterly average in the first half of 2020 | At the completion of the project, Tokelau has enhanced its capacity to effectively prepare, response, and recover from COVID19 and other communicable diseases, as Tokelau remains COVID free to date and also evident in the number of repatriates that have safely returned and undergone the quarantine process. | The national capacity of Tokelau to prepare and respond to COVID-19 pandemic was enhanced through 14 trained health workers (on planning and delivery of SRH services in emergencies); 1716 procured PPE items and 300 procured dignity kits for Tokelau; and the development of SRH risk communication materials for awareness campaigns. Increased utilisation of essential SRH services has been linked to capacity building of health workers. A 50 per cent increase in the number of Family Planning clients served with information and services was noted in the last quarter of implementation when compared to the quarterly average in the first half of 2020
3.2 | Results: Output Level | Please include output level results achieved | At the completion of the project, the following Results were achieved under each Outputs; OUTPUT 1.1: Quarantine Centers & Isolation Wards upgraded, refurbished and equipped with healthcare capabilities conducive for use of full PPE required by staff and support telecom means are in place on each atoll 1.1.: All 3 Atolls (Fakaofo, Atafu, Nukunonu) have completed the Refurbishments of their Quarantine Centers & Isolations Wards with total number of 39 Rooms available, 64 Beds, 11 Isolations Wards, and 21 airconditioning units installed. The Atafu Center has 8 Singles Rooms, 3 Family Rooms, 4 Isolations Units and is equipped with 28 beds, ceiling fans, appliances, and 8 Air Conditioning Units for the Isolations wards. The Fakaofo Center has 6 Single Rooms, 2 Family Rooms, 3 Isolation Units that is equipped with 16 beds, fans, appliances, and 7 Air Conditioning Units for the isolation wards. The Nukunonu Center has 6 Single Rooms, 2 Family Rooms, 1 Staff Room, 4 isolation units, and it equipped with 20 beds, fans, appliances, and 6 air conditioning units for the isolation wards. 1.1. 1,716 PPE items were procured for Tokelau to strengthen infection prevention and control, protect healthcare workers delivering SRH services and enhance continuity of SRH service provision in case of COVID-19 outbreak. 300 dignity kits were procured for Tokelau to protect women and girls and meet their hygiene needs. OUTPUT 1.2: Awareness Programmes on COVID19 for Communities Conducted 1.2. National Multimedia Awareness Campaign via workshops, radio broadcastings, and disseminations of information materials has reached nation wide covered reaching 1500 people OUTPUT 1.3: Healthcare and Operational Capacities Strengthened 1.3. Trainings and Capacity Builidng successfully delivered for 20 Health Workers on handling and case management of suspected COVID19 cases. 1.3. 56% of the health workforce in Tokelau had their capacity built on Minimum Initial Service Package (MISP) for essential SRH services during emergencies including COVID-19 adaptation to ensure continuity of SRH services. The training covered 100% of Tokelau’s atolls and 100% of health facilities with a total of 14 health workers trained. A direct outcome of the capacity building activity was an increase in the knowledge pool across Tokelau health workers and public health managers in planning and delivering SRH services in emergencies. By the end of the training, 100% of health workers had accurate knowledge on prevention of unintended pregnancies, prevention and response to sexual and gender-based violence and prevention of excess maternal and new-born mortality as key MISP components compared with 95% of health workers before the training. OUTPUT 1.4: Socio-Economic Impact Assessment (SEIA) conducted 1.4. Socio-Economic Impact Assessment Survey completed with 20% of the total Population surveyed and 30 businesses providing the provisional data on the impacts of COVID19 on Tokelau, thus informing the development of the SEIA Report that UNDP currently undertaking. | At the completion of the project, the following Results were achieved under each Outputs; OUTPUT 1.1: Quarantine Centers & Isolation Wards upgraded, refurbished and equipped with healthcare capabilities conducive for use of full PPE required by staff and support telecom means are in place on each atoll 1.1.: All 3 Atolls (Fakaofo, Atafu, Nukunonu) have completed the Refurbishments of their Quarantine Centers & Isolations Wards with total number of 39 Rooms available, 64 Beds, 11 Isolations Wards, and 21 airconditioning units installed. The Atafu Center has 8 Singles Rooms, 3 Family Rooms, 4 Isolations Units and is equipped with 28 beds, ceiling fans, appliances, and 8 Air Conditioning Units for the Isolations wards. The Fakaofo Center has 6 Single Rooms, 2 Family Rooms, 3 Isolation Units that is equipped with 16 beds, fans, appliances, and 7 Air Conditioning Units for the isolation wards. The Nukunonu Center has 6 Single Rooms, 2 Family Rooms, 1 Staff Room, 4 isolation units, and it equipped with 20 beds, fans, appliances, and 6 air conditioning units for the isolation wards. OUTPUT 1.2: Awareness Programmes on COVID19 for Communities Conducted 1.2. National Multimedia Awareness Campaign via workshops, radio broadcastings, and disseminations of information materials has reached nation wide covered reaching 1500 people OUTPUT 1.3: Healthcare and Operational Capacities Strengthened 1.3. Trainings and Capacity Builidng successfully delivered for 20 Health Workers on handling and case management of suspected COVID19 cases. OUTPUT 1.4: Socio-Economic Impact Assessment (SEIA) conducted 1.4. Socio-Economic Impact Assessment Survey completed with 20% of the total Population surveyed and 30 businesses providing the provisional data on the impacts of COVID19 on Tokelau, thus informing the development of the SEIA Report that UNDP currently undertaking. | During the implementation timeframe under review, the following output results were achieved: • 56% of the health workforce in Tokelau had their capacity built on Minimum Initial Service Package (MISP) for essential SRH services during emergencies including COVID-19 adaptation to ensure continuity of SRH services. The training covered 100% of Tokelau’s atolls and 100% of health facilities with a total of 14 health workers trained. A direct outcome of the capacity building activity was an increase in the knowledge pool across Tokelau health workers and public health managers in planning and delivering SRH services in emergencies. By the end of the training, 100% of health workers had accurate knowledge on prevention of unintended pregnancies, prevention and response to sexual and gender-based violence and prevention of excess maternal and new-born mortality as key MISP components compared with 95% of health workers before the training. • 1,716 PPE items were procured for Tokelau to strengthen infection prevention and control, protect healthcare workers delivering SRH services and enhance continuity of SRH service provision in case of COVID-19 outbreak • 300 dignity kits were procured for Tokelau to protect women and girls and meet their hygiene needs. • Tokelau’s covid-19 Socio-economic impact Assessment Survey finalized with availability of preliminary report that includes results on impact of the pandemic on access to SRH services, including barriers to utilization of services for women
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Although the implementation of the project was a success, there had been some notable challenges encountered which inhibited the timely progress of activities. • The geographic isolation of Tokelau remained a challenge and as the only port of entry was through Samoa; the continuous border restrictions in Samoa impacted on the timely access and mobilization of the required resources, supplies, personnels to Tokelau to support implementation. As a mitigating measure, the Office of the Council arranged to bulk purchase the required resources and supplies to minimize the time and cost for mobilization and enusre availability of resources on each Atolls for implemenation. • Documentation challenges and operational delays in cash transfer to the implementing Partner (IP). Delays in finalizing agreement with the Implementing partner (IP) and disbursement of funds due to delayed supporting documentation from IP. Measures taken to overcome this challenge include continued dialogue and virtual assistance rendered to IP to strengthen documentation required for financial disbursements; UNFPA exception to cash transfer was granted to IP; enhanced virtual programme management with increased frequency of check-in meetings for programme planning, execution and reporting of results. • Global supply chain disruption with negative impacts on PPE and Dignity kits procurement process. Due to global shortages and disruption of global supply chain, the sourcing for Tokelau’s PPEs and dignity kits was constrained by volatility and high global market prices, high freight cost as well as poor availability of logistics company to deliver supplies increasing the delivery lead time for the supplies. UNFPA course-corrected by adjusting quantities of supplies procured and the distribution timeline to Tokelau. To mitigate risk of further delays, the procurement process was managed in collaboration with UNICEF and UNFPA procurement and supply chain branch to source items from global suppliers and distribute to UNFPA’s sub-regional warehouse with airfreight delivery modality used between the sub-regional warehouse to Tokelau’s liaison office. Operational Lessons: • Constrained human resource capacity for programme implementation. Given Tokelau’s small size and competing priorities of the Department of Health, re-prioritization of programme results and activities had to be undertaken to course correct for implementation delays. This includes no-cost extension to increase implementation timeframe and reduce implementation burden on IP. • Lack of field presence and travel constraints due to COVID-19 restrictions impeded capacity building activities, however, the use of a virtual training modality was a programme delivery innovation for Tokelau and presents a good practice for Tokelau to benefit from future capacity building initiatives even in the context of physical travel constraints. Some of the lessons from implementation of the virtual training include managing number of groups and group sizes per remote location to small numbers; building capacity of a national health worker to facilitate some group sessions, ensuring pre-training access to training content and materials online and ensuring local IT logistical support for the IP during training implementation. • Through participant’s engagement in the virtual training, further health systems strengthening needs for SR became apparent. Lessons include the need for further training to build on knowledge gaps and reinforce knowledge gained by participants through the virtual MISP training; need to establish guidelines for key services including prevention and response to GBV, obstetrics care and support Tokelau to follow these guidelines; strong influence of culture and religion perpetuates certain topics regarded as taboos such as discussing SRHR and empowerment on contraceptive choices, therefore sustained community dialogue and awareness is needed to shift the community’s perception on access to SRHR. • Consider pre-positioned PPEs in countries for future public health emergencies to mitigate delays in access to PPEs during such emergencies accompanied with regular training for healthcare workers on infection prevention and control and use of PPEs As a mitigating measure, the Office of the Council arranged to bulk purchase the required resources and supplies to minimize the time and cost for mobilization and enusre availability of resources on each Atolls for implemenation. • Financial reporting of expended funds transferred to the Government of Tokelau to support implementation, was one of the notable challenges encountered. This stems from how the funds were managed as it was pooled together with the assistance from other development partners into one account dedicate to support Tokelau's COVID19 Resposne. As a corrective measure, UNDP provided assistance and supported the OCOG in generating of more transparent financial reports itemizing the specific and relevant expenditures of the project. OCOG was ammenable to the recommendations made on corrective actions, and challenge has been noted for further review and way forwards under the Micro Assessment and HACT for OCOG that is to be conducted in early 2021. | Although the implementation of the project was a success, there had been some notable challenges encountered which inhibited the timely progress of activities. Of note, the geographic isolation of Tokelau remained a challenge and as the only port of entry was through Samoa; the continuous border restrictions in Samoa impacted on the timely access and mobilization of the required resources, supplies, personnels to Tokelau to support implementation. As a mitigating measure, the Office of the Council arranged to bulk purchase the required resources and supplies to minimize the time and cost for mobilization and enusre availability of resources on each Atolls for implemenation. Furthermore, the financial reporting of expended funds transferred to the Government of Tokelau to support implementation, was one of the notable challenges encountered. This stems from how the funds were managed as it was pooled together with the assistance from other development partners into one account dedicate to support Tokelau's COVID19 Resposne. As a corrective measure, UNDP provided assistance and supported the OCOG in generating of more transparent financial reports itemizing the specific and relevant expenditures of the project. OCOG was ammenable to the recommendations made on corrective actions, and challenge has been noted for further review and way forwards under the Micro Assessment and HACT for OCOG that is to be conducted in early 2021. | Challenges • Documentation challenges and operational delays in cash transfer to the implementing Partner (IP). Delays in finalizing agreement with the Implementing partner (IP) and disbursement of funds due to delayed supporting documentation from IP. Measures taken to overcome this challenge include continued dialogue and virtual assistance rendered to IP to strengthen documentation required for financial disbursements; UNFPA exception to cash transfer was granted to IP; enhanced virtual programme management with increased frequency of check-in meetings for programme planning, execution and reporting of results. • Global supply chain disruption with negative impacts on PPE and Dignity kits procurement process. Due to global shortages and disruption of global supply chain, the sourcing for Tokelau’s PPEs and dignity kits was constrained by volatility and high global market prices, high freight cost as well as poor availability of logistics company to deliver supplies increasing the delivery lead time for the supplies. UNFPA course-corrected by adjusting quantities of supplies procured and the distribution timeline to Tokelau. To mitigate risk of further delays, the procurement process was managed in collaboration with UNICEF and UNFPA procurement and supply chain branch to source items from global suppliers and distribute to UNFPA’s sub-regional warehouse with airfreight delivery modality used between the sub-regional warehouse to Tokelau’s liaison office. Operational Lessons: • Constrained human resource capacity for programme implementation. Given Tokelau’s small size and competing priorities of the Department of Health, re-prioritization of programme results and activities had to be undertaken to course correct for implementation delays. This includes no-cost extension to increase implementation timeframe and reduce implementation burden on IP. • Lack of field presence and travel constraints due to COVID-19 restrictions impeded capacity building activities, however, the use of a virtual training modality was a programme delivery innovation for Tokelau and presents a good practice for Tokelau to benefit from future capacity building initiatives even in the context of physical travel constraints. Some of the lessons from implementation of the virtual training include managing number of groups and group sizes per remote location to small numbers; building capacity of a national health worker to facilitate some group sessions, ensuring pre-training access to training content and materials online and ensuring local IT logistical support for the IP during training implementation. • Through participant’s engagement in the virtual training, further health systems strengthening needs for SR became apparent. Lessons include the need for further training to build on knowledge gaps and reinforce knowledge gained by participants through the virtual MISP training; need to establish guidelines for key services including prevention and response to GBV, obstetrics care and support Tokelau to follow these guidelines; strong influence of culture and religion perpetuates certain topics regarded as taboos such as discussing SRHR and empowerment on contraceptive choices, therefore sustained community dialogue and awareness is needed to shift the community’s perception on access to SRHR. • Consider pre-positioned PPEs in countries for future public health emergencies to mitigate delays in access to PPEs during such emergencies accompanied with regular training for healthcare workers on infection prevention and control and use of PPEs
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | A socio-economic impact assessment was conducted during the implementation period. The assessment was led by UNDP in collaboration with the government of Tokelau with technical inputs from UNFPA. Some key programmatic lessons gleaned from preliminary results of the assessment: • Societal barriers exist in discussing SRH services in Tokelau. Across the 3 atolls, 10-34 per cent of survey respondents refused to answer questions related to difficulty in accessing reproductive health services since the COVID-19 lock down while 40-64 per cent responded they had no need for reproductive health services. These results may stem from sensitivities associated with discussing SRH issues. Planned community dialogues and SRH risk communication activities will explore further these societal norms and aim to dispel myths and misconceptions on SRHR. • Accelerating implementation of activities aim to maintain continuity of SRH services is necessary since the survey results revealed Covid-19 lock-down may have increased difficulties in accessing reproductive health services including contraception across some of Tokelau’s atolls: 1 in 5 women (20 per cent) across Atafu atoll responded they had faced some difficulties or major difficulties in accessing reproductive health services since the lock down while 39 per cent and 13 per cent in Fakaofo and Atafu respectively had faced difficulties in accessing contraception services since the lock down. • Females in Tokelau are disproportionately more affected by mental/emotional health issues since the COVID-19 lock-down compared to males (64 per cent versus 48 per cent respectively) Findings from the SEIA underscore need for the programme activities being implemented as part of this COVID-19 MPTF grant. In addition to lessons from the socio-economic impact assessment, a pre-test and post-test survey was administered to participants before and after the virtual training held for health workers on Minimum Initial Service Package (MISP) for SRH during emergencies. The post test results showed participants improved on their knowledge on the components of MISP, principles for responding to sexual and gender-based violence, components of clinical care for gender-based violence, components of counselling on contraception, identification of danger signs in new-born and clinical skills essential for maternal and new-born care. Despite an overall improvement in knowledge, pockets of learning gaps exist necessitating a tailored and sustained capacity building programme for health workers on SRHR in future. Lastly, engagement of National Governments at every level ranging from the designing to the implementation is very crucial as their participation stimulates proactiveness in implementation, and national ownership and sustainability of the results. This was evident in the commitment and contirbution from National Goverment in driving this project, despite the COVID19 restrictions and border controls in place. | One of the notable lesson learned from the implementation of th Tokelau COVID19 Resposne project was that the engagement of National Governments at every level ranging from the designing to the implementation is very crucial as their participation stimulates proactiveness in implementation, and national ownership and sustainability of the results. This was evident in the commitment and contirbution from National Goverment in driving this project, despite the COVID19 restrictions and border controls in place. | A socio-economic impact assessment was conducted during the implementation period. The assessment was led by UNDP in collaboration with the government of Tokelau with technical inputs from UNFPA. Some key programmatic lessons gleaned from preliminary results of the assessment: • Societal barriers exist in discussing SRH services in Tokelau. Across the 3 atolls, 10-34 per cent of survey respondents refused to answer questions related to difficulty in accessing reproductive health services since the COVID-19 lock down while 40-64 per cent responded they had no need for reproductive health services. These results may stem from sensitivities associated with discussing SRH issues. Planned community dialogues and SRH risk communication activities will explore further these societal norms and aim to dispel myths and misconceptions on SRHR. • Accelerating implementation of activities aim to maintain continuity of SRH services is necessary since the survey results revealed Covid-19 lock-down may have increased difficulties in accessing reproductive health services including contraception across some of Tokelau’s atolls: 1 in 5 women (20 per cent) across Atafu atoll responded they had faced some difficulties or major difficulties in accessing reproductive health services since the lock down while 39 per cent and 13 per cent in Fakaofo and Atafu respectively had faced difficulties in accessing contraception services since the lock down. • Females in Tokelau are disproportionately more affected by mental/emotional health issues since the COVID-19 lock-down compared to males (64 per cent versus 48 per cent respectively) Findings from the SEIA underscore need for the programme activities being implemented as part of this COVID-19 MPTF grant. In addition to lessons from the socio-economic impact assessment, a pre-test and post-test survey was administered to participants before and after the virtual training held for health workers on Minimum Initial Service Package (MISP) for SRH during emergencies. The post test results showed participants improved on their knowledge on the components of MISP, principles for responding to sexual and gender-based violence, components of clinical care for gender-based violence, components of counselling on contraception, identification of danger signs in new-born and clinical skills essential for maternal and new-born care. Despite an overall improvement in knowledge, pockets of learning gaps exist necessitating a tailored and sustained capacity building programme for health workers on SRHR in future.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNDP established a partnership with the Office of the Council of the Government of Tokelau that was instrumental in the successful achievement of the intended targets, outputs, and the overall outcome of the project. Enhancing the Preparedness & Response Plan for COVID19 in Tokelau has enhanced the partnership between Tokelau Department of Health and UNFPA, being the first programme of its kind through which UNFPA is supporting implementation of programme activities within Tokelau. The project complements UNFPA’s existing programme with the DOH – the UNFPA Supplies programme from which Tokelau benefits from in-kind donation of contraceptives and UNFPA sub-regional capacity building initiatives to strengthen supply chain systems with aim to ensure zero stock-out of contraceptives and increase the couple years of protection for contraceptive services in Tokelau. Through the emphasis on continuity of essential SRH services, the MPTF grant to Tokelau through UNFPA has yielded synergies in overall programme results in Tokelau. This project has also engendered key lessons to improve and target future UNFPA programmes and engagement in Tokelau towards closing lingering gaps and barriers preventing universal access to Sexual and Reproductive Health and Rights (SRHR) | UNDP established a partnership with the Office of the Council of the Government of Tokelau that was instrumental in the successful achievement of the intended targets, outputs, and the overall outcome of the project. | Enhancing the Preparedness & Response Plan for COVID19 in Tokelau has enhanced the partnership between Tokelau Department of Health and UNFPA, being the first programme of its kind through which UNFPA is supporting implementation of programme activities within Tokelau. The project complements UNFPA’s existing programme with the DOH – the UNFPA Supplies programme from which Tokelau benefits from in-kind donation of contraceptives and UNFPA sub-regional capacity building initiatives to strengthen supply chain systems with aim to ensure zero stock-out of contraceptives and increase the couple years of protection for contraceptive services in Tokelau. Through the emphasis on continuity of essential SRH services, the MPTF grant to Tokelau through UNFPA has yielded synergies in overall programme results in Tokelau. This project has also engendered key lessons to improve and target future UNFPA programmes and engagement in Tokelau towards closing lingering gaps and barriers preventing universal access to Sexual and Reproductive Health and Rights (SRHR)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: Tokelau's capacity to prevent COVID19 and other communicable diseases is enhanced
Indicator 1a: Number of COVID19 cases disaggregated by age and sex
Baseline: 0
Planned Target 0
Output 1.1: Quarantine centres & isolation wards upgraded, refurbished & equipped with healthcare capabilities conducive for use of full PPE required by staff and support telecom means (mobile phones/ walkie talkies) are in place on each atoll | All 3 atolls have upgraded quarantine centers with a total of 39 rooms available, 64 beds and 11 isolation wards |  | OCOG Tokelau Project Report
Indicator 1.1.a: Number of fully equipped quarantine and isolation beds available on each atolls
Baseline: 0
Planned Target: 60
Indicator 1.1.b: Number of air conditioning units and back up power supply installed | 21 air conditioning units procured and installed at the centers. Atafu - 8, Fakaofo - 7, Nukunonu - 6
Baseline: 0
Planned Target: 15
Indicator 1.1.c: Number of PPE procured and supplied to enhance capacity for infection prevention & control | 1716 | Global supply chain disruption with negative impacts on PPE and Dignity kits procurement process. Due to global shortages and disruption of global supply chain, the sourcing for Tokelau’s PPEs and dignity kits was constrained by volatility and high global market prices, high freight cost as well as poor availability of logistics company to deliver supplies increasing the delivery lead time for the supplies. UNFPA course-corrected by adjusting quantities of supplies procured and the distribution timeline to Tokelau to be accomodated within the period of No Cost Extension ending March 31, 2021. UNDP funds were reprogrammed to support refurbishment of the quarantine centers | Signed delivery slip and distribution list
Baseline:
Planned Target: 3,000 PPE items
Output 1.2: Awareness Programmes on COVID19 for Communities Conducted | 1600 people reached through national multimedia awareness programmes |  | OCOG Tokelau Project Report
Indicator 1.2a: Number of people reached through preventive healthcare awareness campaigns on each atoll, disaggregated by sex
Baseline: 0
Planned Target: 1,000
Indicator 1.2b: Number of adolescent girls and women of reproductive age who received COVID19 SRH risk communication messages | 0 | Implementation delays from: 1. Documentation challenges and operational delays in cash transfer to the implementing Partner (IP). Delays in finalizing agreement with the Implementing partner (IP) and disbursement of funds due to delayed supporting documentation from IP 2. Constrained human resource capacity for programme implementation. Given Tokelau’s small size and competing priorities of the Department of Health, re-prioritization of programme results and activities had to be undertaken to course correct for implementation delays. This includes no-cost extension to increase implementation timeframe and reduce implementation burden on the IP | Government administrative data on distribution of IEC materials
Baseline: 0
Planned Target: 360 (at least 80% coverage of target age)
Indicator 1.2c: Number of adolescent girls (10-14 years) and women of reproductive age (15 - 49 years) who received hygiene/dignity kits | 0 | Global supply chain disruption with negative impacts on PPE and Dignity kits procurement process. Due to global shortages and disruption of global supply chain, the sourcing for Tokelau’s PPEs and dignity kits was constrained by volatility and high global market prices, high freight cost as well as poor availability of logistics company to deliver supplies increasing the delivery lead time for the supplies. UNFPA course-corrected by adjusting quantities of supplies procured and the distribution timeline to Tokelau to be accomodated within the period of No Cost Extension ending March 31, 2021. 300 dignity kits have been procured and the supply to UNFPA sub-regional warehouse is expected by March 2021.
Baseline: 0
Planned Target: 360 (at least 80% coverage of target age)
Output 1.3: Healthcare and Operational Capacities strengthened | 20 health care workers received trainings and capacity building on COVID19 Case management |  | OCOG Tokelau Project Report
Indicator 1.3a: Number of staff of the Department of Health trained and certified to manage suspected cases
Baseline: 0
Planned Target: 20
Indicator 1.3b: Number of additional staff employed for the completion of refurbishment and maintenanve of quarantine facilities per atoll, disaggregated by sex | . | All abled men and women are either employed by the national (Govt) of village public services. From this pool of abled bodies, the required resources are allocated on case by case basis. Eg: laying a foundation which included mixing concrete would have all abled bodies involved including cooking for the workforce, etc. Building, painting etc. - resources allocated as needed | OCOG Tokelau Project Report
Baseline: 0
Planned Target: 10 (F = 5, M = 5)
Indicator 1.3c: Number of health care workers (disaggregated by sex) who have had their capacity built to integrate sexual and reproductive health (SRH) and protection needs of women and girls into national emergency response | 14 (F = 13, M = 1) | Operational delays: The original plan was to select master trainers out of the initial cohort trained to train and share their knowledge with health workers who were not able to participate in the initial training under technical guidance from UNFPA. Contributing factors to the delay in the step-down training include unfavourable weather conditions for travel between atolls impeding plans of the public health staff to facilitate this step-down training and constrained staff availability due to the festive season. | Government administrative data
Baseline: 0
Planned Target: 15 ( at least 60% of health care workers)
Output 1.4: Socio-economic impact assessment (SEIA) conducted | Partial | SEIA Survey conducted covering 20% of population and 30 businesses. SEIA report under development by UNDP | OCOG Tokelau Project Report SEIA Survey Report for Tokelau
Indicator 1.4a: Costed SEIA endorsed by GoT
Baseline: No
Planned Target: Yes
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://www.facebook.com/undpsamoa/posts/4249405901796502?__cft__[0]=AZV_LJ3QMoxyipR3pOg9mJnt9imX7OoBk4ssIrZSFOtnh57Nn6pofGwZdTHiZ1i3QUkKqljVjIw52yBoXxwUeDL5Nyyu625JtC3WCB52y66AvV3mR7qh89OmIEPhk6TYqDwp0Mh5henLfdcX-DE2pFwwOM8zANtlNnUTOBvpGS9M_w&__tn__=%2CO%2CP-R
https://undp.sharepoint.com/:v:/r/sites/ROAR2020team/Shared%20Documents/General/COVID19%20Response/Tokelau/Tokelau%20COVID19%20Response%20Activities.mp4?csf=1&web=1&e=bKhALy
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board