## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting livelihoods and reinforcing the tourism and agriculture sectors in Bhutan | Overall Duration (months) | 11 months (No-cost Extension approved)
Programme Number (if applicable) | NIL | Start Date (dd.mm.yyyy) | 1st May 2020
MPTF Office Project Reference Number: | Project ID 00121886 | Original End Date (dd.mm.yyyy) | 31st December 2020
Country | BHUTAN | Current End date(dd.mm.yyyy) | 31st March 2021 (No-Cost Extension approved)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, WFP | National counterparts (government, private, NGOs & others) and other International Organizations | Tourism Council of Bhutan; Guide Association of Bhutan; National Land Commission; Ministry of Labour and Human Resources; Department of Culture; Private hospitality training institutions; Gross National Happiness Commission; Ministry of Agriculture and Forests; Local Government.
Report Cleared By
o Name: | 1. Mr. Svante Helms; 2. Mr. Tshering Phuntsho; 3. Mr. Tashi Tshering Dukpa.
o Title: | 1. Head of Office 2. National Coordinator, GEF-Small Grants programme, UNDP 3. Development Coordination Officer - Partnerships and Development Finance
o Email address: | 1. svante.helms@wfp.org 2. tshering.phuntsho@undp.org 3. tashi.dukpa@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The shadow impact of COVID-19 pandemic in socio-economic front was heavily felt by people working in tourism and allied sectors in Bhutan which employ more than 50,000 people in a country with population of about 770,000. Tourism is one of the main drivers of the economy in Bhutan with a significant contribution to domestic revenue (17% in 2018) and about 6% of the country’s GDP, second only to hydropower sector. The pandemic has also revealed fragility and vulnerabilities of country’s food systems which risked availability of fresh vegetables especially in urban centres. The uncertain nature of COVID-19 situation and the sudden national lock down imposed from August 11-September 1, 2020 and again from December 20, 2020 which continues as we report, aggravated the overall socio-economic scenario and caused disruption to planned activities across the board. However, following the rapid socio-economic impact assessment by the government with support from UNDP and other UN agencies and WFP’s support to national agriculture stimulus plan along with other UN agencies and development partners, following activities were carried out: 1. Upskilling of laid-off people in the tourism sector: 100 young laid off licensed national cultural tour guides completed upskilling program and trained as trekking guides, of which 97 were certified and licenced as Trekking Guides. These trekking guides have better prospects and marketability. 2. Rehabilitation and development of tourism facilities: One of the popular trekking routes in Bhutan called the Phajoding Culture Trail is fully rehabilitated in partnership with Guides Association of Bhutan engaging 30 laid off people from the tourism sector. The route now have infrastructures such as public wash rooms, canopes and benches as rest areas and signages. The trek route is in the peripherals of capital city Thimphu that can benefit over 100,000 resident population in addition to tourists. Another popular trek and labelled as one of the most difficult routes in the world, the Snow-man trekking route has been surveyed for digitization in partnership with National Land Commission. 3. Through this project and strategic engagement of communiction specialist, Bhutan Tourism Dialogue series was instituted by the Tourism Council of Bhutan. The dialogue is aimed towards rethinking and reinforcing tourism in Bhutan, and sharing knowledge, best practices, and developing the travel sector in Bhutan through discourse. Tourism Council of Bhutan's communication plan has also been developed for 2020-2023. 4. Enhance local vegetable production: In partnership with Ministry of Agriculture and Forests and the Local Government, two poor districts of Zhemgang and Samtse were supported in the production of safe and nutritious vegetables. The intervention enhanced local vegetable production while improving linkages of farmers to markets and facilitating market actors to be effective and efficient in their service delivery. This in turn provided opportunities for job creation in the agricultural sector, providing alternative sources of income to those who lost their jobs in the tourism industry. The project supported smallholder farmers through distribution of high-quality vegetable seeds, tools and implements, distributed green technologies such as drip kits, sprinklers, flexible pipes, mulching plastic, low-cost poly-houses, water storage tanks, water harvesting materials, and electric fencing materials to the beneficiaries. The results are visible in the production increase in both summer and winter vegetables. Through the MPTF project, about 3340 small holder farmers and their household members benefitted from this project, through enhanced production and increased sales and income from their farm produce. There has been a minimum of 20% increase in production compared to past years and at least 668 full time employment was created for the farmers.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Tourism: A total of 286 people benefitted from this intervention with 40% female and 60 % male beneficiaries. Of the 146 direct beneficiaries 122 are male and 24 are female. There were 140 indirect beneficiaries with 35 % male and 65% female beneficiaries. The average age of the direct beneficiaries is 27 years and 80% of whom are laid off licenced but part time tourist guides. The rest 20% are full time employees working in tourism sectors but mostly laid off. Of the 140 indirect beneficiaries, 19% are children and 11 % are senior citizens above the age of 60 years. A large majority of the indirect beneficiaries are either working as part-time tourist guides or working in the tourism sector. Agriculture: Direct beneficiaries reached by the project is 668 smallholder farmers, of which above 70% are women, in the two districts of Zhemgang and Samtse. Indirect beneficaries would number around 2016 additional persons, belonging to the farming households.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Tourism: Livelihood of 146 vulnerable people in the tourism sector and their 140 dependents, who are affected by COVID-19 is protected and secured. Agriculture: Livelihood of at least 668 small holder farmers, with over 70% women, engaged in agriculture sector were protected and secured through enhanced production of vegetables and sales in domestic markets. Over 44 Metric Tonnes of fresh and nutritious local vegetables were produced by the targeted small holder farmers in Zhemgang and Samtse districts, out of which over 35MT was sold with combined earnings of over USD 28,000.
3.2 | Results: Output Level | Please include output level results achieved | Tourism: 100 (82 male and 18 female) laid off national cultural guides (National Certificate Level II) underwent training as trekking guides (National Certificate Level III), out of which 97 were certified and licenced. Nine tourism products and facilities are enhanced/developed by laid off people working in the tourism sector. Agriculture: As targeted, a minimum of 20% of targeted smallholder farmers, more than 70% of them being women, reported increased production of local nutritious vegetables/ crops. The agriculture production and marketing project provided employment to a minimum of 668 small holder farmers of Zhemgang and Samtse, with over 70% of them being women farmers.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Tourism: One of the foreseen operational challenges / risks was the restrictions on mobility (measures to suppress spread of the virus) which had delayed implementation of the project. The two national lockdowns and its related travel restrictions imposed greatly disrupted the field-level activities especially the construction works. Agriculture: The enforcement of two national lockdowns averaging a month each, zoning of the country into red, yellow and green zones, social distancing protocols, and enforcement of strict travel restrictions affected daily lives and livelihoods, especially for movement of people and goods. The farmers suffered due to unavailability of agriculture seeds and inputs in time, reduced frequency of hands-on training and other critical capacity building trainings. The unavailability of transport or higher cost of transportation and logistics compounded issues for marketing of agriculture produce and affected pricing, pushing inflation up and increasing the cost of everything. Farmers also complained of lack of marketing support for their produce. This was partly because of over supply of similar variety of produce from many districts and difficulty in moving goods from one place to another due to travel restrictions and closure of markets in many areas. The market facilitation agencies could not move freely to support the farmers or other value chain actors in providing immeidate support to the farmers. Farmers also reported incessant rainfall which damaged their early nurseries besides the delay in receiving agriculture inputs, supplies and other materials that was supported through this project as well as other projects.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | 1. At the time of announcing the upskilling program, the IP made specific public announcements to attract more women participants and repeat announcements were made through various channels. However, from the 100 slots only 18 were women. 2. Through this project and strategic engagement of communiction specialist Bhutan Tourism Dialogue series was instituted by the Tourism Council of Bhutan. The dialogue was aimed towards rethinking and reinforcing tourism in Bhutan, and sharing knowledge, best practices, and developing the sector in Bhutan through discourse. 3. Through the joint action of Economic Contingency Plan and other programs, the farmers of Bhutan are on overdrive, and remarkable progress has been made in production of agriculture commodities, particularly vegetables. There is going to be huge increase in vegetable production that may lead to excess production, market glut, price fall, etc. in the upcoming harvest season, in the spring of 2021. This may lead to demotivation of the farmers and mistrust in government sponsored programs. The district and technical agencies should advise farmers to properly plan and stagger production to prevent market glut and price fall. The winter crop is dominated by cabbage, broccoli and cauliflower even in those areas where climatic condition favours cultivation of other crops. Dzongkhags should strategize in selecting and promoting different crops in different places to assure marketing advantages. Appropriate post-harvest handling is seen as an issue. Globally and in Bhutan too, approximately 1/3rd of all food produced for human consumption is lost or wasted annually. Recovering food loss on-farm and immediately following harvest can boost the income of smallholder farmers by 15%. Post-harvest handling & storage solutions are recommended to reduce/minimize post-harvest losses both upstream and downstream across the value chain. Adequate support at institutional, farm, and field levels with the provision of training, tools and equipment are important. Some key issues around supply chain are around low unprofitable volume, terrain, low private sector involvement, poor transport and market infrastructure for agricultural supplies. There is no proper transport organisation & management, which affects farmers who face difficulty in finding cheap and easier transporters. Therefore, appropriate transport planning together with proper integration of smallholder farmers in the supply chain along the agriculture value chain should be considered. There is a need for a comprehensive demand study for vegetables in every geog, dzongkhag and national markets. This would help individual dzongkhags to plan their production, for meeting their own food sufficiency, and market their surplus produce to pre-determined markets (local or other districts). Every district should strengthen their marketing strategy with identification of farm aggregators or cooperatives, which could play critical role in strengthening the market linkages and facilitate supply chain from the farms to markets. Capacity strengthening of farmers in terms of business management skills is critical. Most of the farmers are trained regularly and provided with technical assistance by their respective extension officials in production technology and techniques. However, they require more training on the business side of things such as business management, bookkeeping, marketing, and understanding market factors and dynamics.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The fund support through MPTF has helped in complementing national Tourism Stimulus Plan of the Royal Government of Bhutan. This project was also catalytic in nature as it helped UNDP and TCB together with UN World Tourism Organization embark on another project that developed a blue print on "Digitalization of tourism sector in Bhutan" to help re-think and re-inforce tourism in Bhutan. Through this project and strategic engagement of communiction specialist, Bhutan Tourism Dialogue series was instituted by the Tourism Coulcil of Bhutan. The dialogue was aimed towards rethinking and reinforcing tourism in Bhutan, and sharing knowledge, best practices, and developing the travel sector in Bhutan through discourse. UNDP Bhutan is also expected to implement a major GEF project on "Mainstreaming biodiversity conservation into the tourism sector in Bhutan" with Tourism council of Bhutan from 2021-2025. The implementqtion of the MPTF project has helped deepen the patnership and build the project implementation and management capacity of IP. Tourism Council of Bhutan in collaboration with National Land Commission has embarked on developing a web-based application for trekking routes of the country with technical support from University of Twente, Netherlands. Additionally, the Council will also be developing mobile apps for trekking routes which is one of the key areas identified in the upcoming degitalization of Bhutan's tourism sector. A dedicated team is undergoing online training for web application development for three months since 11 March 2021. To support agriculture program, there was seamless cooperation among the Royal Government of Bhutan particularly Gross National Happiness Commission, Ministry of Agriculture & Forests, and Local Government. WFP Bhutan continued to expand its strong partnership with the Government and adapted the Country Strategic Program to national priorities for COVID-19 response. WFP Bhutan supported with the development of the National Food Security Emergency Action Plan, provided mobile storage units for food storage and provided national food safety and quality assistances. To support the national Agriculture Stimulus Plan, WFP Bhutan rolled out its strategy for climate resilient food systems in partnership with the World Bank, the International Fund for Agricultural Development (IFAD) and the Food and Agriculture Organization of the United Nations (FAO).
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | 1. An assessment was conducted for the enhancement of Phajoding trekking route in Thimphu (UNDP Bhutan and the Tourism Council of Bhutan)
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | 1. As a result of the field level assessment for the Phajoding trekking route and upon the recommendation of the Department of Culture, the construction of coffee-shop along this traditional route was considered unsuitable. However the construction of 4 canopies and a washroom is underway (UNDP Bhutan and the Tourism Council of Bhutan). 2. Out of 100 (82 male and 18 female) laid off national cultural guides (national certificate level II) only 97 were able to complete the certification exam as trekking guides (national certificate level III) as three candidates had to attend national service (as COVID-19 frontliners)
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | 1. UNDP Bhutan mobilized USD 20,000 to support Tourism Council of Bhutan to come up with a blue print for digitalization of tourism sector. 2. WFP Bhutan complemented the financial resources of MPTF allocation with resources from its other projects to provide full complementarity and to enhance the support to smallholder farmers, value chain actors and beneficiaries.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 284 | Data was not adequately collected | Data collected by implementing partner (report from Tourism Coulcil of Bhutan)
Outcome 2.1. Livelihood of people in the tourism sector (including allied services) and agriculture sector (focusing on nutritious crop production and sales), who are affected by COVID-19, is protected/secured Indicator: 2.1a People formerly employed in the tourism sector receive income equal to the minimum wage
Baseline:0
Planned Target: 400
Indicator 2.1.1 a Number of tourism facilities rehabilitated, as tourism sites are a key livelihood foundation for people employed in tourism | 9 | NA | Report from Implementing partner (Tourism Coulcil of Bhutan)
Baseline: 0
Planned Target: 6
Indicator 2.1.1 b Number of people who benefitted from re-skilling/ up-skilling | 97 | 3 candidates (out of 100) left training mid-way as COVID-19 frontline worker. | Report from Implementing partner (Tourism Coulcil of Bhutan)
Baseline: 0
Planned Target: 30
Indicator 2.2.a. Value and volume of small holder farmer sales | Value: USD 28000. Volume: 35 MT vegetables | NA | Reports from districts and Department of Agriculture
Baseline:0
Planned Target: To be established during baseline
Indicator: 2.2.1a Percentage of targeted smallholder farmers reporting increased production of nutritious crops disaggregated by sex of smallholder farmer | 20% | 20% | Reports from districts and Department of Agriculture
Baseline:0
Planned Target: 20% increase
Indicator: 2.2.1b Number of jobs created in the agriculture sector | 668 | NA | Reports from districts and Department of Agriculture
Baseline:0
Planned Target: To be established during baseline
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
UNDP Bhutan (Photos uploaded in Sharepoint): 1. Story title: Upskilling tour guides in Bhutan as tourism remains in limbo after COVID-19. Link - https://undp-bhutan.exposure.co/upskilling-tour-guides-in-bhutan-as-tourism-remains-in-limbo-after-covid19 2. Storty title: With their country shut down, Bhutan’s tour guides hone their skills. Link - https://undp.medium.com/with-their-country-shut-down-bhutans-tour-guides-hone-their-skills-8a41fcd70216 WFP Bhutan (Photos and Word document uploaded in Sharepoint): 3. Aum Kinzangmo - Nangkhor's Story of Progress (in Word document) Link - https://www.linkedin.com/feed/update/urn:li:activity:6751063420495384576?updateEntityUrn=urn%3Ali%3Afs_feedUpdate%3A%28V2%2Curn%3Ali%3Aactivity%3A6751063420495384576%29 https://www.linkedin.com/feed/update/urn:li:activity:6676471616446304256?updateEntityUrn=urn%3Ali%3Afs_feedUpdate%3A%28V2%2Curn%3Ali%3Aactivity%3A6676471616446304256%29
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
Tourism: Through UNDP Bhutan and Implementing Partner's media outlets such as Facebook, twitter, exposure.com etc., many projects stories and photo stories were shared targeting Bhutanese audience. Key milestone events such as launching of training program, launching of constrction activities etc., were organized engaging government and UN officials and stories were shared through social media outlets. The Foreign Minister of Bhutan, who is the chairperosn of the Tourism Coulcil of Bhutan made a preliminary assessment visit to the one of the sites i.e Phajoding trekking route to assess the need for rehabilitation, identification for sites for construction of restroom, signages, resting point/benches and identification of new campsite. As a part of the assessment, dozens of recommendations were for the trekking route. Agriculture: The project and its progress featured in several monthly country briefs of WFP Bhutan including its website and country office twitter accounts. Monitoring visits include the Secretary of Ministry of Agriculture and Forests to the project districts which were covered Ministry website and social media.
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board