## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE: 12-Aug-2021
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Supporting emergency measures and recovery actions to tackle COVID-19 in the indigenous territories in the Amazon Region | Overall Duration (months) | 6 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-03-01
MPTF Office Project Reference Number:[2] | 126205 | Original End Date (dd.mm.yyyy)
Country | Brazil | Current End date(dd.mm.yyyy) | 2021-09-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | PAHO/ WHO UNFPA UNWOMEN UNESCO | National counterparts (government, private, NGOs & others) and other International Organizations | State and municipal health secretariats of Amazonas, Maranhao, and Roraima; Legal Consortium of the Amazon; Indigenous and traditional (quilombola) leaders; FUNAI; Coordenação das Organizações Indígenas da Amazônia Brasileira (COIAB); Associação dos Povos Indígenas da Terra de São Marcos (APITSM)
Report Cleared By
o Name: | Silvia Rucks
o Title: | Resident Coordinator
o Email address: | silvia.rucksdelbo@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The Brazilian Federal Constitution guarantees the universality and equality in actions and services for the promotion, protection and recovery of health through the Public and Universal Brazilian System of Health (SUS). The SUS does not discriminate against social class, color, gender and citizenship. SUS may serve Brazilians, legal, illegal immigrants and refugees. The right to universal and equal access to health is one of the great legacies from SUS. COVID-19 UNMPTF program has been developed in the States of Amazonas (4,144,597 habitants), Maranhao (6,851 million habitants), and Roraima (631,000 hab). The recent prioritization (January 2021) of health access, mainly due to the increase of vaccine coverage in the indigenous and traditional population, by the Brazilian government, has made the UN agencies involved in this project work with other vulnerable groups. Such action has not been excluding the primary objectives of the original proposal and it has resulting in the increase of the population attendance (more than 11 million habitants) in those 3 states. Thus, with the main objective of supporting the early diagnosis of cases to reduce lethality, bringing together the effective participation of indigenous women in prevention measures and decision-making, the PAHO/WHO, UN Women, UNFPA and UNESCO have implemented several actions, among them: • Distribution of antigen-based rapid tests (Ag-RDT) and pulse oximeters for all states involved in this project. • Development of guidelines aimed at increasing the knowledge of the health team and decision makers about gender and rights of indigenous peoples. • Engagement with subnational governments to provide technical assistance and defense of gender and race-sensitive strategies. • Evaluation of health emergency response plans, against COVID-19, emphasizing the capacity to respond to gender, race and ethnicity. • Working together with coalitions of indigenous peoples to identify challenges and opportunities to be achieved for the improvement and well-being of indigenous peoples; • Financial support to coalitions of indigenous peoples to increase pandemic response capacity. • Support to assess the needs of women and indigenous peoples during the pandemic. • Development of a Dashboard with scenarios of COVID-19, containing data of the current state of the art and stratified information of diseases related to COVID-19, emphasizing pregnant women, mothers and newborns. • Development of an Open and Distance Education Course (DEC) for Health Professionals, aimed at training in the care and early diagnosis of COVID-19, with a special focus on pregnant women and puerperal women. • State of Maranhao: Hiring of Cultural Mobilizers (Mobilizadores Culturais), who work in the mapping of 06 quilombola territories, as well as in the dissemination of true information and combating fakenews in the care and protection of COVID-19 (this action has covered more than 200 pregnant or puerperal women and their families. • State of Amazonas: Building of Telemedicine Rooms, together with the health departments, secretariat of the indigenous population, as well indigenous leaders. This action provided the implantation of telemedicine for 07 DSE. • Purchase and distribution of Personal Protective Equipment (PPE´s) to prevent SARS-Cov-2 infection for all States. • Promotion of protection and intercultural dialogue among indigenous peoples of the Amazon region in the context of the pandemic COVID-19. The scope of the activities included areas such as education, health, value of cultural heritage, safeguarding of linguistic diversity and sustainable development. • Promotion and support of workshops as well as educational video series with information on COVID-19 prevention. This educational material was outlined as a multilingual and intercultural tool to support indigenous leaders and health workers. The direct beneficiaries were for the following ethnicities: E'ñepa, Warao, Yanomami, Wapichan, Macuxi, Ye'kwana, and Ticuna.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The program has carried out on total of 3,609 trainings for Health care professionals (DEC or face-to-face); More than 143,429 habitants (99,12%)were beneficiaries on the supporting use of pulse oximeters and Antigen-based rapid tests. The program has been fostering the strengthening of the capacity for community mobilization, advocacy, response, and political participation of coalition members. So far, 200 indigenous women have benefited by the project, including mobilization actions/ community resilience and emergency actions in the states of Amazonas (Rede de Mulheres Indígenas do Estado do Amazonas –Makira-êta) and Maranhao. Financial support was employed to purchase and distribute basic products such as foodstuffs, cleaning and personnel hygiene, PPE, fuel, and agricultural tools. These actions have helped directly more than 200 pregnant or postpartum quilombola women and indirectly an accounting managers and health professionals, indigenous women and people impacted by telemedicines and PPE}s, families and communities close to quilombola women. For indigenous people: The beneficiaries were seven indigenous communities from the Amazon region that had access to the videos, especially from the following ethnic groups: E'nepa, Warao, Yanomami, Wapichan, Macuxi, Ye’kwana Ticuna
3.1 | Results: Outcome Level | Please include outcome level results achieved | The UN agencies have supported the decrease of case fatality rate and mortality due to COVID-19 by supporting the COVID-19 response in a intercultural environment, gender-based, providing training to health care workers, and strengthening the health surveillance capacity. AFP's collaboration with local health authorities resulted in strengthening of the health care services and in the ability of the municipalities and states to conduct situation analysis, investigations and monitored cases.Thus helping reduce case fatality rate and mortality related to COVID-19 amongst indigenous communities by promoting the advancement of gender equality and women’s participation, ensuring that their needs and priorities inform the COVID-19 response measures. The successful in strengthening the potential of the indigenous women articulation in the face of the pandemic, assessing needs, giving greater visibility to their demands, and generate evidence to provide inputs to decision-making. Collaboration with civil society organizatins resulted in greater availability of information on the needs of indigenous women in the context of the pandemic. In that sense, groups identified the need for policies to enhance food security (distribution of foodbaskets, equipment and agricultural inputs), to support income generation (sewing machines and craft materials, facilitate contact with buyers), and to support culturally sensitive health care. The grants provided to civil society organizations contribute to mitigate COVID-19’s socioeconomic effects among the indigenous peoples of the Legal Amazon, more specifically, indigenous peoples from the indigenous territories of Roraima (6 comunities of Terra Indígena São Marcos), Maranhão (Terra Indígena Araribóia, Amarante, Arame, Bom Jesus, Governador, Cana Brava, Jenipapo dos Vieiras, Barra do Corda, Bacurizinho and Grajaú) and Amazonas (Rio Negro, Middle Rio Solimões and Middle Rio Juruá). The component emphasizes the interdependence between the political participation/ governance and emergency assistance (food sovereignty and indigenous medicine), reinforcing the need to strengthen women’s institutional capacities in all dimensions so that the response is effective, while also meeting immediate humanitarian needs. Actions that promoted COVID-19 prevention among indigenous communities, increasing vaccination rates, promoting intercultural dialogue, valuing indigenous traditions and beliefs, and avoiding the reproduction of stereotypes as well as the spread of fake news and misinformation. It has been also successfully strengthened indigenous leadership and empowerment in the context of the pandemic as the educational materials took into consideration indigenous inputs and ideas on COVID-19 prevention and vaccines using a multilingual and intercultural approach. The initiative produced excellent results for COVID-19 vaccination and prevention and the indigenous communities E'ñepa, Warao, Yanomami, Wapichan, Macuxi, Ye'kwana, and Ticuna gave a positive feedback about these actions that carried out on total, 3,609 trainings for Health care professionals, both online and/ or face-to-face. As for the population benefiting, it is estimated a total of 143,429 (99,12%), close to surpassing the total proposed number of 144,708 beneficiaries on the supporting use of pulse oximeters and Antigen-based rapid tests.
3.2 | Results: Output Level | Please include output level results achieved | As part of the efforts of the United Nations, in the exercise of its commitment to transparency and efectiveness and to better meet the needs and priorities in the pursuit of the Sustainable Development Goals (SDGs), we have continous populated the UN monitoring platform, called UN INFO*, so that the donors and the general public can monitor our results and achievements. This monitoring process is also part of the local efforts to report the implementation of the Socio-economic Response Plan for Brazil (SERP). The results achieved by the MPTF, despite its short term, are multidimensional and respond to the following pillars (outputs) of the SERP: Pillar 1: Health first, Pillar 2: Protectiong People, Pillar 3: Economic Response and Pillar 5: Social Cohesion and Community Resilience, as well as to SDGs 1.5, 3.1, 3.3, 3.4, 3.5, 3.7, 3.8, 3.10, 5.5, 10.2, 13., due to the expansion of the number of people accessing their rights, strengthening health services and systems, number of children supported, measures to deal with gender-based violence (GBV) and others, which will be added and reflected in the results available on a platform for consultation. More about the output levels results can be seem at the RBM-Interim tab. *UN INFO is provided by the UN Development Coordination Office (UNDCO) to support the UN Sustainable Development Group in its work. The SERP reporting component contains 5 pillars and 18 indicators
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | During the first semester of 2021, Brazil experienced the highest incidence of COVID-19 causing an increase in the demand for health services nationwide, thus leading to the collapse of the health system. From January 2021 to June 2021 the mean Case Mortality Rate (number of deaths per 100,000 Habitants) was in the States of Amazonas of 19.0 Maranhão of 8.4, and in Roraima 15.0. From January 2021 to June 2021 the mean The Case Fatality Rate (CFR), number of deaths divided into the number of confirmed COVID-19 cases, was in the States of Amazonas of 24.7%, Maranhão of 14.2%, and in Roraima 28.2%. When disaggregated by month, of 2021, each state displayed a decrease in deaths, however if more fund is on the verge the results can be expanded to all Legal Amazon with new resources and strategies due to COVID-19 dynamics: Figure 01. Observed decrease on the Case Mortality Rate in the Targeted States (Jan-Jun 2021)(See E6) Figure 02. Observed decrease on the Case Fatality Rate in the Targeted States (Jan-Jun 2021)(See F6) Case Mortality rate The state of Amazonas showed a reduction in the mortality rate from January to June 2021. In Roraima there was an increase in the mortality rate from January to February and a decrease in the rate until June. The state of Maranhão registered an increase in the mortality rate from January to June, the biggest increase observed in the period (630.9%). Case Fatality Rate The state of Amazonas registered an increase in lethality between the months of January and February and presented a reduction in the variation in the period. Roraima showed an increase in lethality from January to February and a decrease between March and June. In the variation of the period, a reduction in lethality is observed. The state of Maranhão has the highest lethality in the period, with an increase of 57.2% in the period. To put on track effective actions in such a large and difficult access geographical areas this was partially overcame by relying on pre-existing partnerships with civil society organizations (indigenous women coalitions) who were able to timely activate their networks on the field to successfully reach all territories of interest, including the most remote ones. A second challenge is related to the limited institutional capacities of the IPs, which contrasts with their long-range reach.The unstable political scenario, aggravated by the pandemic also generated several changes of secretaries and managers in different government instances. Impacting the maintenance of joints for following up the implementation in the short period. the spread of misinformation and fake news related to COVID-19 vaccines and prevention measures among the indigenous communities. Some religious leaders share false information about vaccines to prevent indigenous groups from getting vaccinated. In light of this situation, the intercultural dialogue and the workshops with indigenous leaders took more time than expected.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The program facilitated early detection and appropriate clinical management of COVID-19 case by using Ag-RDT and pulse oximeters for timely detection of signs of severity, through monitoring of silent hypoxemia. This approach contributed in decreasing hospitalization rate and CFR.Operational lessons involve regular Monitoring and Evaluation meetings with IPs whenever they lack ideal institutional capacities. A relevant programmatic is to register the process and results in knowledge products, such as the policy brief with guidelines for local governments. This kind of product can be employed both to inform key partners and other COs, and also as training material for workshops with duty bearers and aims to enhance the capacity of sub-national institutions to incorporate gender sensitive prevention and response strategies.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Implemented in the states of Amazonas, Maranhao and Roraima. The project was responsible for establishing partnerships in the benefited areas with state and municipal health secretariats, health authorities, and community leaders. Furthermore, due to its rapid implementation, new international partnerships were established to finance actions aimed at reducing the case fatality rate in the Amazon Region of Brazil. Also, the establishment of such activities demonstrated the local needs and capacity. As a result of this program, discussion is undergoing among the 3 level (municipality, state and federal) to guarantee the sustainability of access to the timely diagnosis of COVID-19 and adequate case management.Within this programme, in a joint effort from the four UN agencies involved, which have been working with non-traditional partners: local duty bearers and civil society. With that, expanded its ability to create the links of gender equality and develop evident to partners, understand state governments’ needs, and leverage UN power to foster a comprehensive gender mainstreaming approach under the SDG´s especiallly n° 03. In respect to the work alongside civil society in this programme, the consolidated the modality of small grants, emphasizing that being attentive and proactively working side by side on the field. The work with indigenous leaders could be established, educational, and health strategies using an intercultural approach, respecting indigenous culture and beliefs further enhancing a more productive dialogue. Due to the short time of the project, it was important to articulate the implementation with partners that already had a previous relationship, in addition to structuring more assertively the meetings and monitoring with new and old partners for the effective implementation. Which showed the importance of maintaining sustainable relations with territories regardless of the current project. In addition, it was important and decisive for the effectiveness of the project to ensure from the beginning gender perspective, especially for girls and pregnant women, since, in addition to already being vulnerable populations, the worsening of the crisis always intensify the marginality of some populations, such as this was the case of girls and pregnant women in the COVID-19 pandemic.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Mapping with quilombolas, it is still in the finalization process, which we will be reported in the final report, and mapping with other indigenous populations in need of health educational materials, including on COVID-19, in particular: Guajajara, Caapor, Awá. Gamela, Yalapapiti, Kamayurá, Desana, N'hepá.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | PAHO/ WHO, UNFPA, UNESCO and UNWOMEN: no programatic review
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome: Reduced case fatality rate and mortality related to COVID-19- among vulnerable populations in the Brazilian Legal Amazon
Output 1: Intercultural dialogue strengthened with a view to reduced case fatality rate and mortality related to COVID-19- among indigenous people in the Brazilian Legal Amazon | 14 | Fourteen digital health education materials (videos) were developed for indigenous people. Two educational publications related to COVID-19 prevention and education for health issues are currently being revised and are expected to be printed and released soon for the Ticuna and Warao communities. As the work was developed, other indigenous leaders became interested and contacted UNESCO to discuss the possibility to create similar materials and strategies with different ethnicities. | UNESCO reports and registries.
Indicator 1.1: Educational health material developed
Baseline: 0
Planned Target: 1 - Health educational material based on intercultural dialogue produced to be used in social media to indigenous groups.
Output 2: Information and data monitoring systems improved through dashboard with updated and disaggregated demographic and health data | 0 | There was no variance with planned target. The Dashboard are currently in the elaboration phase and will be delivered in August 2021. | UNFPA reports, registries and monitoring
Indicator 2.1: Dashboard developed and implemented
Baseline: 0
Planned Target: 1
Output 3: Health professionals trained on early diagnosis of COVID-19, protocols and case management, in pregnant and postpartum women from vulnerable populations, and acquisition of supplies and equipment to strengthen the response in selected areas
Indicator 3.1: Training developed and disseminated for health professionals on early diagnosis of COVID-19, managing cases of pregnant women and women in postpartum phase | 0 | There was no variance with planned target. The Distance learning are currently in the elaboration phase and will be delivered in August 2021.
Baseline: 0
Planned Target: 1 - Distance learning (Training developed and disseminated for health professionals on early diagnosis of COVID-19, including guidelines on the various stages of infection and protocols aimed at preventing maternal morbidity and mortality and injuries to the fetus, managing cases of pregnant women and women in postpartum phase)
Indicator 3.2: Health professionals trained on early diagnosis of Covid-19, protocols and case management, in pregnant and postpartum women from vulnerable populations, in selected areas | 0 | There was no variance with planned target. The Distance learning are currently in the elaboration phase and will be delivered in August 2021. |  | Haroldo, olhei de novo a tabela e acho que o certo é estar aqui mesmo, e nao como outro output.
Baseline: 0
Planned target: 250 - Knowledge of health professionals increased by means of training on early diagnosis of Covid-19, protocols and case management, in pregnant and postpartum women from vulnerable populations
Indicator 3.3 Number of pregnant and postpartum women from communities of selected areas | 0 | There was no variance with planned target. the facilitators' products are currently in the elaboration phase and will be delivered in August 2021.
Baseline: 0
Planned Target: 200 - Community cultural facilitation / Community resilience
Output 3.1: Supplies and equipment for prevention and early diagnosis of COVID-19 in pregnant and postpartum women acquired and distributed and support to the implementation of remote assistance rooms - in selected areas.
Planned Target: Supplies and equipment for prevention and early diagnosis of COVID-19 in pregnant and postpartum women acquired and distributed - in selected areas. | 142.000 PPEs to Amazonas. 44.640 PPE to Roraima. 16.000 PPEs to Maranhão. | There was no variance with planned target.
Planned Target: Implementation of remote assistance rooms - in selected areas. | 07 smart TV 07 notebook 07 cabo HDMI 07 locks for notebooks 07 Mouse wireless To 07 DSEIs, Amazonas. | The remote assistance rooms was only implemented in Amazonas, as due to the short implementation period, the state of Maranhão did not have time to articulate the counterparts. In any case, if there is a renewal/extension of the project, Maranhão is interested in implementing of remote assistance rooms.
Output 4: Strengthened capacity for Indigenous people from the Amazon Region, and indigenous migrants from Venezuela, offered timely diagnosis by COVID-19 Antigen Based Rapid Test, and monitored mild cases. | TOTAL (3 states): 100,000 Ag-RDT delivered 54,500 Ag-RDT to Amazonas ; 19,000 to Roraima. 26,500 to Maranhão. Please find details on the "beneficiaries"tab. Technical support in the elaboration of protocols to the State Health Secretariats of Amazonas and Roraima All tests were delivered with an instructional video. | There was no variance with planned target. | Invoices, Information note from the Amazonas Health Surveillance Foundation with the distribution of Ag-RDTs in the state, PAHO reports and SitReps
Indicator 4.1: Number of indigenous people from the Brazilian Amazon Region, and indigenous migrants from Venezuela, living in the selected areas.
Baseline: 0
Planned target: 141,015 Indigenous people from the Brazilian Amazon Region, and indigenous migrants from Venezuela, living in the selected areas, who will benefit from the supplies acquired that will allow timely diagnosis by COVID-19 Antigen Based Rapid Test, monitoring of mild cases, and transportation of severe cases to hospitalized care.
Output 4.1: Strengthened capacity for traditional peoples and communities from the Amazon Region, offered timely diagnosis, decreased COVID-19 incidence, and case fatality rate. | TOTAL (3 states): 2,590 pulse oximeters delivered: 2,290 to Amazonas ; 110 to Roraima ; 190 to Maranhão Please find details on the "beneficiaries"tab. Support to elaborate protocols for its use | There was no variance with planned target. | PAHO reports and registries
Indicator: Number of people from the Brazilian Amazon region’s traditional communities living in the selected areas
Baseline: 0
Planned target: 3,693 People from Brazilian Amazon region’s traditional communities, living in the selected areas, who will benefit from the supplies acquired that will allow timely diagnosis by COVID-19 Antigen Based Rapid Test, monitoring of mild cases, and transportation of severe cases to hospitalized care
Output 5: Enhanced capacity of government institutions in charge of the COVID-19 emergency response in the Legal Amazon in incorporate the needs of Indigenous women into COVID-19 prevention and response strategies. | 0 | There was no variance with planned target. The workshops are currently in the elaboration phase and will be delivered in August 2021. | UN Women and partners' atendee list, screenshot of online trainnings
Indicator: Public technical personnel and managers with increased knowledge on gender and indigenous peoples’ rights mainstreaming
Baseline: 0
Planned target: 20 - Knowledge increased by means of training, assessment of the emergency health response plan and related actions focusing on responsivenes to gender, race and ethnicity, and recommendations based on the rapid assessment results and consultations to indigenous leaders.
Output 6: Enhanced capacity of indigenous women who are local community leaders in Legal Amazon territories to meaningfully participate in and influence decision making by presenting recommendations regarding the emergency response to COVID-19. | 0 | There was no variance with planned target. The recommendations are currently been consolidated and will be complemented/ released by August 2021. | UN Women reports and official press
Indicator:Recommendations formulated based on the consultations with indigenous peoples submitted to decision-makers
Baseline: 0
Planned target: 3 - Formulation of recommendations based on consultations with indigenous leaders and community-led campaigns to raise awareness on prevention-measures, symptoms and vaccination

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://pt.unesco.org/news/educacao-em-saude-e-bem-estar-populacoes-indigenas-do-brasil
Communication plan including impactful stories has been developed. Representatives of the participating AFPs'communication teams had a meeting with the RCO Communication Officer regarding the communication material, which will be available at the end of the programme.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words) | The United Nations and UNESCO’s office in Brazil develop health and well-being education actions for indigenous populations with a pedagogical, multilingual and intercultural approach. The objective is to collaborate in the dissemination of information that can foster the protection of indigenous peoples, especially in the current context marked by the health crisis caused by the COVID-19 pandemic. The work is carried in the mother tongue of the populations, an important process to preserve the intangible heritage, involving the traditional knowledge and rights of these communities, as well as to raise awareness of their cultural richness and to promote essential interfaces between indigenous populations and society. Indigenous peoples represent 5% of the world's population, but they are among the 15% poorest ones. They face challenges such as increasing migration, educational disadvantage, pressure to culturally assimilate other values, gender-based violence and other forms of discrimination, as well as limited access to health services and employment. The videos show the work carried out with seven indigenous ethnic groups – Wapichan, Ticuna, Yanomami, Ye’kwana, Macuxi, Taurepang and Warao – all of them present in the Amazon and in Roraima state. The initiative made it possible for indigenous peoples to access information about prevention and treatments for STI/HIV/AIDS, viral hepatitis and COVID-19. UNESCO is committed to protecting the rights of indigenous peoples, and according with the 2030 Agenda, to ensure that they are not left behind while we build a better, more sustainable and more just future for all.
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media. | https://pt.unesco.org/news/educacao-em-saude-e-bem-estar-populacoes-indigenas-do-brasil
Please provide links to any videos that have been produced during implementation. | https://pt.unesco.org/news/educacao-em-saude-e-bem-estar-populacoes-indigenas-do-brasil
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## Additional Quantitative Data
PAHO/ WHO
|  | # Total beneficiaries of |  | # HCW trained
|  | Ag-RDT | Pulse-oximeters |  | TOTAL
| Amazonas | 54.5 | 39.584 | 105 | 94.189
| Maranhão | 26.5 | 3.284 | 155 | 29.939
| Roraima | 19 | 1.901 | 20 | 20.921
| TOTAL | 100 | 44.77 | 280 | 144.77
[6 empty] | Ag-RDT : Number of beneficiaries per group. * Assumption and calculation memory: Each Ag-RDT was used by a single patient. | [13 empty] | Pulse oximeters: Number of beneficiaries per group *Assumption and calculation memory: average use of pulse oximeter 7 days per patient. Each pulse oximeter was used by a single patient during this period. The supplies were used for 121 days (1 March to 30 June 2021) (17 x 7 days).
|  | Target # beneficiaries of |  |  |  |  | Ag-RDT | Indigenous population: women | [5 empty] | Non-Indigenous population: women | [6 empty] | Total # of |  | Indigenous population: women | [5 empty] | Non-Indigenous population: women
|  | Ag-RDT | Pulse-oximeters | TOTAL |  |  |  | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+ | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+ |  | Pulse-oximeters | Beneficiaries | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+ | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+
| Amazonas | 54.5 | 39.529 | 94.029 |  | Amazonas | 54.5 | Amazonas | 3460 | 2768 | 2076 | 7267 | 6229 | Amazonas | 1014 | 739 | 1130 | 1289 | 1278 | Amazonas | 2.29 | 39.584 | Amazonas | 2513 | 2011 | 1508 | 5278 | 4524 | Amazonas | 736 | 537 | 821 | 936 | 928
| Maranhão | 26.5 | 3.28 | 29.78 |  | Maranhão | 26.5 | Maranhão | 1988 | 663 | 663 | 4638 | 2650 | Maranhão | 448 | 325 | 576 | 651 | 651 | Maranhão | 190 | 3.284 | Maranhão | 246 | 82 | 82 | 575 | 328 | Maranhão | 56 | 40 | 71 | 81 | 81
| Roraima | 19 | 1.899 | 20.899 |  | Roraima | 19 | Roraima | 345 | 0 | 345 | 2764 | 4145 | Roraima | 11 | 56 | 134 | 950 | 749 | Roraima | 110 | 1.901 | Roraima | 35 | 0 | 35 | 277 | 415 | Roraima | 1 | 6 | 13 | 95 | 75
| TOTAL | 100 | 44.708 | 144.708 |  | TOTAL | 100 | TOTAL | 5793 | 3431 | 3084 | 14668 | 13024 | TOTAL | 1473 | 1120 | 1840 | 2889 | 2677 | TOTAL | 2.59 | 44.77 | TOTAL | 2794 | 2093 | 1625 | 6129 | 5267 | TOTAL | 793 | 583 | 906 | 1112 | 1084
[8 empty] | Indigenous population: men | [5 empty] | Non-Indigenous population: men | [8 empty] | Indigenous population: men | [5 empty] | Non-Indigenous population: men
[8 empty] | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+ | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+ |  |  |  | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+ | Age group | 0-9 | 10-19 | 20-29 | 30-59 | 60+
[8 empty] | Amazonas | 4088 | 0 | 1363 | 6131 | 10219 | Amazonas | 1122 | 673 | 1047 | 1304 | 1304 |  |  |  | Amazonas | 2969 | 0 | 990 | 4453 | 7422 | Amazonas | 815 | 489 | 761 | 947 | 947
|  | # Total beneficiaries of | [5 empty] | Maranhão | 2120 | 707 | 0 | 3533 | 4240 | Maranhão | 560 | 229 | 560 | 651 | 651 |  |  |  | Maranhão | 263 | 88 | 0 | 438 | 525 | Maranhão | 69 | 28 | 69 | 81 | 81
|  | Ag-RDT | Pulse-oximeters | TOTAL |  |  |  | Roraima | 380 | 760 | 0 | 1520 | 4940 | Roraima | 30 | 10 | 191 | 905 | 764 |  |  |  | Roraima | 38 | 76 | 0 | 152 | 494 | Roraima | 3 | 1 | 19 | 91 | 76
| Amazonas | 54.5 | 39.584 | 94.084 |  |  |  | TOTAL | 6588 | 1467 | 1363 | 11185 | 19399 | TOTAL | 1712 | 913 | 1798 | 2859 | 2718 |  |  |  | TOTAL | 3270 | 164 | 990 | 5043 | 8442 | TOTAL | 887 | 518 | 849 | 1118 | 1104
| Maranhão | 26.5 | 3.284 | 29.784
| Roraima | 19 | 1.901 | 20.901 |  |  |  | Per other age-group | [14 empty] | Per other age-group
| TOTAL | 100 | 44.77 | 144.77
[8 empty] | Indigenous population: women | [5 empty] | Non-Indigenous population: women | [8 empty] | Indigenous population: women | [5 empty] | Non-Indigenous population: women
[8 empty] | Age group | 0-14 | 15-24 | 25-59 | 60+ |  | Age group | 0-14 | 15-24 | 25-59 | 60+ |  |  |  |  | Age group | 0-14 | 15-24 | 25-59 | 60+ |  | Age group | 0-14 | 15-24 | 25-59 | 60+
[8 empty] | Amazonas | 3868 | 4219 | 7384 | 6329 |  | Amazonas | 1384 | 935 | 1854 | 1278 |  |  |  |  | Amazonas | 2809 | 3065 | 5363 | 4597 |  | Amazonas | 1005 | 679 | 1346 | 928
[8 empty] | Maranhão | 2650 | 0 | 5300 | 2650 |  | Maranhão | 611 | 451 | 938 | 651 |  |  |  |  | Maranhão | 328 | 0 | 657 | 328 |  | Maranhão | 76 | 56 | 116 | 81
[8 empty] | Roraima | 345 | 0 | 3109 | 4145 |  | Roraima | 39 | 95 | 1017 | 749 |  |  |  |  | Roraima | 35 | 0 | 311 | 415 |  | Roraima | 4 | 10 | 102 | 75
[8 empty] | TOTAL | 6863 | 4219 | 15793 | 13124 |  | TOTAL | 2033 | 1480 | 3809 | 2677 |  |  |  |  | TOTAL | 3172 | 3065 | 6331 | 5340 |  | TOTAL | 1085 | 744 | 1564 | 1084
[8 empty] | Indigenous population: men | [5 empty] | Non-Indigenous population: men | [8 empty] | Indigenous population: men | [5 empty] | Non-Indigenous population: men
[8 empty] | Age group | 0-14 | 15-24 | 25-59 | 60+ |  | Age group | 0-14 | 15-24 | 25-59 | 60+ |  |  |  |  | Age group | 0-14 | 15-24 | 25-59 | 60+ |  | Age group | 0-14 | 15-24 | 25-59 | 60+
[8 empty] | Amazonas | 4088 | 0 | 7494 | 10219 |  | Amazonas | 1459 | 860 | 1827 | 1304 |  |  |  |  | Amazonas | 2969 | 0 | 5443 | 7422 |  | Amazonas | 1059 | 625 | 1327 | 947
[8 empty] | Maranhão | 2827 | 0 | 3533 | 4240 |  | Maranhão | 674 | 395 | 930 | 651 |  |  |  |  | Maranhão | 350 | 0 | 438 | 525 |  | Maranhão | 84 | 49 | 115 | 81
[8 empty] | Roraima | 760 | 380 | 1520 | 4940 |  | Roraima | 35 | 101 | 1000 | 764 |  |  |  |  | Roraima | 76 | 38 | 152 | 494 |  | Roraima | 4 | 10 | 100 | 76
[8 empty] | TOTAL | 7674 | 380 | 12547 | 19399 |  | TOTAL | 2168 | 1355 | 3758 | 2718 |  |  |  |  | TOTAL | 3395 | 38 | 6033 | 8442 |  | TOTAL | 1147 | 684 | 1543 | 1104