## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Supporting the return of vulnerable Mongolian women and children stranded abroad due to COVID-19 and facilitating labor | Overall Duration (months) | 1.5
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-02-12
MPTF Office Project Reference Number: | 125949 | Original End Date (dd.mm.yyyy) | 2021-09-25
Country | MONGOLIA | Current End date(dd.mm.yyyy) | 2021-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IOM | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Foreign Affairs, State Emergency Commission, National Emergency Management Agency, Ministry of Labor and Social Protection, Authority for Family, Child and Youth Development, National Centre for Mental Health, Border Protection Authority, General Authority for Specialized Inspection, Mongolian Embassies abroad and foreign Embassies in Ulaanbaatar
Report Cleared By
o Name: | Tapan Mishra
o Title: | Resident Coordinator
o Email address: | tapan.mishra@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project responded to the most urgent need of the Government of Mongolia’s priority as identified in the UN Mongolia Socio-Economic Response Plan (SERP) and the national Government COVID-19 Action Plan, which aims to ensure support while abroad and safe return of the most vulnerable Mongolian migrants stranded abroad because of COVID-19. In response to government requests for such assistance, IOM coordinated with the Ministry of Foreign Affairs (MFA) and Mongolian diplomatic missions abroad as well as IOM missions in sending countries, and organized return assistance to 67 Mongolians stranded abroad and cash assistance to 44 Mongolians (31 households) stranded abroad. IOM also supported the digitization of notary services of consular offices that was imperative in the COVID-19 context, and cooperated with the Deputy Prime Minister's Office and specialised agencies, such as General Authority for Border Protection, Mongolian Customs General Authority, Mongolia Immigration Agency, General Authority for Specialized Inspection, working on border-crossing points to increase their capacity and preparedness as well as to estimate further assistance needs that would allow gradual resuming of operation of border-crossing points by implementing the IOM’s “Risk Assessment Tool for Resuming Operations at Points of Entry in the COVID-19 Context” at six major border-crossing points and organizing trainings on “Standard Operating Procedures (SOP) for Front-line Border Officials at the Point of Entry (PoE) in Response to COVID-19 Outbreak” for a total of 237 front-line border officials.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Purpose: Contribute to reducing the vulnerability and ensure safe return of Mongolian migrants stranded abroad as well as increase the level of preparedness of main border-crossing points for operation in the context of persistent COVID-19 threat. Direct beneficiaries of return and cash assistance: 68F 43M; 74 adults and 37 children, in total 111 beneficiaries. Direct beneficiaries of digitization of consular services: 47 consular departments of the MFA in foreign countries Indirect beneficiaries of digitization of consular services: Mongolian nationals receiving notary services abroad. Direct beneficiaries of border risk assessments and trainings: 237 border officials (85F; 152M) of General Authority for Border Protection, Mongolian Customs General Authority, Mongolia Immigration Agency, General Authority for Specialized Inspection
3.1 | Results: Outcome Level | Please include outcome level results achieved | 1. Mongolian migrants stranded abroad have access to emergency assistance Since the introduction of the border closure related to COVID-19 in February 2020, there were over 10,000 Mongolians stranded all around the world, awaiting special chartered flights in increased vulnerable situations induced by the COVID-19 pandemic and risk of infection. Within the project, a total of 111 most vulnerable Mongolian migrants stranded abroad have received return assistance of flight tickets and quarantine costs, and 44 beneficiaries of 31 households received cash assistance to support their livelihood while abroad, in 14 countries including Turkey, The United States of America, Canada, Japan, Hungary, Republic of Korea, United Kingdom, Indonesia, Taiwan R.O.C, Ukraine, Germany, Malaysia, Russian Federation and Lao People’s Democratic Republic. 2. The capacities of border-crossing officials in Mongolia are strengthened for operating in the “new reality” of persistent COVID-19 threat In cooperation with Deputy Prime Minister's Office and border agencies, General Authority of Specialized Inspection, Customs Authority, Border Protection Agency, and Immigration Agency, IOM supported the implementation of border risk assessments at six major border-crossing points. The IOM’s “Risk Assessment Tool for Resuming Operations at Points of Entry in the COVID-19 Context” and the “Standard Operating Procedures (SOPs) for Front-line Border Officials at the Point of Entry (PoE) in Response to COVID-19 Outbreak” were institutionalized in the Mongolian context on January 2021, and served as theoretical and operational carrying framework, and were highly appreciated by the Government. As a result of the risk assessment, the Government took the decision to gradually re-start border operation starting from June 2021. The Government also adapted an Action Plan with interventions necessary for supporting the border opening. The activities also created the space for the Government to do an assessment of already existent SOPs and regulations, and a total of 14 temporary and permanent regulations and SOPs were synergized into one single unified procedure for operating the borders in COVID-19 context, which was later approved by the Government of Mongolia and is now in effect.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 and 1.2. IOM identified the most vulnerable Mongolian migrants abroad with the help of diplomatic missions of MFA and IOM sending missions using the IOM vulnerability checklist and operationalized both direct assistance to beneficiaries while they are still abroad and return assistance, including the flight and quarantine costs. Prior to the project, in Mid-2020, Mongolian MFA carried out a preliminary assessment, identifying the following needs: food, shelter/accommodation, medical treatment, travel tickets (including connection), visa/travel support, etc. As a result of the preliminary assessment and regular consultations with the Mongolian MFA and IOM missions in sending countries when identifying the vulnerable cases at the beginning of the project, direct cash transfers were determined as the most efficient and rapid form of assistance in the given circumstances. Therefore, the project has provided cash assistance to 44 beneficiaries and return assistance to 67 beneficiaries. The Government of Mongolia covered the quarantine costs for these beneficiaries, while IOM provided the cash assistance and flight ticket costs. Output 1.3. IOM cooperated with MFA and Mongolian Consular Offices in foreign countries to support the Mongolian migrants who currently reside abroad by connecting the diplomatic missions to the national e-notary system so that the services provided to the Mongolians abroad are faster and can be done remotely, without direct contact with the beneficiaries and consular officials. Output 2.1 and 2.2. In accordance with the Order of the Deputy Prime Minister of Mongolia, a working group was organized and conducted four in-person and two online meetings and trainings, and established sub-working groups to conduct the risk assessments. The "Standard Operating Procedures (SOP) for Front-line Border Officials at the Point of Entry (PoE) in Response to COVID-19 Oubreak" was institutionalized in January 2021. A total of 84 border officials conducted the risk assessment from 19 - 22 February 2021, while a total of 237 border officials were trained on the “Standard Operating Procedures (SOP) for Front-line Border Officials at the Point of Entry (PoE) in Response to COVID-19 Outbreak” from 13 - 14 February 2021. The risk assessment and the trainings were conducted at six border-crossing points in Mongolia: • Buyant-Ukhaa international airport • The Chinggis Khaan new international airport • Altanbulag Ground crossing • Sukhbaatar Railway station • Zamiin-Uud Ground crossing • Zamiin-Uud Railway station Overall, the risk assessments at six border-crossing points identified 315 risk factors among which 20 risks needed urgent measures to be adopted, 27 needed urgent measures to plan as a priority, 36 needed medium and short-term measures to be planned, 86 needed long-term measures to be planned but do not require urgent action, 36 are accepted risks given low probability and 110 were factors with no significant risks identified. The working group developed an action plan to mitigate the risks through short-, medium-, long-term interventions in cooperation with government agencies, local administration and international organizations on February 28, which was followed by a unified procedure for border operations during disasters and emergencies such as COVID-19, approved by the Government on June 4.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Challenge: Due to a spike in local transmission of COVID-19 in Mongolia, a number of charter flights were cancelled/delayed. However, there were many returnees who were waiting to return and quit their jobs, suspended their rental contracts. Therefore, when the flights were suddenly cancelled, they were left with no place to sleep or means to earn their living. In response to these challenges, there were civil society demonstrations at the Embassies of Mongolia, requesting an urgent return and continuance of charter flights. Measures taken: With the active support and coordination from the MFA, IOM supported the return of 67 returnees who were identified and whose transporation was arranged prior to the charter flight cancellations or right after the charter flight continuance, to reduce the negative impact of flight cancellations on identified vulnerable migrants. In regards to the Risk Management Matrix Risk 1. A larger number of identified beneficiaries are in an extremely vulnerable positions and require comprehensive protection and/or shelter support. Management: To address diverse needs of all identified vulnerable beneficiaries, IOM consulted with the MFA and IOM sending missions and decided that cash assistance is the fastest and the most effective method of support that the benefiaries could use for their most urgent needs, such as food, shelter/accommodation, medical treatment, etc. Risk 2. COVID-19 could impact project implementation itself, with higher risk to IOM and Mongolian Embassies’ staff implementing activities. Management: IOM and diplomatic mission staff implemented the project while upholding strict infection prevention practices. Moreover, the digitization of notary services, which account for 25-30 per cent of the total consular services, have facilitated the remote consular notary services and reduced the number of Mongolians engaging the diplomatic missions, preventing risk of infection.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | During the risk assessment, it has come to our attention that since the beginning of the pandemic, the Government has developed several policies, guidelines and procedures. However, as the policies are at times inconsistent, the border agencies and officials at the PoEs are operating with unclear and insufficient guidance and procedures in the persistent threat of COVID-19. At some PoEs, unclear procedures resulted in improper and overusage of PPEs, establishment of quarantine facilities that do not meet infection prevention requirements, unclear arrangement of movement flows, etc. Therefore, IOM has supported the development of unified procedure for border operations in the COVID-19 context, which integrated 14 temporary and permanent regulations and SOPs. The project applied gender-sensitive approach by recognizing different needs of male and female vulnerable migrants with special attention to reducing the vulnerabilities of women migrants who were found to be more affected by challenges associated with migration and overall COVID-19 impact: direct and socio-economic impact of related restrictions. Mongolian migrant women working abroad usually tend to work in service sectors, such as restaurants, hotels, shops etc. as assistants, which is also the sector that experienced the most restrictions and layoffs. Therefore, the project identified and supported 68 females (out of total 111) in particularly vulnerable situation due to loss of job and income, in need of medical assistance, and additional pressure of taking care of the children who are sick, etc.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project positively impacted the interaction and cooperation between border agencies - General Authority for Border Protection, Mongolian Customs General Authority, Mongolia Immigration Agency and General Authority for Specialized Inspection - through establishment of joint working groups with regular meetings and interactions for preparing and implementing risk assessments, as well as developing a unified procedures for border operations during COVID-19. Prior to the project implementation, border agencies operating at the checkpoints did not have synchronized cooperation which is crucial during emergency situations, but as a result of the project, the border agencies started regularly interacting with each other, learning from each other's experiences, etc. The project facilitated the beginning of integrated approach to safe and regular border crossing, further initiating discussions on developing guidelines for border agencies to cooperate together during emergencies, as well as the need for integrated information systems to facilitate the information sharing between agencies, which IOM is planning to implement in the future through new project. In this matter, IOM has already started reaching out to the border agencies, introducing IOM's MIDAS systems.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | N/a
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | With approval from the donor (UK) the project used the savings from Outcome 2 (about USD9,000) to support an increased number of stranded migrants under Outcome 1.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The project was implemented in a timely and cost-effective manner, given that it delivered more results than planned. The successful implementation of activities under Outcome 2 allowed additional mobilization of CHF35,000 for COVID-19 related interventions at the border from SDC.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Output 1: Mongolian migrants stranded abroad have access to emergency assistance | In total 111 migrants were provided emergency assistance; 44 vulnerable migrants (31 households) assisted abroad and 67 vulnerable migrants safely returned to Mongolia | The project proposed to provide cash assistance to 30 vulnerable migrants, however, in the COVID-19 context, the project provided assistance to 31 households which consisted of 44 vulnerable migrants. With the increased number of returned migrants (as explained below) the total reported figure is 111 instread of 60. | Reports by MFA and MIAT (Mongolian Airlines)
Indicator 1.1: Total number of vulnerable migrants assisted in the countries of residency and with return assistance
Baseline: 0
Planned Target: 60 vulnerable migrants assisted abroad or safely returned to Mongolia
Indicator 1.2: Number of vulnerable migrants returned | 67 vulnerable migrants safely returned to Mongolia | Because the migrants returned from different countries, the cost of flight tickets varied and offered us opportunity to bring more stranded migrants: 67 instead of 30. | Reports by MFA and IOM missions in the countries of residency of migrants
Baseline: 0
Planned Target: 30 vulnerable migrants are returned by March 31st, 2021
Output 2: The capacities of border-crossing officials in Mongolia are strengthened for operating in the “new reality” of persistent COVID-19 threat | 1. “Risk Assessment Tool for Resuming Operations at Points of Entry in the COVID-19 Context” 2. “Standard Operating Procedures (SOP) for Front-line Border Officials at the Point of Entry (PoE) in Response to COVID-19 Outbreak” Two tools available and institutionalized in the Mongolian context. |  | DPM Office, specialised agencies working at PoEs
Indicator 2.1: Number of tools for PoEs activity in COVID-19 context available and institutionalized
Baseline: 0
Planned Target: 2 tools available and institutionalized
Indicator 2.2: Number of frontline border-crossing officials that are trained in SoPs for border operation during COVID-19 | 237 frontline border officials trained | Due to the current COVID-19 situation, the training were conducted online, allowing more officials to join the training: 237 persons. | Reports by border authorities
Baseline: 0
Planned Target: At least 60 frontline border-crossing officials are trained in SoPs for border operation during COVID-19

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
To improve their lives, Ms. B and her husband went to Turkey in 2008. They were living without legal visas and their migration status was irregular. In 2011, Ms. B gave birth to a son in Turkey. In 2018, when their son was 7 years old, he fell down from the stairs and got back and brain injuries. Since the accident, the son has been under constant doctor’s supervision and received special medical treatment twice a month. The treatment was of very high cost, therefore, the father worked full day shift (day and night - 24 hrs) to earn the expenses of the treatment. Due to heavy workload and stress, the father's medical condition deteriorated, and could not receive proper medical services due to the pandemic restriction and passed away on 14 January 2021. Ms. B lost her husband and had to take care of her son, who is sick, and had to earn a living for both of them which was very hard to do in Turkey, especially during the pandemic. Therefore, they wished to return to Mongolia and seek support from their relatives and friends back home. The project has supported the return of Ms. B and her son in February 2021. They're now at their home in Mongolia, safe and sound.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Caption: Two of IOM Mongolia team members - National project officer Oyunbileg Rentsendorj (on the left) and Programme manager Victor Lutenco (on the right) - received the orders of Polar Star, the highiest civiliam award of Mongolia for their contributions helping to bring Mongolians back who were in vulnerable situation due to COVID-19. Photo: IOM, Ulaanbaatar Mongolia, 2021
Press release issued by the Ministry of Foreign Affairs of Mongolia: http://mfa.gov.mn/61359 Facebook post: https://www.facebook.com/IOMMongolia/posts/841381733185695