## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | FUNDING - Social protection and employability promotion to mitigate the socio-economic impacts of COVID-19 | Overall Duration (months) | 10 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | January 12 2021
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | November 15 2021
Country | Antigua and Barbuda and BVI | Current End date(dd.mm.yyyy) | November 15 2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, WFP, ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Antigua and Barbuda: Ministry of of Public Safety, Legal Affairs and Labour Ministry of Social Transformation and the Blue Economy UWI Open Campus National Training Agency BVI: Ministry of Labour Ministry of Health and Social Development Ministry of Natural Resources, Labour and Immigration
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | During the reporting period, activities focused on preparing the social protection systems/ programmes in BVI and Antigua and Barbuda so they can effectively be leveraged to provide temporary cash support to households affected by COVID-19 and be strengthened through the emergency response. The enrolment of potential trainees for the employability training in Antigua and Barbuda, and the BVI is ongoing. Course design is also ongoing: course content editing is completed, multimedia editing is in progress. The course is scheduled to commence on 9 August 2021. Additionally, policy support to review the Social Protection Policy is ongoing in both countries, a draft that considers shock responsiveness is available. More specifically in Antigua and Barbuda: -The joint programme supported the implementation of the new Social Protection Act through technical support to set the new governance institutions and is supporting the recertification process to identify social assistance beneficiaries who are entitled to receive support under the 2020 Social Protection Act using the new targeting mechanism. These beneficiaries will receive the COVID-19 top-ups under the MPTF. The joint programme has also started its support to transition from a paper-based data management system to a digitized one. 10% of intended beneficiaries were registered and their information directly imported in the system for detailed assessment of their eligibility. -The online employability and entrepreneurship training course has been developed and materials are being populated on the UWI Open Campus Learning management System (LMS) for course delivery. In BVI: -Technical support has been provided to the Ministry of Health and Social Development to strengthen social protection systems to meet increased demand and reach additional vulnerable individuals and families as part of its COVID-19 income support programme efficiently and effectively. Support is ongoing, including technical assistance for the design and implementation of the data management system for applications. Capacity strengthening has been provided in the form of trainings to enumerators, the development of technical guidance documents for the use of digital registrations and validation system. Trouble shooting for the technical and non-technical aspects of the registrations (including the conmmunication campaigns and the review of the schedule). - A concept note for the bottleneck analysis of existing grievance mechanisms has been developed and the analysis carried jointly between the Ministry and with technical assistance of the joint programme has started.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | In Antigua and Barbuda: Indirect beneficiaries: 31 staff from the Ministry of Social Transformation and the Social Protection Board have been trained on data collection and 21 on end to end use of the management information system: data collection, targeting, payments, reconciliations and grievances In BVI: Indirect beneficiaries: 18 Staff from Social Development Department have been trained on digital data collection through Kobo
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved | To date, the following has been achieved: In Antigua and Barbuda: - Effective technical assistance to support the set up of the new social protection in Antigua and Barbuda under the new Social Protection Act (Social Protection Board, Fund and Commission that will allow for a more efficient utilization of national resources and provide a foundation based on human rights and equity) - Recertification of beneficiaries under the old legal framework is ongoing to identify the new social assistance beneficiaries under the new Social Protection Act that will benefit from the top-ups - The digitization of the social protection management through the use of UNICEF MIS system is ongoing, key staff were trained and 10% of intended beneficiaries were registered - Shock responsiveness is considered in the two draft social protection policies In BVI: - Effective technical assistance to support the set up of the Income Support Program - The digitization of the registration process and data management system
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Difficulties faced during the reporting period included: - COVID-19 new waves in both countries slowed project progress. In Antigua and Barbuda, the containment measures contributed to support being delivered or conducted remotely. The joint programme team traveled in country as soon as it was possible (with quarantine). In the BVI, Covid 19 cases have dramatically increased since 7 July 2021, resulting in new movement restrictions and limitations on economic activity. This may result in more BVI residents in need of economic assistance due to the impact of Covid 19. This wave resulted in a more complex work environment with Ministry counterparts, as staff have had to reprioritize tasks and activities, as well as take on additional workloads, covering for colleagues who have become sick. Difficulties encountered at programmatic level include: -The ongoing reforms in Antigua and Barbuda in the social protection sector also contributed to delays in the response as the new institutions and systems need to be in place to implement the support. The systemic change created some resistance to change. As a mitigation measure, the programme is complementing its support under the Fund with capacity building and communication on the new Act. - Insufficient staff in Antigua and Barbuda to support the preparatory activities for the recertification and delivery of the cash transfers, with the Ministry focal point being out of office on sick leave for more than half of the reporting period. The Minister appointed additional support from other departments, with experience in data collection to fill the gap. - Insufficient capacity of intermediary institutions in BVI to deliver cash or make payments (ability, reliability, reach). - Communication about the registration period in BVI was delayed, resulting in a lower number of expectations than anticipated. To mitigate the issue, communication was increased, and the registration period was extended for an additional week. - An attempt to implement a self-registration online module was initiated, however, this has proved challenging as those self-registering have not provided all the relevant information required, resulting in additional follow up communication. - The emergency response to the volcanic eruption in Saint Vincent contributed to stretch UN staff resources. To mitigate the impact, additional support was onboarded. - Given the high demand for instructional designers for online instruction delivery, the implementation of the online training did not start as planned. -It was also difficult to secure a Learning Management System (LMS) to populate the learning materials for the delivery of the online employability training. To mitigate this issue, the Open Campus of the University of the West Indies, was contracted to use its existing LMS to deliver the training. The contract with the Open Campus was signed on 14 June 2021, and course design is ongoing. Delivery is scheduled to commence 9 August 2021 to 17 October 2021. Given the challenges in execution a no cost extension is being requested until January 15 2022 to ensure all project results are completed.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Lengthy process to approve the very precise targeting criteria at Cabinet level combined with the rapidly changing concept proved difficult. Having broader criteria validated at Cabinet could allow for adaptation of those, considering the changing contexte to ensure a programme better tailored to the rapidly changing needs (without a lengthy validation process).
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Three Agencies have partnered for the execution of this Joint Programme: UNICEF, ILO and WFP. Work with a number of key national partners have been ongoing. Antigua and Barbuda: Ministry of Social Transformation and Blue Economy (Department of Social Policy and Protection) Ministry of Legal Affairs, Public Safety and Labour BVI: Ministry of Health and Social Development Partnershps and collaboration have been vital to the project and have contributed significantly to achieving project results. Given the pandemic, new partnerships are difficult to establish due to travel and meeting restrictions, however, coordinating committees have been established in both countries. In Antigua and Barbuda, The committee members include officials from the (a) Antigua & Barbuda National Training Agency (b) Ministry of Legal Affairs, Public Safety and Labour, (c) Department of Social Policy, Research and Planning, Ministry of Social Transformation; and (d) The University of the West Indies, Open Campus British Virgin Island (a) Ministry of Natural Resources, Labour and Immigration, (b) Hamilton Lavitty Stoutt Community College (c) Social Development
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | N/A
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Given external factors, the dramatic increase of Covid cases, and preparations for the upcoming start of the hurricane season, the initial registration process in BVI was deferred to the next quarter. In Antigua and Barbuda, given the expected delays that could be expected if the recertification process to identify the new beneficiaries under the new Social Protection Act and to promote more equitable distribution of resources and oversight , UNICEF deployed its global Management and Information System for Humanitarian Cash Transfers- HOPE, to improve collection, storage and management of social assistance beneficiary information and limit any fraud and misappropriation. The UNICEF MIS will provide a ready to use solution for the ministry for emergency programmes while a localized national MIS solution is being developed with support of UNICEF.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Additional human resources: a consultant has been recruited to provide some in-person support to BVI. Budget adjustments: change in budget allocation was completed to decrease travel expense by $14,000 and increase Communication by the same amount, i.e., $7000 per country for the communication strategy.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] The Socio-economic impact of COVID 19 on people (existing beneficiaries and those newly unemployed) is mitigated.
Indicator: Effective delivery of cash transfers and etraining to those in need due to COVID-19. Measures expected: 1) rating of efficiency based on level of delivery in a timely manner and 2) rating of effectiveness of delivery to beneficiaries
Baseline: 0
Planned Target: 0
Output 1.1 Providing cash transfers to households in need through existing social protection systems | Indicator Target: 0 | Main indicators are linked to key activities which are currently ongoing and based on new timelines, will be completed by the end of January 2022. Variances were due to dramatic increases in COVID cases resulting in a more complex work environment with Ministry counterparts and containment measures contributed to support being delivered or conducted remotely, insufficient staff available to support the preparatory activities for the recertification and delivery of the cash transfers, as well as insufficient capacity of intermediary institutions to deliver cash or make payments (ability, reliability, reach). Based on the current design, the project will complete a database of beneficiaries and then apply a scoring criteria to identify eligible beneficiaries to access the support, which has already been created. Enumerators have been trained and verifications of applications is ongoing. 10% of intended beneficiaries registered and a recertification of beneficiaries is ongoing. The digitization of the social protection management through the use of UNICEF MIS system has been completed and it is anticipated that the remaining 90% of the beneficiaries will be registered and the transfers completed by January 2022. | Beneficiaries Database Eligibility Criteria
Indicator 1.1.1: # of COVID 19 affected households who receive transfers through the social protection system
Baseline: 0
Planned Target: 600
Output 1.2 Increasing capacities to provide online entrepreneurship and employability training to existing beneficiaries of social protection programmes and unemployed impacted by COVID 19 | Indicator Target: 0 | Main indicators are linked to key activities which are currently ongoing and based on new timelines, will be completed by the end of January 2022. Variances were due to high demand for instructional designers for online instruction delivery as well as difficulties with securing a Learning Management System (LMS) to populate the learning materials for the delivery of the online employability training. Based on the current design, the project will complete a full training course for the beneficiaries to increase capacity in employability skills and marketability as employees. Preparation to deliver the online employability training to mitage the impact of Covid-19 on beneficiaries of social protection is progressing. More than 70 potential trainees have registered to take the course. Course design and participant selection is in progress, Course delivery has been scheduled. It is anticipated that all beneficiaries will be trained by January 2022. | Signed contract with UWI Open Campus to deliver the online employability and entreprenuership training
Indicator 1.2.1: # of COVID 19 economically affected households who receive entrpreneurship and employability skills training through the e-training platform
Baseline:0
Planned Target: 200
Outcome 2[2] The social protection systems is better able to prepare for and respond to shocks
Indicator: Number of shock responsive features for procedures of key social protection programmes within the national social protection system
Baseline: 0
Planned Target: 4
Output 2.1 Strengthening the key social protection operational tools and processes to be able to prepare for and respond to shocks | Indicator Target: 0 | Main indicators are linked to key activities which are currently ongoing and based on new timelines, will be completed by the end of January 2022. Variances were due to ongoing reforms in the social protection sector which contributed to delays in the response as the new institutions and systems need to be in place to implement the support. Based on the current design, the project will strengthen capacity through trainings enumerators, development of technical guidance documents for the use of digital registrations and validation system. 40 staff from key institutions participated in training course on key social protection issues. Technical assistance to support the set up of the new social protection in Antigua and Barbuda under the new Social Protection Act (Social Protection Board, Fund and Commission and Income Support Program. Digitization of the registration process and data management system. It is anticipated that operational tools and processes will be in place by January 2022. | Social Protection Act Income Support Program Training Reports Data Management System
Indicator 2.1.1: # of tools in place for shock responsiveness. To be measured by manuals/SOPs, toolkits, protocols, reporting mechanisms, templates
Baseline: 0
Planned Target:
Output 2.2 Strengthening the policy, financing, planning and learning environment for social protection by embedding shock responsiveness | Indicator Target: 0.5 | Main indicators are linked to key activities which are currently ongoing and based on new timelines, will be completed by the end of January 2022. Based on the current design, the project will draft social protection policies available in both countries with consideration of shock responsiveness. Draft social protection policy makes attention to SRSP. It is anticipated that social protection policies will be in place by January 2022. | Social Protection Policies
Indicator 2.2.1: Shock responsiveness is integrated into the policy, plan and MEL framework. Measures: Final social protection policies with sufficient attention to SRSP, action plans with clear actions aimed at strengthened shock responsiveness, MEL frameworks with sufficient attention to SRSP
Baseline: 0
Planned Target: 2
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx | - The coordinating committee for the employability training programme have instituted different communication strategies to reach potential trainees and promote visibility. Some of the approaches include Electronic Billboard, Radio/TV interviews, Community Notices, Social Media Page (Facebook/Instagram), and Flyers/Posters.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Fact sheet providing information about the joint programme