## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Climate Resilient Women Centric Economic Empowerment for Inclusive and Greener Post COVID-19 Recovery | Overall Duration (months) | 18 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-04-11
MPTF Office Project Reference Number: | 124670 | Original End Date (dd.mm.yyyy) | 15/04/2022
Country | Djibouti | Current End date(dd.mm.yyyy) | 15/04/2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP and FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Finance, Economy and Industries Ministry of Agriculture
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | During the interim reporting period (Jan 1, 2021 to June 30, 2021), the project progressed further. The project launching was further postponed due to the subsequent wave and the mobility limitations imposed by COVID-19 pandemic. Hence, the Communications teams of the participating UN Agencies developed a concept for virtual launching with a tentative date of July 15, 2021. In February, UNDP and FAO conducted joint field visits and a rapid feasibility assessment of the potential beneficiaries in Arta region identified during the Inception Phase. Similarly, UNDP conducted field missions to Gobaad in Dikhil region and Assamo in Ali Sabieh region. The field missions were undertaken to assess and verify the needs identified by the potential beneficiaries during the Inception Phase. The rapid needs and feasibility assessment undertaken in the agricultural gardens owned by women or women cooperatives in Gobaad and Assamo concluded that stable water availability and proper irrigation are the main challenges and in the absence of capable technicians in the region, these women farmers and entrepreneurs suffered during the pandemic-imposed mobility restrictions. Furthermore, it was found that existing wells need rehabilitation, and existing solar pumping system needs replacement. UNDP developed a feasibility report outlining design and specifications for the solar pumping systems, rehabilitation of the wells and water collection and storage facilities in the regions. Following the field missions, water samples were also taken to test for the water quality and laboratory test results showed that the water is fit for agriculture but not potable. The project will piggy-back on the near completion competitive bidding process initiated by FAO for well rehabilitation services for another project. The well rehabilitation and protection intervention to ensure stable supply of water and installation of drip irrigation will start in August aiming at the harvesting period of October-November. A list of additional potential beneficiaries and a proposed support package based on the results of the needs mapping across all the regions has been prepared. The mapping exercise conducted by UNDP’s Regional CDuring the interim reporting period (Jan 1, 2021 to June 30, 2021), the project progressed further. The project launching was further postponed due to the subsequent wave and the mobility limitations imposed by COVID-19 pandemic. Hence, the Communications teams of the participating UN Agencies developed a concept for virtual launching with a tentative date of July 15, 2021. In February, UNDP and FAO conducted joint field visits and a rapid feasibility assessment of the potential beneficiaries in Arta region identified during the Inception Phase. Similarly, UNDP conducted field missions to Gobaad in Dikhil region and Assamo in Ali Sabieh region. The field missions were undertaken to assess and verify the needs identified by the potential beneficiaries during the Inception Phase. The rapid needs and feasibility assessment undertaken in the agricultural gardens owned by women or women cooperatives in Gobaad and Assamo concluded that stable water availability and proper irrigation are the main challenges and in the absence of capable technicians in the region, these women farmers and entrepreneurs suffered during the pandemic-imposed mobility restrictions. Furthermore, it was found that existing wells need rehabilitation, and existing solar pumping system needs replacement. UNDP developed a feasibility report outlining design and specifications for the solar pumping systems, rehabilitation of the wells and water collection and storage facilities in the regions. In March, UNDP in collaboration with the Ministry of Social Affairs and Solidarity (former name), distribute prevention kits and means of sustenance of COVID-19 to stop the spread to 400 vulnerable people affected by COVID-19 (refugees, elderly people, people with disabilities, etc.) Following the field missions, water samples were also taken to test for the water quality and laboratory test results showed that the water is fit for agriculture but not potable. The project will piggy-back on the near completion competitive bidding process initiated by FAO for well rehabilitation services for another project. The well rehabilitation and protection intervention to ensure stable supply of water and installation of drip irrigation will start in August aiming at the harvesting period of October-November. A list of additional potential beneficiaries and a proposed support package based on the results of the needs mapping across all the regions has been prepared. The mapping exercise conducted by UNDP’s Regional Coordinators (recruited with UNDP Core funding), based in all five regions, identified several individual women and women cooperatives working in poultry, livestock, dairy processing, shops selling the agricultural and/or meat. The preliminary assessment identified need for technical support and trainings in the poultry, livestock rearing and improved goat breeding and fodder cultivation. A further assessment is being undertaken to develop a more appropriate support package to address these needs. FAO has developed tentative support packages based on the mapping and needs assessment undertaken by UNDP for the potential beneficiaries. Considering that the time and budget of the project is considerably small compared to the needs for a sustained response to the socio-economic impact of COVID-19, UNDP ensured complementarity with other UNDP activities focused on climate-resilient women empowerment or promoting women-led agro-enterprises, so to create better value for money and optimize the administrative and operational expenditures. Similarly, FAO will utilize its existing vendors and in-house sector experts to provide technical assistance and need-based trainings for agriculture as well as livestock promotion. oordinators (recruited with UNDP Core funding), based in all five regions, identified several individual women and women cooperatives working in poultry, livestock, dairy processing, shops selling the agricultural and/or meat. The preliminary assessment identified need for technical support and trainings in the poultry, livestock rearing and improved goat breeding and fodder cultivation. A further assessment is being undertaken to develop a more appropriate support package to address these needs. FAO has developed tentative support packages based on the mapping and needs assessment undertaken by UNDP for the potential beneficiaries. Considering that the time and budget of the project is considerably small compared to the needs for a sustained response to the socio-economic impact of COVID-19, UNDP ensured complementarity with other UNDP activities focused on climate-resilient women empowerment or promoting women-led agro-enterprises, so to create better value for money and optimize the administrative and operational expenditures. Similarly, FAO will utilize its existing vendors and in-house sector experts to provide technical assistance and need-based trainings for agriculture as well as livestock promotion.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The main purpose of the project is to support the economic empowerment of the women from poor and marginalized communities through the climate resilient and green MSMEs. The project will target the women and women entrepreneurs whose livelihood has been affected by the COVID. Among the women and women entrepreneurs, the project will prioritize the following categories: 1. People living under extreme poverty and multi-dimensional poverty; 2. People living in the coastal areas and drought and flood prone area; 3. Refugees, migrants and other ‘people on the move’; 4. People with disability (ies) During the preliminary screening process, the project has identified four potential beneficiaries, whose livelihood was impacted by the COVID and whose potential to contribute to economic empowerment of target beneficiaries through employment generation and/or establishment of MSMEs exist. The project will continue the screening and selecting process to reach the beneficiary target mentioned in the project document. 400 vulnerable people affected by COVID-19 (refugees, elderly people, people with disabilities, etc.) received prevention kits and means of sustenance of COVID-19 to stop the spread. The field visit and rapid assessment of the potential beneficiaries identified during the Inception Phase. For example, the women-led civil society organization – Green Care is put on hold until the feasibility assessment of the identified needs will be finalized. The rapid assessment found the land that the government donated to the IDP women in Damerjog is not fit for agriculture and hence alternative support packages need to be developed if the project decides to support these IDP women. In lieu of this CSO, the project identified agriculture cooperatives in Assassan and Ali Addeh of Ali Sabieh region. The revised list of beneficiaries is as follows: A. Cooperative Agricole d'Assasan: 50 women farmers of a women led agriculture cooperative based in Assasan of Ali Sabieh need a) better market access, b) improved technical capacities, c) better farm fencing to protect from livestock invasion and d) improved irrigation facilities. Based on the support package designed by FAO, the project will provide a. Solar powered pumps of new generation which are i) Innovative non submersible system; ii) Suitable for rural wells and river-beds and iii) Lightweight, easy to move even for one person alone. b. Drip Irrigation systems which will allow i) increased water efficiency; and ii) increased crop area B. Cooperative d'Ali-Adeh: 20 women farmers of Cooperative d'Ali-Adeh in Ali Adeh of Ali Sabieh region have identified that to promote agriculture-based economy they need: i) well or a bore-hole for stable water supply; ii) improved technical capacities; iii) better agriculture input material and equipment; iv) a solar water pumping system and v) an improved irrigation system. a. Based on the needs identified and the FAO’s proposed support packages, the project in conjunction with the co-financing from USAID funded project on COVID socio-economic recovery will provide the following support: b. Technical Assistance: FAO through its technical assistance component will provide training on land preparation. c. Agriculture tools: The project will provide shade nets to the cooperative. The cooperative will be able to benefit from the Community Resource Centers that the USAID funded project will equipment with agriculture tools at the regional headquarters. d. Water supply source: Project will conduct a feasibility assessment to find out the best source of water supply for the cooperative. The results of the assessment will provide evidence to make an informed and the most feasible / sustainable decision. If deemed feasible, the project will build or rehabilitate a well and install solar pumping system. C. Women Initiative: A woman-led cooperative with 105 members in Douda of Arta region has been granted a 3-hectare plot by the government. The plot is close to Djibouti ville and has one of the best access to market. Though the farm is adjacent to a much larger cooperative of 43 plots supported by the European Union, World Food Programme and the USAID, the entire agriculture area has not been tended for the last nine months due to lack of water. The crops that were sowed have dried and burnt by the sun. The Women Initiative got a permission from the Ministry of Agriculture to get water from the nearby source. The Women Initiative aims to establish an edu-farm targeting young women affected by the COVID-19 socioeconomic impact, as the priority for 2021. The edu-farm is expected to provide hands-on experience and on-the-job training to 100 young women from Djibouti Ville and adjacent regions in 2021 to undertake kitchen-gardening and poultry farming. Hence the Women Initiative needs are i) provide access to water; ii) provide support with drip irrigation; iii) support to build a pilot greenhouse farming for edu-farm. The project will provide: a. Water Sourcing and Drip Irrigation Support: Details of the support package are yet to be finalized. b. Greenhouse farming feasibility assessment: With co-financing from the USAID funded project, UNDP conducted a preliminary feasibility assessment and developed draft report along with specifications and design for the pilot greenhouse farming to support the edu-farm. c. Innovative Urban Farming Young Woman Entrepreneur: A budding young female agro-entrepreneur, who has completed incubating an urban agriculture business based on the hydroponics technique in Djibouti Ville with technical and financial support from incubation organization – CTID. The support package will have two components – a) enterprise establishment support (with co-financing from the USAID funded and UNDP Core funded projects); and b) technical support. The project is undertaking a needs assessment based on the results and the current status of the intervention in the post-incubation stage. Based on the needs, the project will design the technical assistance support package under the leadership of FAO experts. If the enterprise will need equipment or agriculture input material, the project can provide those based on the assessment results. D. Women Farmers: UNDP conducted field assessment in Assamo and Gobaad to assess the water availability conditions and the needs on the ground faced by the farmers mainly due to existing water conditions. The main water related support asks from the farmers were a) well rehabilitation; b) replacement of the non-functional solar pumping systems; c) irrigation systems and d) water tanks. Among the 16 farmers in Assamo who needed replacement of pumps, 2 were female farmers. Similarly, among the other 17 farmers who needed all the afore-mentioned support, all 17 were female farmers. Similarly, in Gobaad, among the 10 farmers who needed well rehabilitation, solar pumping system and water tanks, one was a female farmer and among the other 11 farmers who needed water tanks and solar pumping system, there was one female farmer. The project has identified 21 female farmers who own their own farm and depend on these farms to support their livelihood. The project will conduct a well-being ranking at the community level to identify the most-needy female farmers in Assamo if the estimated cost of the services to be provided will go beyond the budget of the project. The project will provide the following support packages: a. Well Rehabilitation: The project will procure the services of the service provider to rehabilitate and protect the existing wells thereby benefitting 12 female farmers in Assamo and Gobaad. b. Innovative Solar Pumping Systems: The project will procure the innovative and new generation solar pumping systems for 10 female farmers (8 in Assamo and 2 in Gobaad) c. Drip Irrigation: The project will provide support with water efficient drip irrigation systems to 15 female farmers (13 in Assamo and 2 in Gobaad). The project will conduct a well-being ranking at the community level to identify the most needy 13 female farmers in Assamo. E. Women in Livestock and Poultry: Two women cooperatives on poultry and one on livestock and dairy processing and production were identified in Kalaf, Mehedo and Mouloud. The poultry cooperatives need, a) improved variety of chicks; b) technical training on poultry farming and poultry diets; c) better veterinary support; and d) technique of better separation of incubation eggs and fresh eggs. Similarly, the cooperative on livestock needs a) technical training on goat breeding; b) equipment to measure milk production; c) financial assistance to establish cheese factory; and d) better veterinary support. a. The project will provide technical assistance and capacity building support through the FAO’s in-house experts in poultry farming and livestock and dairy processing and production.
3.1 | Results: Outcome Level | Please include outcome level results achieved | In collaboration with MASS, UNDP provided prevention kits and means of sustenance of COVID-19 to 400 vulnerable people affected by COVID-19, including refugees, elderly people, people with disabilities (Outcome 1, Output 1.1) to prevent the spread. Most of the other project activities include the mapping of the potential beneficiaries, needs assessment of these potential beneficiaries, feasibility assessment of the financial and technical aspects of the needs, development of the tentative support packages based on the needs identified by the potential beneficiaries. In this regard, during the reporting period, the project does not have any outcome level results to be reported.
3.2 | Results: Output Level | Please include output level results achieved | The activities undertaken during the reporting have not achieved the output results yet but are on track and are aligned with the output targets. 1. Output 1.1 Indicator: # of households in all five regions provided with technical and other in-kind support (tools, production input, small equipment, raw material, kits, among others) to contain the COVID-19 triggered vulnerability and accelerate the relaunch of rural economic activities: 400 vulnerable people have been provided with preventive kits and means of sustenance. 2. Output 2.1 Indicator: # of women owned and women centric MSMEs established contributing to green and blue economy in coastal and rural areas: Three cooperatives and one start-up owned or led by women have been identified to provide the technical and financial support 3. Output 2.2 Indicator: # of women user groups and mother groups built to manage a community-based agriculture resource center: Two potential women user groups identified for Ali Sabieh and Arta 4. Output 2.3 Indicator: # of local and regional collection, distribution and sales centers established for locally produced, grown, processed or manufactured products: Not initiated. The activity will start in fourth quarter of 2021 5. Output 2.4 Indicator: # women- and youth-led service-oriented businesses to link production and processing-based enterprise to the consumers: Potential service provider identified to provide support to the women and youth led value-chain based market linkages. UNDP Core funded project had undertaken Value Chain Analysis and Market linkage assessment. The findings of the assessment will be used to link production and processing-based enterprise to the consumers. 6. Output 2.5 Indicator: # community-private sector partnerships built with key private sector actors to widen market for the products of the MSMEs: The activities will start in 2022
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | a. One of the main challenges encountered was the lack of adequate information on the level and type of impact incurred by the women and women entrepreneurs due to the COVID-19, despite efforts put in place through the Socio Economic Impact assessment deployed by the Government, with UN support. b. The second challenge was the lack of information on the nature and extent of support provided to affected population by different organizations. The project is undertaking mapping exercise at the project and the organization, mainly the CSOs in each region with the help of the Regional Coordinator. The project has and will continue to benefit from the ongoing work of the UN Agencies, including the UNDP and FAO administered COVID-19 response projects, to enhance effectiveness and efficiency. In this regard, for better identification of the beneficiaries, the project is taking and will take support from the SME and household survey undertaken by UNDP, the World Bank, IOM, and the government. The project has been taking support from the other ongoing projects related to the women empowerment with special focus on the interventions in the agriculture and livestock/fishery sectors. c. The Project will take support from another UNDP led socio-economic recovery intervention which will undertake participatory and community based "wellbeing ranking" to identify the most vulnerable members of the community to ensure that the project is able to identify the most needy ones under Output 1. The participatory and community-based wellbeing ranking will embrace the "Do No Harm" approach. To address the challenge of potential overlap and duplication of efforts, the project will take support from UNCT coordination initiatives, particularly under the UNDAF Result Group 1 - Employability and Education, as well as the Roundtable Discussions and periodic updating of the Coordination Matrix developed by UNDP. d. Regarding the Risks identified during the project formulation phase, the high-level risk - occurrence of second wave of COVID, has occurred during March-April 2021 causing limitations on the mobility. e. Human resources at the regional level: Lack of human resources that the project could support at the regional level was a challenge. This challenge was addressed by recruiting the regional coordinators co-financed by the other projects under the UNDP Portfolio – Rising Djibouti, which is dedicated to post COVID socio-economic recovery. f. Limited funds to hire the sector experts: The needs identified during the mapping exercise included the training and technical expertise to support the ongoing agriculture and livestock and poultry related enterprises. Due to the limited funds in the project, it was highly unlikely that the project could provide this much needed support. However, FAO through its existing pool of experts, either in-house or the sector experts engaged in other ongoing projects, will be able to address this challenge. g. The issue of water scarcity in the rural and coastal regions has not been a hindrance yet. However, the project has looked into the FAO's past water and soil mapping initiative undertaken in collaboration with Center for Studies and Researches of Djibouti (CERD) and the further soil and water profiling exercise planned for another UNDP project on COVID socio economic recovery, to identify the potential locations for intervention. h. The third risk identified around adequate supply of agriculture tools and equipment, will be assessed thoroughly as support packages will be designed and introduced. Should this become a problem, UNDP will mobilize its vendors listed under the global long-term agreements to manage it.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Qualitative assessments are not under the purview of the current project. However, this project can draw upon the policy gap analysis that other UNDP and FAO led post COVID-19 socio-economic recovery projects will undertake. For example, UNDP through SDG Funding Window and Islamic Financing Project is undertaking a SDG Investor Mapping and Policy Gap Analysis mainly focusing on the agri-business and entrepreneurships. The project will document the journey of the selected women-led or women centric enterprises from gender and women empowerment as well as building social capital perspective. The project results thus documented are expected to create awareness and provide inspiration for similar or scaled-up versions of the project interventions in Djibouti as well as elsewhere. However, during the reporting period, no such assessments or learnings are available to be shared.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project has initiated intra-agency partnerships with other projects/interventions; as well as with other organizations and partners, including national programmes such as the National Development Plan (NDP) formulation process. In addition to the three UNDP projects that this project created synergies during the interim phase- funded by UNDP Core funds, USAID and Islamic Development Bank, additional linkages have been made with the MPTF / SDG Funding Window funded project as well as the Danish government funded project on civic engagement and support to decentralization process. The additional partnerships will provide policy, institutional strengthening and governance related support to the interventions being undertaken by this project focusing on development of agro and fishery based MSMEs and empower the women and youth through technical and financial support packages made available through a comprehensive, inclusive and competitive processes. In addition, this project is collaborating with EU funded UNDP project on Women Empowerment implemented by the Ministry of Women and Family, which has two main pillars – a) improving the literacy rate among rural and vulnerable women and b) providing financial and technical support to enhance economic status of the women. The project is collaborating with the Regional Councils and the Civil Society Organizations to provide a more holistic and local support to the women and interventions supported by the project. The project will also benefit from the criteria developed for Performance Based Grants, Loan Guarantee Schemes and the Access to Microfinance support from parallel UNDP-led projects. Considering that most of these COVID-19 recovery projects have similar timeframe and strong alignment in the thematic focus, the project will have strong synergies with other projects. The strong synergies and coordination and collaboration with other national and regional interventions are expected to provide a much-needed foundation to the ongoing process of drafting the upcoming NDP - Djibouti ICI, 2020-2024. The project results will feed into the upcoming immediate action plan of Djibouti ICI and contribute towards the transformative governance process led by the MEFI.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | For the procurement of the services and goods, UNDP and FAO will piggy-back on the existing vendors and service providers which have been selected through a competitive process as per the respective corporate policies. In addition, the agencies will also piggy-back on each other's existing list of service providers and vendors. For example, in the case of well rehabilitation and new generation solar pumping systems. UNDP conducted the feasibility assessment and developed Bill of Quantity. However, in the interest of time, UNDP will procure the services from the service provider selected by FAO for another project but for similar purposes through a competitive tendering process.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 400
Indicator: # of rural economic activities accelerated in the five regions of the country
Baseline:0
Planned Target:500
Output 1.1 Technical and in-kind support provided to identified beneficiaries | 400 reached
Indicator 1.1.1: # of households in all five regions provided with technical and other in-kind support (tools, production input, small equipment, raw material, kits, among others) to contain the COVID-19 triggered vulnerability and accelerate the relaunch of rural economic activities.
Baseline: 0
Planned Target: 500
Outcome 2: New economic opportunities created and women owned and women centric MSMEs are supported | Under Progress
Indicator: # of women owned and women centric MSMEs established contributing to green and blue economy in coastal and rural areas
Baseline: 0
Planned Target:10
Output 2.1 Services for the creation of women owned and/or women centric MSMEs, mothers group associations, and community based centers are provided | Under Progress
Indicator 2.1.1: # of women user groups and mother groups built to manage a community-based agriculture resource center
Baseline:0
Planned Target: 10
Output 2.2 Access to Market and Market Linkages established | Target for 2022
Indicator 2.2.1: # of local and regional collection, distribution and sales centers established for locally produced, grown, processed or manufactured products
Baseline:0
Planned Target:2
Indicator 2.2.2: # women- and youth-led service-oriented businesses to link production and processing-based enterprise to the consumers | Target for 2022
Baseline:0
Planned Target:2
Indicator 2.2.3: # women- and youth-led service-oriented businesses to link production and processing-based enterprise to the consumers | Target for 2022
Baseline:0
Planned Target:2
Indicator 2.2.4: # community-private sector partnerships built with key private sector actors to widen market for the products of the MSMEs | Target for 2022
Baseline:0
Planned Target:2
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
There is no impact stories to share from the reporting period.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board