## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening of the Educational System to address challenges derived from the Emergency before and after COVID-19 that promote educational care with a gender perspective | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-25
MPTF Office Project Reference Number: | 00121773 | Original End Date (dd.mm.yyyy) | April 30, 2021
Country |  | Current End date(dd.mm.yyyy) | April 30, 2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF; WFP | National counterparts (government, private, NGOs & others) and other International Organizations | Nicaragua's MInistry of Education
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | During the reporting period, the project supported the elaboration of guidelines for the socioemotional support of children and the adaption of school curricula with the aim to better mitigate the devastating impact of the COVID-19 crisis on schools in Nicaragua. In this process, UNICEF specialists in the area of child protection were key to enrich the first draft of the document presented by MINED. The guidelines will be available to all teachers at preschool, primary and secondary level (nearly 60,000 teachers), as opposed to the projected number of teachers (5,500) in the project target, exceeding it by ten times. The project was able to finance the production of 50,000 educational posters, with messages on how to manage stress, how to express solidarity and respect in times of crisis,and how to help children at home with recreational activities, reaching out to nearly 50% (4,500 schools) of the schools located in the most vulnerable to COVI19 geographic areas (most densely populated areas) The project also provided access to a digital platform of which MINED forms part since July 2020. This has resulted in enhanced cooperation of and communication between central offices and offices at the departmental and municipal level with schools and training facilities for 50,000 teachers. The platform is also used for other trainings and administrative processes. The training portfolio includes girls’ pregnancy prevention; art (music and plastics); stress management and learning stimulus; integrated sexual education; as well as neuroscience and emotions. It is estimated that more than 1,000 people attended training sessions in 2020. In the area of WASH, the project jointly with MINED identified beneficiary schools and advanced in the development of a related initiative to install hand washing/drinking water stations with integrated water tanks in schools. Moreover, the project advanced in the procurement of hygienic kits for teachers and school kitchens.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Nearly 1,000 education officials participated in a range of training activities conducted through the digital platform. Some 50,000 teachers and school principals have benefitted indirectly from this, as education officials reproduce the trainings at local level. 60,000 teachers will receive the guidelines on socioemotional support and curriculum adaptation in emergency situations, instead on the 5,500 that were estimated in the project proposal. The guidelines are ready for distribution.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1.1 The educational community, especially in the territories potentially most vulnerable to the impact of the COVID-19 pandemic, is better prepared, guaranteeing safe and protective learning spaces. Partly achieved. During the reporting period, the project conducted online activities with MINED staff at national, departmental and municipal level, taking into consideration the current pandemic and related protocols. Coordination, planning, follow up and training continued in a virtual modality allowing MINED to ensure the necessary flexibility to ensure that the school year could be completed successfully. Moreover, MINED and all of its preschool, primary and secondary teachers are now equipped with concrete guidelines on socioemotional support for children to better recover from trauma and stress related to COVID-19, as well as guidelines on how to adapt school curricula to emergency situations. Provisions have been made for teachers from indigenous and afro Caribbean communities to have access to their training materials in their own languages (Creole, Miskito, Mayangna, Panamaka and Tuaka). To enhance the socioemotional support, 50,000 posters were produced and distributed with messages relating to how best deal with stress in school and at home due to the special conditions that children, the school community and th efamilies have to undergo during the covid19 pandemic. Progress has been made in equipping MINED in the area of WASH identifying beneficiary schools and advancing in the development of a related initiative to install hand washing/drinking water stations with integrated water tanks in schools, which tender will be launched on May 5. The project also acquired hygienic kits for teachers and school kitchens, as well recipientes for water and food storage.
3.2 | Results: Output Level | Please include output level results achieved | 1.1.1 Teachers put into practice a school curriculum adapted to the particular / special situation, which prioritizes the basic and fundamental contents that can guarantee the educational continuity of the students. Achieved. A school curriculum adapting to the new COVID-19 reality in Nicaragua was put into practice.
1.2.1 Girls, boys and adolescents, particularly adolescent girls, have psychosocial support tools that help them better face the challenges that the special situation caused by covid19 poses for them. Achieved. A guidance document for MINED on how to provide socio-emotional support to children at school in times of COVID-19 was produced. The document integrates topics such as resilience, recreational spaces, and socio-emotional support to students and the educational community in general. It also contains a component on practical exercises that help work with emotions during crisis or emergency situations. Originally intended for 5,500 teachers, the document will be reproduced to cover the entire teachers' population from the three different educational levels (preschool, primary, secondary). An additional effort has been made, to include versions of the document in various indigenous and afrocaribbean languages (Creole, Miskito, Mayangna, Panamaka and Tuaka) thus reaching out indigenous and afrocaribbean populations from the Nicaraguan Caribbean Coast. As part of the socioemotional support component of the project, the project was able to produce 5 different posters, with messages supporting the campaign to reduce stress among the school community due to the covid19 pandemic. Each poster was reproduced 12,500 times, for a total of 50,000 posters, reaching out to 50% of the schools (4,500 schools) and nearly 900,000 students.
1.3.1 Municipal and departmental education offices, run mostly by women, are technologically able to carry out on-line administrative and educational processes. Partially achieved. With access to 180 virtual rooms which allow nearly 1,000 attendees in a video-conference setting, the project created a virtual platform that has strengthened the capacities of MINED in planning and institutional communication at central, departmental, municipal and school level. Main activiities included: orientation sessions on strategies to be implemented within the framework of the leadership function; training on the use and management of curricular documents, guidelines for school reinforcement and catching up activities, matrix of prioritized indicators, and self-study guides. Also, the platform was used to train teachers on activities leading to promote values for the care of life in all its forms; how to provide socio-emotional support in crisis situations; and recommendations for parents of children in early learning and/or children with disabilities. Additionally, 221 technological kits (laptops, data-shows, speakers) are being acquired for departmental and municipal delegations of MINED and slected emblematic educational centers that serve as teacher training facilities. Due to the current pandemic, some of the procurement processes are delayed. However, UNICEF will be able to hand in 100% of the technological kits in April 2021.
1.4.1 The educational community has better access to drinking water service in prioritized schools, which contributes to improving school and personal hygiene actions, thus reducing the risk of contagion of communicable diseases, and in particular, in COVID-19 Partially achieved. Water storage recipients were acquired and are been transfered to MINED. Following a joint technical review with MINED at the end of 2020 and challenges related to lacking critical hydrogeological data on the possible construction sites for the planned freshwater wells that may compromise water quality and safety, the project decided to change the approach and developed a concept for the construction of hand washing/drinking water stations with integrated water tanks in schools. This solution will not only maintain the anticipated budget at its current level, but also present a pragmatic response to better integrate remote schools. The anticipated stations will have a metallic prefabricated design, which will allow for quicker tender processes and faster installation. This shifted approach was only approved by MINED and WFP in December 2020, wherefore more time is now required now for successful implementation. Water stations design and tender dossier are ready; tender to be launched on May 5.
1.5.1 Educational community in prioritized schools puts into practice better gender sensitive habits that contribute to guaranteeing food hygiene, in the context of the provision of school meals. Partially Achieved: 3,100 hygienic kits for teachers, 625 kits to safely handle provision of school meal (which includes food storage recipients + hygienic kits) acquired and being transfered to MINED.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The project encountered two main difficulties related to WASH: the provision of clean water for schools due to planning issued related to well construction and the procurement of technological kits as a result of supply chain problems in the context of COVID-19 Risk Management Matrix Due to poor offer, inputs are not locally available The risk materialized when trying to procure technological kits (laptops, datashows) and international suppliers needed to be involved, leading to delays in delivery. Social norms do not favor gender equality This has not been a constraint so far in the process of project implementation Technical and operational demands placed by expanding the MINED’s virtual network are not met due to lack of resources This has not been a constraint so far in the process of project implementation.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The construction of critical infrastructure for emergency projects in an extremely short time frame should be considered a high risk and costly endeavor. Mitigation measures should be clearly stated in the Risk Management Matrix. Moreover, on national emergencies and national institutional capacity, competing priorities should be considered, which may lead to delays in the implementation.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Main partner in this project is the Ministry of Education (MINED). Both UNICEF and WFP have a long working experience with MINED, easing the two-way communication and understanding mutual needs.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | None yet.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The project requests a no cost extension until 31 Octobrer 2021 as a result of construction and procurement delays related to COVID-19 that were not foreseen and the two tropical storms IOTA and ETA that hit Nicaragua last year.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Procurement processes have been carefuly managed to ensure that no negative impact on local markets are made, as well considering local procurement capacities. Some items had to be imported, such as technological equipment, which has added some complexity to the procurement process.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1.1: The educational community, especially in the territories potentially most vulnerable to the impact of the COVID-19 pandemic, is better prepared, guaranteeing safe and protective learning spaces | 0 | School completion rate from MoE not available yet. | 2020 administrative data from MINED
Indicator:1.1.a : % of children who complete their school year with no major challenges due to covid19 crisis
Baseline:
Planned Target:100%
Output 1.1.1 Teachers put into practice a school curriculum adapted to the particular / special situation, which prioritizes the basic and fundamental contents that can guarantee the educational continuity of the students. |  |  | Administrative data
Indicator 1.1.1.a: # of teachers who implement the curriculum adaptation strategy | 60000 | The cost of printing the document was far less than the cost in budget. Also, MINED considered that the material should be accesible to all teachers from the various educational levels.
Baseline:None
Planned Target: 5,500 teachers receive the guidelines for Curriculum adaptation - 63% women n=beneficiaries
Output 1.2.1 : Girls, boys and adolescents, particularly adolescent girls, have psychosocial support tools that help them better face the challenges that the special situation caused by covid19 poses for them.
Indicator 1.2.1.a: # of children who receive sico-social support in the year 2020 | 60000 | The cost of printing the document was far less than the cost in budget. Also, the MINED considered that the material should be accesible to all teachers from the various educational levels. | Administrative data
Baseline:
Planned Target: 5,500 teachers support the psico-social strategy to ensure reintegration of student to school - 63% women beneficiaries
Output 1.3.1: Municipal and departmental education offices, run mostly by women, are technologically able to carry out on-line administrative and educational processes.
Indicator 1.3.1.a: # of municipal education offices connected to the MINED´s national virtual network. | 221 | 221 technological kits are being acquired, which represents an exceeding 77% over the target. More MINED municipal offices (221) will be served. | - Administrative data - Reports of virtual activity by municipal offices
Baseline: 20 education offices are already connected
Planned Target: 125 municipal offices will be connected additionally - 55% women beneficiaries
Output 1.4.1: The educational community has better access to drinking water service in prioritized schools, which contributes to improving school and personal hygiene actions, thus reducing the risk of contagion of communicable diseases, and in particular, in covid19.
Indicator 1.4.1: # of schools that have access to potable water | 0 | We propose to change this indicator: wells will be not constructed; instead there will be hand-washing stations with integrated water tanks for schools with intermitent provision of water. Hand-washing stations tender to be launched on May 5, 2021. | -Administrative registries - field Reports on task completion
Baseline: 3,057 schools have acccess
Planned Target: 40 schools will have access to potable water, permanently
Indicator 1.4.2: # of schools that count with safe storage and distribution of potable water | 0 | As of March 2021, recipients acquired and being transfered to MINED. | Administrative registries
Baseline: 1,386 schools are in need of equipping themselves
Planned Target: 625 schools will have the equipment to storage and distribute potable water in a safe manner – 52% women beneficiaries
Output 1.5.1: Educational community in prioritized schools puts into practice better gender sensitive habits that contribute to guaranteeing food hygiene, in the context of the provision of school meals. |  |  | Administrative registries
Indicator 1.5.1: # of teachers equipped with hygiene kits | 0 | As of March 2021, kits acquired and being transfered to MINED.
Baseline: 0
Planned Target: 12,400 teachers
Indicator 1.5.1.b: # of kits provided to teaches for their classrooms | 0 | As of March 2021, kits acquired and being transfered to MINED. | Administrative registries
Baseline:
Planned Target: 3,100 kits delivered – 54% women beneficiaries
Indicator 1.5.1.b: # of kits to safely handle provision of school meal | 0 | As of March 2021, kits acquired and being transfered to MINED. | Administrative registries
Baseline: 0
Planned Target: 625 kits delivered – 54% women beneficiaries
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
The project produced a logo , which will be used on all project’s communications products and will identify all supplies to be provided to MINED.
For example, WFP - NIcaragua based on this logo, has edited a sticker that will be used on all the 10,600 water and food recipients plus teachers and food preparation kits to be delivered by the project:

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board