## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Concerted action for forcibly displaced women, girls and host communities against consequences of the COVID 19 crisis | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 11th November, 2020
MPTF Office Project Reference Number: | 12472 | Original End Date (dd.mm.yyyy) | 1st November, 2021
Country | Democratic Republic of Congo | Current End date(dd.mm.yyyy) | 1st November, 2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNWOMEN and UNHCR | National counterparts (government, private, NGOs & others) and other International Organizations | Government counterparts: ANR (intelligence), PNC (police), civil affairs offices, social affairs office and territorial administration, Tribunal de paix Implementing partners: Intersos (INGO), AHCOPDI (NGO), Caritas (INGO), AIDPROFEN (NGO) Local women's organisations: Forum Des Femmes, SOFEM, CAFPEDI, Wamama Simameni and ALW Other International organisations: Humanitarian partners participating in the protection cluster benefit from protection monitoring data. IP:Government counterparts; DPS, PNSR, PNSM, DIVISION DU GENRE et des affaires sociales Implementing partners: Hope in Action, Other International organisations; Members of GBV Sub Cluster UN System : MONUSCO, OHCHR, OCHA
Report Cleared By
o Name: | Aboubakri Diaw
o Title: | Head of RCO
o Email address: | diaw2@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Program's results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | During the period from January to June 2021, UNFPA, UNHCR and UNWOMEN as well as their implementing partners were able to begin implementing the project. UNFPA and its implementing partner Hope in Action carried out some activities in particular: Donated of sexual and reproductive health kits to the 8 FOSAs (health facilities) supported by the project ;Trained service providers and care providers on GBV case management, mental health/psychosocial support and on relevant topics by health zone on the prevention and management of COVID-19 cases, SRH, GBV and EAS; Provided psychosocial activities according to the needs of women and girls; Organized awareness-raising activities, community dialogues and information sharing on GBV and COVID-19; Organized community feedback sessions and dissemination of messages on available services with targeted communities, authorities and the population of each health zone and dissemination of the referral pathway; Supported the supervision of the 4 ZS (Health zone) Executive Teams, the DPS (Provincial health authorities) and the Provincial Gender Division; Distribution of dignity kits to vulnerable women and girls, including pregnant women and postpartum women; Supported health facilities targeted in Infection Prevention and Control (IPC) equipment and Institutional support (operating costs and office supplies); Supported the establishment of 4 safe spaces for psychosocial activities with women and girls. UNHCR could easily scale its psychosocial and legal assistance activities, due to preexisting relationships with implementing partners from a pilot in 2020. Early 2021 work mainly revolved around these activities due to its experience and ongoing partnerships with organizations in the field, protection monitoring, support to government actors. A few parts of UNHCR's implementation were delayed due to the search for new implementing partners as well as developments in the field (see below). UNWOMEN supported Police Stations and trained police officers, prison and social agents on the prevention of violence, particularly GBV caused by COVID-19.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Training and capacity building - 53 service providers, including psychosocial agents, Community Health agents, these trainings were facilitated by UNFPA in collaboration with Heal Africa and the PNSM (National Mental Health Program); and - 57 medical providers were trained on sexual and reproductive health (syndromic management of STIs, clinical management of rape cases, family planning, prevention and response to COVID-19. 17 women and 23 men from the 8 targeted health facilities, including the health zone management team, benefited from these training sessions facilitated by the DPS and the PNSR (National Reproductive Health Program). Management of GBV cases and affected person - From February to June 2021, 330 GBV cases were documented (79 in Q1 and 251 in Q2) and benefited from various services such as psychosocial care (330/1085), medical care (182/107), and legal and judicial referrals (33/30); - 242 dignity kits were distributed, 30 in Q1 and 212 in Q2, during the awareness-raising activities for IDPs, women and girls from host communities, including GBV survivors in need and the most vulnerable women; and - 158 dignity kits were pre-positioned in the health zones for GBV survivors and affected person in need for a rapid response to acute crises in intervention areas. GBV/COVID-19 awareness and risk mitigation activities - 13,293 people were sensitized through the local media and the actions of community relays on different topics (GBV prevention, referral pathways and referral towards available services, and prevention and response to COVID-19). - Group discussions with women and some women's organizations on positive masculinity as an entry point for the participation of spouses and intimate partners is planned in future group discussion activities related to women's participation in the fight against GBV and the different GBV/ASI reporting mechanisms, on assistance mechanisms for GBV survivors through the promotion of the referral pathways and the 49-55-55 hotline, and on prevention and referral in case of exposure to COVID-19. The distribution of masks to protect against COVID 19 was the culmination of these awareness-raising activities. A total of 7,181 women, 3,024 men, 2,087 girls and 1,001 boys were reached by these prevention and awareness activities. -Institutional support to the 8 health facilities equipped with hand-washing facilities and equipment to protect against COVID-19. - 2,394 beneficiaries (993 women, 633 men and 495 children, sex disaggregated data was unavailable for others due to the nature of the activities), of which at least 1,360 direct beneficiaries and 1,034 indirect beneficiaries, were reached during the information campaign on the child registration moratorium. - In collaboration with MONUSCO and GBV sub-cluster Coordination, UNWOMEN organized the training of 31 police officers, prison guards and social workers (8 women/25 men) on the prevention of GBV and how it is worsened by COVID-19. At the same time, UNWOMEN provided 14 police offices with equipment as an institutional support to collect evidence and to support the investigation of GBV cases.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1 (85%) Women and girls’ IDPs and refugees and women from host communities receive urgent support for improved health services to cope with and prevent the spread of COVID-19: The capacity-building activities for medical staff and service providers of GBV management services have been completed. Sexual and reproductive health kits have already been made available to the 8 health facilities and the needs of more than 10,000 people have been met through the provision of 5 post-rape kits that can cover the needs of 250 rape survivors. 3 post-rape kits will be provided in the remainder of the project by UNFPA (150 cases). The prevention and risk mitigation activities related to GBV and COVID-19 have reached more than 4,000 people (target) and are still ongoing, especially in the Karisimbi health zone due to the volcanic eruption and in the Masisi health zone due to the large population displacement caused by the clashes between the FARDC and armed groups. 168% of GBV cases have received medical treatment, which shows that the project has reached its target. However, it is important to mention that not all the dignity kits were distributed (60.5%) and the rest were prepositioned in the health zones and at the service delivery points for the management and follow-up of GBV cases and rapid response of crisis in the intervention area. The medical care structures for rape cases will continue to support survivors in need as a result of the current crises in Nyiragongo and Masisi. Psychosocial and mental health support activities will be strengthened as a result of the recent crises. Outcome 2 (20%): Livelihoods and socio-economic resilience of displaced women and host communities vulnerable and at risk of SGBV strengthened through the development of community initiatives: UNHCR supported 44 vulnerable beneficiaries with cash transfers. Outcome 3 (74%): Strengthened prevention, monitoring and accountability measures in North Kivu through the mitigation and protection from human rights violations as negative effects of COVID-19. Sensitization campaigns on the prevention and response to COVID-19 and GBV took place including use of local media. Additional sensitization took place on the civil registration moratorium. Police officers were trained on GBV and their offices were also supported in order for them to take on these cases and treat survivors with dignity. 5 Women's organizations were also given technical and financial support to work with women with disabilities to ensure their rights and sensitization on COVID-19.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1: 85%; Output 1.2: 142%; output 1.3: 50%; output 1.4: 85%; output 1.5: 332%; output 1.6: 34%; output 2.1: 0%, Output 2.2: 6%; output 2.3: 0%; output 2.4: 0%; output 2.5: 0%; Output 3.1:0%; Output 3.2:50%; output 3.3:22%; output 3.4: 20%; output 3.5:102%; output 3.6:90%
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | While the project had noted that security and access issues would be key challenges in this project, there was a clear demarcation point of the worsening of the situation with the declaration of a state of siege in North Kivu. This State of siege led to increased military operations and suspension of civilian rule in the province having an impact on the entire management of the province. Through this state of siege, there is an acceptance of the instability in this province by National Authorities and decisive action was taken after more than 15 years of conflict. Access constraints in Masisi territory hampered implementation and monitoring of already established implementing partners. In May 2021, a state of siege was declared in North Kivu which also hindered the operation of courts acting on SGBV cases due to the suspension of civil authority and justice systems. Cases need to be presented in the Goma courts bringing an additional challenge including delays and unforeseen costs. Implementing partners with support of UNHCR are exploring interventions with the temporary military provincial authorities to address the issue. Field based-work in more remote IDP sites could not be funded due to the geographic limitations of the project despite needs. Flexibility in selection of the geographic zones covered by the project is a must due to the rapidly changing humanitarian context in North Kivu. Particularly with the state of siege, armed clashes, human rights abuses and their consequences such as displacement, SGBV and economic/agricultural disruptions continue to shift on a monthly basis. Access to beneficiaries and government partners will remain dependent on COVID-19 restrictions, which have been reinforced during the third wave (Delta variant). This will affect implementation of the project, such as support to local authorities, information campaigns and activities that gather crowds especially for sensitization targets. Some implementation methods could be altered according to these restraints. It is also difficult to access the health area of Buabo and health zone of Masisi following recurrent clashes between the FARDC and the armed group APCLS. Another unanticipated risk was a volcanic eruption that did not have a warning or an evacuation plan for the population. IDPs settled into unprepared sites leading to tremendous strain on host populations and increased GBV risks in the area. There were also the new needs generated by the volcanic eruption crisis which displaced over 500,000 people in June. This displacement impacted both host communities, and IDPs increasing protection risks due to close quarters living, problems in accessing water, lack of livelihoods, subsistence for the displaced, increased risks of cholera (a new outbreak was noted) as well as increased risk of other communicable diseases. The IDPs were forced to flee in the direction of the Virunga National Park which has been home to rebels, insecurity and violence. From the 22nd of May to the 11th of June, 41% of GBV cases out of the 68 (28/68) registered in the Karisimbi, Nyragongo and Kirotshe health zones were reported by IDPs during flight or in host communities. Other health zones in the territory of Lubero, Rutshuru and Beni were also impacted by the evolution of the state of siege and volcanic eruptions resulting in increased protection needs by population. Much of the local infrastructure was also affected by the volcanic eruption and earthquakes, which was also destructed certain GBV services. To this end, new funds are being mobilized for short term to meet additional needs. Mobilization of additional funds is critical to address emergencies focus on issues of mental health/ psychosocial support, socio-economic empowerment of affected populations with a strengthening of intervention packages in connection with prevention and response to COVID-19. The volcano eruption and the relocation led to delays in the implementation of some activities of the project. Furthermore, exchanges of the provincial ministries, who were suspended because of the state of siege suspending civilian authority, was another challenge to project implementation. In June both of these factors (state of siege and volcanic eruption) led to a significant increase of reported GBV cases (50% increase).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The road between Masisi and Goma was cut when the delivery of kits needed to take place. This blocked traditional transport routes from Goma to Masisi. Working with the community relays and local authorities was a good practice to overcome this challenge. Community relays carrying kits and goods on foot and by bicycles to ensure that they successfully deliver them to the implementation areas. Ensuring the close collaboration with local authorities and the community relays was key to ensure service provision in a timely manner. Subsequent to good community sensitization which had a strong emphasis on Positive Masculinities. Community Action Groups on GBV were established and were constituted of men who now are engaged in sensitization activities. In doing this, ongoing positive masculities sensitization through a peer based approach can take place. One of the lessons learned is that the creation of these groups was very positive and its spontaneity was welcomed. And yet, they need continuous support and capacity development in order to ensure that they maintain their momentum.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | A new implementing partner is being selected to provide legal, technical and operational support on statelessness as needs and reporting efforts exceed the capacity of the former partner (AHCOPDI). Implementation is set to begin shortly after selection procedure is finalized. An agreement has been signed with the Provincial Gender Division to ensure a good implementation and appropriation of the project by the national counterpart. With the participation in the local humanitarian coordination in the area of intervention, UNFPA/HIA facilitated the psychosocial support of the cases referred to it by the other NGOs, shared its experience and its new approaches especially the safe space approach which is not practiced by many local organizations in the field. Practical relationships with community relays and local authorities allowed the project to surmount major challenges related to lack of access by working with local communities who took ownership of these activities. This engagement of local communities was not limited to execution of activities such as kit delivery but also generated additional interest in the project during sensitizations with a strong emphasis on Positive Masculinities. It was possible to establish Community Action Groups on GBV for sensitization. In doing this, ongoing positive masculities sensitization was possible. One of the lessons learned is that the creation of these groups is very positive and its spontaneity was welcomed however they need ongoing support and capacity development in order to ensure that they maintain their momentum.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | HIA participated in several needs’ assessments in the Masisi health zone on the situation of IDPs (needs for GBV responses and protection in general), highlighting needs and gaps on the need for holistic intervention in GBV and particularly on socio-economic reintegration activities and challenges of access to justice.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Base on the security issues, the number of trained police officers was reduced because of the impossibility to deploy several officers in the context of the state of siege. In lieu, the number of supported offices provided with COVID-19 materials have been increased. UNFPA refocused its implementation sites in order to avoid duplication of activities with other similar health projects. This saw the health interventions by UNFPA move from Mweso Zones and intensify its activities in the 3 remaining health zones (Masisi, Karisimbi, and Birambiso). This also put the project in a very strong position to respond to the rise in violence and needs in the Masisi area. UNHCR and UNWOMEN continue work in Mweso.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Outcome1:Displaced women, girls and host communities receive urgent support for improved health services to cope with and prevent the spread of Covid-19
Output 1.1:Strengthen the institutional capacities of health facilities and service providers with 08 IPC and 04 WGSS(Infection Prevention and Control) kits, personal protective equipment and other materials for COVID-19 prevention 400 dignity kits adapted to the cultural realities of the needs of women and girls in targeted health zones, provision of emergency SR kits (1A, 1B, 2A, 3, 4, 5, 6A, 6B, 11A and 11B) and other essential RH commodities at all service delivery points are provided in target areas | 8 |  | Distribution plan, material and equipment receipt form signed by the MCZs
Indicator 1.1.1:1 Number of health centres provided with COVID-19 protection material
Baseline:00
planned target: 08
Output 1.1:Strengthen the institutional capacities of health facilities and service providers with 08 IPC and 04 WGSS(Infection Prevention and Control) kits, personal protective equipment and other materials for COVID-19 prevention 400 dignity kits adap | 12 ( 08 Health facilities and 4 Women and Girls safe Space) |  | Distribution plan, material and equipment receipt form signed by the MCZs
Indicator 1.1.2:Number of IPC (Infection Prevention and Control) kits, personal protective equipment, essential RH commodities and other materials for COVID-19 during the COVID-19 outbreak
Baseline:00
planned target: 12
Output 1.1:Strengthen the institutional capacities of health facilities and service providers with 08 IPC and 04 WGSS(Infection Prevention and Control) kits, personal protective equipment and other materials for COVID-19 prevention 400 dignity kits adap | 242 | 242 kits have already been distributed and 158 dignity kits are prepositioned at the health zone and service providers for case management and possibility to address rapid response for the new crisis | Activity report beneficiaries receipt form/ list of distribution
indicator 1.1.3:Number of women and girls including IDPs, refugees and host communities who received dignity kits, stay-at-home kits and other support material
baseline: 00
planned Target:400
Output 1.2:Training of health personnel on Emergency Obstetric and Neonatal Care, maternal death surveillance and response, prevention and control of Infection in an obstetrical environment and clinical management of rape including infection prevention and control and COVID-19 detection, response and referral/case management including Mental Health and Psychosocial Support to IDPs/host families. |  | Training included additional members from the gender division and Health Zone staff due to increased needs in the covered areas | Training report and participant list
indicator: 1.2.1:midwives, nurse supervisors of health zones and community health workers trained on relevant topics
baseline: 00
planned target: 40 | 57
Output 1.3: Capacity of health providers, community organizations, women's rights advocates, and women's groups strengthened to improve the quality of care provided by health facilities so that they respond holistically to needs of GBV survivors (women, girls, youth, men and boys) during and after the COVID-19 pandemic |  | Planned for the next quarter | Activity Report
indicator 1.3.1:Number of community organizations, women's rights advocates and groups supported
baseline: 00 | 0
planned target: 08
Output 1.4: GBV/EAS referral pathways and entry points for COVID strengthened and promoted |  | large communication and sensitization activities through the local radio, community activities with the RECO and dissemination activities about the referral pathway | Activity Report
indicator 1.4.1: Number of persons informed on referral pathways | 13293
baseline: 00
planned target: 4000
Output 1.4: GBV/EAS referral pathways and entry points for COVID strengthened and promoted | 33 cases: 11 cases of denial of resources, brought before the civil tribunal of Masisi (tribunal de paix), 5 cases of rape (ongoing), 1 case of sexual aggression (ongoing), 1 case of physical aggression (ongoing) and 2 of psychological violence (ongoing). Total = 20+3 = 23 cases. 10 cases referred by UNFPA/HIA : Total: 23+10=33 | 110% ; Many cases remain ongoing as competent legal authorities dealing with SGBV cases (Tripaix and Auditorat) have ben largely inoperative in Masisi due to ongoing insecurity. Solutions are currently being sought through intervention in Goma or advocacy with the military authorities during state of siege to increase judicial capacity. However, the delay in cases also reduces the willingness of clients to seek potential legal solutions. | On-site monitoring to be conducted in the 2nd half of 2021, desk-review of reporting by partner
Indicator 1.4.2: Number of GBV cases that received legal/judicial support
Baseline: 3 cases in November-December 2020
Planned Target: 30
Output 1.4:GBV/EAS referral pathways and entry points for COVID strengthened and promoted |  |  | Activity Report and GBV Dashboard
Indicator 1.4.3: % of survivors of sexual violence who received medical care at service delivery points by trained staff within 72 hours of the rape incident, disaggregated by age and sex | 182 cases reported | Further statistics are being gathered in order to calculate this percentage
baseline: 00
planned target: 80%
output 1.4:GBV/EAS referral pathways and entry points for COVID strengthened and promoted |  |  | Activity Report and GBV Dashboard
indicator: 1.4.4: Number of survivors of sexual violence who received medical care disaggregated by age/gender/disability |  | Target exceeded due to increased sensitization and high rates of GBV due to displacement
baseline: 00 | 182 cases reported
Planned Target: 108
Output 1.4: GBV/EAS referral pathways and entry points for COVID strengthened and promoted |  |  | Activity Report and GBV Dashboard
indicator: 1.4.5: Number of women and girls who participated in psychosocial activities, including survivors who benefited from age-disaggregated/disability case management
baseline: 00 | 330 | This data is from the service provider points but does not cover all activities therefore this number will increase at next data collection
planned target: 1800
output 1.5: Community engagement and social mobilization promoted at local level to manage rumors, build trust between health facilities, health providers and community members, and reinforce awareness and understanding of the COVID-19 pandemic at the community level, and address the risks of gender-based violence |  |  | Activity Report and GBV Dashboard
indicator: 1.5.1:Number of individuals reached with awareness-raising | 13293 | Use of modern media increased sensitization impact of local radio usage , sensitization activities , discussion group with RECO
baseline: 00
planned target: 4000
Output 1.6: Mental health and psychosocial support provided to improve health services response to gender-based violence; | 53 | The MCZ added some personnel of health zone, and DIVISION of Gender to increase impact. | Training report and participant list
indicator 1.6.1: Number of service provider strengthened on mental and psychosocial response including the GBV case management
baseline:00
planned target: 40
Output 1.6: Mental health and psychosocial support provided to improve health services response to gender-based violence; | 614 cases reported; Individual therapy: 207 cases of which 48 in Masisi centre (18) and Katale (30), both in Masisi health zone. Other cases in Mweso (71), Kishjanga (83) and Bukombo (5). Total in Masisi health zone since beginning of project: 77+48=125 and in addition 330 cases are supported by UNFPA.HIA through service provider. total: 207+77 + 330= 614 case | (56,58%) some cases do not reach the care structures because of fear of reprisals and threats, distance and insecurity. | On-site monitoring to be conducted in 2021, desk-review of reporting by partner, activity report and GBV dashboard
Indicator 1.6.2: Number of Cases of GBV that received psychosocial support
Baseline: 77
Planned Target: 1085
Outcome 2: Livelihoods and socio-economic resilience of displaced women and host communities vulnerable and at risk of SGBV strengthened through the development of community initiatives
Output 2.1:Conduct a rapid gender assessment in the four targeted health zones and identify opportunities for Women's Economic Empowerment |  | Not yet done, the process of the recruitment of the consultant by UN Women is ongoing
indicator 2.1.1: Number of assessments of gender and economic opportunities conducted in targeted areas | 0
baseline: 0 |  |  | Assessment report
planned target: 04
Output 2.1:Conduct a rapid gender assessment in the four targeted health zones and identify opportunities for Women's Economic Empowerment |  |  | Desk review of reporting by partner , assessment report
indicator 2.1.2: Report on gender and economic opportunities in targeted areas published
baseline: 00 | 0 | Not yet done, the process of the recruitment of the consultant by UN Women is ongoing
planned target: 01
Output 2.2: Provide cash-transfers to women at high-risk or victims of SGBV to contribute to their socio-economic resilience with post-distribution monitoring and technical support | 44 beneficiaries; 11 candidates identified in Masisi center (1) and Katale (10), in Masisi health zone. Others identified in Mweso (7) and Kitshanga (10). Total is 33+11=44 | Continued implementation in 2021 Cases must be identified, and receive in psycho social or medical services prior to being selected for cash transfer. | Post monitoring Distribution report
Indicator 2.2.1: Number of beneficiaries having received cash transfers/Provide cash-transfers to women at high-risk or victims of SGBV
Baseline: 0
Planned Target: 300
Output 2.2: Provide cash-transfers to women at high-risk or victims of SGBV to contribute to their socio-economic resilience with post-distribution monitoring and technical support | NA | Will be monitored at the end of project | Post monitoring Distribution report
Indicator 2.2.2: Number of Beneficiaries having invested the cash in socio-economic activities
Baseline: 0
Planned Target: 300
Output 2.3: Strengthen the livelihood of vulnerable women-led households including SGBV survivors through the distribution of "resilience kits" followed by post distribution monitoring and technical support |  |  | Beneficiary lists and receipt lists
indicator 2.3.1:Number of beneficiaries having received resilience kits
baseline: 00 | 0 | Currently being procured.
planned target: 600
Output 2.3: Strengthen the livelihood of vulnerable women-led households including SGBV survivors through the distribution of "resilience kits" followed by post distribution monitoring and technical support |  |  | Activity Report
indicator 2.3.2: Number of beneficiaries reporting that they have increased their socio-economic resilience after having received the kits | 0 | This indicator can not be reported until the end of the project to see the impact of kits and interventions.
baseline: 00
planned target: 600
Output 2.4: Support villages savings and credit associations (VSLAs) and Mutuals Solidarity (MUSO) in target areas |  |  | Activity Report and member lists for VSLA
indicator 2.4.1: Number of beneficiaries in VSLA activities | 0 | Activity on standby awaiting the consultant for 2.1.1 and 2.1.2
baseline: 00
planned target: 150
Output 2.4:Support villages savings and credit associations (VSLAs) and Mutuals Solidarity (MUSO) in target areas |  |  | Activity report
indicator 2.4.2: Number of village savings and credit associations created and functional | 0 | Activity on standby awaiting the consultant for 2.1.1 and 2.1.2
baseline: 00
planned target: 16
Output 2.5:Trained beneficiaries selected on the basis of the rapid gender assessment on rapid income-generating activities, savings, life skills and leadership |  |  | Training report and Participant list
indicator 2.5.1: Number of beneficiaries trained in Rapid Income Generating Activities | 0 | Activity on standby awaiting the consultant for 2.1.1 and 2.1.2
baseline: 00
planned target: 150
Output 2.5:Trained beneficiaries selected on the basis of the rapid gender assessment on rapid income-generating activities, savings, life skills and leadership |  |  | Activity report (Monitoring of micro enterprises/IGAs)
indicator 2.5.2: Number of beneficiaries engaged in economic activities after completion of the training | 0 | Awaiting training
baseline: 00
planned target: 100
Outcome 3: Strengthened prevention, monitoring and accountability measures in North Kivu through the mitigation, and protection of human rights violations as negative effects of COVID-19
Output 3.1: Support the Ministry of Gender and its Provincial, territorial and local Gender Thematic Groups for the implementation of the National Strategy against SGBV |  |  | Activity report
Indicator 3.1.1: Number of structures (Provincial, territorial and local Gender Thematic Groups and their sub-groups and the 1325-coordination committee) supported through technical and institutional assistance. | 4 | Selection process and contracting complete, funds transfer occurring to reinforce these groups.
baseline: 0
planned target: 6
Output 3.1: Support the Ministry of Gender and its Provincial, territorial and local Gender Thematic Groups for the implementation of the National Strategy against SGBV
Indicator 3.1.2: Number of structures within territorial and local groups supported | 3 | Selection process and contracting complete, funds transfer occurring to reinforce these groups. | Activity report
baseline: 00
planned target: 4
Output 3.2: Provide material and technical support to the Child and Family Protection Unit of the Congolese National Police to implement its Action Plan against GBV and strengthen the capacities of 200 members of EPEPVS, prison officers, police etc. on the prevention of violence, particularly GBV due to COVID -19 | 1 | New partner selected, implementation as of August 2021 | Partner report. On-site visits to be conducted in 2021
Indicator 3.2.1: Support civil state offices in the registration of births
Baseline: 0
Planned Target: 4
Output 3.2:Provide material and technical support to the Child and Family Protection Unit of the Congolese National Police to implement its Action Plan against GBV and strengthen the capacities of 200 members of EPEPVS, prison officers, police etc. on the prevention of violence, particularly GBV due to COVID -19 | 2121 | Activities ongoing | Partner report. On-site visits to be conducted in 2021.
Indicator 3.2.2: Number of persons reached with information campaigns on the registration moratorium
Baseline: 0
Planned Target: 4000
Output 3.2: Provide material and technical support to the Child and Family Protection Unit of the Congolese National Police to implement its Action Plan against GBV and strengthen the capacities of 200 members of EPEPVS, prison officers, police etc. on the prevention of violence, particularly GBV due to COVID -19
Indicator 3.2.3: Support to children to obtain birth certificates | 255 | New partner selected, implementation as of August 2021 | Partner report and number of legal cases filed
Baseline: 0
Planned Target: 1200
Output 3.3:Provide material and technical support to the Child and Family Protection Unit of the Congolese National Police to implement its Action Plan against GBV and strengthen the capacities of 200 members of EPEPVS, prison officers, police etc. on the prevention of violence, particularly GBV due to COVID -19
Indicator 3.3.1: Number of police offices supported with material and technical assistance | 14 | Due to COVID 19 more offices were supported | Activity Report and donation certificate
Baseline: 0
Planned Target: 5
output 3.3:Provide material and technical support to the Child and Family Protection Unit of the Congolese National Police to implement its Action Plan against GBV and strengthen the capacities of 200 members of EPEPVS, prison officers, police etc. on the prevention of violence, particularly GBV due to COVID -19 |  |  | Activity report/training report/attendance sheet
Indicator 3.3.2: Number of police officers in decentralized territorial entities trained on prevention of violence, particularly SGBV | 31 | Due to COVID 19 and state of siege it was not possible to train many police officers therefore additional support was given to offices.
Baseline: 0
Planned Target: 200
Output 3.4:Support the establishment of 4 “Girl Shine” spaces that aim to strengthen girls' social assets so that they have someone to turn to when experiencing or threatened by |  |  | Activity report
Indicator 3.4.1: Number of "Girl Shine" safe spaces establishes( WGSS) | 4
Baseline: 0
Planned Target: 4
Output 3.4:Support the establishment of 4 “Girl Shine” spaces that aim to strengthen girls' social assets so that they have someone to turn to when experiencing or threatened by
Indicator 3.4.2: Number of girls who benefitted from support in safe spaces | NA | This data will be available only in the next quarter | Activity report and attendance register
Baseline: 0
Planned Target: 2888
Output 3.5: Support the establishment of 4 “Girl Shine” spaces that aim to strengthen girls' social assets so that they have someone to turn to when experiencing or threatened by | Technical support continued to 5 women's structures FORUM DES FEMMES, SOFEM, CAFPEDI, WAMAMA SIMAMENI and ALW on the Masisi center - Katale axis | Ongoing support and training | Partner report. On-site visits to be conducted in 2021.
Indicator 3.5.1: Provide direct technical and financial support to women's organizations and organizations for persons with disabilities
Baseline: 0
Planned Target: 5
Output 3.5: Support the establishment of 4 “Girl Shine” spaces that aim to strengthen girls' social assets so that they have someone to turn to when experiencing or threatened by | 11 | Training conducted end 2020 in Masisi: 11 individuals received training and information on project, including 2 female officials. Officials worked in 5 offices: ANR (intelligence), PNC (police), civil affairs office, social affairs office and territorial administration | Partner report. On-site visits to be conducted in 2021.
Indicator 3.5.2:Number of community leaders provided with technical support and communication material
Baseline: 0
Planned Target: 48
Output 3.5: Support the establishment of 4 “Girl Shine” spaces that aim to strengthen girls' social assets so that they have someone to turn to when experiencing or threatened by
Indicator 3.5.3:Number of persons reached through awareness-raising campaigns |  | The use of media greatly increased the number of beneficiaries that were reached thereby exceeding initial targets | Activity report
Baseline: 0 | 13293
Planned Target: 13000
Output 3.6:Conduct protection monitoring through the reporting and analysis of protection incidents against IDPs and host communities, particularly incidents of SGBV; Referral of incident survivors to medical and legal structures and psychosocial support |  |  | Activity report
Indicator 3.6.1: Number of community monitoring structures supported ( training and financial support) | 0 | Planned for next quarter
Baseline: 0
Planned Target: 4
Output 3.6:Conduct protection monitoring through the reporting and analysis of protection incidents against IDPs and host communities, particularly incidents of SGBV; Referral of incident survivors to medical and legal structures and psychosocial support |  |  | Monitoring reports
Indicator 3.6.2: Number of periodical and thematic reports published | 40 | Calculated on weekly protection monitoring reports and monthly reports
Baseline: 0
Planned Target: 50
Output 3.6:Conduct protection monitoring through the reporting and analysis of protection incidents against IDPs and host communities, particularly incidents of SGBV; Referral of incident survivors to medical and legal structures and psychosocial support | 242 incidents of SGBV registered and referred. Masisi: 132, Mweso: 82, Birambizo: 28. At least 9 of these incidents included cases of collective rape: 4 in Masisi, 4 in Mweso and one in Birambizo. Total = 68+242 = 310 | Ongoing monitoring | Activity Report
Indicator 3.6.3: Monitoring of protection identification and registration of protection and SGBV incidents and victims of SGBV and other human rights violations
Baseline: 0
Planned Target: 250
Output 3.6:Conduct protection monitoring through the reporting and analysis of protection incidents against IDPs and host communities, particularly incidents of SGBV; Referral of incident survivors to medical and legal structures and psychosocial support | 182 Medical Cases, 614 Psychosocial support and 33 Legal services were provided | The percentage of referrals between services is currently being analyzed from total referrals. | Referral notes and activity report and GBV Dashboard
Indicator 3.6.4: Percentage of survivors of SGBV referred to medical and legal structures and psychosocial support structures
Baseline: 0
Planned Target:80%
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Territory ?

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Will be submitted at the end of the project
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board