## Activity
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Cote d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Côte d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Liberia | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Liberia | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Total of two countries Côte d'Ivoire & Liberia | Percent of budget for each output reserved for direct action on gender equality (if any): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Enhanced capacities for conflict prevention and level of trust between state institutions and target communities of the cross-border areas
Output 1.1: | Reduced tensions and increased promotion of social cohesion through strengthened and institutionalized civil-state collaboration mechanisms | 79500 | 72668.26 | 5396.7 | 98.19% | 112500 | 86887 | 0 | 77.23% | 72000 | 71744.62 | 0 | 99.65% | 105740 | 105740 | 0 | 100% | 369740
Activity 1.1.1: | Conduct a baseline study of all targeted communities and security forces on their perceptions/assessments of the levels of border security, cross-border cooperation and social cohesion; | 11500 | 11368.79 |  | 98.86% | 7500 |  |  | 0% | 10000 | 10000 |  | 100% |  |  |  |  | 29000 |  | The baseline study has been completed at 100% delivrable
Activity 1.1.2: | Establish or reinforce Civil-Military Committees (CMC) for Cote d’Ivoire or County Security Council (CSC) for Liberia; | 0 |  |  |  | 50000 | 38596.7 |  | 77.19% |  |  |  |  | 35740 | 35740 |  | 100% | 85740 |  | Dialogue sessions will focus on issues affecting women as well as ways forward; special measures will be taken to ensure women's participation, including provision of transportation and child care.
Activity 1.1.3: | Regularize inclusive dialogue sessions of CMCs and CSCs in respective countries and between CMCs and CSCs of mirroring communities in the two countries | 0 |  |  |  | 30000 | 28000 |  | 93.33% |  |  |  |  | 70000 | 70000 | 0 | 100% | 100000 |  | Dialogue sessions will focus on issues affecting women as well as ways forward; special measures will be taken to ensure women's participation, including provision of transportation and child care.
Activity 1.1.4: | Reinforce the linkage to the existing early warning systems as well as their capacities to report on the issues related to cross-border area to CMCs and CSCs. | 0 |  |  |  | 25000 | 20290.3 |  | 81.16% | [8 empty] | 25000 |  | This includes training on SGBV and gender issues as well as techniques for women to report in safety; special measures will be taken to ensure women's participation, including provision of transportation and child care.
Activity 1.1.5: | Organize a potential crisis simulation at the border to establish humanitarian corridors and ensure the maintenance of essential economic needs. | 68000 | 61299.47 | 5396.7 | 98.08% |  |  |  | #DIV/0! | 62000 | 61744.62 |  | 99.59% |  |  |  |  | 130000 |  | There is an ongoing preparation to bring authorities from both countries together for the crisis simulation activities. This will done in 2021
Output 1.2: | Improved capacities of local authorities, security forces, border management officials and key government actors for border management with a view to preventing conflicts. | 338036.5405 | 278710.83 | 478.21 | 82.59% | 40000 | 11326 | 0 | 28.32% | 355000 | 345000.02 | 0 | 97.18% | 110000 | 100482.5 | 0 | 91.35% | 843036.5405
Activity 1.2.1: | Conduct a capacity assessment. | 10000 | 9977.95 |  | 99.78% |  |  |  | #DIV/0! | 10000 | 10000.02 |  | 100% | 25000 | 25000 |  | 100% | 45000 |  | This activity has been completed at 100%
Activity 1.2.2: | Carry out rehabilitation works in border posts providing the necessary equipment to enhance key actors’ capacities as well as to respond needs of women. | 126536.5405 | 130219.79 |  | 102.9% |  |  |  | #DIV/0! | 140000 | 135000 |  | 96.43% |  |  |  |  | 266536.5405 |  | Contractors are currently mobilizing construction materials for the 4 administrative border posts
Activity 1.2.3: | Provide basic skill trainings to use computers and other electronics to input and manage data. | 21500 | 17489.48 |  | 81.35% |  |  |  | #DIV/0! | 20000 | 20000 |  | 100% | 20000 | 23000 |  | 115% | 61500 |  | Computer vendors have been vetted to start training for the security agencies at the borders
Activity 1.2.4 | Organize trainings in border management for administrative authorities, security forces/agencies and communities’ leader. | 45000 | 35397.44 |  | 78.66% | 5750 |  |  | 0% | 47000 | 47000 |  | 100% |  |  |  |  | 97750 |  | This activity has been completed at 100%
Activity 1.2.5 | Facilitate the organization and institutionalization of joint and cross-border patrols by the security agencies of both countries at the local level. | 90000 | 71221.95 | 144.99 | 79.3% |  |  |  | #DIV/0! | 90000 | 89000 |  | 98.89% |  |  |  |  | 180000 |  | This activity has been completed at 100%
Activity 1.2.6 | Organize two high-level meetings between relevant authorities of both countries. | 45000 | 14404.22 | 333.22 | 32.75% | 34250 | 11326 |  | 33.07% | 48000 | 44000 |  | 91.67% | 65000 | 52482.5 |  | 80.74% | 192250 |  | Activity is scheduled for may 2021 at high level meeting of the two authorities.
TOTAL $ FOR OUTCOME 1: |  | 417536.5405 | 351379.09 | 5874.91 |  | 152500 | 98213 | 0 | 64.4% | 427000 | 416744.64 | 0 |  | 215740 | 206222.5 | 0 |  | 1212776.5405
OUTCOME 2: Improved peaceful co-existence and social cohesion between the target communities of the cross-border areas
Output 2.1: | Strengthened conflict prevention and dispute resolution platforms for dialogue, joint problem-solving and cooperation, including women, youth and refugees, at community level | 17000 | 13852.44 | 0 | 81.48% | 72036.54 | 70770 | 0 | 98.24% |  |  |  |  | 105000 | 107567.61 | 0 | 102.4% | 194036.54
Activity 2.1.1: | Establish or consolidate the community conflict prevention and management mechanisms in the target communities. | 0 |  |  |  | 30000 | 30000 |  | 100% |  |  |  |  | 20000 | 20000 |  | 100% | 50000 |  | Committees will comprise leaders of women's associations as well as take into account conflict prevention and management mechanisms driven by women.
Activity 2.1.2: | Strengthen capacities of CPPCs and CPCs to effectively mitigate disputes and conflicts in their respective communities. | 0 |  |  |  | 32036.54 | 32000 |  | 99.89% |  |  |  |  | 40000 | 42567.61 |  | 106.4% | 72036.54 |  | Trainings will implicate leaders of women's associations and included tailored techniques to women's role in mitigation processes; special measures will be taken to ensure participation, such as child care provision
Activity 2.1.3: | Facilitate the organization of CPPCs and CPCs on a quarterly basis. | 0 |  |  |  | 10000 | 8770 |  | 87.7% |  |  |  |  | 25000 | 25000 |  | 100% | 35000 |  | As part of quarterly meetings, a separate meeting held by women for women will be included; special measures will be taken to ensure participation, such as child care provision
Activity 2.1.4: | Organize Joint Committee meetings between respective mirroring communities. | 17000 | 13852.44 |  | 81.48% |  |  |  | #DIV/0! |  |  |  |  | 20000 | 20000 |  | 100% | 37000 |  | Meetings will include a focus on issues and challenges specific to women in cross-border communities.
Output 2.2: | Improved social cohesion and stability among cross-border communities through joint social, cultural and economic initiatives | 140000 | 127757.83 | 0 | 91.26% | 350000 | 309385 | 0 | 88.4% | 123062.45 | 119062.45 | 2034.43 | 98.4% | 280000 | 296671 | 0 | 106% | 893062.45
Activity 2.2.1: | Provide and/or reinforce basic community infrastructure. | 100000 | 80748.48 |  | 80.75% | 105000 | 108775 |  | 103.6% | 123062.45 | 119062.45 | 2034.43 | 98.4% | 75000 | 84000 |  | 112% | 403062.45 |  | Contractors are currently mobilizing construction materials for the 4 hand pumps to support community engagement
Activity 2.2.2: | Support cross-border women initiative to promote women's rights, fight against SGBV, community development, and social economic exchanges. | 0 |  |  |  | 30000 | 60100 |  | 200.3% |  |  |  |  | 20000 | 20000 |  | 100% | 50000
Activity 2.2.3: | Organize sensitization and awareness campaigns related to social cohesion of cross-border areas and elections through the ECOWAS radio broadcasts and IEC materials. | 40000 | 47009.35 |  | 117.5% | 60000 | 35616 |  | 59.36% |  |  |  |  | 80000 | 78671 |  | 98.34% | 180000 |  | Broadcasts will include specific thematics/segments related to women, their role in local societies as well as challenges and ways forward
Activity 2.2.4: | Facilitate to organize cultural, sport, and economic activities with a view to improving social cohesion. | 0 |  |  |  | 155000 | 104894 |  | 67.67% |  |  |  |  | 105000 | 114000 |  | 108.6% | 260000 |  | At least half of proposed activities will specifically target women; specific provisions will be made to ensure women's participation (such as provision of transportation and child care).
TOTAL $ FOR OUTCOME 2: |  | 157000 | 141610.27 | 0 |  | 422036.54 | 380155 | 0 | 90.08% | 123062.45 | 119062.45 | 2034.43 |  | 385000 | 404238.61 | 0 |  | 1087098.99
TOTAL OUTCOME 1 & 2 |  | 574536.5405 | 492989.36 | 5874.91 |  | 574536.54 | 478368 | 0 | 83.26% | 550062.45 | 535807.09 | 2034.43 |  | 600740 | 610461.11 | 0 |  | 2299875.5305
Project personnel costs if not included in activities above |  | 103416.576 | 90982.31 |  | 87.98% | 68944.38 | 63146.41 |  | 91.59% | 86180.48 | 90060.6 |  | 104.5% | 86180.48 | 77771.71 |  | 90.24% | 344721.916
Project operational costs if not included in activities above | [6 empty] | 93659.39 |  | #DIV/0! | [8 empty] | 0
Project M&E budget |  | 48261.072 | 8235.19 | 17500 | 53.32% | 32174.05 | 27685.61 |  | 86.05% | 36654.27 | 10905 |  | 29.75% | 42051.48 | 40639.81 |  | 96.64% | 159140.872
SUB-TOTAL PROJECT BUDGET: |  | 726214.1885 | 592206.86 | 23374.91 | 84.77% | 675654.97 | 662859.41 | 0 | 98.11% | 672897.2 | 636772.69 | 2034.43 | 94.93% | 728971.96 | 728872.63 | 0 | 99.99% | 2803738.3185
Indirect support costs (7%): |  | 50834.9932 | 41450.25 |  | 81.54% | 47295.85 | 46400.1587 |  | 98.11% | 47102.804 | 44574.0883 | 142.4101 | 94.93% | 51028.0372 | 51127.37 | 0 | 100.2% | 196261.6844
TOTAL PROJECT BUDGET: |  | 777049.1817 | 633657.11 | 23374.91 | 84.55% | 722950.82 | 709259.5687 | 0 | 98.11% | 720000.004 | 681346.7783 | 2176.8401 | 94.93% | 779999.9972 | 780000 |  | 100% | 3000000.0029

## Category
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency IOM Cote D`Ivoire | [5 empty] | Amount Recipient Agency UNDP Cote d'Ivoire | [5 empty] | Amount Recipient Agency IOM Liberia | [5 empty] | Amount Recipient Agency UNDP Liberia | [5 empty] | Total tranche 1 (70%) | Total tranche 2 (30%) | PROJECT TOTAL | Overall Expenses | Overall PO | Overall Del (%)
| Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%)
1. Staff and other personnel | 72391.2 | 31024.8 | 103416 | 90982.31 | 0 | 87.98% | 48261.07 | 20683.3157 | 68944.3857 | 44353.77 |  | 64.33% | 60326.336 | 25854.144 | 86180.48 | 90060.6 |  | 104.5% | 60326.336 | 25854.144 | 86180.48 | 77771.71 |  | 90.24% | 241304.942 | 103416.4037 | 344721.3457 | 303168.39 | 0 | 87.95%
2. Supplies, Commodities, Materials | 76108.781 | 32618.049 | 108726.83 | 111397.75 | 251.85 | 102.7% | 24130.53 | 10341.6557 | 34472.1857 | 16479.17 |  | 47.8% | 22717.5792 | 9736.1054 | 32453.6845 | 18036.72 |  | 55.58% | 8410.36 | 3604.44 | 12014.8 | 13565.89 |  | 112.9% | 131367.2502 | 56300.2501 | 187667.5003 | 159479.53 | 251.85 | 85.11%
3. Equipment, Vehicles, and Furniture (including Depreciation) | 28152.292 | 12065.268 | 40217.56 | 23202.06 | 0 | 57.69% | 32174.04 | 13788.8743 | 45962.9143 | 50255.3 |  | 109.3% | 36359.5047 | 15582.6449 | 51942.1496 | 54945.08 |  | 105.8% | 29436.26 | 12615.54 | 42051.8 | 36472 |  | 86.73% | 126122.0967 | 54052.3272 | 180174.4239 | 164874.44 | 0 | 91.51%
4. Contractual services | 38435.117 | 16472.193 | 54907.31 | 22639.41 | 17833.22 | 73.71% | 100543.9 | 43090.2429 | 143634.1429 | 165207.35 |  | 115% | 73158.3058 | 31353.5596 | 104511.8655 | 83535.26 |  | 79.93% | 105129.5 | 45055.5 | 150185 | 121261.98 |  | 80.74% | 317266.8228 | 135971.4955 | 453238.3184 | 392644 | 0 | 86.63%
5.Travel | 33782.875 | 14478.375 | 48261.25 | 36959.05 |  | 76.58% | 32174.04 | 13788.8743 | 45962.9143 | 20732.43 |  | 45.11% | 30803.4972 | 13201.4988 | 44004.996 | 50612.83 |  | 115% | 29436.26 | 12615.54 | 42051.8 | 40639.81 |  | 96.64% | 126196.6722 | 54084.2881 | 180280.9603 | 148944.12 | 0 | 82.62%
6. Transfers and Grants to Counterparts | 160870.437 | 68944.473 | 229814.91 | 219603.66 |  | 95.56% | 180979.01 | 77562.4329 | 258541.4429 | 286082.02 |  | 110.7% | 152092.2674 | 65182.4003 | 217274.6677 | 231863.28 |  | 106.7% | 168207.2 | 72088.8 | 240296 | 271998.85 |  | 113.2% | 662148.9144 | 283778.1062 | 945927.0206 | 1009547.81 | 0 | 106.7%
7. General Operating and other Direct Costs | 98609.154 | 42261.066 | 140870.22 | 87422.62 | 5289.84 | 65.81% | 54695.88 | 23441.0914 | 78136.9714 | 79749.37 |  | 102.1% | 95570.552 | 40958.808 | 136529.36 | 107718.92 | 2034.43 | 80.39% | 109334.46 | 46857.62 | 156192.08 | 167162.39 |  | 107% | 358210.046 | 153518.5854 | 511728.6314 | 442053.3 | 7324.27 | 87.82%
Sub-Total Project Costs | 508349.856 | 217864.224 | 726214.08 | 592206.86 | 23374.91 | 84.77% | 472958.47 | 202696.4871 | 675654.9571 | 662859.41 | 0 | 98.11% | 471028.04 | 201869.16 | 672897.2034 | 636772.69 | 2034.43 | 94.93% | 510280.376 | 218691.584 | 728971.96 | 728872.63 | 0 | 99.99% | 1962616.742 | 841121.4551 | 2803738.1971 | 2620711.59 | 7576.12 | 93.74%
8. Indirect Support Costs (must be 7%) | 35584.4899 | 15250.4957 | 50834.9856 | 41450.25 |  | 81.54% | 33107.095 | 14188.755 | 47295.85 | 46400.1587 |  | 98.11% | 32971.9628 | 14130.8412 | 47102.804 | 44574.0883 | 142.4101 | 94.93% | 35719.626 | 15308.4112 | 51028.0372 | 51127.37 |  | 100.2% | 137383.1738 | 58878.503 | 196261.6768 | 183551.867 | 142.4101 | 93.6%
TOTAL | 543934.3459 | 233114.7197 | 777049.0656 | 633657.11 | 23374.91 | 84.55% | 506065.565 | 216885.2421 | 722950.8071 | 709259.5687 | 0 | 98.11% | 504000.0028 | 216000.0012 | 720000.0074 | 681346.7783 | 2176.8401 | 94.93% | 546000.002 | 233999.9952 | 779999.9972 | 780000 | 0 | 100% | 2099999.9158 | 899999.9582 | 2999999.8739 | 2804263.457 | 7718.5301 | 93.73%