## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Inclusive Economic Recovery through Sustainable Enterprises in the Informal Economies of Fiji, Palau, Tonga and Vanuatu | Overall Duration (months) | 11
Programme Number (if applicable) | 502521 | Start Date (dd.mm.yyyy) | 2020-10-01
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2021-11-01
Country | Fiji | Current End date(dd.mm.yyyy) | 2021-11-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | ILO, UNESCO, UNDP | National counterparts (government, private, NGOs & others) and other International Organizations | National Employer/Private Sector Organisations, National Workers Organiations/Trade Unions, Ministry of Commerce/Economic Development,Ministry of Emplyment/Labour, Ministry of Agriculture, Ministry of Tourism, National Superannuation/Pension Funds, Farmer Organisations, Ministry of Education, Heritage and Arts (Fiji), Ministry of Community and Cultural Affairs (Palau), Ministry of Tourism (Tonga), Ministry of Justice and Social Welfare (Vanuatu), Vanuatu Culture Centre, World Vision,
Report Cleared By
o Name: | Edward Bernard
o Title: | Project Coordinator - ILO
o Email address: | bernard@ilo.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | For the first time, the informal sector workers in Tonga have a collective identity and able to dialogue with government on key employment and business policy issues, including COVD-19 recovery. The establishment of 7 informal sector association’s saw their representatives meet with the CEO of the Ministry of Economic Development, to present their challenges relating to COVID-19 recovery. These recommendations will inform Tonga’s COVID-19 strategy and the development of the National Employment Policy (NEP). The Tonga Public Service Association (TPSA) lobbied for the inclusion of the informal sector in governments COVID-19 recovery grants. In April, for the first time, the government released its 3rd COVID-19 assistance package committing T$9.2M and included an Informal Business Support Fund, available to individuals that are currently conducting informal business activities. In the project supported 1,045 informal sector entrepreneurs to access the funding. In Fiji the project has supported representatives of approximately 3,000 MSME’s, including from the informal sector, to dialogue directly with government on challenges they face in relation to governments COVID Safe Business Protocols and provide solutions to them, including for the national budget. These specific challenges and solutions were also included in the UN submission to the Fijian Government. In addition, these specific challenges and recommendations will also inform the review of National Employment Policy (NEP). For the first time, specific solutions submitted by the MSME’s has been included in the national budget. The project has also developed digestible advisory materials, as part of strengthening Business Development Services (BDS), on governments COVID Safe Business Protocols, allowing MSME’s partculaly those in the informal sector, to understand and comply, so they are able to open for business and continue to employ others. In Fiji, 24 administrators from 15 dance companies are receiving online training on successfully running a dance company and offering an original and creative product and brand for the first time since they have been in existence. The project, by providing a professional ‘learning and sharing’ space for these companies and their managers, is creating a sense of cohesion in what has traditionally been a fragmented sector, while lifting standards across the board. Similarly, 15 individual artists have been receiving online training in both technical skills and product development, branding and supply chain in the area of visual arts. The training will assist them create quality work and understand the whole visual arts value chain. In the area of design, 15 artisans, including weavers, welders, carvers and potters will be beginning training, also online, in August. All training has moved to online to ensure workshops could be held in spite of the current COVID-19 situation. In Palau, Tonga and Vanuatu, training in the Creative and Cultural industries will begin in mid-August, and will target, handcrafts, visual arts, fashion, performing arts and music. In Fiji, two collective bodies, the Fiji Islands Dance Association and the Viti Association of Visual Artists have met, consolidating the dance and visual arts sectors. The two bodies are currently in the process of becoming legally registered entities. The programme of activities to support smallholder farmers, informal sector workers engaged in agriculture and agri-preneurs have now been finalised with Government. The activities are aligned to each country’s COVID-19 response strategies to strengthen domestic food and nutrition security as well as provide an alternative source of livelihoods for workers made redundant by the pandemic.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Approximately 2,000 informal sector workers and entrepreneurs have been reached in Tonga and organized into 7 associations, 3 in the agriculture sector and 4 in creative industries. Of the 2,000, about 30% are women, 45% youth and 3% persons with disabilities. In addition, 1,045 of the organised beneficiaries have been supported to access government’s informal sector business grants. 19 business trainers in Fiji have been trained in ILO’s enterprise development tool, using activity based learning (ABL) methods, called Community Based Enterprise Development (C-BED). In addition, they have been trained on delivering on-line business training, in response to the current COVID-19 crisis. Of the 19 trained, 50% were women and 20% youth. These trainers will use the skills acquired to reach out to their respective beneficiaries, through their respective programmes, collectively targeting 400 micro enterprises this year. 4 private sector Business Development Service (BDS) in Fiji have been capacitated to deliver COVID safe services to approximately 200 micro enterprises this year, as part of this project and through their respective programmes. Besides the training mentioned above, this includes digestible development of business advisory materials (eg. registering a business, opening bank account, etc) that can be used for ease of knowledge transfer with MSME’s, partculaly for informal sector. The number of direct beneficiaries of training in the CCIs in Fiji is 76. In the other countries it is estimated that the number of direct beneficiaries will be between 40 to 50. All the trainings are designed to be gender balanced. The number of indirect beneficiaries will be measured through the training evaluations.
3.1 | Results: Outcome Level | Please include outcome level results achieved | No outcomes to report as of yet.
3.2 | Results: Output Level | Please include output level results achieved | Outcome 1/Output 1: In Fiji 4 Business Development Service (BDS) have been strengthen to support MSMEs including 19 local trainers capacitated to deliver on-line business training. Outcome 1/Output 1.4: UNDP together with ILO is supporting the Pacific Islands Private Sector Organization (PIPSO) to review the PIPSO BCP guidelines that were developed in partnership with the Pacific Community (SPC) to incorporate appropriate exigency measures to mitigate against the economic and health impacts of the COVID 19 pandemic. The PIPSO BCP guidelines will assist small and micro enterprises: • Protect their employees and customers from contracting and passing COVID-19. • Rapidly take measures that can protect their businesses from the incoming disruptions, especially in countries that have not yet been severely impacted by COVID-19. • That have been impacted by COVID-19 to utilize all resources that might be available to them to remain solvent and operational. UNDP together with ILO to roll out BCP training to small and micro enterprises in both the formal and informal sectors in Fiji, Palau and Vanuatu. The main implementing partners are Vanuatu Business Resilience Council, Fiji Business Resilience Development Business Council, Fiji Commerce and Employers Federation and the Palau Small Business Development Centre. Outcome 1/Output 4: In Tonga, 7 informal sector associations have been established. All 7 associations are linked to and supported by the Tonga Public Service Association (TPSA). Through the support of the TPSA, the executives of the associations have met with and submitted 7 policy recommendations to government, as critical areas for informal sector COVID-19 recovery. Outcome 2/Output 1: The traditional master–apprentice scheme is re-established in Fiji, Tonga and Palau where in total 9 master trainers have been mobilized in a diversity of sub-sectors of the local cultural and creative sector, ranging from traditional carving to dance. Outcome 2/Output 3: Specially designed business training for creatives have been launched in Fiji focusing on branding, product development and effective supply chain management. Outcome 2/Output 4: An international call for experts has been launched for the assessment of existing e-commerce opportunities for creatives. Outcome 2/Output 2.1: UNDP is facilitating training of small holder farmers and exporter in Tonga in Financial Literacy and Basic Business Management. A training is schedule for the 4th week of August for 45 farmers and exports from the island of Tongatapu. The main implementing for this activity is the Ministry of Agriculture, Food, Fisheries and Forestry as well as ANZ. UNDP is facilitating training for agriculture-based communities in Vanuatu in Financial Literacy, Basic Business Management, Access to life insurance and pension funds, Agriculture Productive and value adding. A total of 52 market vendors/farmers were trained from the local area of Melemaat in Efate. A total of 64 market vendors/farmers were train from Stonehill settlement in Santo. A mission is planned to conduct the same training in North Pentecost communities in the first week of August, 2021. UNDP together with UNCDF, ILO and UNESCO are working with new or existing aggregator e-commerce platforms in Fiji, Palau, Tonga and Vanuatu to facilitate and onboard local enterprises that are struggling to undertake business physically. This involves working with registered and operating entities to design, develop and manage aggregate e-commerce platform to host local micro and small enterprises in Fiji, Palau, Tonga, and Vanuatu especially from the agriculture industry, arts and crafts industry, creative industry, fashion and design industry, local cosmetics, and health care products, food and catering industry, and the entertainment industry. The e-commerce platform and execution will include the following components/considerations: • A mobile based platform (mobile app) to host the micro and small enterprises detailed above which can run on mobile devices such as smartphones and tablet computers. • A sustainable operational model that can be scaled up over the years, which should include the criteria, cost structure for onboarding local micro and small enterprises, and registration of retail and wholesale customers on to the e-commerce platform. The framework to include cost structure for transactions, and ongoing maintenance fees, etc. as applicable. It is important that costs for onboarding and using the platform is affordable for low income earning entrepreneurs. • A detailed plan for marketing, communications, promotional, and outreach strategy that will raise awareness of the aggregate e-commerce platform, attract local entrepreneurs, and retail/wholesale customers to get registered on the platform. • A practical and realistic integrated payment system for local/overseas buyers and local sellers. • An appropriate and effective end to end delivery system capable of locally delivering small packages to retail consumers or consignments to wholesale customers. • Well defined policies and procedures applicable for the return of damaged goods, refunds, and customer complaint handling.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Since the start of the project, 2 cyclones have hit three project countries – Fiji, Vanuatu and Tonga. COVID-19 is having a prolonged impact in all pacific countries with Fiji facing its second wave triggering additional challenges to movement and gatherings. Both these events were highlighted in the Risk Management Matrix and classified as high. In Fiji, the roll out of training for cultural and creative industries has been slowed down by the difficulties of working in a COVID-19 context with lockdowns, movement restrictions and curfews. The training programs have shifted to an online format to adapt. Although not ideal for the cultural and creative industries where face to face learning is best, the fact that the training is running and artists are able to meet online, is providing relief and a sense of cohesion and togetherness among artists. This ‘slow’ period also affords an opportunity for artists who are usually very busy, to take the time to reflect and rethink their work and how to manage their businesses. The limited institutional capacity of national partners have caused delays. This has primarily been linked to a lack of experience around direct project management by institutional partners as well as competing priorities for the few staff available in the relevant Ministerial departments. To ensure the activities proposed under this initiative complements and adds value to the existing COVID-19 response by Governments through their respective Ministries of Agriculture, Civil Society Organisations and development partners, IFAD pursued a thorough consultative process. The targeting of beneficiaries was a key area of discussion with Government and partners to ensure those already vulnerable prior to the pandemic are supported as well as those whose livelihoods have been impacted and thus are now vulnerable due to the pandemic. Equally critical was to ensure the proposed interventions aligned with Government’s immediate and medium term Response Plans. As a consequence, the commencement of activities targeted at the agriculture sector was been delayed.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Aligning the projects strategies and activities to governments COVID-19 recovery priorities has the potential to create meaningful and greater impact. This is being experienced in Tonga through aligning to its 3rd COVID-19 assistance grants for informal sector enterprises and in Vanuatu where the project is aligning to government’s COVID and TC Harold Recovery Strategy 2020-23. Informal sector COVID-19 challenges and solutions are being considered in Tonga and Vanuatu through the development of their first ever National Employment Policies (NEP). In Fiji, they are being considered in the review of the current NEP. Notwithstanding the current delay in commencement of activities related to agriculture, a key lesson emerging from the consultative process with Government and partners was the need for clarity in defining beneficiaries e.g. ‘vulnerable’ households. Without an agreed definition of vulnerability within the project’s context, identifying beneficiaries is challenging, particularly when resources are limited. Achieving operational synergy across projects of development partners and Government can be much smoother if there is a common definition adopted for targeted beneficiaries. This will provide operational clarity on who our eligible target groups are and ensure scarce resources are utilised efficiently and effectively.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | At the national level, the project is working with ministries of Commerce/Economic Development, Employment/Labour, Culture and Agriculture. The private sector through national private sector organizations are engage on the business components of the project. Trades Unions are supporting and leading activities leading to organizing and national superannuation funds are leading the work on social security. The funds availed through this project has enable these partners to implement activities and plans they had identified in their respective work plans/recommendations as a result of national surveys/assesmeent. The project has developed partnerships with United Nations Capital Development Fund (UNCF), Australian Funded Market Development Facility (MDF) and New Zealand funded Business Link Pacific (BLP). These agencies are bringing in additional technical assistance and funding to the project activities. The project has fostered greater understanding of and appreciation for the cultural and creative industries through the facilitation of dialogue and consultations between artists, cultural producers and government ministries and development agencies. Most notably this was achieved through the consultative meetings for the establishment of professional associations, bringing together members of the creative sector and development partners. This is an important first step towards raising the visibility and voices of those working in the cultural and creative industries and helping move them into the formal sector. The consultative process pursued by IFAD has fostered greater in-country coordination and interaction amongst stakeholders, particularly between the Ministries of Agriculture and Civil Society Organisations, including the private sector. The delivery of activities in the agriculture sector has traditionally been the domain of Government, particularly in relation to activities supporting a national response to a crisis. However, given that the agricultural activities earmarked in this initiative will be delivered by non-Government implementing partners, it has created virtual bridges with the ministries of Agriculture, and has allowed exchange of information on existing areas of work, potential areas for joint implementation, particularly within the country pandemic response plans, as well as future collaboration. There is strong political will within Government to revive Pacific agriculture. There is also recognition now that a strong partnership with Civil Society Organisations, including the private sector, will play a pivotal role in achieving this goal.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | None undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The ILO will not be focusing on Outcome 1/Output 3 (Social Security) in Palau. Palau has the American Social Security System where all nationals are registered and have access to the pension scheme. Due to the challenges mentioned above, the UN agencies have decided to request for project non-cost extension. The extension is sort for a period of 6months, ending 30th April 2021. In addition, some of the strategies and targets may need to be adjusted to reflect the challenges.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Due to the challenges mentioned above, delivery rates are being impacted. Through a no-cost extension, the project will have more time to address the challenges and deliver better. Recruitment of staff and technical consultants has been a challenge due to the current labour market conditions. This is also applicable to the area of cultural and creative industries where hiring national coordinators took longer than planned due to the limited numbers of qualified consultants in that area of expertise. Two of the coordinators have a background in cultural and creative industries but the other two are new to this area: one has expertise in cultural heritage and the other in the field of human rights and leadership. This project is useful in helping build human resources in the cultural and creative industries but specific training in this field in the Pacific Islands Countries is much needed. The current project facilitated the establishment of a new partnership between UNESCO and the Pacific Community (SPC), and provided the backdrop for the design of a new project focusing on audio-visual productions as a specific sub-sector of the cultural and creative industries. The joint proposal was submitted to the ACP-EU call and has been pre-selected for approval. Similarly, the current project forms the basis for a Joint UN proposal being developed with ILO as lead agency. It is envisaged that this project will allow to roll out and scale up the activities under the current project. A Communications Consultant has been hired to support visibility of the project. A project portal has been created in on the UN Pacific website https://pacific.un.org/en/131555-un-mptf-informal-economies-recovery, hosted by the UN Resident Coordinator’s Office. The ILO has also established a project website https://www.ilo.org/suva/projects/WCMS_776240/lang--en/index.htm , where stories of project activities are uploaded. Through the Communications Consultant, 3 project newsletters have been released and can be found on the project portal. The project has developed partnerships with United Nations Capital Development Fund (UNCF), Australian Funded Market Development Facility (MDF) and New Zealand funded Business Link Pacific (BLP). These agencies are bringing in additional technical assistance and funding to the project activities. The ILO is in discussion with the ADB regarding their project on Supporting Recovery by Micro, Small, and Medium-Sized Enterprises in the Pacific from the Effects of the COVID-19 Pandemic ¦ Asian Development Bank (adb.org) to explore potential collaboration. Through its country implementing partners, the project is leveraging resources, capacity and learnings from IFAD’s projects in Fiji (Farmers Organisation for ACP), Tonga (Tonga Rural Innovation Programme II) and Vanuatu (Melanesian Rural Markets and Innovation Driven Programm), as well as funding of AUD5 million from DFAT for the regional Pacific Islands Rural & Agriculture Stimulus Facility programme.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1: Capacities of BDS providers to deliver innovative and relevant support to informal sector women and youth led creative-prenures and agri-prenures strengthened. | In Fiji 19 local trainers have been capacitated to deliver on-line training and 4 private sector BDS providers will soon launch their 6 weeks on-line training and advisory programme for the creative sector. | Training to start in Fiji and Tonga in August and Palau in September | Newsletter artciles, reports, attendence list
Indicator 1.1.1: # of BDS providers delivering innovative, including virtual services to informal sector women and youth led creative-prenures and agri-prenures.
Baseline:0
Planned Target: At least 3 in each country
Output 1.2: COVID-19 and disaster resilient incubator and accelerator programmes targeting informal sector women and youth led creative-prenures and agri-prenures launched. | No reporrtable achievement yet.The target is 45 creative enterprises in each country and 166 in three countries. | Since IFAD is not covering Palau, the project will not target the agricultural sector.
Indicator 1.2.1: Number of informal sector women and youth led creative-prenures and agri-prenures accessing innovative and relevant BDS.
Baseline: 0
Planned Target: 300
Indicator 1.2.2: % of informal sector women and youth led creative-prenures and agri-prenures adapted disaster resslience strategies as part of their business plan. | ToR finalised and consultant identified.
Baseline:0
Planned Target: At least 50%
Output 1.3: Digital platform for ease of social security access for informal sector workers and women and youth led creative-prenures and agri-prenures established | In Vanuatu the mobile app (M-VATU) has been launched and a local bank will soon launch its payment gateway. In Fiji, actvities are on hold due to the 2nd wave COVID emergency, although the mobile phone platform is available. Tonga will launch its digital platform in the comming months. | No work is envisaged in this area on Palau, as they have a social security system that covers all citizens. | Newsletter articles, reports,
Indicator 1.3.1: # of electronic platform available for making direct contribution to Provident Funds.
Baseline: 1 in Fiji
Planned Target: At least one in each country
Indicator 1.3.2: % of project supported workers and entrepreneurs making contributions to the pension fund through the electronic platform. | No reportable achievement yet.
Baseline:0
Planned Target: At least 50% of beneficiaires
Output 1.4: Representative informal sector workers and women and youth led creative-prenures and agri-prenures groups with links to national workers and employer organisations established. | 4 informal sector creative associations and 3 informal sector agriculture associations established in Tonga. |  | Newsletter articles, membership list, association work plans,
Indicator 1.4.1: # of workers and entrepreneurs associations formed in the creative industries and agricultural sub-sectors.
Baseline: 0
Planned Target: At least 4 in each country
Indicator 1.4.2: % of supported associations linked to national workers and employers organisations | The 7 informal sector associations in Tonga has been linked to the National Union. The 7 informal sector associations have presented 7 policy recoemndations to government and is also been considered for inclussion in the National Employment Policy. |  | Report presented to government.
Baseline: 0
Planned Target: At least 50% of supported associations
Indicator 1.4.3: # of policy recommendations to support informal sector workers and entrepreneurs progressed by national workers and employers organisations.
Baseline: 0
Planned Target: At least 3 policy recommendations per country.
Output 2.1: A master–apprentice scheme is re-established in Fiji, Vanuatu, Palau and Tonga to enable specialized skills transfer in the cultural and creative industry sector | 76 apprentices identified in Fiji; 40 currently undergoing training | Trainings yet to start in Tonga, Palau and Vanuat | Participants lists and Zoom recordings
Indicator 2.1.1: # number of master-apprentice collaborations created in Fiji, Vanuatu, Palau and Tonga
Baseline:0
Planned Target: 20
Indicator 2.1.2: # number of beneficiaries indicating an emerging sense of social cohesion in the communities applying the apprentice scheme | 270 | Indicator measured for only one of the subsectors in one country (Dance subsector in Fiji). | Training reports and participants evaluation
Baseline:0
Planned Target: 450
Output 2.2: At least 500 persons, including agri-prenures trained in agricultural production in Fiji, Vanuatu and Tonga | 0 | Delay in finalising implementation arrangements with IFAD partners in-country (i.e. NGO partner and Ministry of Agriculture for each country). Resources will be mobilised within next few weeks to begin training. | Progress update from IFAD Pacific team based in Fiji.
Indicator 2.2.1: # number of persons trained in agricultural production
Baseline: 0
Planned Target: 500
Output 2.3: Cultural and creative industry entrepreneurs, partculaly women and youth, have improved capacity in developing narratives, labelling and packaging for their products and services to achieve improved market linkages | 40 entrepreneurs undergoing training in Fiji | Trainings yet to start in Tonga, Palau and Vanuatu | Participants lists and Zoom recordings
Indicator 2.3.1: # number of creative entrepreneurs trained in Fiji, Vanuatu, Palau and Tonga
Baseline:0
Planned Target: 300
Indicator 2.3.2: # number of women and young entrepreneurs that indicate abiltiy to engage with target market and have increased ability to define their business venture course of action | This indicator will be measured through the training evaluations which have not been competed yet | Trainings still ongoing | Training reports
Baseline:0
Planned Target: 200
Output 2.4: 4. On-line platforms for e-commerce are harnessed to enhance business development and South to South knowledge exchange is facilitated | Activity not yet started
Indicator 2.4.1: # number of cultural products and services made available on e-commerce platforms in Fiji, Vanuatu, Palau and Tonga
Baseline:
Planned Target: 8
Indicator 2.4.2 :# number of beneficiaries that have developed skills to use existing e-commerce platforms | Activity not yet started
Baseline:0
Planned Target: 300
Output 2.5: E-platform for agricultural sales rolled out in Fiji, Tonga and Vanuatu | No progress | IFAD/UNDP coordinating in delivery of this output. IFAD has mobilised a consultant in mid July to develop a strategy on the use of ICT tools for its projects in the Pacific in areas such as nutrition awareness, farm management information system, and e-commerce. IFAD consultant report will feed into work to be undertaken by UNDP witih a yet-to-be identified service provider to expand coverage of existing e-commerce platforms as oppossed to developing a new one. | Progress update from IFAD Pacific team based in Fiji.
Indicator 2.5.1: # of new users of agricultural e-commercial platform
Baseline:0
Planned Target: 500
Output 2.6: Provision of tools and inputs to family farms | 0 | Delay in finalising implementation arrangements with IFAD partners in-country (i.e. NGO partner and Ministry of Agriculture for each country). Resources will be mobilised within next few weeks to begin distributiion of tools and inputs to targeted beneficiaries.. | Progress update from IFAD Pacific team based in Fiji.
Indicator 2.6.1: # number of family farms provided with inputs & tools
Baseline: 0
Planned Target: 250
Output 2.7: Safety and Health awareness and improved practices communicated to targeted family farms in Fiji, Vanuatu and Tonga | 0 | Delay in finalising implementation arrangements with IFAD partners in-country (i.e. NGO partner and Ministry of Agriculture for each country). Resources will be mobilised within next few weeks to begin training. | Progress update from IFAD Pacific team based in Fiji.
Indicator 2.7.1:# number of persons trained in safe post-harvesting handling and COVID-19 compliant supply chain management
Baseline:
Planned Target: 600
Output 2.8: Knowledge sharing on food preservation and trainings in processing methods provided in Fiji, Vanuatu and Tonga | 0 | Delay in finalising implementation arrangements with IFAD partners in-country (i.e. NGO partner and Ministry of Agriculture for each country). Resources will be mobilised within next few weeks to begin training. | Progress update from IFAD Pacific team based in Fiji.
Indicator 2.8.1: # number of persons trained in food processing and preservation techniques
Baseline: 0
Planned Target: 60
Output 3.1: Audio-visual knowledge tools developed for sharing experience with non-project countries | 3 videos have been developed and has reached approx. 800 people through facebook. 3 Project eNewsletters have been circulated including via social media and has reached approx. 300 people. |  | ILO Facebook page, project webpage. https://pacific.un.org/en/131555-un-mptf-informal-economies-recovery
Indicator 3.1.1: # number people accessing audio-visual knowledge tools developed
Baseline: 0
Planned Target: 1,200
Output 3.2: Study elaborated on the contribution of informal creative industries and agriculture to economic recovery | No progress | The project will produce one regional study that will capture situation in the four project contries and in the two specific subsectors
Indicator 3.2.1: # number of studies on the contribution of informal sub-sectors to economic recovery disseminated
Baseline: 0
Planned Target: 40
Output 3.3: Knowledge sharing of good practices and lessons learned through social media and webinars with project and non-project countries and development partners | 3 Project eNewsletters have been circulated including via social media and has reached approx. 300 people. | The project will organise national level advocacy and promotional events during national and internatioanl day celebrations. | https://pacific.un.org/en/131555-un-mptf-informal-economies-recovery
Indicator 3.3.1: # number of stories and lessons learned shared through various channels
Baseline: 0
Planned Target: 32
Output 3.4: Measures and tools established for effective project management, coordination and reporting support | Project Sterring Committee, Project Techncal Team, Communications Strategy, Project Work Plans | Working on final M&E plan | Project documents
Indicator 3.4.1:# number of project management tools developed to ensure timely and efficient implementation
Baseline: 0
Planned Target: 4

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Tonga informal sector workers empowered:
COVID-19 and the World of Work: “We could all do with a bit of hope” – What the informal economies recovery project means for Tonga (ilo.org)
COVID-19 and the World of Work: 1,045 informal sector workers and entrepreneurs supported to access COVID-19 grants (ilo.org)
Informal Economy: Tonga’s first ever tapa trade show to commence in August (ilo.org)
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
COVID-19 and the World of Work: “We could all do with a bit of hope” – What the informal economies recovery project means for Tonga (ilo.org)