## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Concerted action for forcibly displaced women, girls and host communities against consequences of the COVID 19 crisis | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 11th November, 2020
MPTF Office Project Reference Number: | 00124720 | Original End Date (dd.mm.yyyy) | 1st November, 2021
Country | Democratic Republic of Congo | Current End date(dd.mm.yyyy) | 1st November, 2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNHCR and UNWOMEN | National counterparts (government, private, NGOs & others) and other International Organizations | UNFPA: Government - Ministry of Gender, Family and Children through the Gender Division and social affair division, - Ministry of Health through the Provincial Health Division, the National Sexual Health Program and the National Mental Health Program and their decentralized service. Operational implementing Partner, International NGO Hope in Action Other international and national Organisations: GBV sub clusters and humanitarian partners in the targetted localities UNHCR: Government counterparts: ANR (intelligence), PNC (police), civil affairs offices, social affairs office and territorial administration, Tribunal de paix; Implementing partners: Intersos (INGO), AHCOPDI (NGO), Caritas (INGO), AIDPROFEN (NGO) Local women's organisations: Forum Des Femmes, SOFEM, CAFPEDI, Wamama Simameni and ALW Other International organisations: Humanitarian partners participating in the protection cluster benefit from protection monitoring data.
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The 2020 activities focused mainly on: i) the development and implementation of the SRH kit procurement plan, targeting the intervention localities with the participation of MCZs in the targeted health zones, ii) coordination with key project partners including UNFPA, UNHCR and UN-Women on the approval of the intervention location, iii) selection of responsibilities and distinct areas of project implementation. According to its mandate and strategic objectives, UNFPA targeted eight health structures (HGR Birambizo, Bishusha HC in the Birambizo health zone, HGR Virunga Karisimbi; Bujovu HC and Mungunba HC in the Karisimbi health zone, Busumba HC, Burungu HC in the Mweso health zone; HGR of Masisi Center) with the collaboration of the Health zone Manager that will benefit from the project as well as the targeted populations in addition to the psychosocial support through service delivery points and safe spaces for women and girls and GBV prevention and risk reduction activities. Due to its experience and ongoing partnerships with organisations in the field, UNHCR was able to easily continue or rescale activities such as psychosocial and legal assistance (2020 pilot), protection monitoring, support to government actors and assistance to prevent statelessness.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | So far, the project reached 2007 beneficiaries, of which 658 women, 614 men and 495 children. No sex disaggregation was recorded for the 255 statelessness cases supported, as children still required official registration at the time of reporting. Besides these 255 children, some 119 girls and 121 boys directly benefited from the project.
3.1 | Results: Outcome Level | Please include outcome level results achieved | No specific, project-related insights yet as the project is in startup phase
3.2 | Results: Output Level | Please include output level results achieved | No specific, project-related insights yet as the project is in startup phase
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Unifying the different operating methods and mandates of the different consortium members and project partners proved to be a challenge. However, the flexibility of the partners allowed of "marriage" between the ongoing field activities and UNHCR presence and the new projects and expertise of UN-Women and UNFPA. Access constraints due to insecurity in Masisi territory also hampered the implementation and monitoring of already established implementing partners. Minor problems were also noted. For example, with regard to birth registration and legal action to address delays in registration, parents of IDPs reported that they lacked transportation to attend meetings with lawyers and to travel to civil registry offices to register their children. Clear communication and encouragement of free legal assistance should reduce the risk to the project. However, fieldwork in the more remote IDP sites - although necessary - could not be funded due to the geographic limitations of the project. Therefore, providing holistic support to IDPs and GBV survivors in all targeted health zones and localities remains a real challenge and gap due to budget restriction. Access to beneficiaries and government partners will continue to depend on the restrictions of COVID-19, which will affect specific areas of the project, such as support to local authorities, information campaigns and others. Some implementation methods could be modified in light of these restrictions, but also the changing climate of insecurity could negatively impact the efficient implementation of the project on the field.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | No specific, project-related insights yet in early stage.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The MPTF funding allowed for the continuation of cooperation with local implementing partners which would otherwise have been reduced due to COVID-related budget restrictions. For UNFPA, the sustained cooperation with health facilities and the implementing partner Hope in Action (a key GBV partner that provides holistic support to GBV survivors in North Kivu) allows UNFPA to provide services and strengthen local technical and material capacities that are aligned with a sustainable exit strategy. It also allows the MPTF to provide support in terms of essential medical inputs (sexual and reproductive health kits), thus ensuring the optimization of service delivery to support access to quality services for women and girls, IDPs and GBV survivors. Capacity building and outreach work allows for targeted support that takes into account the needs of the affected populations, allowing them to formulate their action plans against GBV and strengthen their leadership. These sustainable efforts complement emergency and relief interventions such as those funded by the CERF and the DRC Humanitarian Fund to provide sustainable responses. For UNHCR, sustained cooperation with local implementing partners such as AHCOPDI (legal support and communication on statelessness, human rights monitoring) and AIDPROFEN (legal and psychosocial support in the context of SGBV) allows UNHCR to both provide services as well as build local capacities which fit in a durable exit-strategy. MPTF funding also allows UNHCR to elaborate on pilot projects with local women's organizations (Forum Des Femmes, SOFEM, CAFPEDI, Wamama Simameni and ALW), ensuring the continuation of funding to support the professionalization of women's civil society groups. Community-based work allows for targeted support which takes into account the needs of affected populations, allowing them to formulate their SGBV action plans and capacitating them to liaise directly with local authorities. Such sustainable efforts complement emergency- and relief-based interventions such as those funded by CERF and ECHO to provide durable responses. Long-term, targeted work with women’s and IDP communities also builds connections and systems which foster preparedness and resilience in a context of repeated displacement such as in the territory of Masisi.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The various evaluations, including a gender and socio-economic analysis and a safety audit of women and girls will be possible in the first quarter of 2021. For UNHCR, Cash-based interventions will be followed up on-site, allowing the beneficiaries to address any shortcomings.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | A new implementing partner will be selected to provide legal, technical and operational support on statelessness as needs and reporting efforts exceed the capacity of the current partner (AHCOPDI).
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The annual work plan, UNFPA Procurement plan for the project were developped to implement the project in a timely maner.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
output 1.1 |  | Distribution will be possible in February 2021, following the contracting process with the implementation partners which extended into January 2021.
indicator 1.1.1: Number of health centres provided with COVID-19 protection material |  |  | Distribution plan, material and equipment receipt form signed by the MCZs
Baseline: 0 | 0
Planned Target: 8
output 1.1 |  | Distribution will be possible in February 2021, following the contracting process with the implementation partner which extended into January 2021 and the selection process and establishment of 4 Women and Girls safe spaces.
indicator 1.1.2: Number of IPC (Infection Prevention and Control) kits, personal protective equipment, essential RH commodities and other materials for COVID-19 during the COVID-19 outbreak |  |  | Distribution plan, material and equipment receipt form signed by the MCZs
Baseline: 0 | 0
Planned Target: 12
output 1.1 |  | Contracting process with the implementing partner is being finalized, distribution possible in 2021 according to the distribution plan and the project work plan
indicator 1.1.3: Number of women and girls including IDPs, regugees and host communities who received dignity kits, stay-at-home kits and other support material |  |  | beneficiaries receipt form
Baseline: 0 | 0
Planned Target: 400
output 1.2 |  | Targeting process for health structures started in December and finalized in January 2021 on the basis of MCZ proposal and consortium approval
indicator 1.2.1: Number of midwives, nurse supervisors of health zones and community health workers trained on relevant topics |  |  | Training report and participant list
Baseline: 0 | 0
Planned Target: 40
output 1.2 |  | Contracting process with the implementing partner being finalized in January, activities will be implemented in 2021 based on the work plan
indicator 1.2.2: Number of community organizations, women's rights advocates and groups supported |  |  | Training report and participant list
Baseline: 0 | 0
Planned Target: 8
Output 1.4 | 0 | Contracting process with the implementing partners being finalized in January, activities will be implemented in 2021 based on the work plan | Activities reports
Indicator 1.4.1: Number of persons informed on referral pathways
Baseline: 0
Planned Target: 4000
Output 1.4 | 3 cases: 2 cases of rape, 1 case of sexual assault | Implementation will continue over 2021. Despite many cases registered and provided psychological support, most cases are only at initial stage of providing legal information. So far only 3 cases were refered to legal services. | On-site monitoring to be conducted in 2021, desk-review of reporting by partner
Indicator 1.4.2: Number of GBV cases that received legal/judicial support
Baseline: 0
Planned Target: 30
Output 1.4 | 0 | Contracting process with the implementing partner being finalized in January, activities will be implemented in 2021 based on the work plan | Activities reports, GBV dashboard
Indicator 1.4.3: % of survivors of sexual violence who received medical care at service delivery points by trained staff within 72 hours of the rape incident, disaggregated by age and sex
Baseline: 0
Planned Target: 80%
Output 1.4 | 0 | Contracting process with the implementing partner being finalized in January, activities will be implemented in 2021 based on the work plan | Activities reports, GBV dashboard
Indicator 1.4.4: Number of survivors of sexual violence who received medical care disaggregated by age/gender/disability
Baseline: 0
Planned Target: 108
Output 1.4 | 0 | Contracting process with the implementing partner being finalized in January, activities will be implemented in 2021 based on the work plan | Activities reports, GBV dashboard
Indicator 1.4.5: Number of women and girls who participated in psychosocial activities, including survivors who benefited from age-disaggregated/disability case management
Baseline: 0
Planned Target: 1800
Output 1.5 | 0 | Contracting process with the implementing partner being finalized in January, activities will be implemented in 2021 based on the work plan | Activities reports, GBV dashboard
Indicator 1.5.1: Number of individuals reached with awareness-raising
Baseline: 0
Planned Target: 4000
Output 1.6 | 0 | Implementation planned in 2021 | Training report and Participant list
Indicator 1.6.1: Number of service provider strengthened on mental and psychosocial response including the GBV case management
Baseline: 0
Planned Target: 40
Output 1.6 | Individual therapy: 201 cases of which 77 in Masisi. Others in Kitshanga, Burungu, Mweso and Katale. November: 129 (118 women and 11 girls). December: 78 (71 women and 7 girls). | Continued implementation in 2021 | On-site monitoring to be conducted in 2021, desk-review of reporting by partner
Indicator 1.6.2: Number of Cases of GBV that received psychosocial support
Baseline: 0
Planned Target: 1085
Output 2.1 | 0 | Implementation planned in 2021 | assessment reporting
Indicator 2.1.1: Number of assessments of gender and economic opportunities conducted in targeted areas
Baseline: 0
Planned Target: 4 ( one assessment in the 4 health zones)
Output 2.1 | 0 | Implementation planned in 2021 | On-site monitoring and desk-review of reporting by partner
Indicator 2.1.2: Report on gender and economic opportunities in targeted areas published
Baseline: 0
Planned Target: 01
Output 2.2 | 122 young women at risk, of whom 9 in Masisi center, 24 in Katale (Maisisi center), 13 in Burungu in Masisi, 40 and 36 in Mweso. | Continued implementation in 2021 | Distribution report
Indicator 2.2.1: Number of beneficiaries having received cash transfers
Baseline: 0
Planned Target: 300
Output 2.2 | 0 | Cash transfers began but monitoring of activities to take place in 2021 for investments | Post distribution monitoring report
Indicator 2.2.2: Number of Beneficiaries having invested the cash in socio-economic activities
Baseline: 0
Planned Target: 300
Output 2.3 |  | Implementation planned in 2021 | Beneficiary lists and receipt lists
Indicator 2.3.1: Number of beneficiaries having received resilience kits | 0
Baseline: 0
Planned Target: 600
Output 2.3 |  | Implementation planned in 2021 | Activity report
Indicator 2.3.2: Number of beneficiaries reporting that they have increased their socio-economic resilience after having received the kits
Baseline: 0 | 0
Planned Target: 600
Output 2.4 |  | Implementation planned in 2021 | Activity report/ trainign report /Attendance sheets
Indicator 2.4.1: Number of beneficiaries participating in VSLA
Baseline: 0 | 0
Planned Target: 150
Output 2.4 |  | Implementation planned in 2021 | Activity report
Indicator 2.4.2: Number of village savings and credit associations created and functional
Baseline: 0 | 0
Planned Target: 16
Output 2.5 |  | Implementation planned in 2021 | Activity report/ trainign report /Attendance sheets
Indicator 2.5.1:Number of beneficiaries trained in Rapid Income Generating Activities | 0
Baseline: 0
Planned Target: 150
Output 2.5 |  | Implementation planned in 2021 | Activity report (monitoring of micro enterprises)
Indicator 2.5.2:Number of beneficiaries engaged in economic activities after completion of the training | 0
Baseline: 0
Planned Target: 100
Output 3.1 |  | Implementation planned in 2021 | Activity report
Indicator 3.1.1: Number of structures (Provincial, territorial and local Gender Thematic Groups and their sub-groups and the 1325-coordination committee) supported through technical and institutional assistance | 0
Baseline: 4
Planned Target: 6
Output 3.1 |  | Implementation planned in 2021 | Activity report
Indicator 3.1.2: Number of structures within territorial and local groups supported | 0
Baseline: 3
Planned Target: 4
Output 3.2 | 1 office was supported in Masisi centre, which registered 124 births in the reporting period (November: 33 boys and 31 girls. December: 34 boys and 26 girls). | Restrictions on zones of implementation do not allow to take into account offices supported in Nyamaboko 1, Mahanga, Biiri and Buabo/Mashaki
Indicator 3.2.1: Support civil state offices in the registration of births |  |  | Partner report. On-site visits to be conducted in 2021
Baseline: 0
Planned Target: 4
Output 3.2 | Ongoing campaign in Masisi territory reached 3.158 IDPs (987 men, 560 women, 802 boys and 809 girls). Of these IDPs, some 1034 reside in sites around Masisi centre (605 men, 331 women, 54 boys and 44 girls). | Ongoing campaign
Indicator 3.2.2: Number of persons reached with information campaigns on the registration moratorium |  |  | Partner report. On-site visits to be conducted in 2021
Baseline: 0
Planned Target: 4000
Output 3.2
Indicator 3.2.3: Number of children provided with birth certificates with project support | Files of 255 children supported before the Tribunal de Paix of Masisi Center. | Ongoing support, dependent on COVID-19 situation | Partner report and legal case file numbers. Further checks to be conducted in 2021.
Baseline: 200
Planned Target: 1200
Output 3.3 |  |  | Activity report and donation certificates
Indicator 3.3.1: Number of police offices supported with material and technical assistance | 0 | ongoing support in 2021
Baseline: 0
Planned Target: 5
Output 3.3 |  |  | Activity report/ trainign report /Attendance sheets
Indicator 3.3.2: Number of police officers in decentralised territorial entities trained on prevention of violence, particularly SGBV | 0 | ongoing support in 2021
Baseline: 0
Planned Target: 200
Output 3.4 |  |  | Activity report
Indicator 3.4.1: Number of Women and Girls"Girl Shine" safe spaces establishes | 0 | ongoing support in 2021
Baseline: 0
Planned Target: 04
Output 3.4 |  |  | Activity report and attendance register
Indicator 3.4.2: Number of girls who benefitted from support in safe spaces including women | 0 | ongoing support in 2021
Baseline: 0
Planned Target: 04
Output 3.5: Provide direct technical and financial support to women's organisations organisations and organisations for persons with disabilities | Initial training was provided and action plans elaborated with 20 women of the 5 women's structures FORUM DES FEMMES, SOFEM, CAFPEDI, WAMAMA SIMAMENI and ALW on the axis Masisi center - Katale | Ongoing support and training | Partner report. On-site visits to be conducted in 2021.
Indicator 3.5.1: Number of women's organisations organizations and organizations for persons with disabilities provided with direct, technical and financial support
Baseline: 0
Planned Target: 8
Output 3.5: Provide direct technical and financial support to women's organisations organisations and organisations for persons with disabilities | 0 | Ongoing support and training | Partner report. On-site visits to be conducted in 2021.
Indicator 3.5.2:Number of community leaders provided with technical support and communication material
Baseline: 0
Planned Target: 48
Output 3.5: Provide direct technical and financial support to women's organisations organisations and organisations for persons with disabilities | 0 | Ongoing support and training | Partner report. On-site visits to be conducted in 2021.
Indicator 3.5.3:Number of persons reached through awareness-raising campaigns
Baseline: 0
Planned Target: 13000
Output 3.6 | 0 | Capacity building to be conducted in 2021 | Activity report
Indicator 3.6.1: Number of community monitoring structures supported ( training and finacial support)
Baseline: 0
Planned Target: 4
Output 3.6 | 0 | Capacity building to be conducted in 2021 | Reports
Indicator 3.6.2: Number of periodical and thematic reports published
Baseline: 0
Planned Target: 50
Output 3.6 | 68 incidents of SGBV registered and referred. Masisi: 53, Mweso: 11, Birambizo: 4 | Ongoing monitoring | Occasional on-site monitoring of implementing partner to be held in 2021 and desk review of cases.
Indicator 3.6.3: Monitoring of protection identification and registration of protection and SGBV incidents and victims of SGBV and other human rights violations
Baseline: 0
Planned Target: 250
Output 3.6 |  |  | Activity report, training report and attendance register
Indicator 3.6.4: Strengthen the capacities of local authorities (administrative and traditional) on the key concepts of GBV, human rights, the legal framework, and their involvement, responsibilities and role in the prevention and protection of women and girls, displaced/returnees and very vulnerable/marginalized people, including the referral circuit, in GBV and COVID 19 | 11 individuals received training and information on project, including 2 female officials. Officials worked in 5 offices: ANR (intelligence), PNC (police), civil affairs office, social affairs office and territorial administration | Capacity building to continue in 2021
Baseline: 0
Planned Target: 5
Output 3.6 | 0 | Ongoing 2021 | GBV Dashboard and activity report
Indicator 3.6.5: Percentage of survivors of SGBV referred to medical and legal structures and psychosocial support structures
Baseline: 0
Planned Target:80%

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board