## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Enabling Guinea Bissau to timely respond and stop COVID-19 transmission | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-01
MPTF Office Project Reference Number: | 00121766 | Original End Date (dd.mm.yyyy) | 2021-04-01
Country | Guinea Bissau | Current End date(dd.mm.yyyy) | 2021-09-23
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO ($250K); IOM ($250K) | National counterparts (government, private, NGOs & others) and other International Organizations | VIDA, NADEL and ADPP
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | National authorities’ capacities to effectively implement the National Contingency Plan was enhanced: By organizing capacity development activities for health workers (men and women) and the staffs of the Points of Entry, developing the SoP and providing hygiene material to the health structure, the project gave to the national authorities the capacities to implement the contingency plan. The consequences of this capacity strengthen are the improvement of the laboratory which is able to collect and analyze more and more sample. In the other way the health care workers trained easily demonstrated ability, via exercises or real life event, to respond appropriately to a public health event. Urgent medical assistance for COVID-19 related needs of local population was addressed: The risk communication and community engagement team conducted several communities based discussion on the risk, the prevention and the management of the pandemic. Information were developed and diffused by local radio and social media. This campaign was focused especially on women and young girls and boys. As result the knowledge of the community was improved and the community management of the pandemic was a success
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 1624 health care workers trained: - In 2020: 1 393 health workers - In 2021: 231 technicians (146 men and 85 women 217 Points of Entry authorities trained: - In 2021: 217 authorities (53 female and 164 male) 252 Community leaders, traditional healers, religious leaders (190 men and 62 women) received key messages related to COVID-19 The 252 Community Leaders constitute a network and continue to do sensibilisation at community level. thousands of people were indirect beneficiaries.
3.1 | Results: Outcome Level | Please include outcome level results achieved | OUTCOME 1: Enhanced national authorities’ capacities to effectively implement the National Contingency Plan -Continual increasing of number of specimens. Week20 in 2020: 543; Week50 in 2020: 1303 and Week15 in 2021: 1533 -Continual reduction of new cases: Week20 in 2020: 197; Week50 in 2020: 2 and Week15 in 2021: 32 OUTCOME 2: Urgent medical and assistance COVID-19 related needs of local population addressed. -Three treatment centers were set with 20 ventilators and 45 oxygen concentrators and all health care workers were trained in the correct use and maintenance of the equipment; -Additionally Bubaque (island) health center received two oxygen concentrators and WHO provided on-the-job training in the use and maintenance of the equipment
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1: Strengthened national capacities to detect, isolate, manage and refer suspected cases of COVID-19 Infections Prevention and Control (IPC) developed 4 SoPs: - Guidelines to Prevent and Control COVID-19 in Hotels, restaurants, bars and other entertainment Places; - Tools to assess COVID-19 infection among healthcare professionals - Correct Use of Masks - Concepts and procedures for IPC during the COVID-19 vaccination 8 SOPs developed for air (4) and land (4) Points of Entry: - In line with IHR, guidelines, concepts and procedures to detect, notificate, isolate and manage suspected cases of COVID-19 at land and air borders. Output 1.2: Improved laboratory capacities and provision of supplies needed to assure proper infection control -All results of CVID test are provided during the day (less than 24 hours) - 6197 supplies acquired to equip al PoE. - 2 gender sensitive temporary isolation (in Fulamori PoE and Djeguê PoE. - 6 health checkpoints equipped with water tank, beds and solar panels. Output 1.3: Strengthened clinical gender sensitive management of severe cases of COVID-19 patients -All trainees supervised on the ground shown the abilities to respond appropriately, and continuous on-the-job training and formative supervision provided -On 29th April 2021 87% (3259 recovered / 3726 COVID+) of all COVID-19 patients recovered (60% male and 40% female) - 8 SOPs developed for air (4) and land (4) Points of Entry: - 217 points of entry (PoE) authorities enhanced capacities to detect, notificate, initially manage and refer ill cases at the borders. - 18 digital thermometrs to the PoE authotititrs to data gathering in the epidemiologic response. - Osvaldo Vieira International aIrport infrared thermal scan activitation: device calibration, temperature reading and preventive maintenance procedures of the Infrared Thermal Scan. Output 2.1: National authorities, and Civil Society Organizations (CSOs) are effectively sharing key messages related to COVID-19 among vulnerable populations -From March 2020, virtual daily PHEOC meetings -From April 2021, 2 weekly meetings -Availability of the IPC materials in all health centers, confirmed by IPC evaluation in the Health centers -702 individuals (404 male and 298 female) from 16 PoE (11 official PoE) in Guinea Bissau were sensitized, among them: border authorities, community leaders, traditional healers, religious leaders, local administrators and vulnerable groups. Output 2.2: Enhanced information of all the population, especially the most vulnerable on fundamental health human rights in the COVID 19 pandemic Community visits and communication by the Risk Communication and Community Engagement Team Community radios programs in regions: -Tombali: 2 radios with 2 spots/day -Quinara: 1 radio with 2 spots/day -Bafata: 4 radios with 10 spots/day -Gabu: 6 radios with 22 spots/day Cacheu: 7 radios -Farim: 1 radio -Oio: 1 radio - 10530 COVID-19 preventive supplies delivered to migrants and border population in situation of vulnerability; - 674 households, in the border communities, supported with hygiene items. - 13 key messages from the High Commissioner for COVID-19 disseminated by 7 radios stations through spots and radio programs in local languages. Community radio programs in regions: - Gabu: 2 radios with 12 spots/day - Bafata: 2 radios with 12 spots/day - Cacheu: 1 radio with 22 spots/day - Bissau (SAB): 3 radios with 3 spots/day
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The island region is not well covered in term of surveillance. It is very difficult to work in these islands Guinea-Bissau has no ICU beds Lack of well trained staff in IPC and Case Management Lack of infrastructures and equipment in the PoE to respond to health emergencies (lack of water, isolation/health checkpoint facilities, vehicules, adequate space for health surveillance)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Creating a foundation for the management of hospital waste in Guinea-Bissau is a start to the implementation of a sustainable policy. With COVID-19 and the need to eliminate various hazardous waste produced, the national IPC task force created a guideline, considering the real conditions in the country for waste management. And, in a cascade, the country received several supporters for their management: purchased equipment, some already in the country, and others in the pipeline. We trained 49 trainers (35 male and 14 female) in human and animal health to teach HW management at the national level. Today, we have 441 health technicians (285 female and 156 male) from the SAB and Biombo regions trained on HW management. The aim is to reach all technicians at the national level in human and animal health by the end of 2022. Also, it is expected to validate and introduce the HW management policy in the national waste policy, elaborated by the Ministry of Environment. Rehabilitation of the temporary isolation posts in the Fulamori (Gabu region) and Djegue (Cacheu) PoEs, since these were quite degraded. Construction of health checkpoint in the International Airport of Bubaque (Bijagos region), Pirada (Gabu region), Burumtuma (Gabu region) and Cuntabane (Tombali region). These facilities are equipped with beds, solar panels and water tanks. In these PoE there was any health facility. Now with these facilities, PoE are more prepared to face health emergencies, such as COVID-19.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | WHO and IOM works with different parteners at National and International levels. Points of Entry activities were done by IOM in collaboration with WHO, COVID-19 High Commission and INASA.. Infection Prevention Control and Risk Communication / Community Engagement (CREC) activities were in collaboration with the High Commission of COVID-19 CREC worked with different national association: National Red Cross, NADEL, Battoden Golle, AMB (Associacao de Moradores de Bairos), CNI (Coseil National Islamique), Women Christian and Islamique Associations... For Case Management training and other activities were organised with AFAEM
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Enhanced national authorities’ capacities to effectively implement the National Contingency Plan
Improved good health and well being | -Continual increasing of number of specimens. Week20 in 2020: 543; Week50 in 2020: 1303 Week15 in 2021: 1533 -Continual reduction of new cases: Week20 in 2020: 197; Week50 in 2020: 2 Week15 in 2021: 32
Indicator 1.1.1: Confirmed COVID-19 cases in month
Baseline: 52
Planned Target: 30
Timely detection and response to COVID19 |  |  | Number of Specimens collected and analyzsed by the laboratory
Indicator 1.1.1: Detection Time
Baseline: 72 hours | All results are provided during the day - less than 24 hours
Planned Target: Less than 24 hours
Output 1.1: Strengthened national capacities to detect, isolate, manage and refer suspected cases of COVID-19.
Output Indicator 1.1.1a | Infections Prevention and Control (IPC) developed 4 SoPs: - Guidelines to Prevent and Control COVID19 in Hotels, restaurants, bars and other entertainment Places; - Tools to assess COVID-19 infection among healthcare professionals - Correct Use of Masks - Concepts and procedures for IPC during the COVID-19 vaccination 8 SOPs developed for air (4) and land (4) Points of Entry: - In line with IHR, guidelines, concepts and procedures to detect, notificate, isolate and manage suspected cases of COVID-19 at land and air borders. |  | SOPs developed
# of SoPs developed for case detection, notification and surveillance
Baseline: 0
Planned Target: 3
Output Indicator 1.1.1.b |  |  | Training reports Training modules
# male and female health workers, including trained allied workers | 1624 health care workers trained:
Baseline: 0 | In 2020: 1 393 health workers
Planned Target: 1500 | In 2021: 231 technicians (146 men and 85 women)
Output Indicator 1.1.1.c |  |  | Training report
% of female and male trainees who demonstrate ability, via exercises or real-life event, to respond appropriately to a public health event | WHO: All trainees supervised on the ground shown the abilities to respond appropriately, and continuous on-the-job training and formative supervision provided. IOM: 100% (23% female and 77% male) demonstrate ability, via simulation exercise between 9 to 2 march 2021, to respond appropriately to a public health event
Baseline: 0
Planned Target: 100
Output 1.2: Improved laboratory capacities and provision of supplies needed to assure proper infection control
Output Indicator 1.2.1 a | 6197 supplies acquired to equip al PoE. |  | Number of supplies delivered for each 15 PoE
# of supplies acquired to equip all PoEs
Baseline: 0
Planned Target: 7
Output Indicator 1.2.1b | WHO: 10 Health Care Facilities (HCF): 5 Regional hospitals and 5 centers type A in 9 Regions set up and equipped one isolation room for COVID-19 suspected case. 14 HCF close to the PoE that attended the PoE directly. In total, 38% of the 159 HCF in Guinea-Bissau have an isolation room for COVID-19. IOM: 2 gender sensitive temporary isolation; 6 health checkpoints equipped with water tank, beds and solar panels. |  | Isolation centres set up and equipped
# of gender-sensitive temporary isolation areas available at PoEs and health centres and equipped with water and solar panel
Baseline: 0
Planned Target: 1 Isolation area for each PoE and 1 per health centre per region
Output 1.3 Strengthened gender sensitive clinical management of severe cases of COVID-19 patients
Output Indicator 1.3.1a |  |  | Laboratory confirmed negative results
% of female and male COVID19 patients recovered | On 29th April 87% (3259 recovered / 3726 COVID+) of all COVID-19 patients recovered
Baseline: 0
Planned Target: 60%
Output 1.4 Strengthened surveillance capacities and collection of real-time and reliable data in the country, including at points of entry
Indicator: Number of radio/TV spots aired in all the regions
Baseline: 0
Planned Target:
Output Indicator 1.4.1 a | (3) Case Management: -1 SOP for CM of COVID-19 suspected, and confirmed patients developed, -2 updates, accordingly WHO guidelines. (3) Infections Prevention and Control (IPC) - Hospital environmental cleaning - Rational use of Personal Protective Equipment in the context of limited resources - Hospital Waste Management Guide in Guinea-Bissau 8 SOPs developed for air (4) and land (4) Points of Entry: - In line with IHR, guidelines, concepts and procedures to detect, notificate, isolate and manage suspected cases of COVID-19 at land and air borders. | Note contradicting responses from two responsible entities. WHO listed SOPs support the argument for completion of 6 SOPs. | Drafted SOPs
#of SOPs in place for detect, isolation, initial management and referral of an ill passenger
Baseline: 0
Planned Target: 4
Output Indicator 1.4.1b |  | Not reported by responsible entity (IOM). Possibly due to project extension | Reports of INASA/COES and PoE
# of female and male PoE personal with enhance capacities to initially manage and refer ill cases | 217 points of entry (PoE) authorities enhanced capacities to detect, notificate, initially manage and refer ill cases at the borders.
Baseline: 0
Planned Target: 200
Output Indicator 1.4.1c |  | Not reported by responsible entity (IOM). Possibly due to project extension | Reports of INASA/COES and PoE
# of data gathering tools efficiently used at PoE and institutions involved in the epidemiologic response | 19 data gathering tools for the epidemiologic response: 18 digital thermometrs to the PoE authotititrs and 1 infrared thermal scan
Baseline: 0
Planned Target: 15
Outcome 2 | Guinea-Bissau has no ICU beds, however three treatment centers were set with 20 ventilators and 45 oxygen concentrators and all health care workers were trained in the correct use and maintenance of the equipment; Additionally Bubaque health center received two oxygen concentrators and WHO provided on-the-job training in the use and maintenance of the equipment
Urgent medical and assistance COVID-19 related needs of local population addressed.
Indicator: Number of ICU beds with ventilators in the country
Baseline: 0
Planned Target: Ventilators and other clinical services set up in all regions
Output 2.1: National authorities, and Civil Society Organizations (CSOs) are effectively sharing key messages related to COVID19 among vulnerable populations. |  |  | Minutes Number of IA activities conducted
Indicator: Coordination Meetings | From March 2020, virtual daily PHEOC meetings From April 2021, 2 weekly meetings
Baseline: 0
Planned Target: At least 1 coordination meeting health per month
Output Indicator 2.1a
Indicator: # of national authorities and CSOs disaggregated by sex with improved capacities to communicate key messages related to COVID-19 | 702 individuals (404 male and 298 female) from 16 PoE (11 official PoE) in Guinea Bissau were sensitized, among them: border authorities, community leaders, traditional healers, religious leaders, local administrators and vulnerable groups.
Baseline:
Planned Target: 200 |  |  | Pre and postquestionnaire during awareness raising sessions
Output Indicator 2.1b
Indicator: # of community leaders and local population disaggregated by sex actively involved in COVID 19 prevention and protection | 252 Community leaders, traditional healers, religious leaders (190 men and 62 women) were trained
Baseline: 0
Planned Target: 200
Output 2.2: Enhanced availability of protective material to health staff and vulnerable population
Indicator: Availability of the IPC materials in all health centres
Baseline: 0
Planned Target: 2000 health personnel with adequate IPC materials
Output Indicator 2.2a |  |  | Activity report
Indicator: # of preventive supplies available for female and male migrants and population in situation of vulnerability | IOM delivered 10530 COVID-19 preventive supplies to migrants and border population in situation of vulnerability.
Baseline: 0
Planned Target: 500 COVID-19 preventive supplies to migrants and population in situation of vulnerability
Output Indicator 2.2b |  |  | Pre and postquestionnaire during awareness raising sessions
Indicator: # of households supported with hygiene supplies and other forms of direct assistance | Households were supported by local associations with the support of WHO | WHO did not provide exact figure
Baseline: 0
Planned Target: 200 households supported with hygiene items | IOM supported 674 households, in the border communities, with hygiene items.
Output 2.3: Enhanced information of all the population, especially the most vulnerable on fundamental health human rights in the COVID 19 | Community visits and communication by the Risk Communication and Community Engagement Team Community radios programs in regions: -Tombali: 2 radios with 2 spots/day -Quinara: 1 radio with 2 spots/day -Bafata: 4 radios with 10 spots/day -Gabu: 6 radios with 22 spots/day Cacheu: 7 radios -Farim: 1 radio -Oio: 1 radio |  | Number of radio/TV spots aired in all the regions
Indicator: Number of radio/TV spots aired in all the regions
Baseline: 0
Planned Target: At least 3 programmes in community radios are being aired per week with COVID-19 information
Output 2.3: Enhanced information of all the population, especially the most vulnerable on fundamental health human rights in the COVID 20 | Community radio programs in regions: - Gabu: 2 radios with 12 spots/day - Bafata: 2 radios with 12 spots/day - Cacheu: 1 radio with 22 spots/day - Bissau (SAB): 3 radios with 3 spots/day |  | Number of radio/TV spots aired in all the regions
Indicator: # Realization of key messages in local languages about COVID-19 to be broadcast by 7 regional radios and national TV (SAB, Cacheu, Bafatá and Gabú)
Baseline: 0
Planned Target: 7
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
In order to help the community, Miguel and the team delivered a communication session on individual and collective protective measures. This was attended by 40 participants, including religious leaders, national and regional authorities, women and youth associations leaders. "When we returned to the village the day after, the community was adopting protective measures. This made me feel proud," he recalls.
First childbirth of a patient with COVID-19 in Guinea-Bissau- Aissato Ture Barai
During May 2020 the number of COVID-19 cases were rising in Guinea-Bissau. This put even more pressure on an already fragile health system. The situation was chaotic in the Hospital of Cumura, which is one of the three hospitals identified in the country to receive COVID-19 patients. An outbreak of COVID-19 started in the maternity ward and infected several health workers. The midwife Aissatu Ture Barai, working in Cumura for 7 years, told us that “the Hospital almost closed, with the health workers going to quarantine in their homes. For us that stayed it was a serious challenge: we didn’t have enough protective equipment, we worked several long hours, and yes, I can’t deny we were afraid, because this was a new disease and we didn’t have enough information”.
In the maternity ward of Cumura, R.S, a young lady almost 9 months pregnant started to show symptoms of COVID-19. The tests-results came two days later, she was infected with COVID-19, and the baby was expected to be born in the next days. It was also a high-risk pregnancy (pre-eclampsia). Later, the Cumura Hospital staff found out that R.S previously had been a COVID-19 patient at another hospital (one of the two other COVID-19 Centre) and, out of fear of COVID-19, left the hospital early.
Aissatu Ture Barai, was prompt in volunteering herself to assist in the childbirth. She told us, “I had no choice, I needed to assist in the childbirth, it was my duty as a health worker. I was very afraid, and my family and friends told me to not help her and that I would infect all of them. However, my husband, who is also a health worker, supported me in my decision.” On the 18th of May at 21:00 the first contractions started. Aissatu Ture Barai still remembers “when the childbirth started, all my fears of COVID-19 went way, the only thought that I had in my mind was to save the baby and this lady”. After a long labor, on the 19th of May at 17:40 R.S gave birth to a healthy boy, Julinho. R.S, with tears in her eyes, thanked the midway Aissatu Ture Barai.
Few days after, Aissató Ture was tested positive with COVID-19. Only 3 months later, she could come back to the hospital, the 3rd of August. Despite all the challenges, the risks and being infected with COVID-19, Aissatu still remembers this childbirth positively. “It was a special moment in my life, and I will never forget it. I was aware that I was taking part in the first childbirth of a patient with COVID-19 in Guinea-Bissau.”
22 Oct 2020, Placement of physical distance markers at Osvaldo Vieira International Airport.
In order to guarantee physical distance between passengers at Osvaldo Vieira International Airport, IOM proceeded with the elaboration and placement of markers approved by MoH and WHO on the airport's ground.
Photo 20 Physical distance markers at Osvaldo Vieira International Airport
Photo 21 Physical distance markers at Osvaldo Vieira International Airport