## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Tunisia: Strengthening social protection and economic relief systems for vulnerable and marginalized segments of the population as a response to COVID-19 | Overall Duration (months) | 10 May to April 31
Programme Number (if applicable) | 121683 | Start Date (dd.mm.yyyy) | 10 May.2020
MPTF Office Project Reference Number: | UNDP Tunisia | Original End Date (dd.mm.yyyy) | 30.12.2020
Country | TUN | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UN Habitat, UN Women,WFP | National counterparts (government, private, NGOs & others) and other International Organizations | South Development office (Ministry of development) , the ministry of youth and sports, ,Tunisian National instiute of stastic,the national Tunisian office of handcrafts ,Local civil society
Report Cleared By
o Name: | Mohamed Nahali
o Title: | M&E Officer (RCO)
o Email address: | mohamed.nahali@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Through the COVID-19 MPTF-funded programme in Tunisia, UN agencies in Tunisia achieved the following results: 1) UNFPA and its implementing parterns were able to provide social support to vulnerable women and women victims of gender-based violence, as well as members of the LGBTG community and people with disabilities in Tunisia. Psychological support was also provided to the LGBTQ community and vulnerable youth and adolescents in remote areas. In addition, people with disabilities had better accessibility to essential information on COVID19 and youth needs in relation with the impact of COVID19 were assessed. 2) UNWomen: More than 46 public servants have been involved in Gender Responsive Budgeting training sessions. 33 of them are working in different sectoral ministries and 13 from the National Institute of Statistics (INS). The most important thing was that through MPTF project, UN Women Tunisia succeeded to bring onboard very interesting partners such as the Ministry of Economics, finance and support to investment in addition to the INS. Moreover, The six operators working on the hotline 1899, in addition to 5 members from the National Observatory of fighting violence against women have been trained on Law 2017-58 giving the growing number of abused women in Tunisia during the confinement. In addition, 6 knowledge products have been produced under MPTF project and dealing mainly with pandemic impact on women socio-economic conditions and access to health services. Among them, 2 policy briefs (PB) have been already published. 2 other PB, a national methodology on violence against women and a legal report are in the printing process and should be ready for the closure event planned to take place on March 08th. A last report on Socio-economic, taxation, spending, and SDG policies during Covid-19 pandemic in Tunisia, is in its final stage of drafting. 3) UNDP team, as lead on the Outcome 3 of the MPTF project, was able to work on helping people become more resilient by providing them equal access to business opportunities that will make them resist to the Covid shock through financial instruments and technical/digital tools, allowing them to adapt their activities according to the Covid-19 context. Also UNDP team worked on supporting the Government in scaling-up its actions and strengthening women-headed micro enterprises resilience to the Covid-19 pandemic, preventing this segment of the population from further marginalization and impoverishment. In that sense, the project has identified 740 vulnerable women microentrepreneurs in the Southern regions of Tunisia, has filed them in a database, in order to target them as beneficiaries of the capacity strenghtening and support their microentreprises on the other project activities. 4) IOM Tunisia engaged in emergency interventions to help those vulnerable and marginalised segments of the population cover their immediate needs, by distribution of vouchers and support in accessing social aid protection and health information services. During the reporting period, IOM Tunisia realized 12 distributions actions of vouchers. The vouchers could be used in over 100 stores over the country. The distributions were for the benefit of a total of 2 298 (including 1 410 men, 888 women,) migrants residing in various neighbourhoods of Greater Tunis, Sfax and Zarzis, where IOM has offices and also and in other regions such as Nabeul, Korba, Gabes and Djerba. Progress was also made in increasing the access of vulnerable groups to information about COVID-19, prevention measures and communication with local health services but also with IOM through the IOM free hotline. 5)UN-Habitat has supported homeless people, and persons evicted from their homes as a result of the COVID outbreak which has been done through two urgent measures: A concrete support to the Orientation and Social Support Centres in charge of hosting the homeless people and their SAMU Social (Emergency Social Support Service) was given in 3 major cities of Tunisia, namely Tunis, Sousse and Sfax to provide the homeless with shelters, access to basic hygiene facilities and socio-psychological support; this was done with the collaboration of the Ministry of social affairs who provided a list of needs. 6)WFP during the project period conducted a diagnosis of the existing social protection system, and advocacy was undertaken to make it shock responsive inclusive and accessible to the most vulnerable populations. A concreate support was given to ministry of social affairs and minisitry of education to improve the targeting of vulnerable groups and the governance of programs by identifying vulnerable groups, digitizing and modernizing the social protection system; Set up the OOESCO/Ministry of Education database and connect it to the Ministry of Social affairs database to include the 73% of households with children benefiting school meals as safety nets which are currently excluded.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 1)Beneficiaries from UNFPA interventions: - 406 vulnerable women received social aid consisting mainly of treatments, cash-based aid, food, medicine, transportation, rent reimbursement, and utilities bills. - 378 women victims of violence have benefitted from legal, medical, psychological and social services from the new shelter for women victims of violence - 258 persons from the LGBT groups received mental health support (164) and social aid (94). - 637 young people with disabilities received social aid consisting on mainly treatments, medical fees, medical equipment, hygiene kits and dignity kits - 328 747 people with disabilities were reached by the accessible sensitization supports - 1676 young people (15-29) reached to participate to the study on the impact of COVID19 on young people - 339 young people (63% F; 37% M) called the green line for the psychological support 2)Beneficiaries from UNDP interventions: Direct Beneficiaries: *61 craftwomen supported on product design - Gabès : 15 - Gafsa : 16 - Kébili : 15 - Tozeur : 15 *57 vulnerable micro-entrepreneurs craftwomen trained in the fields of communication, digital marketing and e-commerce ; - Gabès : 8 women - Gafsa : 15 women - Kébili : 9 women - Médenine : 3 women - Tataouine : 5 women - Tozeur : 17 women Indirect beneficiaries : * 1.111 vulnerable women microentrepreneurs identified desagregated by region as follows: - Gabès : 140 women - Gafsa : 141 women - Kébili : 157 women - Médenine : 156 women - Tataouine : 197 women - Tozeur : 220 women * 45 women, former victims of trafficking, supported through 3 national NGOs 3) Beneficiaries from UN Women: Training on the law 2017-58 on violence against women : 11 women 0 men Training on GRB and gender sensitive statistics : 30 women 16 men 4) Beneficiaries from IOM: During the reporting period 2 298 (1 410 men, 888 women) beneficiaries received a financial assistance in the form of vouchers to cover their immediate economic needs. All beneficiaries received information about the preventive measures against the spread of COVID-19 and were briefed on channels of communication with health services and with IOM through the IOM free hotline. 5) Beneficiaries from UN-Habitat: The center of Tunis has hosted about Tunis 178 men and 230 women since June 2020.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1: Government agencies are equipped with tools to target more effectively vulnerable and marginalized populations with their COVID-19 responses. Key Result1: Beneficiaries received unconditional cash to cover daily minimum existential needs, with shelter, food, medication and health services, and hygiene products being the top expenditures. Key Result2: DataBase of benficiaries is now finalised. Key Result3: collaboration with the Ministry of social affairs is effective, who provided a list of needs. Key Result4: Capacity building (trainings) in favor of government intitution representatives and public partners have been organized. Outcome 2: Emergency interventions help vulnerable and marginalized segment of the populations to cover their immediate needs during the COVID-19 crisis Key Result 1: The socio-economic needs of vulnerable women were met Key Result 2: The access to information and social protection for people with disabilities was strengthened. Key Result 3: The access to mental health support and social protection for LGBT groups was strengthened. Key Result 4: The access to psychological support to vulnerable youth and adolescents was Increased. Key Result 5: The Impact of COVID19 on young people was assessed Key Result6: The light rehabiliatation work was done, the Van fo 15 seat the car was purchased, An assessment of the capacities of the homeless centers in Tunis, Sousse and Sfax in terms of reception conditions and psychological support for the homeless has been done and Social exclusion analysis was done Key Result 7: The project allowed works of a light rehabilitation of the women's living unit in the Homeless Center of Tunis, in particular interior and exterior painting, maintenance of the sanitary blocks, and maintenance of the garden. Outcome 3: The marginalized women entrepreneurs reinforce their economic resilience Key Result: The economic resilience of marginalized women micro entrepreneurs is reinforced
3.2 | Results: Output Level | Please include output level results achieved | Output 2.1: Increased access of vulnerable groups to social aid, protection and health information and services Key result 1: The access of vulnerable women to protection and health information and services was increased. A total of 378 women have benefited from the services of the newly renovated and equipped shelter for women victims of violence. The shelter, that belongs to the National Union of Tunisian Woman (UNFT), offers psychological, medical, and legal aid serices to women and children victims of violence. The access of vulnerable women to social aid was increased. A total of 406 vulnerables received social aid through CSOs centers of women victims of violence and without shelter. Key Result 2: UNFPA Tunisia supported the strengthening of the access to information on COVID-19 and SRH and GBV to persons with disabilities by translating into sign language information and communication tools and messages on social networks and on media to allow increased access to treatments and liaison with care services. In addition, UNFPA Tunisia and the Arab Institute for Human Rights (AIHR) launched, on November 2020, a campaign to support people with disabilities in times of COVID19 crisis. In partnership with an Organization of People with Disabilities “Ibsar Association”, UNFPA and AIHR implemented a programme of action that consisted on the Provision of social aid consisting on mainly treatments, medical fees, medical equipment, hygiene kits and dignity kits to 637 young people with disabilities across the country in coordination with national structures and organizations of persons with disabilities. Key Result 3: As a response to COVID-19, UNFPA Tunisia supported national partners in the provision of social aid and psychological support to 258 persons from the LGBTQ community through several support groups and through the recruitment of dedicated psychologist. Key Result 4: Increased access to psychological support to vulnerable youth and adolescents in Tunisia: The first hotline for psychological support to adolescents and youth was launched in Tunisia on November 2020. This activity initiated by UNFPA Tunisia in partner with Nebras Institute - The Tunisian Institute for the Rehabilitation of Survivors of Torture, aimed at addressing the impacts of COVID19 on the mental health of young people. The green line is managed by psychologists and with the contribution of a network of psychiatrists and child psychiatrists across the country that are available to provide psychological support confidentially and for free. Key Result 5: The Impact of COVID19 on young people assessed: In partnership with the Arab Institute for Human Rights, an assessment on the impact of COVID19 on young people (15-29) was conducted. A team of 46 field investigators have reached out 1676 young people from different regions of Tunisia. Results will be analyzed during the first quarter of 2021 in order to develop policy briefs on the impact of COVID19 on young people, especially on their access to SRH services and information, their mental health and on gender based violence during the COVID19 outbreak. Key Result 7: The project allowed works of a light rehabilitation of the women's living unit in the Homeless Center of Tunis, in particular interior and exterior painting, maintenance of the sanitary blocks, and maintenance of the garden. This intervention allowed to improve the conditions of reception of women in the center and generated other interventions financed by other donors such as the purchase of beds by the center of Tunis, equipped the two living units with air conditioning by the Samu Social International. Compared to the other centers, the center of Tunis is the center where reception conditions are very critical and needs more follow up from UN-HABITAT side in the following months. As the budget allocated to the works was very low, UN-Habitat in coordination with the Head of the center decided to prioritize and rehabilitate the women's living units and a burnt room which was not used during more than 2 years in the men's living units. This allowed the improvement of the living conditions of women and their children and the reception conditions and increase capacities of having more homeless men. The transfer of the Van to the center of Tunis was done ont April 12, 2021 An inauguration ceremony by the Minister of Social Affairs was held on April 12, 2021 An assessment of the capacities of the homeless centers in Tunis, Sousse and Sfax in terms of reception conditions and psychological support for the homeless has been done. The mission was carried out by a psychologist and allowed to raise several failures of supervision and orientation of the homeless, in particular specific human rights challenges. the results of these two studies have been used to develop proposals and respond to calls to mitigate the problems identified in relation to vulnerability in times of crisis . Output 3.1 The digital transition and capacity development for vulnerable women, especially in southern areas, are supported The MPTF project is helping people become more resilient by providing them equal access to business opportunities that will make them resist to the Covid shock through financial instruments and technical/digital tools, allowing them to adapt their activities according to the Covid-19 context. It works on supporting and strengthening women-headed micro enterprises resilience to the Covid-19 pandemic, preventing this segment of the population from further marginalization and impoverishment. Under this output, an initial phase to assess the digital divide southern Tunisia was carried out and supported by consultancy firm to perform the study at field level. The objective of the study was to inform on the digital divide and digital exclusion degree of vulnerable women entrepreneurs in the targeted governorates of the South (Gabes, Tozeur, Médenine, Gafsa, Kebili, Tataouine). It targeted vulnerable women micro-entrepreneurs (including women artisans) in both the formal and informal sectors in the governorates mentioned above and It assessed and analyzed the opportunities and actual challenges in terms of digital inclusion in Southern areas, to identify the roots of this deficiency. Based on this study, adapted solutions will help the integration of the vulnerable women micro-entrepreneurs in the ecosystem and being (re)employed or launching their own project through digitalization, through: - Capacity building training - Partnership with associations - Identification of opportunities - Training on financial and administrative management Output 3.2: The financial inclusion of vulnerable women micro-entrepreneur is supported In order to better target beneficiaries and assess their needs in terms of financial services, a mapping of the most vulnerable women micro-entrepreneurs was conducted in the governorates of Gabès, Gafsa, Kébili, Médenine, Tataouine and Tozeur and a database created. Following the definition of vulnerability criteria specific to the target regions, 1'111 women micro-entrepreneurs were identified and integrated in the database. An assessment of the needs of women entrepreneurs in the Southern governorates has been conducted in terms of financial inclusion and specific trainings has been designed in accordance with the identified needs, namely : i) launch and expansion of a business ; ii) Marketing and Management ; iii) Identification of financial services ; iv) Setting up a financing request To support project's scaling up processes, specific assistance and coaching has been provided to 60 craftwomen on product design. This assistance has been conducted in different steps : i) Assessment of the group of craftswomen in relation to their know-how ; ii) Supervision of craftswomen for the development of new products and improvement of existing models; iii) Structuring of the creative work of the craftswomen; iv) Creation of synergies between craftswomen of the same Governorate. Also, to support women-led businesses scaling up process, training session has been provided to 57 vulnerable micro-entrepreneurs craftwomen in the fields of communication, digital marketing and e-commerce. The trainings provided the women the productive skills necessary to have a more effective presence in the local economy, to improve their social conditions in their communities, to enhance their resilience to shocks and particularly to the COVID 19 impact. 3 national NGOs have been identified, selected and strengthened in terms of capacities to directly support women led entrepreneurship projects. These NGOs are currently supporting 45 women, former victims of trafficking, to develop their micro-entreprises in the South of Tunisia. To support entrepreneurs in the e-health sector, including women entrepreneurs, a digital hackathon was organized in April 2021 in partnership with Attijari bank. The hackathon allowed i) to provide digital solutions for specific health issues in Tunisia in the context of the covid-19 pandemic ; ii) to give the chance to women entrepreneurs in this sector to access funding ; iii) to enhance entrepreneurs' digital and financal inclusion through networking (with financial institutions, pharmaceutical companies, digital experts, etc). In addition, as part of the celebration of the National Women's Day on August 13th 2020, the project supported the Ministry of Women's Affairs for the organization of a forum under the theme: "Sustainable Development Goals from a Gender Perspective: Tunisia's Priorities after the COVID-19 pandemic ". This forum, bringing together various stakeholders was an opportunity to present Tunisia's achievements in the field of women's protection and the strengthening of their rights in the fight against COVID-19 pandemic. The creation of a photo library that includes vulnerable women microentrepreneurs supported through the different activites of the project. The library will allow to showcase and promote the women's businesses in future UNDP initiatives. The results of UNDP spport has been presented during a national workshop that gathered participants from government (ministries and SDO), civil society, private sector, UN agencies, development partners, experts and beneficiaries. The workshop also allowed to conduct discussions and provide recommendations on future actions to be undertaken in terms of financial and digital inclusion to ensure the resilience of vulnerable women micro-entrepreneurs in southern Tunisia. The results have been achieved through collaborative work with the Ministry of Youth, Sports and Professional integration, the South Development Office (SDO) and local civil society organizations.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | 1)The main challenge in achieving the results is the persistence of the pandemic for almost one year, which was not expected when launching the project's activities. The sanitary measures imposed by the government, which some of them are still currently ongoing in 2021, caused important delays in the implementation of the planned activities (consultants unable to conduct their missions and meet with stakeholder, impossibility to organize workshops). 2)Mission for data collection for the vulnerable women's database has been seriously impacted by the travel restrictions from a region to another. After a period of adaptation to the new working conditions and tools, the project was able to continue the implementation of some of the initially planned actions, mainly by shifting to digital activities (especially training and capacity strengthening). 3) Due to COVID 19 restrictions, the trainings and direct supports planned to be provided to women entrepreneurs in the southern governorates had to be adapted and digitalized. However, the digitalization of the activities didn't allow to reach the expected results as many women beneficiaries don't have access to digital tools. 4)A major challenge faced was the aggravation of the COVID-19 pandemic that has imposed mouvement restrictions and therefore, has limited the beneficiaries' ability to seek help. The shelter had to adapt its way of operating by resorting to phone and home consultations. For the mental support of LGBT groups: ATL MST SIDA Tunis has created several support groups for LGBTI plus community facilitated by 2 recruited psychologists. The hotline for psychological assistance didn’t attract many users. The beneficiaries preferred support groups rather than assistance phone calls. For the green line: The number of young people that called the green line is lower than expected and that might be explained by the sensitivity of the topic considered as a taboo by young people. Thus, UNFPA invested more in the communication and the sensitization about the importance of the mental health among young people and launched a huge communication and advocacy campaign to reach a larger number. 5) During the previous months, working with Tunisian government within a very incertain pandemic climate was not easy in the sense that on one side political instability and socio-economic continuous problems were handicapping our works with many partner institutions; and, on the other side, the pandemic spread during the second vague has largely contributed to the uncertainty of number of events that have been scheduled during the fourth quarter of 2020. Also, in terms of data collection, it was expected to organize qualitative and quantitative surveys focusing on marginalized population. This was not allowed because of the pandemic spread and travel restrictions imposed by the government, and in some other cases, due to social tensions that happened from time to time in some places within the country. 6) Support to homeless people and persons evicted from their homes as a result of the COVID-19 outbreak. Under the responsibility of UN-Habitat. The critical situation of the homeless center made it difficult to prioritize activities. A small number of homeless care staff with low skills made it difficult to diagnose and assess the capacity of the centers Following the same procedures for transferring a donation (van 15 seater) caused a huge delay in delivering the van to the Samu-social service. the budget did not allow to reach the homeless in the other centers
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The digital divide study helped the project to understand the needs of these women southern Tunisia. While the infrastructure & the access to the digital at country level have one of the best indicators in the region, the Gender inequalities in access to digitization is among the top findings of this study. A conservative society paired to a lack of awareness regarding the importance of the Digital transition are two major factors preventing different entrepreneurship actors, especially women, from ensuring their socio-economic resilience. Tunisia has also to strengthen the digital and ICT capacities and awareness among the actors in the south. There is a need to formulate concrete policies supporting activites and generating new ones in ICT and FinTech field, There is a need to involve public institutions and private sector to enhance the entrepreneurship and financial landscape (to support digital and FinTech services + to strenghten skills of these women entreprepreneurs) The distributions allowed IOM to gain access and support vulnerable migrants in regions where the organization does not have offices or used to implement acitivities. These activities extended IOM’s assistance outreach as it gave the opportunity to the teams to share the communication channels of IOM but also inform migrants about the services available. Moreover, they gave the chance to collaborate for the first time with the local municipalities and CSOs, which can be included in future programming The project has contributed significantly to gender equality and the empowerment of women and girls by offering shelter, medical, psychological and legal aid and well as socio-economic services to women victims of violence. The project has also contributed to enhance the access of young people to mental health services by offering a free and accessible solution wich is the greenline. Through this innovative initiative, new challenges regarding the mental health care of young people were raised and that will be adressed within the national strategy to promote the health of adolescents and youth. In addition the Youth needs assessment on the impact of COVID19 on young people will inform national reponse strategies (mainly the national strategy to promote the health of adolescents and youth). Noting that this assessment is the first in its kind to be conducted in Tunisia and that is targeting young people.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNWomen: Three important partnerships have been drawn under MPTF program. All of them are not new certainly but due to the project activities we bring them again on board. First, the National Observatory of fighting violence against women, was in-depth involved in all our activities related to capacity building that benefited to operators working on the hotline 1899 devoted to answer, guide and follow up with abused women who are calling. The National Observatory also has benefited from a small grant that has been dedicated to equip the operators with headsets, smartphones and one printer. The second partner is the National Institute of Statistics (INS) whose partnership is very important especially with regards to our 2021 annual work plan and following years. Our work with INS has been focusing more on training its staff on the importance of producing more gender sensitive data and how to adopt their budget to be gender sensitive. Discussions have been made to continue our partnership after the end of MPTF. Meanwhile, our partner has benefited from a small grant that has been used to purchase three high-end laptops allowing its staff to do data analysis. The laptop specifications have been requested by INS according to its own needs. Our third important partner is the Ministry of economics, finance and support to investment through the Central Unit of Objective Based Budgeting (Unité centrale de la Gestion du Budget par Objectifs). This institution has been involved in a very interesting training session on GRB and helped in gathering representatives from sectoral ministries for one-day training where colleagues from HQ have intervened and presented GRB tools in addition to a presentation on SDG 5c1. Our work with these three partners will continue through a new project that will be launched on March 08th, the same day of MPTF restitution seminar. The called new project will be an occasion to have our partners on board and continue working with based on (i) the outcomes of MPTF and (ii) to develop more perspectives dealing with violence and gender issues but from an economic view. UNFPA's partnership with the UNFT has allowed for the reopening of an out-of-service shelter for women victims of violences and has insured the continuity of its services despite the COVID-19 pandemic. In addition, UNFPA's partnership with 4 centers for women victims of violence and the setting of procedure for distirbution of socioeconomic aid facilitated the process of allocation of aids. The youth needs assessment required strong local partnerships to access young people out of connectivity. Thus coordination with local NGOs covering many regions allowed to reach the target. For the implementation activities under Outcome 3 (UNDP): The project collaborated with the South Development office (Ministry of development) , the ministry of youth, sports and professional integration, the Tunisian National institute of statistics, the national Tunisian office of handcrafts, Local civil society and the private sector (Attijari Bank). IOM partnered up with Associamed in Sfax region in order to provide sensitization to Covid prevention measures to beneficiaries during the distributions. Furthermore, IOM strengthened its relationships with the municipalities of Nabeul, Gabes, Djerba, Sfax, Sousse, Ariana. The UN-Habitat intervention allowed to improve the conditions of reception of women in the center and generated other interventions financed by other donors such as the purchase of beds by the center of Tunis, equipped the two living units with air conditioning by the Samu Social International.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | A Participatory diagnosis of hosting capacities of the Centers for Social Guidance and Orientation (CSGO) was done within the project demonstrated serious problems in the care of the homeless at public centers
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Based on the outcomes of the previous reporting period, the planned target for the number of women who receive GBV services through the newly-established shelter was revised upwards. UNFPA:The implementation of the psychological assistance of youth has known few changes to avoid exacerbating inequalities and vulnerability. The loophole in addressing young adolescents (13 yo-17 yo) made us rethink the mechanisms of reaching out to youth :it is possible to offer listening but not medicines prescriptions and if a dangerous situation is suspected, we must alarm the Infantile protection delegate. We needed to consult with the head of pedopsychiatry department and psychiatry. We initially planned to recruit young psychologists to ensure listening and management of young people for a peer to peer approach. Thanks to recommendations from specialists we choosed an improved structure of experienced psychologist in charge of listening and orienting towards more specialized mental healthcare professionals. This allowed a safe service for young adolescents and youth. For the others UN Agencies, no major adjustment in targets or keys outcomes was made
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNDP: The project benefitted from the human ressources of UNDP's Accelerating SDGs unit and Entrepreneurship for Development project for the implementation of its activities (output 3.1 and 3.2 respectively). The project Entrepreneurship for Development is collaborating with Attijari Bank for the implemtation of its activities on vulnerable women financial inclusion. An MOU was signed as part of the ongoing UNDP project "Entrepreneurship for Development" and MPTF benefitted from this developped synergie. UNWomen: Even if it was very helpful having three more months in the duration of the program giving the Covid-19 pandemic spread, it was a bit difficult to adjust the budget to pay human ressources for the additional period under MPTF project without any additional fund. At this level, UN Women manages to reallocate the initial budget in order to ensure the payment of all stakeholders until the new end date. IOM:All operational ressources have been spent for the activities as of Dec 31st, 2020 UNFPA:Recruitement of a consultant in charge of the follow-up of the project (PwD, LGBT and Youth components). The UN-Habitat intervention allowed to improve the conditions of reception of women in the center and generated other interventions financed by other donors such as the purchase of beds by the center of Tunis, equipped the two living units with air conditioning by the Samu Social International.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Outcome 1. Public policies and budgets at national and local levels are gender sensitive and are enhanced by comprehensive and dynamic normative frameworks and standards
Indicator:
Baseline:
Planned Target:
Output 1.1 : Enhanced capacity of sectoral ministries and local authorities to implement gender sensitive strategies and make strategic budget allocations | Achieved with 10/7 | Due to the importance of GRB and the high awareness level revealed by many institutions’ representatives, UN Women has enlarged the number of institutions targeted by the training sessions | Institutions participating in the training sessions on GRB, photos, videos and minutes of our meeting with the Central unit of GBO in the Ministry of economics, finance and support to investment
Indicator 1.1.1: Nbr of national/local institutions integrating GRB principles/initiatives in Tunisia
Baseline: Baseline: Year: 2017 Value: 0
Planned Target: Target: Year: 2020 Value: 7
Indicator 1.1.2: Women gender analysis reports produced on legal framework and socio-economic measures | Achieved with 6/5 knowledge products | Due to the abundance of information with regards to Gender and Covid-19 crises in Tunisia, it was suggested to add one more PB which was not initially planned. | Published products (5 already published, 1 being printed and will be published during July 2021)
Baseline: Baseline: Year: 2020 Value: 0
Planned Target: Target: Year: 2021 Value: 5
Output 1.2 : Enhanced capacity, tools and knowledge enabling monitoring of gender-related SDGs | To enhance capacity building of our partners, a training sessions have been organized on SDG 5c1 (participants were from government institutions)
Indicator 1.2.1: Number of quality based tools produced to monitor the SDGs
Baseline: Baseline: Year: 2018 Value: 2
Planned Target: Target: Year: 2020 Value: 3
Photos, Videos, list of participants, agenda, presentations, etc.
Indicator 1.2.2: Research methodology for report on the socio-economic situation of women including economic violence developed | YES (Achieved) |  | National methodology will be published during July 2021
Baseline: Baseline: Year: March 2020 Value: No
Planned Target: Year: December 2020 Value: Yes
Outcome 2: Emergency interventions help vulnerable and marginalized segment of the populations to cover their immediate needs during the COVID-19 crisis
Indicator 2a: Number of beneficiaries receiving support
Baseline: 0
Planned Target: 13,148
Output 2.1: Increased access of vulnerable groups to social aid, protection and health information and services
Indicator 2.2.b: Number of women* who receive social aid * Women who do not receive aid through the government’s Covid-19 response plan | 406 | Higher demand than planned | Periodic reports from the CSOs involved
Baseline: 0
Planned Target: 300
Indicator 2.1c: Number of women who receive GBV services through the newly- established shelter | 378 | Higher demand than planned | Periodic report from the UNFT
Baseline: 0
Planned Target: 256
Indicator 2.1d: Number of young people who receive psychological support by sex | 339 (63% F; 37% M) | Low number that might be explained by the sensitivity of the topic considered as a taboo by young people | Statistics’ Reports of the green line / Nebras report
Baseline: 0
Planned Target: 5000
Indicator 2.1e: Number of persons with disabilities who receive adapted information related to COVID19 by sex | 328747 | A large communication campaign to reach this large number | Monthly and quartely reports of the Arab Institute for Human Rights / Social media interactions reports
Baseline: 0
Planned Target: 2000
Indicator 2.1e: Number of persons with disabilities who receive social aid by sex and age group | 637 | Higher demand | Monthly and quartely reports of the Arab Institute for Human Rights / Field visits and follow-up meetings
Baseline: 0
Planned Target: 500
Indicator 2.1f: Number of LGBTQ who receive psychological consultations, access totheir treatment and social aid | 258 | Higher demand | Monthly and quartely reports of the Tunisian Association Against STIs & AIDS / Field visits and follow-up meetings
Baseline: 0
Planned Target: 200
Indicator:2.1.g: Number of homeless people who benefit from shelter or assistance by sex and age group
Baseline: 86 in Social Centres, 200 in the streets | 408 in center | Higher demand than planned and no data available for street | official data from the center
Indicator: Number of young people that participated to the Youth needs assessment (Impact of COVID19 on young people) | 1676 | Higher outreach (in coordination wil local NGOs) | Reports from the Arab Institute for Human Rights / Online google form report with responses of all participants
Baseline: 0
Planned Target: 1200
Outcome 3: The marginalized women entrepreneurs reinforce their economic resilience |  |  | Activity report
Indicator 3.a: Number of digital infrastructure enabling vulnerable women micro-entrepreneur to access to economic solutions
Baseline:0
Planned Target:1
Indicator 3.b Proportion of women supported by the project with increased resilience capacity to shocks, and its ability to support productive activities, decent job creation, entrepreneurship, creativity and innovation | 57% (206 women supported and 118 achieved indicator target) |  | Outputs 3.2.1 and 3.2.2 Reports and surveys
Baseline: 0
Planned Target: 50%
Indicator 3.c Proportion of micro, small and medium-sized supported enterprises, encouraged to be formalized, and in a scaling up process, including through access to financial services (inspired from SDG 8, target 8.3) | 57% (205 women led microentreprises supported and 117 achieved indicator target) |  | Outputs 3.2.1 and 3.2.2 Reports and surveys
Baseline: 0
Plannet Target: 50%
Output 3.1: The digital transition and capacity development for vulnerable women, especially in southern areas, are supported |  |  | Activity report
Indicator 3.1.a Number of women (supported by the project) in the South demonstrating integration in the ecosystem or being (re)employed or launching their own project through digitalization
Baseline: 0
Planned Target:300
Output 3.2: The financial inclusion of vulnerable women micro-entrepreneur is supported
Indicator 3.2.a Number of women-headed micro enterprises in a scaling up proces | 118 micro-projects headed by women scaled up through new product desgin and marketing & networking tools |  | List of Beneficiaries
Baseline: 0
Planned Target: 90
Indicator 3.2.b Number and type of new services (financial, technical) available for women entrepreneurs | 2 (design of new products and facebook page for craftswomen ) |  | Activity Report
Baseline: 0 |  |  | Facebook page
Planned Target:2
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on C7: Auteur: added comment
Note on C14: Auteur: added comment
Note on D14: Auteur: comment added
Note on B19: Auteur: The first item was not finalized due to a very serious health problem of our international consultant

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
craftwomen supported on product design
UNDP:
Media_ Video coverage of tne national workshop on output 3
https://www.youtube.com/watch?v=C_nc3y4f35s
https://www.youtube.com/watch?v=Bdms91Jw-xk
links Press releases of the national workshop on output 3
- https://www.lemanager.tn/2021/03/25/les-recommandations-du-pnud-pour-ameliorer-linclusion-digitale-et-financiere-et-assurer-la-resilience-des-femmes-entrepreneures/
- https://www.webmanagercenter.com/2021/03/25/465547/digitalisation-un-concept-meconnu-chez-les-micro-entrepreneures-du-sud/
- https://www.espacemanager.com/la-digitalisation-meconnue-par-les-micro-entrepreneures-du-sud-tunisien.html
- https://www.tap.info.tn/fr/Portail-Economie/13824845-tunise-pnud-les
- https://www.webmanagercenter.com/2021/03/25/465456/atelier-sur-les-realisations-du-pnud-en-faveur-de-lautonomisation-economique-des-femmes/
Link Press release: Digitalization's defiency roots on output 3.1
https://www.webmanagercenter.com/2021/03/25/465547/digitalisation-un-concept-meconnu-chez-les-micro-entrepreneures-du-sud/
links Press releases of the hackathon on output 3.2
http://www.tustex.com/bourse-communiques-de-presse/attijari-bank-le-pnud-tunisie-et-attijaribank-organisent-le-hackathon-tek%D8%B5%D8%AD%D9%80%D9%80vers-une-sante%CC%81-plus-connectee-en
https://www.ilboursa.com/marches/le-pnud-tunisie-et-attijari-bank-organisent-le-hackathon-tek%D8%B5%D8%AD%D9%80%D9%80-vers-une-sante%CC%81-plus-connectee-en-tunisie_27678
UNHabitat:
UNFPA:
On March 31 2021, UNFPA Tunisia achieved targeted goals related to strengthening social protection and economic relief systems for vulnerable and marginalized segments of the population as a response to COVID-19. Indeed, several actions in response and recovery from COVID-19 consequences were supported by UNFPA Tunisia from June 1st 2020 to March 31, 2021. Hence, UNFPA and its implementing partners were able to provide social support to vulnerable women and women victims of gender-based violence, as well as members of the LGBTG community and people with disabilities in Tunisia. UNFPA Tunisia succeeded in reaching 1043 persons who received social aid consisting mainly of treatments, cash-based aid, food, medicine, transportation, rent reimbursement, utilities bills, medical fees, medical equipment, hygiene kits and dignity kits. 328 747 people with disabilities were also reached by an accessible sensitization tools: Indeed, UNFPA Tunisia supported the strengthening of the access to information on COVID-19 and SRH and GBV to persons with disabilities by translating into sign language information and communication tools and messages on social networks and on media to allow increased access to treatments and liaison with care services. Besides, a shelter of women victims of violence in Tunis was renovated, equipped and reopened to provide listening, orientation and hosting services to around 240 women victims of violence as well as capacity building sessions. |  |  | BEFORE
Psychological support was also provided to the LGBTQ community and vulnerable youth and adolescents. And finally, the impact of COVID19 on young people in remote areas was assessed in order to inform national strategies on adequate interventions targeting this group.
AFTER
IOM:
UNWomen:
Each one of the organized events under MPTF program has been widely disseminated through social media, especially through twitter. Links (but not exhaustive) : https://twitter.com/onufemmestn/status/1338451590857052160?s=09 https://twitter.com/onufemmestn/status/1338748195539705856?s=03 https://twitter.com/TapNewsAgency/status/1369054309158182912?s=19 https://twitter.com/onufemmestn/status/1368909100713644033?s=19 https://twitter.com/blolazabal/status/1368833231714476033?s=19 https://twitter.com/blolazabal/status/1369224332170428428?s=09 https://twitter.com/onufemmestn/status/1369639765503524869?s=09 https://twitter.com/onufemmestn/status/1369294586804379658?s=09 The photos are here Publications and disseminations of knowledge products : PB N°1 Gender and Crisis of COVID-19 in Tunisia: Challenges and Recommendations ¦ UN Women – Arab States This brief summarizes challenges and recommendations of the impact of the recent pandemic of COVID-19 in Tunisia on gender-based violence, access to justice, women and health, and women’s leadership and political participation. arabstates.unwomen.org  PB N°2 Tunisian women in the face of COVID-19: during and after confinement ¦ UN Women – Arab States This brief provides a set of recommendations to take stock of health, economic and social aspects of this unprecedented crisis to develop an exit strategy and to take advantage of this exceptional period to upgrade the mechanisms and structure in Tunisia. It also makes recommendations to adopt a gender approach in government post-COVID-19 strategy. arabstates.unwomen.org PB N°3 Santé des femmes en Tunisie: Les défis pendant et après la COVID-19 ¦ UN Women – Arab States This Policy Brief focuses on the different forms of impact of COVID-19 on women's health in Tunisia. During the first period of the pandemic, many health services were postponed as hospital staff focused on preparing health services to tackle COVID-19. arabstates.unwomen.org PB N°4 Où en sont les Tunisienne au regard de l’ODD3 pendant et après la COVID-19? ¦ UN Women – Arab States It is true that care in the public sector has improved in terms of the existence of health structures and basic health centers distributed throughout the country. However, violence in some of these structures, including the obstetrical environment, is frequent and leaves invisible but painful scars. arabstates.unwomen.org Rapport cadre juridique et genre Rapport analytique: Crise de COVID-19 en Tunisie Cadre juridique et genre ¦ UN Women – Arab States The normative watch provided by UN Women Tunisia during the COVID-19 crisis shows positive actions but also certain flaws in the effective consideration of equal opportunities between women and men. Nearly 50 recommendations have been issued for an inclusive and egalitarian response to the COVID-19 crisis. arabstates.unwomen.org
Note on A311: Auteur: added comment