## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | UN COVID-19 Response and Recovery Multi-Partner Trust Fund(UN Covid-19 MPTF) | Overall Duration (months) | 11 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.05.2020
MPTF Office Project Reference Number: | 121682 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Senegal | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNESCO UNICEF UNHCR ITU | National counterparts (government, private, NGOs & others) and other International Organizations | *Ministry of Education *Ministry of Employment, Vocational Training, Apprenticeship and Integration *African Office for Development and Cooperation (OFADEC)
Report Cleared By
o Name: | Mariama SAGNA
o Title: | Project coordinator
o Email address: | m.sagna@unesco.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In Senegal, the Education and Training sector has not been spared from the impact of the COVID-19 pandemic, affecting around 3.5 million learners, in addition to the 1.5 million 'children already out of school, and triggered closures of schools, universities and vocational training institutes across the country for an extended period from March 2020, until the new school year which began in November 2020 In this context, this joint program supported the deployment of distance learning solutions and helped restore the continuity of learning for particularly vulnerable learners, in collaboration with the Ministry of Education in the framework of the national initiative "Learn at home" and the Ministry of Employment, Vocational Training, Learning and Integration within the framework of the distance learning platform called "ejang". Overall , the joint program strengthened the education system resilience and service delivery capacities, and has reached approximately 654,960 learners, including at least 652,960 learners through the roll-out of a national radio learning program focused on fundamental skills in literacy and numeracy, which was delivered in partnership with national radios and a network of 120 community radios operating across the country; 360 disabled children who received adapted assistance and learning devices; and 1000 refugee learners from more than 60 middle and high schools that were able to receive course materials, school supplies, tablets with a memory card, a USB stick containing course materials in the form of video and files and a connection chip for a period eight (8) months,and 1,000 tablets (for 750 TVET learners and 250 secondary school girls) are acquired and handed over to the ministry in charge of vocational and technical training and to the ministry of education respectively. 'National Education. These students were able to follow the lessons through the radio but also with the connection, visit the sites of educational channels and "Learn at Home". This situation allowed them to have access to the courses taught in the national curriculum whenever needed and to strengthen their knowledge, beyond the lessons learned in class. In addition, 200 teachers have been trained in techno-pedagogy . For the three virtual laboratories to be equipped with multimedia equipment and simulation software, the equipment has already been acquired by UNESCO but there was a delay in the shipment of the equipment and its delivery by the supplier because of the delays. borders which were closed relative to the pandemic with covid 19. However the delivery of the material and the installation of the virtual laboratories will be done during this month of June 2021 Regarding connection, ITU initiated and completed the market for the provision of Internet access to 1,000 vulnerable students (250 girls and 750 TVET students) and the contract was awarded to Orange Senegal. Consultation and coordination with stakeholders (UNESCO, Orange Senegal, Ministry of Education and Ministry of TVET) continued in order to provide the services. The provision of Internet access to 1,000 vulnerable students (250 girls and 750 TVET students) will begin in October 2021 for 10 months. Also, UNESCO was able to save money which enabled it to purchase 107 laptops which will be distributed to trainers at the three vocational training institutions targeted under this project.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | At least 654,320 learners have benefited from the program - including 360 with disabilities (300 with visual and 60 with hearing impairment respectively), 1000 refugee learners and 320,051 girls. The refugee students from sixth to fourth grades received a set of booklets and notebooks. For those in third to final grade, they received, in addition to the booklets and notebook, a tablet plus a memory card, a key and a connection chip. Each student could in turn as well benefit their brothers and sisters, which can lead to more than 1,000 indirect refugees beneficiaries
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1: All children enrolled in primary and secondary school in Senegal, in particular the most vulnerable, have access to education during school closure due the COVID 19 pandemic : The education system effectively deployed a multi-faceted distance learning initiative (including radio, TV, digital and paper-based solutions) to ensure learning continuity in response to the impact of the COVID-19 pandemic, and responded to the variety of learners' needs in considering their contexts and conditions, in considering the impact of the digital divide. Approximately 83% of learners were able to continue some kind of learning during school closure, including 12% through digital, TV or radio solutions.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 New distance learning solutions are effectively deployed to the benefit of marginalized children and youth in primary and secondary education, particularly in rural areas, and with particular focus on digital learning solutions and radio programming: The pre-recorded radio lessons developed by UNICEF (72 lessons on literacy and 72 lessons on numeracy) were validated by the MoE in June ; an MoU was signed between the MoE and the national network of community radios (URAC) on 02 July ; and the programme has been aired on community radio channels from 10 August onwards. National radio operators have also strated broadcasting the programme since September and the programme has continued to be aired even after the new academic year resumed in November. Also, 300 visually impaired learners received learning materials in braille and assistive devices, and 60 with hearing impairments received digital devices (in collaboration with the MoE, and civil society organizations including SightSavers and Humanity & Inclusion). In addition, UNHCR provided 1,000 refugee learners from more than 50 middle and high schools who were able to receive course materials, school supplies, tablets with a memory card, a USB stick containing course materials in the form of video and files and a connection chip for a period of eight (8) months. UNESCO also made 1,000 tablets available to 250 secondary school girls and 750 vocational and technical training learners.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | In the implementation, four main challenges were encountered. The first challenge was targeting refugee students. Targeting refugees has been a real challenge, especially for the Senegal River Valley, as the distances are long and the sites are scattered. In addition, it was difficult to identify the refugee students, especially since many of them use a different name to stay at school. Faced with this situation, it was decided to keep the name registered on the UNHCR information sheet, which was more authentic. Also, as the deadlines for the distribution of the kits were short, distribution and training centers in zones, each bringing together between 50 and 120 students, have been set up. This strategy made it possible to distribute more than 520 kits. The rest of the kits were distributed to remote sites that could not reach the distribution centers. The second challenge was related to the time allotted for the distribution of the kits. Indeed, the students go to class in the morning. This is why, for all the centers, the distribution of the kits had to be carried out in the afternoon in the high schools and colleges with the participation of the teaching teams in order to facilitate the follow-up and the appropriation by the school authorities. For city dwellers, the strategy has been to invite students to the UNHCR Social Orientation Office as a group to ensure distribution and training in the use of tablets. Regarding Thiès and Saint Louis, the distributions were made by regrouping the refugees in the houses of the refugee officials. The third challenge concerned the radio program. The roll-out of the radio learning program involved 120 community radios across the country and initially raised some coordination challenges. Local committees were therefore set up with representatives of decentralized entities of the Ministry of Education and community radios in order to ensure a harmonious and successful broadcast of the radio program. The effective reach of the radio learning program was also supposed to be measured through a third party monitoring agreement, but the context did not allow this activity to continue. Awareness was estimated on the basis of data collected by the National Statistics Institute (ANSD) and the Ministry of the Environment. The estimates presented in this report are based on the lowest estimates. However, it is likely that the radio learning program has benefited over a million learners. The fourth challenge relates to the equipment acquisition process vis-a-vis the duration of the project implementation. The current context linked to the COVID-19 pandemic has made it difficult for many suppliers to deliver the needed quantity of IT equipment at a very short notice. In addition, procurement procedures are sometimes cumbersome and time-consuming. Indeed, the acquisitions of computer hardware and internet access took much longer than initially expected. Moreover, acquisition of certain equipments - particularly those intended for virtual laboratories and certain tablets, as well as the connection has taken time.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The Programme has served as a catalytical instrument to help the MoE formulate and implement the COVID-19 education sector response plan as far as the distance learning component thereof is concerned. As such, the Programme has mobilized both government resources and additional resources from development partners to support the implementation of the different learning solutions while this Programme particularly focused on digital and radio solutions. Other development partners included e.g. AFD and the GPE (paper-based distance learning solutions) and the Word Bank for digital learning solutions (digital platform). The Programme also developed partnerships to ensure the implementation of distance learning solutions, including with civil society (e.g. SightSavers and Humanity & Inclusion for children with disabilities ; URAC for community radios) and the private sector (e.g. national radio operators).
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Internally displaced persons, although indicated as project beneficiaries (450), have eventually not been able to benefit from this project. During the project implementation, it was jointly decided by the implementing UN Agencies that the implementation among vulnerable internally displaced persons in Casamance, will not be handled by UNHCR due to not having a physical presence in this Southern region in Senegal, but by UNICEF. Regarding the connection, the funds available for the connection being very limited, it was decided after consultation between agencies that the provision of the connection targets the 1000 learners who will receive the tablets provided by UNESCO
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | *UNESCO has recruited the main coordinator of the project. UNHCR's partner - the African Office for Development and Cooperation (AODC) - recruited additional staff (senior digital education assistant, an MPTF visibility officer, an assistant responsible for monitoring digital learning). *As for acquisitions, they took longer than necessary because of the context linked to the COVID-19 pandemic, suppliers most often feared the availability of equipment on time. Also, the other problem noted is the rigidity of the procurement procedures which have not been made much more in response to the contexts linked to the COVID-19 pandemic.
.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:All children enrolled in primary and secondary school in Senegal, in particular the most vulnerable, have access to education during school closure due the COVID 19 pandemic
Baseline:
Planned Target:
Output 1.1New distance learning solutions are effectively deployed to the benefit of marginalized children and youth in primary and secondary education, particularly in rural areas, and with particular focus on digital learning solutions and radio programming
Indicator 1.1.1:Number of distance learning solutions deployed through the project, with particular focus on digital learning and radio programming | 1 | The indicator reached concerns the learning by radio which has started. the second indicator concerns learning via the digital platform of the Ministry of Employment, Vocational Training, Apprenticeship and Integration with regard to the digital learning platform. For the moment, only teachers have been trained via the distance learning platform.This indicator will be achieved with the implementation of virtual laboratories underway | MoE official documentation and administrative data
Baseline:0
Planned Target:2
Indicator 1.1.2:Number of learners reached by the project (primary, secondary and TVET)
I)Through digital learning | 1000 | The target is achieved | MoE and ministary of TVET, UNESCO mission report
Baseline:0
Planned Target:1000
(ii) Through radio programming | 653320 | Achievements are based on lowest estimates, but the radio-based learning programme is likely to have benefited well over 1,000,000 learners | ANSD and MoE data, activity reports
Baseline:0
Planned Target:1000000
Indicator 1.1.3:Number of refugee learners reached by the project | Among 950 project beneficiaries, 700 students/pupils received the complete education kit containing a tablet with a sim card, a memory card, a USB key, as well as school supplies. The remaining 250 project beneficiaries received the school supplies, including writing journals and course books. | The target is achieved and surpassed | Report from UNHCR
Baseline:0
Planned Target:900
Indicator 1.1.4:Number of vulnerable learners reached by the project | 471 devices distributed to vulnerable and disadvantaged girls in rural areas in secondary schools | The target was achieved and surpassed. | Report from UNHCR
Baseline:0
Planned Target:450
Output 1.2:Vulnerable and disadvantaged girls in rural areas equipped with connected devices to be able to engage in online learning | 250 | The target was achieved. UNESCO has handed over the 250 tablets to MEN. However, since we are almost at the end of the year, also in order to prevent learners from using the connection that will be made available by ITU, for other purposes during the holidays, the ministry has decided to activate the chips only from the month of October | MoE, UNESCO mission report concerning the tablets
Indicator 1.2.1:Number of vulnerable and disadvantaged girls in secondary education equipped with connected devices
Baseline:0
Planned Target:250
Output 1.3:Teachers in primary and secondary education are equipped with techno-pedagogies and skills for tutoring and monitoring of student learning for effective distance education | 100 | The target was achieved | General Inspectorate of Education and Training of the National Ministry of Education
Baseline:0
Planned Target:100
Outcome 2:
Indicator:All youth in vocational and technical training in Senegal have access to training during the closure of TVET institutions due to the COVID-19 pandemic
Baseline:
Planned Target:
Output 2.1:Selected TVET institutions are equipped with the tools and equipment for creating virtual laboratories and video content development to teach technical and practical skills through distance education | 0 (targets to be achieved in the upcomming day) | Multimedia equipment as well as simulation software have been purchased but are still under customs control, they will be delivered to us by the suppliers during this month of June. The suppliers had great difficulty in having the equipment shipped to Senegal because all the computer equipment is ordered abroad.The context linked to the Covid 19 pandemic did not facilitate large-scale acquisitions | UNESCO office
Indicator 2.1.1 Number of TVET institutions equipped with tools and equipment for virtual laboratories and video content development
Baseline:0
Planned Target:3
Indicator 2.1.2:Number of TVET learners equipped with connected devices | 750 | The target was achieved. UNESCO has handed over the 250 tablets to MEN. However, since we are almost at the end of the year, also in order to prevent learners from using the connection that will be made available by ITU, for other purposes during the holidays, the ministry has decided to activate the chips only from the month of October | ministary of TVET
Baseline:0
Planned Target:750
Indicator 1.2.2:Number of TVET teachers equipped with techno-pedagogies and skills for tutoring and monitoring of student learning for effective distance education | 100 | The target was achieved | Directorate of Vocational and Technical Training
Baseline:0
Planned Target:100
Output 2.2:internet access is available, affordable and inclusive of vulnerable and disadvantaged learners and teachers in primary and secondary education and TVET from the targeted regions |  | Consultations with local mobile internet providers was done | Documentation and network coverage maps
Indicator 2.2.1:Number of vulnerable and disadvantaged children in secondary education and TVET connected to available internet | 0 | The internet access acquisition process for 1000 learners(250 girls in secondary education and 750 TVET learners) completed | Contract for provision of internet access issued to Orange Sonatel by ITU
Baseline:0
Planned Target:4500
Indicator 2.2.2:Number of secondary education and TVET teachers connected to available internet | 0 | The funds provided for the connection will only be able to ensure the connection of the 1000 learners | Contract for provision of internet access issued to Orange Sonatel by ITU
Baseline:0
Planned Target:4500
Output 2.3:Data management systems are established to monitor project beneficiaries
Indicator 2.3.1:Number of data management systems put in place | 1 | setting up the refugee database | UNHCR
Baseline:0
Planned Target:2
Indicator 2.3.2:Number of awareness/communication sessions on the COVID 19 conducted | 43 | The target was achieved and surpassed. | MoE and URAC activity reports
Baseline:0
Planned Target:6
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on C70: Sagna, Mariama: The funds provided for the connection will only be able to ensure the connection of the 1000 learners

## Communication-final2
1. Impact Stories from the Field (On the square of the 3rd row column A, position your mouse over it and deactivate your creation mode of the developer tab to watch the video testimony of Mr. Ndiogou FALL, Director of the vocational training center of Ourossogui, on techno pedagogy training they received as part of the MPTF)
https://www.facebook.com/UNESCODAK/photos/pcb.3970015123109583/3970013703109725/
· https://www.youtube.com/watch?v=ouQXExE1gc0&feature=emb_logo
· https://www.dakaractu.com/Covid-19-Education-Le-Hcr-dote-les-eleves-refugies-du-Senegal-de-kits-scolaires-numeriques-d-un-cout-unitaire-de-100-000_a197593.html
· ONU Magazine (p. 27) https://senegal.un.org/sites/default/files/2021-03/SNU%20MAGAZINE%20FEVRIER_0.pdf
https://web.facebook.com/UNESCODAK/photos/r%C3%A9ponse-nationale-%C3%A0-la-covid-19-lappui-%C3%A0-la-continuit%C3%A9p%C3%A9dagogique-est-une-des-pr/3004336593010779/?_rdc=1&_rdr
https://bit.ly/37CvCEl
The photos and reports are contained in the narrative part of the report as attachments.
https://youtu.be/ouQXExE1gc0
Children with disabilities using materiels in braille at home
radio based learning programme (Kaffrine region)
Radio learning programme
Radio learning programme
Remise des kits au élèves de Podor, Ngaolé, Antenne Dabaye, Ouro Madiw et Ndiawara
Remise des kits au élèves de Podor, Ngaolé, Antenne Dabaye, Ouro Madiw et Ndiawara
Children with disabilities using materiels in braille at home
radio based learning programme (Kaffrine region)
Formation des professeurs du lycée Seydina Limamou Laye de Dakar à la techno pédagogie
Formation des enseignants du centre de formation professionnelle d'Ourossogui à la techno pédagogie
Remise tablettes destinées au 250 filles du secondaire
Remise des 750 tablettes destinées aux apprenants de la formation professionnelle et technique
Image plaque comémorrative qui sera insatllé dans les trois laboratoires virtuels