## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual (hidden)
Programme Title & Project Number |  | Programme Duration
Programme Title: |  | Overall Duration (months) | 18
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-04-01
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2021-12-31
Country | Cambodia | Current End date(dd.mm.yyyy) | 2021-03-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNCDF UNDP IOM | National counterparts (government, private, NGOs & others) and other International Organizations | MEF CGCC BOC PFIs
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual (hidden)
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Although the project is within its very early phases of implementation some quick win activities have been implemented that have yielded results. The following summarizes the activities and results to date; (i) organization and implementation of an international dialogue on credit guarantees to support the formulation process of the policy and legal framework for the establishment of the Credit Guarantee Corporation of Cambodia (CGCC), (ii) support to finalize CGCC legal framework and policy, (iii) establishment of the CGCC as a legal entity to support the governments COVID recovery strategy, (iv) support CGCC to develop the operationalization road map to enable credit guarantees to be issued Q2 2021, (v) facilitation of partnership development (Moody's and CGCC) and the introduction of risk management unit and policy and (vi) procurement of IC missions. The key result delivered to date is the legal establishment of the CGCC, the formal government approval of the CGCC policy framework and critical partnership development between the government, neighboring countries CG organizations and the private sector.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Underpinned by the LNOB principle, the objective of the programme is to support the women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement. To do so, the programme will support the RGC to introduce policy and innovative financial solutions in the form of credit guarantee scheme, which has never existed in the country before COVID-19, to provide low-cost and reliable financing to M/SME businesses. It is anticapated that 1000 MSMEs will benefit from from the CG via acceess to new finacial prodcuts being made avalable by the PFIs.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1 - Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement (on-going - 2/12 outputs complete)
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 - Consolidated Review Paper issued to MEF for CGCC Framework COMPLETE Output 1.2 - New regulatory framework for CGCC establishment for CGCC COMPLETE Output 2.4 - Pilot Credit Guarantees - Operationalization Support Ongoing Output 3.1 - Data and Performance Monitoring of CGCC early performance report - Strategic partnership development for the introduction of a risk management system (Moody’s)
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The RIF will be subject to review and ammendment as the speed of the operationalizing CGCC is over-taking the previuolsy designed MPTF intervention. More demand based inputs are emerging from the government as they rapdily develop the CGCC and their first guarantees as a policy priorty for COVID Impact (ie to free up capitial so that existing companies can maintain productove capacity and retain their workforce through partial salary payments - a form of shared extension of the social protection system.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The rapid establishment of the CGCC has been accelerated through the development and consultation of a policy framework that was initially shared and amended by private sector and neighboring countries CGCCs. These professional and peer reviews that bring in best international practice has been a key development driver for CGCC. The project is also bringing in professional solutions to support the CGCC in terms of risk management (Moody's) and capacity building via partnering and arranging staff embeddment with Thai Credit Gurantee as opposed to developing in-house solutions, thus optimizining the projct budget, implemnetation and providning industry standard professional solutions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | From its outset the project has taken a partnership approach to support establishment of the CGCC. This included initial meetings with the development banks (ADB and WB) to establish the division of labor related to the operationalization of the CGCC. This feature will support both the ADB and WB to provide operational capital to the CGCC to compliment the US$ 200 million allocated through the national budget. New partnerships have been forged with the private sector especially in terms of risk management systems with Moody’s analytics and operational support and institutional capacity building support through partnership with Thailand Credit Guarantee
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Investment requirement analysis for Cambodia to retain pre COVID trajectories and regain lost GDP
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Revisons to be made Q2 2021 based on results of survey works
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources mobilized todate
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On the result (last paragraph), do you mean: - the legal framework of the CGCC is established? - the CGCC policy framework is officially approved? - critical partnership development between the government, neighboring countries CG organizations and the private sector created? Reply: These are factual and stand
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I understand the JP has not yet officially launched. So the high level results has not yet achieved. Thus, in this response, i would prefer to add another paragrah to explain that
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should write down results achieved, or explain reasons why results not being delivered.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think we should add the results or key activities completed (in case results at output has not yet been delivered) not the list down of all outputs. We should also explain reasons if outputs have not yet been delivered

## RBM-Annual (hidden)
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 0 | on going | CGCC Portfollio
Indicator: Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement
Baseline:0
Planned Target:CGCC Operational 1 min of credit guarantee issued 2021
Output 1.1 support the policy design and the operational roll-out of the credit guarantee facility, which targets the marginalized groups from the first phase of the RGC’s support, particularly the women owned M/SMEs in informal sector. | Consolidated review paper issued | none work completed | Project files / email
Indicator 1.1: Consolidated Review Paper issued to MEF for CGCC Framework (CDF)
Baseline:0
Planned Target: 1
Indicator 1.2: new regulatory framework for CGCC (CDF / UNDP) | CGCC Framework and Law passed, CGCC established under law | none - work completed | CGCC Framwork
Baseline:0
Planned Target:Approved framework and sub decree
Indicator 1.3: Comparative study on how the investment into women owned M/SMEs and/or informal sector could trigger positive ripple effects in Cambodia’s economy (Know Prod) | Planned Q3
Baseline 1
Planned Target:1
Indicator 1.4: Guidelines for the selection criteria to prioritize the under-supported groups for 1st phase of support, particularly the women owned M/SMEs in informal sector (CDF / UNDP) |  | To revisit q2 with CCGG
Baseline:0
Planned Target: SOP
Indicator 1.5: Policy brief - Using fintech to increase women's access to business finance (CDF) | Planned Q3
Baseline:1
Planned Target: Policy Brief
Output 2: quick action research on women’s economic empowerment (WEE), employment, poverty alleviation and reducing inequality aspects of the credit guarantee scheme
Indicator 2.1: Review paper - existing CGS in the M/SMEs sector in other countries to identify best practices in respect of WEE (Know Prod) - CDF / UNDP
Baseline:0 | ongoing 2001 Q3 | Publication and blogs | UNDCF UNDP web Portals
Planned Target: Knowledge Product CGS and WEE
Indicator 2.2: Rapid surveys reach of CGCC to women businesses by sector and geo location (UNDP)
Baseline:0 | on going
Planned Target: 2 Surveys and Stratgic Options Paper
Indicator 2.3: Research Paper - gender-specific barriers women face and the gendered impact of COVID-19 from the perspective of WEE. (IOM)
Baseline:0 | on going
Planned Target:1 Publication |  |  | RCO and IOM website
Indicator 2.4: Survey female economic migrants impacted by COVID-19 and lost livelihoods (IOM)
Baseline:0 | on going
Planned Target:1 Survey and Findings Report Published
Output 3: pilot the credit guarantee schemes with selected women owned M/SMEs (CDF) |  | to review to match fund operations
Indicator 3.1: Pilot Guarantee Roll Out - early impact assessment
Baseline:0 | Highlight results here | To review scope with CGCC
Planned Target: Short narrative report Benficaries unknown to be defined through PFI portfollios
Indicator 3.2: Data and Performance Monitoring of CGCC early performance report (UNDP)
Baseline:0 | Highlight results here | To review and phase to launch of CGCC
Planned Target:1 CG Perfromance Report
Indicator 3.3: Women Business CGCC User Group meetings
Baseline:0 | Highlight results here
Planned Target:2 Meetingand and 2 Blogs (UNDP)
Indicator 3.4: digital platform for accessing information on job opportunities for economic migrant workers, e linking with provincial job centres and women owned M/SMEs (IOM/IFAD)
Baseline:0 | Highlight results here
Planned Target:(IOM to fill)
Indicator 3.5: Raise awareness rasining events and publications on accessing financing and employment opportunities (IOM)
Baseline:0 | Highlight results here
Planned Target:2 Blogs, 2 migrant journeys |  | on going | IOM website
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: i see on the left you put "consolidated review paper issued" so why you give reasons of variance with planned target as "none work completed?"
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same comment as indicator 1.1
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: in the document Baseline is 0 right?
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In doc, baseline is 0 right?
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should focus on result not process
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Here is the place to give reasons of variance with planned target
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should put the result not process
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pls kindly give reasons of variance with planned target
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above

## Communication-Annual (hidden)
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-MT
Programme Title & Project Number |  | Programme Duration
Programme Title: | The UN COVID-19 Response and Recovery Multi Partner Trust Fund. | Overall Duration (months) | 12 Months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 31.12.2021
Country | CAMBODIA | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNCDF UNDP IOM | National counterparts (government, private, NGOs & others) and other International Organizations | MEF CGCC
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 90 LoGs issued to womens owned business out of a total of 323 LoGs equating to 27.8 percent | Results achived are beyind expected targets | CGCC Portfollio and loan management database
Indicator: Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement
Baseline:0
Planned Target:CGCC Operational 1 min of credit guarantee issued 2021
Output 1.1 support the policy design and the operational roll-out of the credit guarantee facility, which targets the marginalized groups from the first phase of the RGC’s support, particularly the women owned M/SMEs in informal sector. | Consolidated review paper issued | no variation work completed Q1 2021 | Project files / email
Indicator 1.1: Consolidated Review Paper issued to MEF for CGCC Framework (CDF)
Baseline:0
Planned Target: 1
Indicator 1.2: new regulatory framework for CGCC (CDF / UNDP) | CGCC Framework and Law passed, CGCC established under law | none - work completed | CGCC Policy Framework approved by Minister of Ecnomyc and Finance and Issue of Prakas No 140 ONKrBK
Baseline:0
Planned Target:Approved framework and sub decree
Indicator 1.3: Comparative study on how the investment into women owned M/SMEs and/or informal sector could trigger positive ripple effects in Cambodia’s economy (Know Prod) | Deep dive resarch study completed to support economci diversificaton through GCGG issued guarantees and WEE specific low cost finance window
Baseline 1 |  | Work completed | UNDP Issued Report
Planned Target:1
Indicator 1.4: Guidelines for the selection criteria to prioritize the under-supported groups for 1st phase of support, particularly the women owned M/SMEs in informal sector (CDF / UNDP) | Gudileines incorprated in UNCDF commissioned CGCC organisational development strategy and the formulation of the WEE affordable finace window for CGCC concpet note issued to UNCDF for capital finance | Work completed | UNCF issued Report WEE Concpet Note issued to UNCDF for Capital Finance through UNCDF Build Fund
Baseline:0
Planned Target: SOP
Indicator 1.5: Policy brief - Using fintech to increase women's access to business finance (CDF) | Policy brief on WEE developed and presented within CGCC OD stratgey |  | UNCDF Comisisoned OD Strategy Issued to CGCC Decemebr 2021 - https://www.cgcc.com.kh/en/women-entrepreneurs-guarantee-scheme/
Baseline:1 |  | Work Completed
Planned Target: Policy Brief
Output 2: quick action research on women’s economic empowerment (WEE), employment, poverty alleviation and reducing inequality aspects of the credit guarantee scheme
Indicator 2.1: Review paper - existing CGS in the M/SMEs sector in other countries to identify best practices in respect of WEE (Know Prod) - CDF / UNDP | Blog issued, CGCC highligted as best South South Practice Policy Research Paper completed a- Credit Guarantees as effective policy instruments for COVID recovery and Response in ASEAN | Work Completed | UNCDF Publications & https://www.southsouth-galaxy.org/publications/good-practices-in-south-south-triangular-cooperation-in-least-developed-countries-from-the-istanbul-programme-of-action-to-achieving-sustainable-and-resilient-development/
Baseline:0
Planned Target: Knowledge Product CGS and WEE
Indicator 2.2: Rapid surveys reach of CGCC to women businesses by sector and geo location (UNDP) | This was realligned to Indicator 1.3 as requsted by CGCC | Not undertaken resourse redirected to 1.3 as agreed at project board due to COVID restrictons | Not Applcable - See Indicator 1.3
Baseline:0
Planned Target: 2 Surveys and Stratgic Options Paper
Indicator 2.3: Research Paper - gender-specific barriers women face and the gendered impact of COVID-19 from the perspective of WEE. (IOM) | Research document completed Economic Empowerment of Women Migrant Workers in Cambodia | Completed but delays incurred due to travel restrictions | https://publications.iom.int/books/economic-empowerment-women-migrant-workers-cambodia
Baseline:0
Planned Target:1 Publication
Indicator 2.4: Survey female economic migrants impacted by COVID-19 and lost livelihoods (IOM) | Survey completed - provided input evidnece and data to the report under indicator 2.3 | Size and scope of the Survey was servely limited a COVID related travel restrictions and safe distancing had to be observed rendering meetinsg and breifings small | https://publications.iom.int/books/economic-empowerment-women-migrant-workers-cambodia
Baseline:0
Planned Target:1 Survey and Findings Report Published
Output 3: pilot the credit guarantee schemes with selected women owned M/SMEs (CDF) | 323 LoGs issued USD 31.5 million unlocajed as guaranteed bueinss loans from Domectic Banks, 90 LoGs issued to women owned business (28% of total LoGs issued) increasining fisical space for women bueinsess by US$ 9.7 million | Above target performance | CGCC Database
Indicator 3.1: Pilot Guarantee Roll Out - early impact assessment | Presentations develped and provided at CGCC event in December 2021 illustrating impacts of issued LoGs in terms of sector financing, geodetic spread and womens entreprenurship fact sheets developed with CGCC under the title Credit Guarantee – Benefits & Opportunities to Support SME Development | Work Completed | https://www.cgcc.com.kh/en/events-and-activities/support-sme-development/
Baseline:0 |  |  | https://www.cgcc.com.kh/en/publications
Planned Target: Short narrative report Benficaries unknown to be defined through PFI portfollios
Indicator 3.2: Data and Performance Monitoring of CGCC early performance report (UNDP) | TA and grant support to establish CGCC internal management systems and external reporting | Grant and TA completed | https://www.cgcc.com.kh/en/publications/
Baseline:0
Planned Target:1 CG Perfromance Report
Indicator 3.3: Women Business CGCC User Group meetings | Training sessions held with CGCC and CWCA High level fora organised with CGCC - finacnining womens SMEs and MSMEs | This work emeraged through a demand driven request by CGCC that has been endorsed at the project board meeting | https://www.cgcc.com.kh/en/events-and-activities/cambodia-aims-to-close-financing-gap-for-women-entrepreneurs-joint-conference-held-to-promote-credit-guarantee-scheme-and-support-women-led-msmes-as-part-of-covid-19-recovery/
Baseline:0
Planned Target:2 Meetingand and 2 Blogs (UNDP)
Indicator 3.4: digital platform for accessing information on job opportunities for economic migrant workers, e linking with provincial job centres and women owned M/SMEs (IOM/IFAD) | TA to support update of Ministry of Labor and TVET web portal | Delayed work flow due to travel restrictions and self distancing related to COVID | https://www.fwcms.mlvt.gov.kh
Baseline:0
Planned Target:
Indicator 3.5: Raise awareness rasining events and publications on accessing financing and employment opportunities (IOM) |  | Not undertaken due to COVID travel and self distancing restrictons
Baseline:0 | Not undertaken due to COVID travel and self distancing restrictons
Planned Target:2 Blogs, 2 migrant journeys
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same comment as indicator 1.1
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: in the document Baseline is 0 right?
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In doc, baseline is 0 right?
Note on B64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project “Unlocking Cambodian Women’s Potential through Fiscal Space Creation” was designed and implemented in a rapidly moving policy space to support the Royal Government of Cambodia to address the immediate challenges of COVID and develop a sustainable post-pandemic recovery policy. The project has successfully met its objectives and through its actual results (creating fiscal space) has delivered a policy objective that is becoming far-reaching with a very high level of sustainability. From the outset of the project, the design provided three levels of support these being (i) policy support, (ii) systems operational and monitoring support, and (iii) policy research and women migrant and women entrepreneur outreach. The policy support component has been implemented through UNCDF and UNDP and also included regional actors such as the Thailand Credit Guarantee Corporation, Central Bank of Bangladesh, and Moody’s Analytics. The policy support has provided advisory to RGC in terms of the finalization of the Policy Framework for the Credit Guarantee Scheme for Cambodia (CGCC) that includes its roles in terms of COVID response and COVID recovery. Phase I of the policy calls for the CGCC to function as a response facility, providing liquidity to the domestic market to assure the retention of the critical productive sectors of the economy (garments, apparel, tourism) Phase 2 of the policy moves the CGCC to function as a financial instrument to diversify the national economy by unlocking domestic capital for startups in agriculture, manufacturing, and service sectors. The CGCC was inaugurated through an issued government decree with the unit being established in May 2021. UNCDF grant facility was used to operationalize the unit through the provision of equipment and training for incoming staffs. CGCC issued its first letter of Guarantee in May 2021 and since that period a total of 323 LoGs have been issued that has increased domestic fiscal space for SME and MSME capital by US$ 31.5 million through the issue of business loans through the domestic banks. A total of 90 LoGs (28% of the total) have been issued to women’s owned business accounting for 30.7 percent of the total fiscal space developed (US$ 9.663 million). Through these issued loans to Women owned business the CGCC has eliminated to a great extent the requirement of securities for loans. Out of the issued loans to women’s business 75 precent have been issued as un-secured, i.e. personal collateral was not required by the bank issuing the loan.The project has reached out to women’s existing businesses and entrepreneurs through two distinct research studies, one targeting migrant women, the impact of COVID and their needs to start up small businesses in local communities, whilst the other large-scale research has been conducted to provide forward thinking policy for the government to accelerate women’s businesses and in particular identify sectors of the economy for which the CGCC can actively encourage growth. The project was selected as a best case example within the South-South Galaxy 2021 publication Good Practices in South-South & Triangular Cooperation in LDCs.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Underpinned by the LNOB principle, the objective of the project was to support the women-owned M/SMEs, predominantly operating in the informal sector, for their recovery from COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement. To do so, the project supported the RGC to introduce policy and innovative financial solutions in the form of a credit guarantee scheme, which has never existed in the country before COVID-19, to provide low-cost and reliable financing to M/SME businesses. As per data received from CGCC a total of 323 business of which 90 are women-owned have received letters of guarantee that has secured the issuance of domestic loans. The 28 percent coverage of LoGs to women-owned businesses directly aligns with the current business environment found in Cambodia. The project research has generated new data sets that reveal that the business environment maintains high levels of MSMEs that are owned and operated by women but given their size and limited information are unregistered thereby unable to classify for a bank loan that can be supported by CGCC. The project using the developed data has worked with CGCC and MEF to design and launch a specific window to address this issue and also to help formalize the MSME sector. The recently launched CGCC product Women Entrepreneurs Guarantee Scheme (WEGS) has been co-developed through a demand-driven approach whereby the project has provided advisory and TA. The WEGS fully emerged as a feasible and viable financing instrument only after the establishment of the guarantee facility and the extensive partnerships that have been forged between the CGCC and Cambodia-based PFIs. Although the WEGS is just entering into service at the end of the project cycle it will be further supported post-project through UNCDF capital. The WEGS has essentially been established through the project policy research and TA. The number of beneficiaries that have directly benefitted from these loans cannot be readily quantified as such data is beyond the scope of the project and subject to lenders' confidentiality clauses and legal requirements. However, through the survey that directly targets migrant women participation of 1,000 women, migrants in focus group meetings and research is acknowledged. In addition, UNDP worked directly with Cambodia Women’s Entrepreneurs Association (CWCA) and the Ministry of Women’s Affairs facilitating policy dialogues and building entrepreneur profiles for 500 women. A critical component of the latter works is the linking of women businesses leaders and future entrepreneurs to CGCC. Both UNCDF and UNDP participated in two CGCC webinars that promoted the use of credit guarantees and their application to accelerate women’s economic empowerment. These two events reached over 300 persons with 60 percent attendance being recorded by women. Beneficiaries The project beneficiaries are considered at three levels these being (i) participating financial institutions that have partnered with CGCC and have accessed the credit guarantee facility, (ii) the companies who have received loans that are backed by the credit guarantee and (iii) a proxy measure for drip down to beneficiaries based upon assumptions related to company size, and sector. These proxy measures provide only a crude estimation of end beneficiaries of the credit guarantee facility. Although the project has provided capacity building through various exchanges at webinars and has also organized workshops these are not being counted in terms of reach or beneficiaries. Since the project's design was based upon systems development that focused on the introduction of a sustainable credit guarantee facility, only metrics related to the credit guarantees issued are considered. The proxy measurements for direct and indirect beneficiaries based on a crude analysis of CGCC official data are provided below. Constituents beneficiaries Indirect beneficiaries Female Male Refugees and migrants PFI 14 323 n/a n/a n/a Companies 323 9733 7743 2102 Employees of companies retaining positions 9733 7743 2102 | Constituents beneficiaries Indirect beneficiaries Female Male Refugees and migrants PFI 14 323 n/a n/a n/a Companies 323 9733 7743 2102 Employees of companies retaining positions 9733 7743 2102
3.1 | Results: Outcome Level | Please include outcome level results achieved | The outcome of the project was defined through the concept note as “Underpinned by the LNOB principle, the objective of the project is to support the women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement.” To a large extent, given the legal constraints related to the issue of business loans through domestic banks that require businesses to be registered the core objective of the project has been realized. The establishment and operationalization of a sustainable credit guarantee system that has inbuilt safeguards for women businesses and which through its policy supports women’s business by providing preferential interest rates and reduction of application costs has enable women’s business to survive the impacts of the pandemic and allowed 90 women’s businesses to benefit for affordable capital to either open up or expand a business. In addition, the CGCC has provided capital to many existing companies in the garments and food sectors. Many of these businesses have a predominantly female workforce, thereby providing a trickle-down effect of the CGCC to women who have retained their employment. The project has also support two distinct sets of training, one for women entrepreneurs through CWCA and through CGCC webinars and the other targeting economic migrants, providing them with knowledge and knowhow on entrepreneurism and guiding would be business owners to specialize within specific sectors of the economy.
3.2 | Results: Output Level | Please include output level results achieved | Output 1: support the policy design and the operational roll-out of the credit guarantee facility, which targets the marginalized groups from the first phase of the RGC’s support, particularly the women owned M/SMEs in informal sector. This area of work has been fully realized with the CGCC policy framework being completed and a law issued (Prakas No 140 ONKrBK). The CGCC was inaugurated as a semi-independent unit of the Ministry of Economy and Finance in March 2021 and issued its first letter of guarantee in May 2021. To-date March 2022 CGCC has issued 323 letters of Guarantee that has unlocked 31.5 million of domestic capital for SME and MSMEs response dan recovery to the pandemic. Output 2: quick action research on women’s economic empowerment (WEE), employment, poverty alleviation and reducing inequality aspects of the credit guarantee scheme has in general been mostly completed with the project completing two surveys that have informed the formulation of policy briefs to CGCC in terms of potential economic sectors for growth and women’s entrepreneurship financing needs. The detailed research on migrant women provides policy evidence for the MEF to update their national COVID recovery strategy and will additionally be utilized within the scope of the INFF financing strategy. In addition, various media articles have been developed illustrating the positioning of credit guarantees as a definitive COVID recovery policy instrument that has been successfully deployed in ASEAN. Output 3: pilot the credit guarantee schemes with selected women owned M/SMEs has been successfully tested with 323 LoGs being issued and the development of a Women’s Economic Empowerment window being designed and opened within the CGCC as a women’s business accelerator. The latter has been supplemented with specific training and advocacy works with CWCA for women business leaders and business developers. Unfortunately given the travel restrictions of COVID field-based work and outreach has been limited impeding on the work of the JP in the context of migrant stories and the establishment of digital platforms. However, work has been completed with the Ministry of Commerce to update their business platforms.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main issues that have delayed implementation and quality of implementation have been the extensive travel restrictions encountered due to the pandemic and its second wave. These restrictions have made impossible any regional travel that has impacted on 2/3 of the PUNOs being able to visit Cambodia, relying on technology and virtual meetings to conduct business. However, perhaps more importantly field visits and focus group discussions have been severely hampered as Cambodia varied its policy through lockdowns, internal travel restrictions and safe distancing, the latter impacting in size of meetings that could be arranged with the final project beneficiaries. The project concept did not identify or detail any operational risk but considered the risks of sustainability of the CGCC in terms of claims and loss. It was envisaged that a 20 percent loss would provide the underlying risk factor. After 1 year of operation no claims have been made against any LoG as risk management of individual LoGs formed part of the CGCC strategic framework and training provided by the project to CGCC staffs. The lack of claims is quite promising in that it illustrates that the participating financial institutions (PFIs) have correctly managed and applied their own risk matrices to each loan application covered by CGCC, being in alignment to policy framework. Nationally the current level of NPLs was 2.1 percent (2020) and remained flat due to government debt relief measures, but is expected to rise during 2022 as the relief polices are withdrawn.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The project has allowed for deep dive analysis and research related to credit guarantees as being essential policy instruments to part address and mitigate the impacts of external shocks to a country. Deep dive research into the application of credit guarantees by the project has illustrated that such instruments can, if designed correctly, provide immediate policy response and forward-looking recovery policy. This feature is exemplified within the CGCC Policy Framework and Organizational Strategy that has been developed by the project. Additionally, the project has highlighted the speed at which governments can work at to develop approve and implement policies, based upon detailed research and inclusive dialogue. The project has also highlighted South-South Triangular cooperation that can be used as a key component in policy decision making processes. During the initial policy framework discussions, the UNJP facilitated such dialogue between the government of Cambodia, the Central Bank of Bangladesh, Credit Guarantee of Thailand and Moody’s Asia. These frank peer to peer exchanges assisted the government to rapidly pass and approved the framework policy and the associated CGCC establishment law. The South-South cooperation is recorded as a best practice in the South-South Galaxy publication Good Practices in South-South & Triangular Cooperation in LDCs (2022). Ideally the lessons learnt need be further disseminated so that national public sector capitalized credit guarantees can be established across all LDCs and SIDS in Asia-Pacific. On a M&E base the project with CGCC has developed a data-base to effectively track the utilization of the LoGs by women businesses, collecting disaggregated data in terms of (i) ownership, (ii) collateralization, (iii) volume – loan, (iv) economic sector, (v) economic sub sector, and (vi) geodetic data. These data points are allowing CGCC to better target its products in terms of accelerating women’s business development and expansion, sector financing to support post COVID diversification and Geodetic spreads – that support the components on LNOB and also reducing in country provincial disparities and addressing ethnic and gender inclusiveness.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project has been able to support the capitalization of CGCC through the public sector budget, with the government setting aside US$ 200 million to cover the LoGs. The current portfolio is indicating that the average loan size is US$ 97,618 with the average LoG coverage being 71 percent. These figures suggest that with their current capital CGCC is in a position to guarantee an additional 1800 loans at 100,000 per loan unlocking in excess of US$ 302 million. New partnerships have been forged with Moody’s analytics a leading private and public sector advisory that is sharing detailed businesses and sector intelligence to CGCC and by extension the MEF policy department to better understand market opportunities and the private sector appetites. The project is providing a pivotal intersection providing a nexus for public and private finance to work together to support not only a government recovery policy that mainstreams the principles of the UN Build Back Better strategy but also supports economic and geodetic economic diversification that will be the engines of new green growth as defined in the government’s recovery strategy. Indeed, the functioning of a sustainable national credit guarantee system is indiscriminately unlocking domestic capital, providing accessible and affordable finance to all groups of the citizenry of Cambodia, and also providing very target finance to accelerate and support the stabilization and growth of women’s owned businesses. The intervention has provided one of the cornerstones of the UN SERP and made concrete the UN systems support to COVID response and recovery in a very measurable manner. Additionally, the project has made outreach and deepened the partnership with the IFIs working on the credit guarantee and capital markets. UNCDF with ADB the project co-created the policy framework, supported the government in the development of the Law and the development and signing of the legal partnership agreements between CGCC and the PFIs, and will continue to support the CGCC to possibly raise a bond on the CSX. IFAD has continued to offer advisory, especially in the context of boosting SME finance within the agricultural sector and its relevant sub-sectors in financing. Post-project CGCC is in the process of working with UNCDF to secure capital for a specific women’s financing window, whilst the World Bank may be supporting CGCC with sovereign loans via the MEF. Additionally, strong policy and capacity-building partnerships with CWCA have been forged that will further the financing of women’s businesses and start-ups.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Non undertaken. Continual monitoring of the project has been undertaken by the PUNOs and regular montly meetings held with the PUNOs and RCO. In addition the project has supported the montly collection and update of the CGCC data based and prortfillio managment reporting system that has been developed through the grant conponent of the project
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The dynamic policy environment coupled with the restrictions on travel and gatherings imposed by the pandemic resulted in some activity changes to the original project design. Such changes were fully discussed at the project board meeting with relevant stakeholders and endorsed by the project steering committee. The following inputs have been changes as new demand driven needs emerged, this being in alignment to the discovery nature of the project as indicated in its theory of change. Critical changes have included the following; Indicator 2.2: Rapid survey reach of CGCC to women businesses by sector and geo location was realigned with Indicator 1.3 to conduct survey with MSMEs and the organization a conference on financial inclusion with over 100 women entrepreneurs. As part of this reworked activity the project presented a learning session on behavioral Insights for women-owned businesses in partnership with CWCA. Indicator 3.2: Data and Performance Monitoring of CGCC early performance reporting has been led by UNCDF and has been completed within the framework of the UNCDF grant, with CGCC procuring a finance management and client relationship management software solution would need a redirection. UNDP reallocated the budget will be to the development of a web-based interactive learning platform to expand outreach and for sustainability of the access to finance training. Indicator 3.3. on CGCC women business users group meetings could not be conducted due to COVID restrictions with the budget being redirected to the training programme developed with CWCA on access to finance to women-owned businesses.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | All PUNO budgets have been exhaused and PUNO contrubtions realised

## Communication-Final
1. Impact Stories from the Field | 1. Impact Stories from the Field
Please refer to UN South South Galaxy Publication - https://www.southsouth-galaxy.org/publications/good-practices-in-south-south-triangular-cooperation-in-least-developed-countries-from-the-istanbul-programme-of-action-to-achieving-sustainable-and-resilient-development/ | Please Refer to the following https://www.cgcc.com.kh/en/events-and-activities/cambodia-aims-to-close-financing-gap-for-women-entrepreneurs-joint-conference-held-to-promote-credit-guarantee-scheme-and-support-women-led-msmes-as-part-of-covid-19-recovery/
Please refer to https://publications.iom.int/books/economic-empowerment-women-migrant-workers-cambodia
2. Upload here: Communications and Visibility (OPTIONAL) | 2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words) | Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries. | To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media. | Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation. | Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board. | Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board | See - Fund's Trello Board