## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Accelerating COVID-19 Socio-Economic Recovery in Myanmar through Resilient and Gender Transformative Enterprises | Overall Duration (months) | 18 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-10-28
MPTF Office Project Reference Number: | 124563 | Original End Date (dd.mm.yyyy) | 2022-04-01
Country | Myanmar | Current End date(dd.mm.yyyy) | 2022-04-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UN Women, and UNCDF | National counterparts (government, private, NGOs & others) and other International Organizations | BopInc (as of now)
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 pandemic brought socio-economic shock at significant scale and severity, which further aggravated pre-existing structural weaknesses in the Myanmar MSME sector vis-à-vis its potential to drive inclusive economic growth. On top of this, the country encountered a political and economic crisis following the military takeover on 1 February 2021, which sparked serious protests accumulating severe impacts to many businesses who have been unable to operate fully for several months. Aside from business disruptions, security challenges and staff absence, cash withdrawal restrictions are further limiting operations. Several accelerators and incubators had to substantially scale down their operations due to the withdrawal of investors, and funders’ non-committal to new programmes. In response to the coup, the UNCT developed and adopted a set of engagement principles, to guide its engagement with the de facto authorities. The engagement principles direct the PUNOs to ensure that the benefits of programming accrue directly to the people or local communities without discrimination, that programming supports the strengthening of the rule of law and the protection and promotion of human rights, and that it contributes to preserving, to the extent possible, the democratic space. As engagement principles require, programmes and activities involving government agencies and/or engaging government officials will be paused until further notice. The PUNOs undertook a reprogramming exercise in Q1 and Q2 to assess the programme’s alignment with the engagement principles. The review also included the revision of its due diligence and partner screening processes to align to the new guidelines. During the reporting period the PUNOs were able to complete the following activities: · A rapid gender needs assessment survey, to identify the needs of women entrepreneurs and ways for the Joint Programme (JP) to support them in the upcoming phase. The survey confirmed the interest of women entrepreneurs to participate in the JP and identified areas of most relevance to them. · A Terms of Reference (TOR) for the accelerator program has been developed and it is undergoing the procurement process. The accelerator programme will function as a best practice example on how to go from inclusive acceleration to gender transformative acceleration. · A needs assessment amongst six stakeholders, including incubators, accelerators and investors on their existing capacities and resources for making the ecosystem gender transformative. None of the assessed entities were yet truly gender transformative. · A training of trainers workshop to help accelerators and entrepreneurs to become gender transformative. Attendees were guided to assess gender representation in their organizations, and in a future training will be trained to develop action plans towards becoming more gender transformative. · The programme conducted secondary research on the existing SME finance landscape in Myanmar, and a pipeline of potential investors and financiers has been built. The programme carried out almost all of its activities online, including the training, surveys and assessments that were conducted. The programme reached 45 beneficiaries in the MSME ecosystem, including 30 entrepreneurs (24 women), 14 trainers (8 women), and the Myanmar Private Equity and Venture Capital Association.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | During the reporting period, the programme worked with or reached the following people: • As part of quick assessment, interviews were conducted to 22 women owned/led MSMEs, 54.5 percent of which are medium enterprises, 22.7 percent of them are small enterprises and 22.7 percent are micro enterprises (definitions used are from the Myanmar SME Development Agency) • Needs assessment carried out amongst 6 entrepreneur support organizations (2 women, 6 men) • A background interview conducted with Myanmar Private Equity and Venture Capital Association (2 women, 1 man) • Training of trainers workshop (14 participants: 8 women, 6 men)
3.1 | Results: Outcome Level | Please include outcome level results achieved | The military takeover had significant effect on political and economic environment in the country. Based on Myanmar UNCT Engagement Principles, PUNOs initiated the process of reprogramming impacted project activities by assessing the impact of the military coup and finding ways to effectively pursue the objectives of the programme. This reprogramming process analyzed the scale of impact of the coup, on-going societal trends, and the current needs of some of the programme partners and beneficiaries. The process delayed the implementation of the project and contributed to its late start than planned originally. At this moment PUNOs are yet to achieve targeted results at outcome level. However, at output level, despite immense external challenges, PUNOs are completed several important activities with certain positive and promising results that paved the road for further programmatic advancement.
3.2 | Results: Output Level | Please include output level results achieved | The currently unfolding situation in the country has restricted the operating space for PUNOs and also slowed down the implementation pace. In the reporting period, programmatic activities were mainly concentrated on implementation of components related to Output 2: The entrepreneurship ecosystem of Myanmar, including in its accelerators has strengthened capacity to effectively support women impacted by the COVID-19 crisis in an integrated way. Efforts to implement activities related to Output 3: Access to finance strengthened for capacitated women SMEs are underway. Output 1: The non-state entrepreneurship ecosystem of Myanmar has strengthened capacity to include gender and women owned enterprises in its socio-economic response to COVID-19 in the short and medium-term reforms. Secondary research was completed in Q1 to collect data and insights on the existing SME finance landscape in the country, which included various products from different types of institutions, and the necessary requirements for applicants, and a pipeline of potential investors and financiers has been built. Output 2: The entrepreneurship ecosystem of Myanmar, including in its accelerators has strengthened capacity to effectively support women impacted by the COVID-19 crisis in an integrated way. A rapid needs assessment survey to identify the needs of women entrepreneurs and ways for the Programme to support them was undertaken in the reporting period. Preliminary findings indicate that almost all the women entrepreneurs interviewed expressed their interest in participating in the accelerator programme and believed that they would be able to benefit from it, and also expressed urgent need for both financial and non-financial support. Non-financial support includes capacity development and knowledge transfer mechanisms. Particularly, women-led MSMEs are interested in provision of business mentorship through: - better planning and strategizing business decisions to effectively navigate through emerging challenges in the economy caused by the pandemic and military takeover. - developing new products and services to meet production challenges and unstable demand side. - application of digital tools and solutions for better marketing and communications with both buyers and suppliers; understanding digital literacy (payment and transactions). - participating in business networking for new opportunities and peer-learning on business development practices. Another needs assessment was also undertaken for assessing existing capacities and resources of the different entities for making the ecosystem gender transformative amongst six ecosystem stakeholders that included incubators and accelerators and investors as well as with the Myanmar Private Equity and Venture Capital Association. According to the assessment, the accelerators vary in their capacity for gender transformative procedures from fairly low, e.g. only setting some targets to include women as participants, to quite good, such already adjusting marketing messages to attract more women. However, none of the assessed entities were yet truly gender transformative in their practices; addressing challenges specifically faced by women entrepreneurs, nor supporting businesses to become more inclusive. The respondents did however show a substantial appetite to work on becoming more gender transformative as shown by achieving a universal representation (14 participants: 8 women and 6 men) from all the relevant organizations into the first trainer of trainers workshop In the first phase of the training, the accelerators were guided to assess the level of representation of all genders in their organizations and in their accelerator programs. In the subsequent phases, the accelerators will be introduced to different tools and ideas for how to make their organizations and programmes more inclusive and supported in developing their own action plans towards becoming more gender transformative. The findings from assessments presented above are contributing to the design of accelerator programme that is expected to be launched in Q3. Output 3: Strengthening access to finance for capacitated women SMEs A supply side survey to gain insights from local banks, impact investors, NBFIs and other finance providers, on the outlook of the investor scene/landscape to understand better how those entities are adapting in the current environment, and how they have evolved their operational plans in the MSME sector is currently being designed. This will allow a strong basis for engagement with investors in the coming phase including in identifying the most suitable instruments to deploy to support the women entrepreneurs. The survey will also serve as an initial opportunity to share with local banks and investors details of this joint initiative as more results from the entrepreneurs’ needs assessments are received.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Implementation of planned activities have been delayed as an impact of the military takeover of the civilian government on 1 February 2021. In response to the coup, the UNCT developed and adopted a set of principles to guide the UN’s engagement with the de facto authorities. This required the PUNOs to undertake a review of the Joint Programme’s planned activities against to the UNCT’s engagement principles and reprogramming and/or redirecting activities previously aimed at strengthening government capacities towards activities with non-state partners and entities. Many entrepreneur support partners had to scale down their activities. This meant that the partners were unable to engage with the MPTF programme for a few months that caused some delays in programme implementation. Military coup also has shifted the priorities and challenges within the country. Due to the crumbling economic and financial sector the outlook for future economic growth and opportunities is uncertain making it difficult to attract investors, funding into the country. Banking sector has halted which makes it difficult for business to access cash, make payments. This is a challenge likely will continue to be an issue if the crisis persists creating further difficulties for SMEs to access any capital as any disbursements made by banks and investors will not be possible. In addition, continued violence, network disruptions, ongoing pandemic make the environment not only fragile and uncertain but also unsafe and there is possibility that some SMEs are unwilling to continue their operations.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | • “Needs Assessment: Engendering the Entrepreneurial Ecosystem of Myanmar” - interviews with accelerators, incubators and associations. • [Draft] “Rapid needs assessment of women entrepreneurs in Myanmar after 1 February 2021”. • The investor/supply side survey planned for the upcoming quarter (Q3) is expected to further help to reengage financial institutions and local partners enabling synergies between the programme and other projects implemented by the PUNOs to be explored.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | • The needs assessment exercises resulted in the creation of a platform for peer and experience sharing amongst the entrepreneur support partners • A series of consultations for knowledge/experience sharing with other UNDP Units in Myanmar, UNDP Bangkok Regional Hub and UNDP country offices in Armenia and India with experience in designing and managing accelerators programmes were facilitated. • As part of MPTF visibility and external communication efforts, PUNOs delivered a presentation about the Joint Programme activities and objectives in the virtual knowledge sharing event organized by the Women Peace Security Coordination Group.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | N/A
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Following the coup in February 2021, the UN Country Team developed and adopted a set of principles to direct the UN’s engagement with the de facto authorities. The UNCT Engagement Principles specify that under the current context the UN will suspend all policy work, technical assistance, capacity building and institutional strengthening with the de facto authorities and associated government bodies/agencies and focus instead on its life-saving humanitarian and COVID-19 health response mandates as well as on programming that benefits directly the population of Myanmar and does not require working with or legitimizes the de facto authorities. To comply with the engagement principles, the PUNOs paused implementation to re-assess which of its activities could still go forward. As a consequence of the assessment, the programme suspended activities that require direct working relationship with the de-facto authorities and refocused its approach instead only on engendering the business ecosystem and building the capacity of the women entrepreneurs directly. The following adjustments were made to the programme: • Output 1 to focus on engagement with non-state actors engaging non-state actors in Myanmar to promote programmatic and evidence-based approach in supporting women led businesses. This activity will be implemented through better coordination and advocacy mechanisms in cooperation with associations, service providers, and private sector; • Output 2 will focus on enhancing the capacity of women-led enterprises through business acceleration, digital transformation, and innovation support; and • Output 3 has a key focus on supporting women-led businesses through improved knowledge and technical capacity to have better access to finance. The review had minimal financial implication to project resources.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | *All indicators are to be achieved at later stages of the project implementation process. | *The unstable situation in Myanmar may cause changes/amendments in the planned targets.
Indicator: Increase in number of gender transformative MSMEs impacted by COVID-19 supported by UN in Myanmar
Baseline: To be confirmed based on mapping done
Planned Target: 100
Output 1
Indicator 1.1.1: Gender responsive M&E framework to measure implementation of CERP
Baseline: 0
Planned Target: 1
Indicator 1.1.2: Status of adopting fiscal, monetary and legislative stimulus packages for COVID-19 economic response and recovery that are inclusive and gender-sensitive (Global DCO)
Baseline: 0
Planned Target: 1
Indicator 1.1.3: No. of women-led SMEs receiving technical support through ICT services (SERF)
Baseline: 0
Planned Target: 20
Output 2
Indicator 1.2.1: Number of women MSMES having clear action plans coming out of the accelerators’ programme based on training/coaching imparted to adapt their business model to COVID-19 scenario and its impact.
Baseline: 0
Planned Target: 50
Indicator 1.2.2: Change in ratio of female to male participants in ecosystem programmes, such as accelerators and incubators, that will be supported to be more gender smart.
Baseline: TBC with mapping exercise to create baseline
Planned Target: 20 percent
Output 3
Indicator 1.3.1: Proportion of investments from DFIs, Banks and Impact Investors incrementally going into women-led MSMEs at a portfolio level
Baseline: TBC with mapping exercise to create baseline
Planned Target: Increased by 10 percent
Indicator 1.3.2: Additional number of financiers to women-led MSMEs
Baseline: 0
Planned Target: 3
Indicator 1.3.3: Amounts of additional financing (debt, equity, guarantees or reimbursable grants) attracted by women- led MSMEs
Baseline: USD 0
Planned Target: USD 150,000
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board