## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Mitigating socioeconomic impact of COVID19 on employment and income of own-account women workers in the informal economy. | Overall Duration (months) | 13 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-11-30
MPTF Office Project Reference Number: | 124712 | Original End Date (dd.mm.yyyy) | 2021-10-31
Country | Bolivia | Current End date(dd.mm.yyyy) | 2021-12-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | International Labour Organisation United Nations Development Programme UN Women | National counterparts (government, private, NGOs & others) and other International Organizations | National Confederation of Own-Account Women Workers Ministry of Labour and Social Welfare
Report Cleared By
o Name: | Ignacio Trabadela Robles (on behalf of the RC)
o Title: | Development Coordination Officer, Partnerships and Development Finance
o Email address: | ignacio.trabadela@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The implementation of the Joint Programme (JP) is well on its tracks, and has proven to capture the attention of certain key stakeholders. In terms of the activities, the main study of the JP has been finalised (characterisation of own-account women workers), and the remaining core studies are underway (sectors with potential for the establishment of formal enterprises; value chains with potential for employment; and, a mapping of laws, actors and programmes within the ecosystem in which own-account informal women workers operate in). The key stakeholder of the project has been identified - The National Confederation of Own-Account Women Workers - and the JP has begun talks to provide technical assistance to them, particularly with the creation of a database of the members of the institution. The Confederation will also be a key actor during the processes of training and capacity-building set out by the JP, as it is present in the four cities in which the JP will carry out its actions, and has an estimated 2,000 members, with varied ages, educational levels, and family responsibilities, and of which around 200-300 will be direct beneficiaries. In particular, the responsible party for the implementation of capacity-building, including financial education trainings to own-account informal women workers, and for the provision of technical assistance to government institutions, has been chosen after a competitive process. The elected civil society organization, called the "Asociación de Concejalas de Bolivia (ACOBOL)", has a proven track record of work on care economy issues with local governments, and has developed a strategic alliance for the implementation of the JP with the National Confederation of Own-account Women Workers. It will improve its already existing own online training platform in order to start the trainings remotely as soon as possible (with the advantage to potentially reach a bigger number of women through that virtual space), and will propose some in-person trainings with biosecurity measures, associated with the prevention of COVID-19’s spread. This also depends on the vaccination rollout, since some own-account informal women workers have expressed their preference for in-person meetings, as they face difficulties using digital technologies. In addition, and for other identified demands, the JP is preparing the TORs for a responsible partner to work jointly with the target group in defining the main bottlenecks of financial service providers and, based on this information, to carry out a process of co-creation and experimentation with different groups of actors, from account holders, financial agents, academia and other stakeholders, for the development of a proposal of solutions adjusted to the identified bottlenecks (for example, facilitating the preparation of requirements for a loan, adjusting the organization of meetings in the case of community banking, organization for the application of care services, among others). With the result of these inputs and according to the demand segment, we intend to achieve a more fluid articulation with the DFIs and the National Productive Development Bank. Nonetheless, the JP has encountered certain difficulties that have delayed the implementation of the activities, which will be explained in section 3.3.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The direct beneficiaries of the JP will be own-account women workers, particularly those that are already members of the different organised institutions throughout the country, which tend to have an average age-range of 18-60 years. The JP is expected to reach 340 direct beneficiaries in the skills/entrepreneurship training, and 425 direct beneficiaries with the financial education activities. The JP has not yet reached any direct beneficiaries, as its training activities are scheduled to beging in August - September, but has begun the necessary coordination with its counterpart to carry out the training in the appropriate manner. In addition, the goals established in the project document are still valid and guiding the actions of the JP.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Given that the JP is still focused on the outputs and activities, results at the outcome level are still not tangible.
3.2 | Results: Output Level | Please include output level results achieved | In terms of Output 1.1 (Evidence-based knowledge on the characterisation of own-account women workers in the informal economy, for the promotion of targeted public policies and programmes to address their needs in relation to formalization, social protection and co-responsibility for care, has been generated), the study designed to characterise own-account women workers has been finalised, and is now in the style-correction and design processes. In terms of Output 2.1 (Studies to identify the emerging and most dynamic sectors of the economy, for the generation of entrepreneurship and labour insertion of women during and after the COVID-19 crisis, have been elaborated) both studies are underway and expected to be concluded at the end of september/october, respectively. In terms of Output 1.3 (strengthening of capacities of governmental institutions and other stakeholders to design and implement policies and programmes related to the care economy) and Output 3.3 (financial education programme that improves financial management skills and the sustainability of monetary resources), the Responsible Party for their implementation, ACOBOL, has been chosen after a competitive process. The civil society organization has started to work for the JP on the 19th of July and is expected to start providing capacity-building trainings and technical assistance to governmental institutions on the development of a co-responsibility care system in August.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | As previously mentioned, the JP has encountered certain challenges that have posed difficulties to the implementation of the activities, particularly due to Bolivia's political climate and the situation of Covid-19 in the country. Firstly, in the past 8 months, the country has undergone a national election (in November) and a sub-national election (in March), which meant that the authorities in all the pertinent ministries, vice ministries, and directorates, changed. In fact, most ministries finished designating their authorities within the first trimester of 2021, which slowed-down the approach the JP was able to have with the new national and regional counterparts. To serve as an example, the Ministry of Labour and Social Welfare designated a focal point to work with the JP at the end of April, which delayed the implementation of the activities, as a presentation of the JP's structure had to be made to the Ministry and we had to wait for their feedback before proceeding. Secondly, the second wave of Covid-19 in the country began at the end of December 2020 and lasted until around the beginning of March 2021. Currently, the country is on the downward slope of the third wave. This situation created difficulties in coordinating with potential counterparts of the project (particularly own-account women's organisations and capacity-building institutions), as many got sick and decided to pause their inter-institutional activities until the Covid-19 waves slowed down. Additionally, in conversations held with the National Confederation of own-account women workers, the Director expressed that the target group is currently focused on the economic recovery of their micro-enterprises and their families, and do not have sufficient time to be involved in training activities, and that they would prefer for these activities to begin in august/september, beggining with virtual trainings and then exploring the possibility of in-person activities. In addition, the national vaccination initiative is underway, and anyone over 18 can access the vaccines, which can help in improving the potential to carry out face-to-face training activities. In terms of the Risk Management matrix of the ProDoc, two risks have materialised. The first one is "political instability, due to the context of uncertainty caused by the presidential elections, delays in coordination with government", and the second is "the Covid-19 pandemic restricts mobility and the ability to hold face to face activities". Both risks are being mitigated by constantly analysing the political situation and maintaining professional and stable relationships with our counterparts, and by aiming to establish immediate digital training mechanisms for some of the JP's direct beneficiaries, in order to start the capacity-building activities as soon as possible, and analyse the possibility to carry out in-person trainings, depending on the country’s vaccination rate. With the mitigation mechanisms in place, and the continuation of the activities, the JP will send a No Cost Extension form to the Fund, to explore the posibility of extending the project until the end of March 2022 (the current end date is 31 December 2021).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Insofar, the characterisation study carried out by the JP is a novel and up-to-date research endeavour, which can potentially influence public policy. Once the remaining three studies have concluded, the JP is aiming to publish them in a book format and invite governmental institutions, academic counterparts, and civil society actors to participate in its launch, to create interest and debate surrounding the issues pertaining to own-account women workers of the informal economy. The JP is aiming to publish the studies at the end of the year or the first months of 2022, if the No Cost Extension is approved. The characterisation study has been helpful in determining the interconnection between the care needs of own account women and their concentration in the informal economy, as a way to deal with their productive and reproductive work, sometimes all at the same time, in the same place. In particular, the testimonies of the interviewed women expressed the need to develop an integral care system in Bolivia, as a first step to support their formalization. It is important to note that the whole JP is centred as a gender lens (GEN 3), which implies that it is aiming to positively impact women's rights. For that aim, virtual coordination meetings have been held with the National Confederation of Own-Account Women Workers and a partner agreement has been signed with “Asociación de Mujeres Concejalas de Bolivia (ACOBOL)”. In the coming months, and once the remaining JP’s activities are underway, policy and programme discussions will take place with national counterparts, in order to display the results of the activities and initiate discussions on how to formulate future programmes and initiatives that benefit own-own account women workers.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | So far, the JP has not developed partnerships that complement activities by other global instruments or fostered catalytic financial or programmatic outcomes. Nonetheless, once the training activities begin, as well as the policy-based initiatives, the JP is aiming to present the structure and results of the Programme to the GRUS (Grupo de Socios para el Desarrollo de Bolivia), to create interest in the structure of implementation, display its results, and aim to receive further funding for a phase 2 of the JP.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Besides the five studies that have been previously mentioned, the JP has not undertaken any other assessments, evaluations or studies.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Regarding the implementation of the activities, no major adjustments in strategies, targets or key outcomes/outputs have taken place.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The JP has a dedicated staff structure, with a National Project Coordinator, a Project Assistant, and an International UNV Specialist, all working to achieve the indicators and goals established in the ProDoc. In financial terms, the ILO has, between encumbrances and actual expenditures, executed over 30% of its assigned budget. With the payment of the first tranche to ACOBOL, UN Women has executed over 34% of its assigned budget. As UNDP is developing the last stages of the project, it has so far executed about 15% of the allocated budget, but a larger execution is expected soon (August) with the development of products that focus on women's financial demands.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator: Number of public policies or programmes, developed in consultation and coordination with governments, employers, workers and civil society representatives, that promote the effective transition from the informal to the formal economy of own-account women workers, submitted to the government for their enactment and efficent implementation in the sectors and cities identified.
Baseline: 0
Planned Target: At least 2 | 0 | The coordinating mechanisms are being established. | 4 meetings with the Federation of own-account women workers and 1 with Ministry of Labour and Social Welfare
Output 1.1
Indicator 1.1.1: Number of assessments and studies carried out in consultation with government, workers, employers and civil society representatives, to generate reliable and accurate evidence about the target group's situation, needs and characteristics.
Baseline: 0
Planned Target: At least 2 | 2 | The characterisation study has been finalised, and the mapping of actors, policies, and programmes within the framework in which own-account informal women workers operate in, is currently underway. | Document of Studies finalized
Output 1.2
Indicator 1.1.2: Number of agreements generated through the multi-stakeholder mechanism with women's organisations, trade unions, and the identified strategic governmental institutions, in order to promote the transition of own-account women workers from the informal to the formal economy.
Baseline: 0
Planned Target: At least 4 | 0 | The coordinating mechanisms are being established. | Agreement documents
Output 1.3
Indicator 1.1.3.a: Number of public policy proposals for social protection that identify an integral care system under a rights-based approach for own-account women workers, designed by the JP with effective and efficient standards.
Baseline: 0
Planned Target: 1
Output 1.3.
Indicator 1.1.3.b: Number of own-account women workers of the informal economy who participate in the dialogue spaces for the design and validation of the proposals for public policies and programmes focused on meeting their needs towards formalization, social protection and an integral care system under a rights-based approach.
Baseline: 0 | 1 | Validation workshop of the study of characterization in women of own account workers organization participated and validated the findings of the study | Recording of the workshop
Planned Target: 150 |  | The dialogue spaces are expected to start in September with ACOBOL and public authorities | Recording of the dialogue spaces / attendance lists
Indicator 1.1.3.c: % of own- acccount young women who participate in the dialogue spaces
Baseline: 0
Planned Target: 30%
Outcome 2
Indicator 1: Percentage of own-account women workers identified by the assessment on their characterisation in the informal economy, with strengthened entrepreneurial skills, that have established their own formal business or have joined a formal associative venture through the JP's technical assistance.
Baseline: 0%
Planned Target: At least 40%
Indicator 2: Percentage of the trained (through 2.A) own-account women workers that have entered the formal labour market through the JP's technical assistance.
Baseline: 0%
Planned Target: At least 30% | 0 | The different trainings are planned to begin in september.
Output 2.1
Indicator 1.2.1: Number of studies to identify dynamic and emerging sectors in Bolivia with their corresponding skills needs, that are conducive to generate labour market inclusion and the establishment of sustainable formal entrepreneurial enterprises and ventures.
Baseline: 0%
Planned Target: At least 2 | 2 | Currently both studies are underway, and expected to be finalised by the end of september / mid october. | Document of Studies finalized
Output 2.2.
Indicator 2.2.A: Number of own-account women workers in the target group that have effectively benefitted from entrepreneurship training at the end of the JP.
Baseline: NA
Planned Target: At least 170 | 0 | The different trainings are planned to begin in september. | Recording of the workshops
Output 2.2.
Indicator 2.2.B: Number of own-account women workers in the target group that have effectively benefitted from skills development training to increase their employability at the end of the JP.
Baseline: NA
Planned Target: At least 170 | 0 | The different trainings are planned to begin in september. | Recording of the workshops
Outcome 3
Indicator 1: Number of own-account women workers (from the urban area of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) that reached access to inclusive and effective financial and non-financial mechanisms adapted to their needs
Baseline: NA
Planned Target: At least 85
Output 3.1
Indicator 3.1.1: Number of own-account women workers associated in ventures, that have been involved in the fast-prototyped mechanisms, have accessed agile financing for their jobs.
Baseline: 1
Planned Target: 80
Output 3.2
Indicator 3.2.1: Number of development finance institutions and commercial banks that have designed and/or adapted financial products and services, adapted to the needs of own-account women workers, based on the incentives developed by the JP.
Baseline: NA
Planned Target: 2
Output 3.3
Indicator 3.3.A: Number of own-account women workers trained in financial management through the financial education program developed by the project.
Baseline: 0
Planned Target: 425 |  | The trainings are expected to start at the end of August | Recording of the workshops / attendance list for presential trainings
Indicator 3.3.B: % of own- acccount young women workers trained in financial management
Baseline: 0
Planned Target: 30%

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
All the communicational innitiatives will begin in tandem with the capacity training activities. Hence, the materials will be reported in the next MPTF report
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board