## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: |  | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy)
Country |  | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNCDF UNDP IOM | National counterparts (government, private, NGOs & others) and other International Organizations | MEF CGCC BOC PFIs
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The programme although being operational was officially launched jointly with another Joint Programme, the INFF, in April. Considerable achievements have been attained during the early phases of the project that has included; (i) organization and implementation of an international dialogue on credit guarantees to support the formulation process of the policy and legal framework for the establishment of the Credit Guarantee Corporation of Cambodia (CGCC), (ii) the finalization and approval of CGCC legal framework and policy, (iii) establishment of the CGCC as a legal entity to support the governments COVID recovery strategy, (iv) support CGCC to develop the operationalization road map to enable credit guarantees to be issued Q2 2021, (v) facilitation of partnership development (Moody's and CGCC) and the introduction of risk management unit and policy. The credit guarantee is now operational with the following data being applicable; (i) commercial loans released with CG = 53, (ii) value of loans = US$ 7.1 million, (iii) value of guarantees = US$ 5.1, (iv) Avg Loan / Guarantee Ratio 72%, (v) smallest loan = US$ 10,000, (vi) largest loan US$ 1 million, (vii) average loan size US$137,464, (viii) 21% of the guarantees were issued to womens owned busiensses, (ix) a total value of US$ 669,600 of guarantees were issued to women business (13% total by volume) and (x) a total loan value of US$ 929,000 has been unlocked for womens business to-date.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Underpinned by the LNOB principle, the objective of the programme is to support the women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement. To do so, the programme will support the RGC to introduce policy and innovative financial solutions in the form of credit guarantee scheme, which has never existed in the country before COVID-19, to provide low-cost and reliable financing to M/SME businesses. It is anticipated that 1000 MSMEs will benefit from the CG via access to new financial products being made available by the PFIs.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1 - Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement (on-going - 2/12 outputs complete) The credit guarantee is now operational with the following data being applicable; (i) commercial loans released with CG = 53, (ii) value of loans = US$ 7.1 million, (iii) value of guarantees = US$ 5.1, (iv) Avg Loan / Guarantee Ratio 72%, (v) smallest loan = US$ 10,000, (vi) largest loan US$ 1 million, (vii) average loan size US$137,464, (viii) 21% of the guarantees were issued to womens owned busiensses, (ix) a total value of US$ 669,600 of guarantees were issued to women business (13% total by volume) and (x) a total loan value of US$ 929,000 has been unlocked for womens business to-date.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 - Consolidated Review Paper issued to MEF for CGCC Framework COMPLETE Output 1.2 - New regulatory framework for CGCC establishment for CGCC COMPLETE Output 1.3 - The study is underway and the consultant has completed the inception report.Indicator 2.3: Research Paper - gender-specific barriers women face and the gendered impact of COVID-19 from the perspective of WEE. ACTIVITY ONGOING: literature review has been completed; the survey among women migrants will be conducted to inform the research paper. Indicator 2.4: Survey female economic migrants impacted by COVID-19 and lost livelihoods ACTIVITY ONGOING: IOM is in the process of hiring the consultant to undertake the survey Indicator 3.4: digital platform for accessing information on job opportunities for economic migrant workers, e linking with provincial job centres and women owned M/SMEs ACTIVITY ONGOING: Communication and coordiantion on outreach activity with other relevant partners such as provincial job centres have been discussed, initial coordination meetings with IFAD and NEA Indicator 3.5: Raise awareness rasining events and publications on accessing financing and employment opportunities (IOM) ACTIVITY ONGOING: ongoing efforts to identify outreach activities conducted by NEA
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Output 1.1 - Consolidated Review Paper issued to MEF for CGCC Framework COMPLETE Output 1.2 - New regulatory framework for CGCC establishment for CGCC COMPLETE Output 1.3 - The study is underway and the consultant has completed the inception report. Output 2.4 - Pilot Credit Guarantees - Operationalization Support Ongoing Output 3.1 - Data and Performance Monitoring of CGCC early performance report - Strategic partnership development for the introduction of a risk management system (Moody’s)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The rapid establishment of the CGCC has been accelerated through the development and consultation of a policy framework that was initially shared and amended by private sector and neighbouring countries CGCC. These professional and peer reviews that bring in best international practice has been a key development driver for CGCC. The project is also bringing in professional solutions to support the CGCC in terms of risk management (Moody's) and capacity building via partnering and arranging staff embedment with Thai Credit Guarantee as opposed to developing in-house solutions, thus optimizing the project budget, implementation and providing industry standard professional solutions. The application of the MPFT grant facility has accelerated the operationalization of the CGCC providing a sound integrated IT systems, supporting human capacity development and helping toe CGCC to sign on participating financial institutions, all of which has accelerated the CG operations and issues of the first guarantees.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | From its outset the project has taken a partnership approach to support establishment of the CGCC. This included initial meetings with the development banks (ADB and WB) to establish the division of labour related to the operationalization of the CGCC. This feature will support both the ADB and WB to provide operational capital to the CGCC to compliment the US$ 200 million allocated through the national budget. New partnerships have been forged with the private sector especially in terms of risk management systems with Moody’s analytics and operational support and institutional capacity building support through partnership with Thailand Credit Guarantee
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Investment requirement analysis for Cambodia to retain pre COVID trajectories and regain lost GDP
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Revisions to be made Q2 2021 based on results of survey works. Given the rapid development of the pandemic and associated lockdown scenarios in Cambodia and neighbouring Thailand
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources mobilized to date apart from the initial government capitalization of US$200 million, Issues are emerging related to international procurement, whereas it is becoming problematic to (i) obtain applicants to meet minimum thresholds on international open competition procurement, we are finding that the number of applications is lowering considerably which is possibly liked to working modalities and travel restrictions.
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On the result (last paragraph), do you mean: - the legal framework of the CGCC is established? - the CGCC policy framework is officially approved? - critical partnership development between the government, neighboring countries CG organizations and the private sector created? Reply: These are factual and stand
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I understand the JP has not yet officially launched. So the high level results has not yet achieved. Thus, in this response, i would prefer to add another paragrah to explain that
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should write down results achieved, or explain reasons why results not being delivered.
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think we should add the results or key activities completed (in case results at output has not yet been delivered) not the list down of all outputs. We should also explain reasons if outputs have not yet been delivered

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 0 | on going | CGCC Portfolio
Indicator: Support to women owned M/SMEs, predominantly operating in the informal sector, for their recovery from the COVID-19 and their turning into the driving force for accelerating Cambodia’s recovery from COVID-19 and the SDG achievement
Baseline:0
Planned Target: CGCC Operational 1 min of credit guarantee issued 2021
Output 1.1 support the policy design and the operational roll-out of the credit guarantee facility, which targets the marginalized groups from the first phase of the RGC’s support, particularly the women owned M/SMEs in informal sector. | Consolidated review paper issued | none work completed | Project files / email
Indicator 1.1: Consolidated Review Paper issued to MEF for CGCC Framework (CDF)
Baseline:0
Planned Target: 1
Indicator 1.2: new regulatory framework for CGCC (CDF / UNDP) | CGCC Framework and Law passed, CGCC established under law | none - work completed | CGCC Framework
Baseline:0
Planned Target: Approved framework and sub decree
Indicator 1.3: Comparative study on how the investment into women owned M/SMEs and/or informal sector could trigger positive ripple effects in Cambodia’s economy (Know Prod) | The study is being conducted and the inception report is completed |  | Report
Baseline: 0
Planned Target:1
Indicator 1.4: Guidelines for the selection criteria to prioritize the under-supported groups for 1st phase of support, particularly the women owned M/SMEs in informal sector (CDF / UNDP) | Early results highlight 21 percent of guarantees have been allocated to womens owned business alligning to framework (indicator 1.2) | TA to support PFI agreements completed and agreements reached with 7 PFIs. OD strategy for CGCC being Developed (q2 and Q3 2021) | Signing ceremony photographs and agreement documents
Baseline:0
Planned Target: SOP
Indicator 1.5: Policy brief - Using fintech to increase women's access to business finance (CDF) | Planned Q3
Baseline:1
Planned Target: Policy Brief
Output 2: quick action research on women’s economic empowerment (WEE), employment, poverty alleviation and reducing inequality aspects of the credit guarantee scheme
Indicator 2.1: Review paper - existing CGS in the M/SMEs sector in other countries to identify best practices in respect of WEE (Know Prod) - CDF / UNDP | Planned Q3
Baseline:0 |  |  | UNDCF UNDP web Portals
Planned Target: Knowledge Product CGS and WEE
Indicator 2.2: Rapid surveys reach of CGCC to women businesses by sector and geo location (UNDP) | The output has been redirected. For the baseline survey, the sample has been changed from CGCC beneficiaries to MSMEs as a whole, building on the UNDP's existing MSMEs Survey. Additional questions and sample size will be added. For the follow up survey, it is aimed to focus on CGCC beneficiaries, depending on the number of beneficiaries of CGCC. | Phase 1 of the scheme was just rolled out and the number of beneficiaries are still very minimal, not sufficient enough as a sample for the rapid survey. In addition, Phase 1 of the scheme is expected to be fully released by December 2021, thus it is not possible to conduct and complete the follow-up survey by the end of the programme unless there is an extension. | Reports
Baseline:0
Planned Target: 2 Surveys and Strategic Options Paper
Indicator 2.3: Research Paper - gender-specific barriers women face and the gendered impact of COVID-19 from the perspective of WEE. (IOM)
Baseline:0 | on going
Planned Target:1 Publication |  |  | RCO and IOM website
Indicator 2.4: Survey female economic migrants impacted by COVID-19 and lost livelihoods (IOM)
Baseline:0 | on going
Planned Target:1 Survey and Findings Report Published
Output 3: pilot the credit guarantee schemes with selected women owned M/SMEs (CDF) |  | to review to match fund operations
Indicator 3.1: Pilot Guarantee Roll Out - early impact assessment | Initial fiscal assessment being undertaken by UNCDF during Q3 - The credit gurantee is now operational with the following data being applicable; (i) commerical loans released with CG = 53, (ii) value of loans = US$ 7.1 million, (iii) value of guarantees = US$ 5.1, (iv) Avg Loan / Guarantee Ratio 72%, (v) smallest loan = US$ 10,000, (vi) largest loan US$ 1 milllion, (vii) average loan size US$137,464. In terms of women owned business - 21% of the guarantees was issued to women owned business, this figure to assess against national company registers for parity
Baseline:0 |  | UNDP in discussion with CGCC and MoEF related to the scope of the impact assessment
Planned Target: Short narrative report Beneficiaries unknown to be defined through PFI portfolios
Indicator 3.2: Data and Performance Monitoring of CGCC early performance report (UNDP) | The target is not yet achieved | Ongoing discussion with CGCC and concept note will be finalised in September | CG performance framework/ report
Baseline:0
Planned Target:1 CG Performance Report
Indicator 3.3: Women Business CGCC User Group meetings | The target is not yet achieved | UNDP will work closely with women business association and specifically target a number of women-owned businesses and arrange for a, this work is being considerably hampered by the current COVID restrictions associated with the 3rd wave of infections in Cambodia | 2 Meetings and 2 Blogs on UNDP web portal
Baseline:0
Planned Target:2 Meeting and and 2 Blogs (UNDP)
Indicator 3.4: digital platform for accessing information on job opportunities for economic migrant workers, e linking with provincial job centres and women owned M/SMEs (IOM/IFAD)
Baseline:0 | Highlight results here
Planned Target:(IOM to fill)
Indicator 3.5: Raise awareness raising events and publications on accessing financing and employment opportunities (IOM)
Baseline:0 | Highlight results here
Planned Target:2 Blogs, 2 migrant journeys |  | on going | IOM website
Please include all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: i see on the left you put "consolidated review paper issued" so why you give reasons of variance with planned target as "none work completed?"
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same comment as indicator 1.1
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: in the document Baseline is 0 right?
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In doc, baseline is 0 right?
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above
Note on B64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
The COVID pandemic has severely impacted a number of LDCs, graduating and middle-income countries in South East Asia. Cambodia is one such country where its growth has been borne out from an export led growth strategy, that placed heavy reliance on global value chains. The pandemic hit hardest the Cambodian labour-intensive industries associated with the garments and tourism sectors that have a workforce employing 80 percent women. As orders were delayed and cancelled, global value chains stalled, and tourism halted employees were at best furloughed and at worst were made redundant. In addition, it is estimated that 3 informal jobs (primally women) in Cambodia are reliant upon a single garment sector job (ILO). As the global impacts of the pandemic deepened many garment and tourist companies became debt distressed. Scaring of the economy was taking effect, the question of whether it was permanent or not relied heavily on the response the Royal Government of Cambodia (RGC). Swiftly, the RGC embarked on a far-reaching policy response that included the rapid extension of social security and which also looked at the economic sectors in terms of the retention of production capacity through firm level survival. As part of this concept the Ministry of Economy and Finance (MEF) reached out to the UN and UNCDF to support the establishment of the Credit Guarantee Corporation of Cambodia (CGCC). Building on from the initial work of Asian Development Bank (ADB) UNCDF and the RCO initiated with the MEF an international deep dive policy consultation that brought in south south expertise from the Bangladesh Bank, Thai Credit Guarantee Corporation and Moody’s Analytics to provide advisory for the establishment a credit guarantee facility in an emerging and graduating economy. A rich discussion ensued that was supported through an underpinning knowledge of all participants related to the common challenges being faced by south south countries in the face of the far-reaching socio-economic impacts of the pandemic. At this juncture a coalition of like-minded institutions and individuals was formed based on mutual understandings and similar socio-economic backdrops created by the pandemic. As traction was gained from these early south-south exchanges between the MEF and counterparts from government, central banks and the private sector it became evident that the near neighbourhood experiences of credit guarantees provided a more suitable vehicle to assist the RGC to expedite their decision-making process. The deep dive dialogues fully supported the RGC to finalize the policy framework and pass relevant legislation to establish the CGCC as an independent government agency some two months after the initial dialogues with a public sector capitalization of US$ 200 million. However, with the physical establishment of the CGCC, the pressing need to support flagging companies that employ large sections of the female workforce, providing necessary financial lifelines to rural and peri urban lower income households remained to be addressed. With the pro-active support of the RCO, MPTF funding UNCDF UNDP and IOM through continued south south partnerships have assisted the CDGG to operationalize, signing up 7 participating financial institutions and issuing guarantees valued at US$ 1.4 million in May 2021 some five months after the initial dialogues. With a guarantee ratio of 4:1 over US$ 5.6 millions of previously locked domestic liquidly has entered the economy, buoying the balance sheets of garment sector factories and tourism companies to maintain staff thereby helping households across the country and especially women workers. This innovative financial model is fast becoming a leading policy trend in the region. With deepening south south cooperation and dialogue the concepts of professional inclusive and sustainable credit guarantees can be introduced as a proven COVID recovery instrument.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
The project has funded the development of CGCC literature through the production of a three fold leaflet as shown. In addition the project supported the launch of the CGCC and the signatory of participation agreements with the participating financial institutions

## FINANCE
PUNO | Total Budget | Expenditures Nov 2020 to July 2021 | Planned Commitment Q3 & Q4 2021 | Total Expenditure | Delivery
| A | B | C | D = B+C | E = D/A
UNCDF | 369991 | 242947.19 | 80000 | 322947.19 | 0.87285
UNDP | 147528.39 | 4656.03 | 50600 | 55256.03 | 0.37455
IOM |  |  |  | 0 | #DIV/0!
Totals | 517519.39 | 247603.22 | 130600 | 378203.22 | 0.7308

## General Information-MT
Programme Title & Project Number |  | Programme Duration
Programme Title: | The UN COVID-19 Response and Recovery Multi Partner Trust Fund. | Overall Duration (months) | 12 Months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 31.12.2021
Country | CAMBODIA | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNCDF UNDP IOM | National counterparts (government, private, NGOs & others) and other International Organizations | MEF CGCC
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Report of Provincial Health Departments and Provincial Level Authorities and CSO’s Monthly report from border points Ministry of Social Affairs case management system Project monitoring report Survey
Monthly report from Provincial Health department
Distribution report Activity monitoring sheet
Monitoring report
Monitoring report
Monitoring report
Distribution report
Monitoring report
Project and training report
Project monitoring report Activity monitoring sheet
Assessment report
Monitoring report
Monitoring report
Monitoring report
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | As Cambodia avoided a large scale COVID-19 community transmission to date, the program has achieved its overall objective. Between June and December 2020, over 113,000 migrant workers returned to Cambodia, mainly from Thailand, following the COVID-19 related impact on their livelihood opportunities abroad. The joint program implemented by IOM, WHO, UNICEF and UNFPA under the MPTF COVID-19 Recovery Fund protected migrant communities from large-scale COVID-19 transmission and mitigated the socio-economic impact of COVID-19 in three target provinces: Siem Reap, Beantey Meanchey and Battambang. Fostering a whole-of-government and whole-of-society approach, the joint program strengthened multi-sectoral coordination at sub-national and national level, involving government and civil society actors in COVID-19 prevention and socio-economic recovery efforts. Through a joint implementation approach, the program delivered a comprehensive assistance package of multi-sectoral interventions to the returning migrants throughout the mobility continuum from the Points of Entry (POE), through quarantine facilities and to the home communities. The impact of the program is visible in the increased knowledge, information and utilization of essential health and MHPSS services, newly created economic opportunities for migrants and communities delivering daily income for their families and their increased resilience. As there has been no nationwide lockdown or mobility restrictions, the implementation took place without major delays with project staff following strict COVID-19 preventive measures. When schools re-opened in September 2020, many district authorities moved away from using school buildings as quarantine facilities and instead used home quarantine for returning migrants. This resulted in some program interventions shifting to the host communities, but allowed for a more synergized approach between the program partners to leverage the impact. Thanks to the joint implementation approach, the local Commune for Children and Women Committees were empowered to support 7,319 returning migrants and host communities on COVID-19 prevention, and to provide improved access to essential health services, namely MHPSS support, maternal care support and GBV victims’ support at the community level. To respond effectively to the risk of violence and neglect, the joint program supported capacity building of 35 district social affairs and social welfare officers and 334 social service workers to monitor the situation of children, with particular attention to children of returning migrants. These interventions contributed to strengthening social cohesion, community empowerment, participation and a sense of ownership demonstrated not just by migrants and communities but also local authorities. The program has contributed to mitigating the socio-economic impact of COVID-19 by facilitating successful integration of returning migrants into their host communities and reducing their vulnerabilities through improved access to essential health services and information and socio-economic opportunities. Through a collaboration involving CSOs and local authorities, 744 most vulnerable migrants have accessed individual economic reintegration package, which consisted of short skill training and small grants to purchase equipment and materials (on average $250-350 per beneficiary), to support income generating activities such as chicken raising, vegetable growing or small business ownership. These activities are implemented in close consultation with beneficiaries to ensure the sustainability of the program and to generate income within 2-3 months from implementation.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | s.

## Communication-Final
1. Impact Stories from the Field | 1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx | Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL) | 2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words) | Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries. | To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media. | Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation. | Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board. | Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board | See - Fund's Trello Board