## Activity
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Cote d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Côte d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Liberia | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Liberia | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Total of two countries Côte d'Ivoire & Liberia | Percent of budget for each output reserved for direct action on gender equality (if any): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Enhanced capacities for conflict prevention and level of trust between state institutions and target communities of the cross-border areas
Output 1.1: | Reduced tensions and increased promotion of social cohesion through strengthened and institutionalized civil-state collaboration mechanisms | 79500 | 27181.81 | 23496.41 | 63.75% | 112500 | 86887 | 0 | 77.23% | 72000 | 34907.45 | 19885 | 76.1% | 105740 | 85920 | 3550 | 84.61% | 369740
Activity 1.1.1: | Conduct a baseline study of all targeted communities and security forces on their perceptions/assessments of the levels of border security, cross-border cooperation and social cohesion; | 11500 | 11593.41 |  | 100.8% | 7500 |  |  | 0% | 10000 | 10000 |  | 100% |  |  |  |  | 29000 |  | The baseline study has been completed at 100% delivrable
Activity 1.1.2: | Establish or reinforce Civil-Military Committees (CMC) for Cote d’Ivoire or County Security Council (CSC) for Liberia; | 0 |  |  |  | 50000 | 38596.7 |  | 77.19% |  |  |  |  | 35740 | 35740 |  | 100% | 85740 |  | Dialogue sessions will focus on issues affecting women as well as ways forward; special measures will be taken to ensure women's participation, including provision of transportation and child care.
Activity 1.1.3: | Regularize inclusive dialogue sessions of CMCs and CSCs in respective countries and between CMCs and CSCs of mirroring communities in the two countries | 0 |  |  |  | 30000 | 28000 |  | 93.33% |  |  |  |  | 70000 | 50180 | 3550 | 76.76% | 100000 |  | Dialogue sessions will focus on issues affecting women as well as ways forward; special measures will be taken to ensure women's participation, including provision of transportation and child care.
Activity 1.1.4: | Reinforce the linkage to the existing early warning systems as well as their capacities to report on the issues related to cross-border area to CMCs and CSCs. | 0 |  |  |  | 25000 | 20290.3 |  | 81.16% | [8 empty] | 25000 |  | This includes training on SGBV and gender issues as well as techniques for women to report in safety; special measures will be taken to ensure women's participation, including provision of transportation and child care.
Activity 1.1.5: | Organize a potential crisis simulation at the border to establish humanitarian corridors and ensure the maintenance of essential economic needs. | 68000 | 15588.4 | 23496.41 | 57.48% |  |  |  | #DIV/0! | 62000 | 24907.45 | 19885 | 72.25% |  |  |  |  | 130000 |  | There is an ongoing preparation to bring authorities from both countries together for the crisis simulation activities. This will done in 2021
Output 1.2: | Improved capacities of local authorities, security forces, border management officials and key government actors for border management with a view to preventing conflicts. | 338036.5405 | 148233.53 | 114304.15 | 77.67% | 40000 | 11539 | 0 | 28.85% | 355000 | 278567.27 | 44366.53 | 90.97% | 110000 | 40588 | 0 | 36.9% | 843036.5405
Activity 1.2.1: | Conduct a capacity assessment. | 10000 | 7348.96 |  | 73.49% |  |  |  | #DIV/0! | 10000 | 10000.02 |  | 100% | 25000 | 25000 |  | 100% | 45000 |  | This activity has been completed at 100%
Activity 1.2.2: | Carry out rehabilitation works in border posts providing the necessary equipment to enhance key actors’ capacities as well as to respond needs of women. | 126536.5405 | 69258.82 | 6702.65 | 60.03% |  |  |  | #DIV/0! | 140000 | 122688.91 | 7021.53 | 92.65% |  |  |  |  | 266536.5405 |  | Contractors are currently mobilizing construction materials for the 4 administrative border posts
Activity 1.2.3: | Provide basic skill trainings to use computers and other electronics to input and manage data. | 21500 | 4991 | 13211.61 | 84.66% |  |  |  | #DIV/0! | 20000 | 11400.12 | 8500 | 99.5% | 20000 | 5000 |  | 25% | 61500 |  | Computer vendors have been vetted to start training for the security agencies at the borders
Activity 1.2.4 | Organize trainings in border management for administrative authorities, security forces/agencies and communities’ leader. | 45000 | 20831.18 | 23777.32 | 99.13% | 5750 |  |  | 0% | 47000 | 47000 |  | 100% |  |  |  |  | 97750 |  | This activity has been completed at 100%
Activity 1.2.5 | Facilitate the organization and institutionalization of joint and cross-border patrols by the security agencies of both countries at the local level. | 90000 | 40542.95 | 50495.17 | 101.2% |  |  |  | #DIV/0! | 90000 | 70000 |  | 77.78% |  |  |  |  | 180000 |  | This activity has been completed at 100%
Activity 1.2.6 | Organize two high-level meetings between relevant authorities of both countries. | 45000 | 5260.62 | 20117.4 | 56.4% | 34250 | 11539 |  | 33.69% | 48000 | 17478.22 | 28845 | 96.51% | 65000 | 10588 |  | 16.29% | 192250 |  | Activity is scheduled for may 2021 at high level meeting of the two authorities.
TOTAL $ FOR OUTCOME 1: |  | 417536.5405 | 175415.34 | 137800.56 |  | 152500 | 98426 | 0 | 64.54% | 427000 | 313474.72 | 64251.53 |  | 215740 | 126508 | 3550 |  | 1212776.5405
OUTCOME 2: Improved peaceful co-existence and social cohesion between the target communities of the cross-border areas
Output 2.1: | Strengthened conflict prevention and dispute resolution platforms for dialogue, joint problem-solving and cooperation, including women, youth and refugees, at community level | 17000 | 3504.73 | 10896.47 | 84.71% | 72036.54 | 65770 | 0 | 91.3% |  |  |  |  | 105000 | 88320 | 0 | 84.11% | 194036.54
Activity 2.1.1: | Establish or consolidate the community conflict prevention and management mechanisms in the target communities. | 0 |  |  |  | 30000 | 30000 |  | 100% |  |  |  |  | 20000 | 20000 |  | 100% | 50000 |  | Committees will comprise leaders of women's associations as well as take into account conflict prevention and management mechanisms driven by women.
Activity 2.1.2: | Strengthen capacities of CPPCs and CPCs to effectively mitigate disputes and conflicts in their respective communities. | 0 |  |  |  | 32036.54 | 32000 |  | 99.89% |  |  |  |  | 40000 | 40000 |  | 100% | 72036.54 |  | Trainings will implicate leaders of women's associations and included tailored techniques to women's role in mitigation processes; special measures will be taken to ensure participation, such as child care provision
Activity 2.1.3: | Facilitate the organization of CPPCs and CPCs on a quarterly basis. | 0 |  |  |  | 10000 | 3770 |  | 37.7% |  |  |  |  | 25000 | 22320 |  | 89.28% | 35000 |  | As part of quarterly meetings, a separate meeting held by women for women will be included; special measures will be taken to ensure participation, such as child care provision
Activity 2.1.4: | Organize Joint Committee meetings between respective mirroring communities. | 17000 | 3504.73 | 10896.47 | 84.71% |  |  |  | #DIV/0! |  |  |  |  | 20000 | 6000 |  | 30% | 37000 |  | Meetings will include a focus on issues and challenges specific to women in cross-border communities.
Output 2.2: | Improved social cohesion and stability among cross-border communities through joint social, cultural and economic initiatives | 140000 | 44722.7 | 87775.21 | 94.64% | 350000 | 263769 | 0 | 75.36% | 123062.45 | 105062.76 | 8665.12 | 92.41% | 280000 | 278671 | 0 | 99.53% | 893062.45
Activity 2.2.1: | Provide and/or reinforce basic community infrastructure. | 100000 | 23474.08 | 60531.83 | 84.01% | 105000 | 98775 |  | 94.07% | 123062.45 | 105062.76 | 8665.12 | 92.41% | 75000 | 75000 |  | 100% | 403062.45 |  | Contractors are currently mobilizing construction materials for the 4 hand pumps to support community engagement
Activity 2.2.2: | Support cross-border women initiative to promote women's rights, fight against SGBV, community development, and social economic exchanges. | 0 |  |  |  | 30000 | 40100 |  | 133.7% |  |  |  |  | 20000 | 20000 |  | 100% | 50000
Activity 2.2.3: | Organize sensitization and awareness campaigns related to social cohesion of cross-border areas and elections through the ECOWAS radio broadcasts and IEC materials. | 40000 | 21248.62 | 27243.38 | 121.2% | 60000 | 20000 |  | 33.33% |  |  |  |  | 80000 | 78671 |  | 98.34% | 180000 |  | Broadcasts will include specific thematics/segments related to women, their role in local societies as well as challenges and ways forward
Activity 2.2.4: | Facilitate to organize cultural, sport, and economic activities with a view to improving social cohesion. | 0 |  |  |  | 155000 | 104894 |  | 67.67% |  |  |  |  | 105000 | 105000 |  | 100% | 260000 |  | At least half of proposed activities will specifically target women; specific provisions will be made to ensure women's participation (such as provision of transportation and child care).
TOTAL $ FOR OUTCOME 2: |  | 157000 | 48227.43 | 98671.68 |  | 422036.54 | 329539 | 0 | 78.08% | 123062.45 | 105062.76 | 8665.12 |  | 385000 | 366991 | 0 |  | 1087098.99
TOTAL OUTCOME 1 & 2 |  | 574536.5405 | 223642.77 | 236472.24 |  | 574536.54 | 427965 | 0 | 74.49% | 550062.45 | 418537.48 | 72916.65 |  | 600740 | 493499 | 3550 |  | 2299875.5305
Project personnel costs if not included in activities above |  | 103416.576 | 88084.95 |  | 85.17% | 68944.38 | 64152.61 |  | 93.05% | 86180.48 | 81884.09 |  | 95.01% | 86180.48 | 68359.37 |  | 79.32% | 344721.916
Project operational costs if not included in activities above | [6 empty] | 68659.39 |  | #DIV/0! | [8 empty] | 0
Project M&E budget |  | 48261.072 | 4432.16 | 24022.03 | 58.96% | 32174.05 | 20000 |  | 62.16% | 36654.27 | 10520 | 2025 | 34.23% | 42051.48 | 36626.81 |  | 87.1% | 159140.872
SUB-TOTAL PROJECT BUDGET: |  | 726214.1885 | 316159.88 | 260494.27 |  | 675654.97 | 580777 | 0 | 85.96% | 672897.2 | 510941.57 | 74941.65 |  | 728971.96 | 598485.18 | 3550 |  | 2803738.3185
Indirect support costs (7%): |  | 50834.9932 | 18419.91 |  | 36.23% | 47295.85 | 40654.39 |  | 85.96% | 47102.804 | 35765.9099 | 5245.9155 |  | 51028.0372 | 38975.52 | 0 | 76.38% | 196261.6844
TOTAL PROJECT BUDGET: |  | 777049.1817 | 334579.79 | 260494.27 | 76.58% | 722950.82 | 621431.39 | 0 | 85.96% | 720000.004 | 546707.4799 | 80187.5655 | 87.07% | 779999.9972 | 637460.7 | 3550 | 82.18% | 3000000.0029

## Category
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency IOM Cote D`Ivoire | [5 empty] | Amount Recipient Agency UNDP Cote d'Ivoire | [5 empty] | Amount Recipient Agency IOM Liberia | [5 empty] | Amount Recipient Agency UNDP Liberia | [5 empty] | Total tranche 1 (70%) | Total tranche 2 (30%) | PROJECT TOTAL | Overall Expenses | Overall PO | Overall Del (%)
| Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%)
1. Staff and other personnel | 72391.2 | 31024.8 | 103416 | 88084.95 | 0 | 85.18% | 48261.07 | 20683.3157 | 68944.3857 | 58568.14 |  | 84.95% | 60326.336 | 25854.144 | 86180.48 | 81884.09 |  | 95.01% | 60326.336 | 25854.144 | 86180.48 | 68359.37 |  | 79.32% | 241304.942 | 103416.4037 | 344721.3457 | 296896.55 | 0 | 86.13%
2. Supplies, Commodities, Materials | 76108.781 | 32618.049 | 108726.83 | 82422.01 | 21305.42 | 95.4% | 24130.53 | 10341.6557 | 34472.1857 | 25214.91 |  | 73.15% | 22717.5792 | 9736.1054 | 32453.6845 | 12116.19 | 5521.53 | 54.35% | 8410.36 | 3604.44 | 12014.8 | 9060.81 |  | 75.41% | 131367.2502 | 56300.2501 | 187667.5003 | 128813.92 | 26826.95 | 82.93%
3. Equipment, Vehicles, and Furniture (including Depreciation) | 28152.292 | 12065.268 | 40217.56 | 2.5 | 0 | 0.006216% | 32174.04 | 13788.8743 | 45962.9143 | 50255.3 |  | 109.3% | 36359.5047 | 15582.6449 | 51942.1496 | 52290.08 | 855 | 102.3% | 29436.26 | 12615.54 | 42051.8 | 11806.7 |  | 28.08% | 126122.0967 | 54052.3272 | 180174.4239 | 114354.58 | 855 | 63.94%
4. Contractual services | 38435.117 | 16472.193 | 54907.31 | 4532.97 | 24375.12 | 52.65% | 100543.9 | 43090.2429 | 143634.1429 | 149855.55 |  | 104.3% | 73158.3058 | 31353.5596 | 104511.8655 | 76200.26 | 2025 | 74.85% | 105129.5 | 45055.5 | 150185 | 129033.13 |  | 85.92% | 317266.8228 | 135971.4955 | 453238.3184 | 359621.91 | 2025 | 79.79%
5.Travel | 33782.875 | 14478.375 | 48261.25 | 11593.41 | 19764.31 | 64.97% | 32174.04 | 13788.8743 | 45962.9143 | 31732.85 |  | 69.04% | 30803.4972 | 13201.4988 | 44004.996 | 47922.22 |  | 108.9% | 29436.26 | 12615.54 | 42051.8 | 36626.81 |  | 87.1% | 126196.6722 | 54084.2881 | 180280.9603 | 127875.29 | 19764.31 | 81.89%
6. Transfers and Grants to Counterparts | 160870.437 | 68944.473 | 229814.91 | 68583.51 | 159492.64 | 99.24% | 180979.01 | 77562.4329 | 258541.4429 | 205000 |  | 79.29% | 152092.2674 | 65182.4003 | 217274.6677 | 149684.76 | 66540.12 | 99.52% | 168207.2 | 72088.8 | 240296 | 240296 |  | 100% | 662148.9144 | 283778.1062 | 945927.0206 | 663564.27 | 226032.76 | 94.04%
7. General Operating and other Direct Costs | 98609.154 | 42261.066 | 140870.22 | 60940.53 | 35556.78 | 68.5% | 54695.88 | 23441.0914 | 78136.9714 | 60150.25 |  | 76.98% | 95570.552 | 40958.808 | 136529.36 | 90843.97 |  | 66.54% | 109334.46 | 46857.62 | 156192.08 | 103302.36 |  | 66.14% | 358210.046 | 153518.5854 | 511728.6314 | 315237.11 | 35556.78 | 68.55%
Sub-Total Project Costs | 508349.856 | 217864.224 | 726214.08 | 316159.88 | 260494.27 | 79.41% | 472958.47 | 202696.4871 | 675654.9571 | 580777 | 0 | 85.96% | 471028.04 | 201869.16 | 672897.2034 | 510941.57 | 74941.65 | 87.07% | 510280.376 | 218691.584 | 728971.96 | 598485.18 | 0 | 82.1% | 1962616.742 | 841121.4551 | 2803738.1971 | 2006363.63 | 311060.8 | 82.65%
8. Indirect Support Costs (must be 7%) | 35584.4899 | 15250.4957 | 50834.9856 | 18419.91 |  | 36.23% | 33107.095 | 14188.755 | 47295.85 | 40654.39 |  | 85.96% | 32971.9628 | 14130.8412 | 47102.804 | 35765.9099 | 5245.9155 | 87.07% | 35719.626 | 15308.4112 | 51028.0372 | 38975.52 |  | 76.38% | 137383.1738 | 58878.503 | 196261.6768 | 133815.7299 | 5245.9155 | 70.86%
TOTAL | 543934.3459 | 233114.7197 | 777049.0656 | 334579.79 | 260494.27 | 76.58% | 506065.565 | 216885.2421 | 722950.8071 | 621431.39 | 0 | 85.96% | 504000.0028 | 216000.0012 | 720000.0074 | 546707.4799 | 80187.5655 | 87.07% | 546000.002 | 233999.9952 | 779999.9972 | 637460.7 | 0 | 81.73% | 2099999.9158 | 899999.9582 | 2999999.8739 | 2140179.3599 | 316306.7155 | 81.88%