## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Ensuring the continuity of essential primary healthcare and hospital services for the most vulnerable and developing prevention and hygiene measures for essential non-health sectors during the COVID-19 pandemic | Overall Duration (months) | 7 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.06.2020
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | MOROCCO | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO, UNFPA, UNIDO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health-Ministry of Solidarity, Social Development, Equality and Family - Ministry of Industry, Trade, Green and Digital Economy- Ministry of Labor and Professional Integration-- International Labor Organization (ILO)-General Confederation of Moroccan Enterprises (CGEEM)-National Federation of Agro-Food (FENAGRI)-Coalition pour la valorisation des déchets (COVAD)-Information Technologies, Telecommunication and Offshoring Federations (APEBI)-Ministry of Culture, Youth and Sport-- General Delegation of the Penitentiary and Reintegration Administration Civil Society Organization : Pan African Organization to fight against AIDS (OPALS)-The Network of Counselling and Shelters centers for women victims of violence ANARUZ
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 pandemic and the measure taken to contain the virus have had an impact on access to health services. Through the UN Covid19-MPTF Funded Programme, WHO, UNFPA and UNIDO have supported the Moroccan Government in 1) strengthening protection measures in the workplace and 2) maintaining the continuity of basic public services, particularly in the field of sexual, reproductive, maternal and neonatal health as well as for patients with chronic diseases, and for women victims of GBV. Based on these two complementary components, the joint action has adopted an innovative, holistic, inclusive and human rights-based approach for the most vulnerable populations, women, young, migrants, prisoners, cancer patients, women victims of violence and front-line workers. With the approval of the Ministry of Foreign Affairs and Cooperation and in close collaboration with the designated focal points from the various Ministries involved, in 7 months (June-December 2020), the three UN agencies implemented all planned activities in order to achieve the expected outputs and outcome. In order to insure the governance of the action, a Steering Committee, co-chaired by the Ministry of Health and the WHO was set up at the beginning of the project. All the activities carried out have contributed to improving the quality of the services and their continuity in particular in the post-confinement period (after the 20th of June 2020) during which the number of cases has increased exponentially, if compared to the first five months of the pandemic. The project has a national geographic coverage but, with respect to the digital application for the reproductive health, the Ministry of Health has chosen the Tanger-Tetouan-Al Hoceima Region as a pilot area. Specific regions have been targeted for the continuity of palliative care (Beni Mellal, Agadir, Oujda, Errachidia) and others (Marrakech and Fez) with regard to the support to the Units for Women Victims of Violence (UWVV) operating inside the public hospitals. Despite the difficulties caused by the spread of the virus and the limits on public gatherings, the project adopted a combination of different approaches in order to ensure the continuity of services. In particular : the self-care service, the use of new information and communication technologies (ICT), communication and community awareness, the distribution of protective equipment for health professionals, for the population and the front-line workers, as well as some awareness tools in order to support the recovery of the agri-food, waste management and trade/e-commerce sectors. The activities undertaken are part of several areas of intervention, and have all contributed to: 1 Ensuring the continuity of essential primary health services through the digitalization, both in hospitals and in prisons; 2. Improving the quality of sexual, reproductive, family planning, maternal and neonatal health services and strengthen health professionals’ capacity building; 3. Improving the quality and continuity of the service (led by the State and civil institutions) for cancer patients, including those at the end of their life requiring in-home palliative care, as well for women and girls victims of violence by promoting their economic empowerment; 4. Covid-19 screening and protection of health professionals; 5. Awareness and communication about Covid19 infection and the protection of front-line workers in the industrial sectors.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The targeted population is variegated, composed of health professionals, pregnant women and women of childbearing age, patients with chronic diseases, women survivors of violence, migrants, prisoners, as well as front-line workers in priority sectors other than health, particularly in the industry (agri-food, waste management, trade and e commerce sectors). Direct bénéficiaires : - 21400 women benefiting from the 30 health facilities equipped with the digital application; - 139 women victims of violence (aged between 20 and 70) hosted in the three shelters centers managed by ANARUZ; - 504 women victims of violence received a psychological and legal support by ANARUZ; - 50 women integrated in 3 cooperatives; - 200 women victims of violence received hygiene and protection kits against Covid19; - 3200 health professionals received personal protective equipment; - 765 healthcare professionals benefited from the online training on capacity-building on medical care for women victims of violence; - 400 healthcare professionals have benefited from the online training on the essential newborn care; - 72 health professionals working for the General Delegation of the Penitentiary and Reintegration Administration DGAPR trained on the use of the teleconsultation; - 267 managers and 37 administrative managers of the“ Young Structures” owned by the Ministry of Culture, Youth and Sport, trained on hygiene measures and community outreach in the face of Covid19 ; - Within the OPALS’ centers, 3500 sex workers sensitized on Covid-19 barriers through communication tools developed in different languages (Arabic for Moroccans and French or English for migrants). - Within the OPALS’ centers, an average of 250 women, Moroccan and foreigners, received consultations (gynecological, dermatological) and advice about Family Planning and HIV/cervical cancer screening, in optimal conditions of protection against contamination of the virus; - An average of 60 people living with HIV among key populations received psychological support, within OPALS’s centers; - An average of 1050 migrants benefited from HIV prevention and Sexual and Reproductive Health promotion programmes provided by OPALS; - 400 cancer patients in the 4 pilot provinces received in-home palliative care; - 2000 front-line workers in industrial sectors benefited from the awareness/communication actions; Indirect beneficiaries: - 13700 prisoners detained in the 24 targeted prisons will benefit from the teleconsultation service provided ; - 3000 women will have the opportunity to receive a high-quality prenatal care; - 4500 women victims of violence will receive the emergency contraceptive pills that has been provided to the 113 Units for WVV; - All families of cancer patients that will receive in-home palliative care; - All patients in the two provinces of Agadir and Beni Mellal requiring palliative care will benefit from the two newly palliative care units created inside the Regional Centre of Oncology; - 5000 frontline workers in industrial sectors awarded by the communication tools;
3.1 | Results: Outcome Level | Please include outcome level results achieved | PROPOSAL OUTCOME 1.1 The government ensures continuity of essential health services to deal with the COVID-19 crisis and its impacts on vulnerable populations, while fully protecting against the spread of infections. All the implemented activities have contributed to the achievement of the project outcome: ensuring the continuity of essential health services for the most vulnerable populations and the protection of front-line workers, in the priority sectors of health and industry. In particular, with regard to sexual, reproductive health and family planning, the informatics tools and the digital application that have been installed in 30 Health facilities in the Tanger Tétouan Al Hoceima Region, have contributed to provide a better care service and a computerized monitoring of women’s reproductive health. The digital application allows health professionals to actively follow the women registered in the system, to launch automatic reminders on the next medical consultation, follow up on the correct use of family planning methods, and even schedule appointments in order to avoid gatherings in the primary healthcare facilities. A field training on the correct use of the application has been provided to 15 health professionals in 4 pilot health facilitates, as well as to some executives of the Ministry of Health, in order to strengthen their capacities and ensure the sustainability of the action. A technical follow-up and the maintenance of the system during three months after the end of the project is ensured by the team of engineers who developed the application. Moroever, the improvement of the sexual and reproductive health service has been ensured through the procurement of medical equipment and consumables which will provide a high-quality prenatal care to the benefit of more than 3000 women. With regard to maternal and neonatal health, more than 400 health professionals have strengthened their capacities through an online training organized in two sessions of 6 weeks each on the e-learning platform of the National School of Public Health. The training, managed by an expert in neonatal care and reanimation with the support of school teachers, has been focused on the care of the new-born, in the birthing room and in the immediate postpartum. Various categories of health professionals have benefited from the training: midwife, general practitioners, nurses and pediatricians. Moreover, an assessment study on the impact of the COVID-19 national response measures on the health care cost for expensive chronic diseases has being conducted. The study aims to : I) Access the economic impact of Covid-19 on patients affected by heavy and expensive pathologies; II) Estimate the cost to be mobilized by the State to mitigate the impact of the crisis on households; III) Propose recommendations to guide decisions-making concerning mitigation actions to be taken during and after the crisis. Concerning capacity-building related to gender-based violence, on the occasion of the celebration of the International Days for the elimination of violence against women (from 25 November to 10 December) more than 700 health professionals at national level received a capacity-building online training – with certificate –on health care of women victims of violence. In addition, in order to strengthen the system of evaluation of the quality of the care of 12 Regional Maternity Hospitals, which are Covid19 Reference Centers, the project contributed to develop an interactive dashboard of monitoring and evaluation. On the other hand, , the setting up of a training-conference room at the National Reproductive Health Centre “Les Orangers”, that is a WHO collaborating center and a University Maternity Hospital with a pedagogical role in providing continuous training, has contributed to strengthen its educational and training role both at national and international level. Having linked the conference room to the operating room, the project has helped to expand the number of students receiving distance training and, at the same time, has given to the Centre the possibility of being connected with its national and international partners in order to promote cooperation and the exchange of good practices in the field of reproductive health. At community level, the project contributed to develop a digital platform for the maintenance and the enhancement of the quality of sexual and reproductive health services provided by Pan-African Organization to fight against AIDS (OPALS) for the most vulnerable population, including pregnant women and migrants, mainly from sub-Sahara Africa. Through an interactive dashboard, the application makes it possible to monitor AIDS testing activities, consultations on Sexual and Reproductive Health, and contributes to better manage the stocks and the performance of the regional sections of the Association. In addition, in order to guarantee a hospitable environment and physical distancing, some tents have been placed in the external area of the OPALS Ambulatory Treatment Center in Rabat, that is an exemplary center of self-care, so to humanize the reception of patients. A different entrance and exit system has been adopted, in order to avoid contacts and gatherings, and 6 regional sections of the Organization (Casablanca Fès, Meknès, Marrakech, Taza and Guercif) have received protective equipment (face shield, masks, hydro alcoholic gel, perspex screens for the reception, etc.) so to ensure continuity of service in compliance with hygienic standard and distancing measures. Inside the 24 targeted prisons that do not have a full-time doctor, the project contributed to the creation of a teleconsultation service able to optimize health coverage and ensure the continuity of essential health services for a population of more than 13,000 inmates. At the same time, thanks to some informatics tools (PC, scanners) the internal and external communication system has been strengthened, allowing data sharing concerning health programs and inmates’ personal medical record. As a pilot project of healthcare digitalization within prisons, this teleconsultation system has strengthened the capacity of 24 penal institutions to provide a quality care service through a regular video-based consultation with an external referring doctor. Moreover, hygiene kits and personal protective equipment have been distributed in order to protect both the healthcare professionals and the inmates and thus contribute to limiting the spread of Coronavirus within these penal institutions. With regard to cancer patient care, the project has putted in place and equipped two hospital palliative care units within the two Regional Oncology Centers in Agadir and in Beni Mellal. These units will go operational from January 2021. At the same time, four mobile health units have been bought in order to insure the in-home palliative care in 4 provinces (Agadir, Tiznit, Beni Mellal and Errachidia) to the benefit of more than 400 bedridden patients who are not able to travel to the Regional Cancer Center. A 2021 Action Plan for the in-home palliative care service for cancer patients has been developed and it will be implemented in the 4 targeted. The in-home health service wants to be also an opportunity to facilitate access for patients and their families to nutritional information and spiritual counselling. With respect to gender-based violence, in order to ensure continuity of the service for women victims of violence, the project has contributed to the improvement of the follow-up system by providing information technology equipment to the 113 Units for women victims of violence existing at national level, as well as medical supplies and furniture to guarantee women’s privacy and create a welcoming reception area in compliance with quality standards, norms of human rights protection as well as the essential service package recommended by international health authorities. In addition, in order to strengthen the quality of the health service for women victims of violence and prevent the risk of unwanted pregnancies, the Units for Women victims of Violence (UIPECFVV in French) have been endowed with the morning-after pill, that has been chosen by the Ministry as the emergency contraception that has to be available inside health facilities and in particular in the UIPECFVV, in accordance with the essential service package for women subjected to violence . At local level, in three cities (Oujda, Meknes and Errachidia) the civil society Organization ANARUZ was supported to ensure the continuity of the shelter service as well as the psychological and legal support for women and girls victims of violence. Moreover, hygiene and protection kit against Covid19 has been distributed to women and children living in the shelters. Throughout the course of the project, 139 women have been hosted in three centers, 504 women benefited from the support of lawyers, social workers and psychologists and 50 women have been integrated into three craft and agricultural cooperatives, in order to develop technical skills and become economically autonomous. At the same time, this multi-partner project has supported Moroccan Government in detecting Covid19 by strengthening the diagnosis capacities of the National Institute of Hygiene, which is the 1st national laboratory in molecular diagnosis of the virus. The joint action has also helped to strengthen the COVID19 National screening Strategy, that includes the involvement of primary health care facilities. To this end, more than 200 health centers in the priority regions of Casablanca-Settat, Rabat-Salé-Kenitra, Marrakech-Safi and Fez-Meknes have been equipped with the necessary medical equipment (oxymeters, electrocardiograms, tensiometer, etc.) so to improve care quality and contributing to the assessment of patients’ health status. The protection of front-line workers is an imperative condition to ensure the continuity of essential services and prevent the transmission of the virus among health professionals and patients. In this sense, following the epidemiological trend of Covid-19 in Morocco, regions with a high prevalence of cases have been prioritized in receiving protective equipment, especially the regions of Casablanca-Settat , Rabat-Salé-Kenitra, Marrakech-Safi and Tangier-Tetouan-Al Hoceima, insuring the protection of more than 3200 health professionals and 800 health facilities. Another component of the project was the communication and community awareness about the risk of Covid-10 contagion and the barrier measures required. In this sense, within the OPALS, volunteers and community development agents have received vests and caps bearing the words “Anti COVID19 Action” in order to be easily recognized and an average of 3.500 female sex workers received awareness sessions on sexually transmitted infections–AIDS as well as flyers containing messages on how to be protected from Covid-19. Similarly, 267 managers and 37 administrative officers responsible for “youth structures” managed by the Ministry of Culture, Youth and Sport, have been trained on Covid19 safety rules in order to guarantee the continuity of the service and put in place community awareness actions. In the three targeted industrial settings (agri-food, waste management and trade/e-commerce) the project aimed to bring awareness on Covid19 protection measures through communication tools for front-line workers, by supporting the awareness programs already established by the Ministry of Industry and the Federation of enterprises. After having carried out an inventory of communication tools produced by the partners, some new media content has been created highlighting issues that had not previously been developed, like the resilience, the profitability after recovery and the long-term business continuity. These tools have been adapted to the Moroccan reality in order to be easily understood by the target audience. The content of these communications tools has been beneficial to approximately 5.000 workers and managers of more than 100 companies.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1.1 Continuity of essential primary and hospital health services during the COVID-19 pandemic is maintained for women and men, girls and boys, including adolescent girls and adolescent boys. Many activities have been undertaken in order to achieve the expected results. They can be organized by different areas of intervention, namely: 1. CONTINUITY OF ESSENTIAL HEALTH SERVICES FOR PREGNANT WOMEN, WOMEN OF CHILDBEARING AGE, CANCEROUS PATIENTS AND INMATES 1.1 Computer tools (PCs, printers, Internet connection) provided for 30 primary health care facilities (15 in urban and 15 in rural) located in the Tanger-Tetouan-Al Hoceima region; 1.2 Development and implementation of a digital application (within 30 health facilities ) able to monitor the sexual-reproductive health and family planning 1.3 Training on the use of the application for the benefit of the Ministry of Health Officers (Division of Informatics and Methods, and managers of programs of Sexual and Reproductive Health); 1.4 Purchase and installation of technical equipment to establish a training-conference room linked to the operating room within the National Reproductive Health Centre in Rabat, which is a University Maternity Hospital providing continuing education to doctors, nurses and resident students; 1.5 Development of a digital dashboard to the benefit of the OPALS’ sections at national level, in order to computerize the internal management of procedures, and improve performance monitoring of programmes on Sexual and Reproductive Health; 1.6 Purchase of informatics tools (computers, scanners, microphones, etc.), for 24 targeted prisons without a full-time doctor in order to initiate the teleconsultation able to ensure a continuous health service for the population composed of about 13.700 inmates ; 1.7 Purchase of four mobile health unit for the provinces of Agadir, Oujda, Beni Mellal and Errachidia in order to ensure the movement of health professionals toward cancer patients and thus guarantee the continuity of in-home palliative care; 1.8 Establishment of 2 hospital palliative care units at the Regional Oncology Centers of Agadir and Beni Mellal and purchase of specific medical equipment (alternating pressure mattress, oxygen concentrators, oximeters); 1.9 Capacity building and training in palliative care for cancer patients and bedridden patients to the benefit of 50 health professionals from different backgrounds (general practitioners and specialists, nurses, medical social worker, program leaders and mobile palliative care teams) and from different provinces (Beni Mellal, Agadir, Oujda and Errachidia); 2. IMPROVING THE QUALITY OF SEXUAL AND REPRODUCTIVE HEALTH SERVICE, FAMILY PLANNING, MATERNAL AND NEONATAL HEALTH AND CAPACITY BUILDING 2.1 Purchase of specific medical equipment for the measurement of blood glucose, hemoglobin, and for the detection of urinary infection for the benefit of 30 Health Facilities in order to ensure a quality prenatal care through a rapid screening of high-risk pregnancies and thus contributing to the reduction of maternal and neonatal mortality and morbidity; 2.2 Purchase of 4500 doses of the morning-after pill as a contraceptive method for the 113 Units for Women Victims of Violence existing at national level; 2.3 Development of a monitoring and quality evaluating system of care and services provided by the Regional Maternity Hospitals, COVID-19 reference centers; 2.4 Distance learning on the essential newborn care, benefiting more than 400 health professionals (midwives, nurses, general practitioners and pediatricians); 3. IMPROVING THE QUALITY AND THE CONTINUITY OF THE SUPPORT SERVICE FOR WOMEN AND GIRLS VICTIMS OF VIOLENCE 3.1 Purchase of computer resources (tablets) for the 113 Units for Women and Girls Victims of Violence existing at national level within public Hospitals, in order to support the operationalization of the information system for monitoring cases of violence; 3.2 Purchase of office and medical equipment (medical examination tables, medical screen, etc) for 18 Units for women victims of violence in the Regional Hospitals of Fez-Meknes and Marrakech-Safi, in order to ensure women’s privacy, a warm reception and a support in line with the standards of quality and respect of human rights and the essential service package recommended by the international health authorities. 3.3 Production of a monitoring and evaluation tool of the Units for of Women Victims of Violence; 3.4 Elaboration of an analytical case report on cases of women victims of violence received and processed between 2019 and 2020 by integrating the impact of Covid-19 on gender-based violence; 3.5 Online training, with a final certificate, focused on the medical, social and legal support for women and girls victims of violence, benefiting more than 765 health professionals at national level; 3.6 Purchase of 200 Covid19 protection kits for women hosted in the three shelters for Women and Girls Victims of Violence managed by the Network of Local Associations ANARUZ, in the cities of Oujda, Meknes and Errachidia; 3.7 Continuity of counselling and legal service provided by the three local associations members of the ANARUZ Network, through the designation of 3 lawyers, 3 psychologists and 3 social workers. 3.8 Implementation of a rolling fund system with three targeted associations of the Anaruz Network for the integration of 50 women victims of violence into three cooperatives active in the craft and food sector and thus contribute to their economic empowerment; Output 1.2.1 Access to health and protection and prevention material against COVID-19 in vital workplaces is strengthened. 4. COVID-19 TESTING, PROTECTION OF HEALTH PROFESSIONALS 4.1 Purchase of laboratory equipment for the National Institute of Hygiene in order to use three thermocyclers machines for PCR; 4.2 Purchase of personal protective equipment (masks, gel, gloves, face shield, blouses, etc.) against Covid-19 for the benefit of more than 800 Health Centers and 3.200 health professionals, as well OPALS and ANARUZ social workers and population (migrants, pregnant women and girls); 4.3 Purchase of medical equipment (electrocardiograms, oximeters, blood pressure monitors, medical tuning forks, ophthalmoscope kits and otoscopes, among others) for the benefit of 200 Health Centers in order to allow health professionals to have an overall opinion of the patient’s health and ensure a minimum package of care and continuity of service. 5. COMMUNICATION AND COMMUNITY AWARENESS, AND PROTECTION OF FRONT-LINE WORKERS IN INDUSTRIAL SECTORS 5.1 Training of peer educators and OPALS local development agents (Moroccan and sub-Saharan ) to raise awareness on personal hygiene and barriers measures to prevent the spread of Covid19; 5.2 Production and distribution of communication and awareness tools, including flyers, in Arabic, French and English, vests and caps to attract the attention of the population; 5.3 Online awareness raising training on protection measure for the benefit of 37 administrative officers and 267 officers of the Ministry of Culture, Youth and Sport managers of the “youth structures”; 5.4 Production and dissemination of 18 video clips on hygiene barrier gestures to adopt inside the enterprises, the resumption of business and the development of a business continuity plan; 5.5 Production and dissemination of 6 practical guides to support companies in business recovery while integrating the resilience dimension to deal with the pandemic; 5.6 Development of an online training platform for COVID-19 focal points inside the enterprises ; 5.7 Development of a Simplified Workers Information Guide on vaccination; 5.8 Development of a COVID-19 Prevention Charter including general information about labour law, circulars and guidelines; 5.9 Production and diffusion of 4 short thematic video clips and an institutional video on the activities carried out and good practices implemented in the framework of this multi-partners project.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The short-term action and the plurality of partners involved are among the main challenges of the project. Despite that, the collaboration and constant communication between all stakeholders, NU Agencies, institutional and civil society partners, have facilitated the decision-making process and the implementation of all the activities. In addition, in order to overcome the slowness of the UN internal administrative procedures, the action benefited from the fast track procedures, that contributed to speed up the procurement and recruitment process, minimizing the advertising period for the call for tenders. The summer did not stop the spread of the virus and, faced with the resurgence of Covid-19 cases throughout the project implementation period (july-december2020), the Moroccan government extended the state of health emergency. This represented another challenge in purchasing certain medical equipment (out of stock) and caused delays in the procurement of some medical equipment coming from abroad. In addition, because of restrictive measures in force even after the summer, including ban on gatherings of more than 20 people, some project activities have been cancelled. In particular those planned with the civil society organization AMPF that was supposed to organize some medical caravans, thus causing a community mobilization. Therefore, the funds originally allocated to these activities have been redeployed. A portion of the funds has been used to strengthen both health professionals’ skills on the use of the health teleconsultation inside the prisons, and officials managers of the “youth structures” on the barriers measures against Covid-19; another portion has been invested in purchasing specific medical equipment for primary health facilitates and thus improve the quality of care service provided. The increase of Covid19 positive cases and the launch of the National Covid-19 Vaccination Campaign have been other challenges for the project, particularly with respect to the field training for the health professionals on the use of the digital app. After the application testing phase inside fours primary health facilities in the region of TTA, health professionals have been increasingly occupied with the logistical aspects of the campaign co-organized by the Ministry of Health and the Ministry of the Interior in application of the orders coming from the country’s highest authorities. To overcome this challenge, in agreement with the concerned Department of the Ministry, it has been decided to adopt the cascade training method. In this way, a pool of trainers made up of 20 officials from the central and regional department of the Ministry will transfer the acquired knowledge to the number of health professionals targeted by the action. The cascade training will be carried out in the coming months, under the supervision and technical support of the engineers who have developed the application and who committed themselves to ensuring the monitoring and maintenance of the system during three months after the end of the project. In the industrial sector, in the first months of implementation, the technical validation process and the collection of needs among partners took more time than expected due to limits on meetings. In addition, sectors’ priorities have changed over time, depending on the evolution of the health situation. This obliged UNIDO to adapt to changing needs and follow constantly the evolution. Furthermore, given the existing constraints and challenges imposed by the pandemic, and the short duration of the project, UNIDO found some difficulties in receiving constant feedback from partners and meet the deadlines set for each activity. Often implementation partners were already caught up in many types of emergencies, not making them available on time, having a direct impact on planned activities.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Confronted with the restrictive measures imposed by the Covid19 pandemic, the adoption of health digitalization has been one of the main innovations of the action, ensuring the continuity of health services, both in primary hospital settings and in prisons. With regard to SRH and family planning, the digital system developed for the benefit of 30 Primary Health Facilities, both in urban and rural areas, is a highly innovative tool for managing and monitoring consultations of pregnant women and women of childbearing age, as well as for data collection, work organization and appointments management. Similarly, the implementation of a teleconsultation system in the 24 targeted prisons, as a pilot initiative in the country, was an effective response to ensure the health coverage inside these centers, which do not have a full-time medical team and have a population of more than 13.000 inmates. On the other hand, in terms of continuity of service for women victims and survivors of violence, the project paid particular attention to strengthening the functioning of the 113 Units that, at national level, provide a support to these women (UIPECFVV in French), by making the Units more welcoming and appropriate for the target population and, at the same time, providing them with more efficient informatics tools so to improve the electronic collection of data related to violence. In this sense, portable and lightweight computer (tablets) have been distributed to the social workers operating in the UIPECFVV, making easier and faster their daily case monitoring work. A project good practice worth mentioning is the creation of the Steering Committee, co-chaired by the WHO and the Ministry of Health, which ensured the project governance and monitoring, the validation of the strategic choices and the additional requests that occurred during the implementation.This steering body has also contributed to the development of a broader consensus among stakeholders. At the same time, on the one hand, good relations and effective communication between UN Agencies and the relevant Ministerial departments contributed to strengthen the partnership and, on the other hand, in front of unexpected changes imposed by the pandemic, to strengthen the culture of anticipation and resilience, of adaptation and revision in programming and execution of activities, ensuring a rapid and coordinated response. In addition, the project has promoted an action-research approach, that has contributed to the acquisition of knowledge required to implement concrete and transformative actions on the ground. In this framework, an Analytical Report of Gender-Based Violence cases received and processes has been developed, by integrating the impact of the COVID crisis. Among the report’s recommendations is the strengthening of the medico-legal support component through continuing training, as well as the digitalization of the medical records by using new technologies. To this end, a cycle of online training on the legal and health management of women victims of violence has been organized, reaching more than 700 health professionals, and, at the same time, health professionals received technological resources in order to computerized data on violence and guarantee the optimal use of the collected information. The several health, economic and social measures taken as part of the response to the COVID-19 pandemic, have affected the well-being of households, particularly the most vulnerable at risk of slipping into poverty. Among the affected households, those with some members suffering from severe and expensive pathologies are even more likely to be affected in terms of health but also economically. This is even more crucial as households in Morocco bear a significant share of the costs of accessing health services. To further investigate this problem, a study was launched to assess the impact of the COVID19 pandemic on households where a member lives with one or more heavy and expensive pathology. The study also aims to provide evidence and recommendations to the decision-makers in order to mitigate the impact of this crisis on the most affected populations.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The joint action carried out by the three UN agencies for the benefit of the Moroccan government, is in line with the Resolution WHA 73.1 on the “COVID-19 response” of the World Health Assembly, that encouraged a comprehensive and coordinated response by the UN system to support all countries in implementing their multi-sectoral national action plans, in strengthening their health systems to respond to the COVID-19 pandemic, and in maintaining the safe provision of all other essential public health functions and services. Also, it is in agreement with I.) the guidelines of the «National Response Plan» adopted by the Kingdom of Morocco in March 2020 in line with the SPRP of the WHO and II.) the recommendations resulting from the tripartite strategic note published in August 2020, with which the High-Commission for Planning (HCP in French), the United Nations System in Morocco and the World Bank have called for investing in the continuity of essential public health care, education and administration services during and after this health crisis caused by the Covid19 pandemic. The implementation of the UN-COVID19 MPTF project in a very short time (7 months) has been possible thanks to the strong involvement and the very close collaboration of all stakeholders: the three UN agencies, the different competent Ministerial departments and the civil society organizations. On 17 June, 2020, the project kick-off meeting was held with the representatives of the various UN Agencies, including WHO, UNFPA, UNIDO, UNAIDS, UNICEF, ILO, UNDP and IOM, to present the work plan and define the governance mechanisms and project’s complementarity with the different interventions of each Agencies. On 26 June 2020 the three UN Agencies carrying the UN-COVID19 MPTF Programme (WHO, UNFPA and UNIDO), held a second coordination meeting with the designated focal points of the institutional departments involved, including the Ministry of Health, the Ministry of Solidarity, Social Development, Equality and Family, the Ministry of Industry, the Ministry of Labour and the Ministry of Economy and Finance. As agreed, a Steering Committee, co-chaired by the Ministry of Health the WHO was formed to oversee and ensure the good governance of the project. Communication with the many partners, both institutional and civil society representatives, was ensured on a constant and regular basis by the project team and Programme Managers. The responsiveness of the Ministerial Focal Points has contributed considerably to ensuring the implementation of the activities in accordance with the timetable. During the month of August, a third follow-up meeting was organized between UNFPA, WHO and UNIDO and in October a second meeting of the Steering Committee took place, to present project progress, the challenges and the follow-up on the first recommendations. During the last quarter of the project, the partners kept a constant and fruitful communication in order to achieve all the results in compliance with the project’s schedule and closing date (31 December 2020). On 15 January 2021, the last Steering Committee was held, which also celebrated the official closing of the project and which was the occasion to discuss the results and share recommendations. As a whole, the project has contributed to strengthening strategic partnerships at the Ministry level so to jointly address the global challenge of ensuring the continuity of essential health services and the protection of front-line workers in priority sectors.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | 1.UNFPA: Analytical Report of Gender-Based Violence Cases received and processed by Integrating the Impact of the COVID-19 Crisis. The report, conducted in a participatory and collaborative manner involving Ministerial officers of the National health program and professionals in the field, has analyzed data recorded during the years 2019 and 2020 when the lookdown took place. The data showed, among other things, that physical violence increased by 9 points during the year 2020, and that 80% of perpetrators remain the spouses. 2.UNFPA: Creation of an interactive dashboard for the benefit of the Ministry of Health for monitoring and evaluate quality improvement of maternal and neonatal health care and services; 3.UNFPA: Creation of a informatics software to monitor and evaluate the Integrated Units for Women Victims of Violence (UIPECFF in French), in order to assess their performance in a standardized way. The implementation of this tool aims to establish transparency, quality and equity of activities at UIPECFVV level, to develop the culture of dissemination of good practices and to support the access of women and children who are victims of violence to an acceptable, accessible, ethical, effective, egalitarian and secure medical-social service. 4.UNFPA: The organization for the benefit of the health staff of the UIPECFVV of an online training on the essential service package for women and children victims of violence, with a focus on the medical-legal, gynecological, psychological, on the reception and communication in the context of Covid19, on the information system and the mechanisms of coordination of management. Two cycles of 5 sessions each were carried out using the “Stop Violence” platform of the National Programme Against Gender-Based Violence, drawing the attention of more than 700 health professionals. More than 300 people took the online quiz and obtained the certificate of completion of the training. 5.WHO: Neonatal Health E-learning : 6-modules training programme for more than 400 health professionals (midwives, nurses, general practitioners and pediatricians) about early essential newborn care. 6.WHO: Economic Study for Assessing the Impact of Covid-Response Measures on patients with severe and expensive pathologies; 7.UNIDO: A gender assessment about the impact of communication tools on the gender dimension in industrial sectors; 8.UNIDO: Creation of 6 practical guides to support companies in business recovery while integrating the resilience dimension to deal with the pandemic. 9.ILO/UNIDO: Development of an online training platform for COVID-19 focal points inside the enterprises ; 10.ILO/UNIDO: Development of a simplified workers Information Guide on vaccination; 11.ILO/UNIDO: Development of a COVID-19 Prevention Charter including general information about labour law, circulars and guidelines.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The alarming increase in Covid-19 positive cases after the lockdown shutdown (20 June, 2020) and even after the summer period, as well as the extension of the ban on gatherings, imposed the cancellation of certain activities carried out by the Moroccan Association of Family Planning (AMPF), partner of UNFPA. Those funds were thus redeployed to new activities proposed by institutional partners. In particular for I) strengthening health professionals skills on the use of teleconsultation in prisons; II) building community awareness on prevention measures of Covid19 for the benefit of the officials who manage the “youth structures” of the Ministry of Culture, Youth and Sport, and the community development officers who are in direct contact with youth and III) purchase medical-technical equipment for the benefit of some health centers in order to strengthen their Covid-19 screening capabilities. With regard to continuity of care for cancer patients, during the first months of the action, the Ministry of Health has expressed to the WHO the will to substitute the activity of teleconsultation by the provision of in-home palliative care to cancer patients and bedridden patients. This is due to the fact that from July 2020 the prohibition to circulate h24 on the whole national territory has been removed. This change did not have a negative impact on the expected result because the continuity of service for patients with chronic diseases was ensured via the in-home service. This activity, which is an innovation of the national health system, was critical for patients who are very vulnerable to COVID-19 and cannot travel to hospital to receive the necessary palliative care.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The nature of the project, characterized by a large number of purchases and consultations in a very short period of time, required the full-time recruitment of a 3 people. The team, composed by a Project Manager, an Associate and a Procurement and Logistics Manager, ensured the technical and financial management of the project, the project visibility and follow-up with institutional and civil society partners, in close collaboration with the Programme Managers of the UN Agencies. During the implementation of the joint action, in order to support the COVID19 screening strategy of the Ministry of Health that involved primary health care facilities, UNFPA and WHO have mobilized additional funds for a total amount of US$ 115,000 (US$ 15,000 UNFPA, US$100,000 WHO) to respond favorably to the Ministry’s request to purchase medical equipment for a hundred health centers and thus guarantee a minimum package of service and health care. In particular, electrocardiograms, oximeters, blood pressure monitors, and other medico-technical equipment have been acquired, covering more than 200 health facilities. These actions have helped to improve the quality of care and have ensure the continuity of essential primary health care services. Other additional funds, amounting to USD 14,000, have been mobilized by UNFPA for the acquisition of medical consumables for 30 Health Facilitate,to help enhance the quality of prenatal care and thus contribute to the instantaneous detection of hematological disorders complicating pregnancy.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] The government ensures continuity of essential health services to deal with the COVID-19 crisis and its impacts on vulnerable populations, while fully protecting against the spread of infections.
Indicator: 1.1a Number of components of the essential primary health care package strengthened by ensuring continuity of service through the mobile health service. | 3 Target achieved: 1. Sexual and reproductive health services strengthened ; 2. Chronic diseases – services for cancer patients strengthened ; 3. Health services for Gender-based violence victims/survivors strengthened ; |  | Reports of the Ministry of Health; Reports of consultancies undertaken; Photos of the equipment and application developed, installed and used by health professionals
Baseline: 0
Planned Target: 3 1. Sexual and reproductive health 2. Chronic diseases, cancer patients 3. Health services for Gender-based violences
Indicator 1.1b Number of non-health sectors supported to provide protective measures to their employees and maintain their essential services interrupted by COVID-19 | 3 target achieved: food industry, trade /e-commerce and waste management 2000 employees (40%women) |  | UNIDO –ILO Reports
Baseline:0
Planned Target: 3 (food industry, trade and waste management) 40 % target beneficiaries are women
Indicator 1.1c Availability of economic analysis studies to measure the impact of access to health care during and after confinement (disaggregated by sex, age, Moroccan citizen/migrant/ refugee, geographic area: rural, urban, incomes etc). | Preliminary study available |  | Study Protocol Preliminary Report WHO
Baseline: study not available
Planned Target: Analysis study available
Output 1.1 Continuity of essential primary and hospital health services during the COVID-19 pandemic is maintained for women and men, girls and boys, including adolescent girls and adolescent boys
Indicator 1.1.1 a: Number of people, including migrants and refugees, benefiting from the mobile health service disaggregated by sex, age, geographic coverage (e.g., rural, urban) Moroccan citizen/migrant/ refugee and pregnant women (including adolescents) | 21473 women benefiting from the mobile health service in the 30 Health facilities; 400 cancer patients ; | Number of women : according to the estimation of the Ministry of Health, taking into consideration the expected number of birth compared to the population using the health facilities that have been equipped with the digital application. | Ministry of Health Report
Baseline: 0
Planned Target: Women 10 000 (5000 per region)- Male and female Cancer patients (400) (OMS) - Male and female NCD patients (1000)
Indicator 1.1.1.b Availability of patient database disaggregated by sex, age, geographic coverage (e.g., rural, urban) and Moroccan citizen/migrant/ refugee | 4 Patient database available in 4 health facilities in the Tanger Tetuan Al Hoceima Region (2 in Urban and 2 in rural areas). 400 bedridden cancer patients have received in-home palliative care | The first phase of data entry in the data base has been conducted in 4 pilot health facilities. The launch of the vaccination campaign- that is a national priority- caused a delay in the data entry process in the others health facilities. The Ministry of Health and the engineers that developed the application signed an agreement in order to ensure the adaptation of the application after the test and follow-up within three months after the end of the project | Ministry of Health Report UNFPA Report WHO Report
Baseline: 0
Planned Target: Patients database. Bedridden cancer patients who have received palliative care at home (400 patients).
Indicator: 1.1.1.c Number of healthcare facilities benefiting from the mobile health service disaggregated by geographic location (e.g., rural, urban) | 30 sexual and reproductive health care facilities, (50% in urban area and 50% in rural area) equipped with computer tools and the digital application. 2 hospital palliative care units (in the Regional Oncological Center of Agadir and Beni Mellal) have been created. 4 mobile health units for ensuring in-home palliative care have been bought. | The planned target (20) has been exceeded. The mobile health units have replaced the teleconsultation for cancer patients. | Ministry of Health Report; Delivery forms. UNFPA Report WHO Report
Baseline: 0
Planned Target: Sexual and reproductive health care facilities (20: 12 Rural, 08 URBAN). 2 hospital palliative care units, in Agadir and Beni Mellal.
Indicator : 1.1.1.d Number of men and female Health professionals and Health professionals trained to use the mobile health services disaggregated by sex, age, geographic coverage (e.g., rural, urban) | 15 health professionals of 4 pilot primary health centers have received a field-training on the use of the digital application (70%women, 30%men); 20 health managers at the Informatics Department of the Ministry of Health have received a training on the use of the digital application; 20 trainers of the Ministry of Health have been trained in order to train other 200 health professionals on the field; 72 health professional operating in prisons have been trained to use the teleconsultation service developed to the benefit of 24 prisons; | With the launch of the vaccination campaign in November 2020, and the increase of Covid19 positive cases, the field training for health professionals has been interrupted and replaced with a cascade training method, involving a team of 20 people of the Ministry of Health. Within three months after the end of the action, each one has to train at least 10 people, in order to reach more than 200 professional health. | Ministry of Health report
Baseline: N/A
Planned Target: 200 health workers :(150 Health professionals (100 women and 50 men, 50 Health managers)
Indicator 1.1.1.e Number of men and female professional health workers provided with protection material against COVID-19 to health service continuity during confinement and beyond. | 3200 health workers (70% women and 30% man) and 852 centers have been provided with protection material and products against Covid-19 (masks, gloves, face shield, hydro alcoholic gel, etc). |  | Delivery forms and Ministry of Health receipt form .
Baseline: 0
Planned Target: 200 Health professionals and managers : (150 Health professionals (100 women and 50 men), 852 centres de santé et plus de 3000 professionnels (OMS)
Indicator 1.1.1.f Number of male and female prisoners and prisons equipped with protection material to enhance protection against COVID-19 and ensure service continuity. | 24 prisons have been equipped with protection material and products against Covid19. These prisons have a population of more than 13.000 inmates. | The 24 prisons, located nationwide , have been defined as a priority by the DGAPR since they do not a have full time doctor. The hygiene kit for Covid19 will contribute to ensure that the medical examination is done in compliance with hygiene measures. | Delivery forms and DGAPR receipt form.
Baseline: 0
Planned Target: 1000 prisoners, 62 prisons
Indicator 1.1.1.g Number of operational health units for women survivor of violence, supported to ensure service continuity during and beyond confinement | 113 Health units located in several provincial hospitals have been equipped with informatics tools to facilitate the health professionals’ daily job in collecting electronic data about women having benefitted from the service. Moreover, 18 Units in the Region of Marrakesh and Fes have been equipped with medical and office equipment in order to ensure women’s privacy and create a welcoming reception area within the quality standards and norms for human rights protection. | The planned target (12 units) has be exceeded. Due to the increasing number of gender-based violence during the lockdown, a priority has been given to this action and 5 more unites have been targeted. Moreover, the Ministry of Health developed the application « Stop violence » and the IT tools provided will facilitate social workers’ daily job, since they have to respond rapidly to complaints of women victims of violence. | UNFPA delivery form and Ministry of Health receipt form.
Baseline: 0
Planned Target : 12 (7 in Marrakech and 5 in Fes
Indicator 1.1.1.h Number of survivors of gender-based violence accessing support through provincial hospital units, disaggregated by age, pregnancy status, geographic coverage (rural/urban), socio-economic status (which includes female/male migrants, female/male refugees and migrants) | 137 Moroccan women and 3 migrants have been hosted in the three shelters managed by ANARUZ. 504 women victims and survivors of violence have received counselling and legal support within the ANARUZ centers. Ministry of Health estimates that at national level, les 113 UIPECFVV will receive about 20.000 women survivors of GBV, who will be supported in compliance with quality standards, norms of human rights protection and the essential service package recommended by international health authorities. | The planned target (200) has be exceeded. | Ministry of Health report UNFPA report .
Baseline: 0
Planned Target: 200 survivor of gender-based violence
Indicator 1.1.1.i Number of stakeholders able to reach target populations equipped and mobilized (communities, CSOs, community workers, migrant and refugee organizations) to disseminate information regarding the Mobile Health service and refer patients to it. | 80 OPALS’ local development agents have been equipped with Covid19 protection kit and mobilized to disseminate information regarding the virus prevention measures and the continuity of the service (sexual and reproductive health); 267 officials and 37 managers of « youth structures” run by the Ministry of Culture, Youth and Sport, have been trained on Covid19 prevention measures and on specific communication tools for raising awareness among young people. | The planned target (50) has be exceeded. | Delivery forms, UNFPA Report.
Baseline: 0
Planned Target: 50
Indicator 1.1.1.l Number of communications tools, including Gender and cultural sensitive tools, disseminated to the targeted population, including female population like female migrants, female refugees, women with chronic illnesses. | 1000 flyers (in English / French/ Arabic) have been produced by OPALS in order to raise awareness about virus prevention measures; 100 vest have been produced in order to ensure visibility of the local development agents; 80 caps have been produced in order to ensure visibility of the local development agents; 4 videos clips (5 min) and 1 video (20 minutes) have been created (French and Arabic/ English and Arabic) in order to give visibility to project results; 18 video clips have been produced for the recovery of the enterprises’ activities targeted by UNIDO 8 video clips have been produced by the ILO in order to convert into images the guidelines of the Ministry of Labour; |  | Delivery forms, We links, photos of communication materials produced and disseminated.
Baseline: 0
Planned Target :10 tools, 3 languages
Output 1.2 Access to health and protection and prevention material against COVID-19 in vital workplaces is strengthened
Indicator 1.2.1 a: Number of people (Men and women including workers and targeted population) benefiting from the communication tools developed | 2000 front-line workers (40% women) have been sensitized thanks to the communication tools developed; 5000 employees in the targeted sectors have been sensitized through the enterprises members of the Federation. |  | UNIDO Report
Baseline: 0
Planned Target: 2 000 workers (50% women) 5 000 people
Indicator 1.2.1 b : Number of private companies reached with the toolboxes for each target critical sector | Target achieved: 100 enterprises Production and dissemination of 6 practical guides to support companies in business recovery while integrating the resilience dimension to deal with the pandemic; Development of an online training platform for COVID-19 focal points inside the enterprises ; Development of a Simplified Workers Information Guide on vaccination; Development of a COVID-19 Prevention Charter including general information about labour law, circulars and guidelines; |  | UNIDO Report
Baseline: 0
Planned Target: 100 companies
Indicator 1.2.1.c Number of equipment for analysis of COVID "PCR analyzer" biological tests provided | 3 thermocycler PCR machines used in the diagnostic testing and screening for Covid19 have been putted into use thanks to laboratory equipment provided to the National Hygiene Institute (NHI). | The planned target (2) has be exceeded. | Delivery form and NHI receipt form.
Baseline: 0
Planned Target: 2
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Testimony of Mrs Salwa, midwife in the AMAL Health Center in Tangier. This Heath Center has been equipped with the IT tools and the digital application for the monitoring of the Sexual and Reproductive Health.
“The app has facilitated my work because it gives me the opportunity to ensure a better patients follow up and to manage appointments effectively, especially in this time of health crisis for the COVID19, when movement and public gathering are more dangerous. All women, married or not, who come to this Health Centre and wish to receive a contraceptive method, are supported. Thanks to this application, women receive messages in Arabic on their phones reminding them the date of the next consultation. In this way we ensure the continuity of the service in a safe environment”.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
Throughout the project, several communication and visibility materials have been produced by the implementing partners. The communication and awareness-raising tools produced by the OPALS in Arabic, French and English have been used to sensitize Moroccan and migrants on the Covid19 preventive measures. Also, the volunteers of the association and the community development agents were equipped with face shield, caps and vests bearing the words “Anti COVID19 Action” in order to be easily recognizable, attract public’s attention and increase awareness. Key information and images of the first results of the project were published on the 12th and 13th edition of the UNFPA newsletter in Morocco in October and December 2020, and several posts were published on the UN Agency’s facebook page. https://morocco.unfpa.org/fr/publications/12%C3%A8me-%C3%A9dition-du-bulletin-dinformation-de-unfpa-au-maroc https://morocco.unfpa.org/fr/publications/13%C3%A8me-%C3%A9dition-du-bulletin-dinformation-de-unfpa-au-maroc https://web.facebook.com/UNFPAMorocco The visibility of the project was also ensured on the occasion of the many international days celebrated by the United Nations, including World Contraception Day on September 26; during the “Orange the world” 16 days of activism against gender-based violence from 25 November to 10 December, and the 1 December during the World AIDS Day. Still, 4 video clips and a global video of the MPTF project have been produced and disseminated on the Agencies and partners social networks and websites. Links to UNIDO’s video-clips will be available once they will be published on the UNIDO official website.
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board