## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Support to the governance of the overall national response and assistance to populations made vulnerable by the COVID-19 crisis | Overall Duration (months) | 9
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-07-15
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2021-01-31
Country | Côte d’Ivoire | Current End date(dd.mm.yyyy) | 2021-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF (lead agency) UNODC UNDP FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Prime Minister Minister of Agriculture and Rural Development CSOCOVID-19 Operational Monitoring Committee General Directorate of Social Protection, Ministry of Employment and Social Protection Directorate of Child Protection, Ministry of Women, Families, Children Directorate of Social Action, Ministry of Employment and Social Protection Penitentiary Administration National Institute of Statistics NGOs: Cavoequiva, CIP, DDE-CI, AFJCI, etc.
Report Cleared By
o Name: | Serghei Toma BURUIANA
o Title: | Head of Social Policy, UNICEF
o Email address: | sburuiana@unicef.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## CdINar1
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | During the reporting period, the UN agencies implementing the project focused their interventions on two strategies: 1) supporting the Government with the overall coordination of the COVID-19 response; and 2) providing financial and in-kind support to the most vulnerable and affected segments of the population. Thanks to the project’s assistance, the Government of Côte d’Ivoire set up an indicator coordination and monitoring matrix, which was set at the level of the Operational Monitoring Committee of the Prime Minister's COVID-19 Response Plan (CSOCOVID-19). Two project experts contributed to the collection, centralization, and analysis of data on COVID-19, which helped better plan the response and better monitor the evolution of the pandemic in Côte d'Ivoire. The Government was supported to carry out two studies, one focused on the social determinants of the prevalence and accentuation of gender-based violence (GBV), and one on the perception of the coronavirus by populations in emergency situations in Côte d'Ivoire. These reports help all actors in planning gender-sensitive responses. Monetary transfer mechanisms for targeted small producers of palm oil and rubber trees have been put in place by the organizations of the two sectors. The lists of targeted beneficiaries are being finalized for the two sectors. The audit firm was selected. It will be responsible for verifying disbursement procedures, checking the identification, profiling, and targeting the small rubber and oil palm producers, and assessing the impact of cash transfers relative to the mitigation of the socio-economic impacts of COVID-19. The project supported 1,691 women and girls aged 15 and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months. It also supported 2,313 children aged 1-17 who experienced physical punishment and/or psychological aggression by caregivers during the past months. All national social services received hygiene and handwashing kits. All 224 social services received cash transfers to care for victims of violence, abuse, and exploitation. The inmates for two of Côte d’Ivoire's major prisons received hygiene kits. In addition, a training on COVID-19 prevention measures for prison workers is ongoing.
2 | Purpose (and Beneficiaries) | CFIn | The project contributed to the reinforcement of the reponse's governance systems, and the creation of a conducive environment for the delivery of support by governmental COVID-19 funds to the most affected groups of the population. It also provided food protection kits to four NGOs accommodating and hosting victims of trafficking in their transit centres, hygiene and sanitary kits to more than 3,000 inmates, psychologic support to approximately 1,700 victims of violence and exploitation, psychological first aid training for 244 social workers, as well as parenting, family skills, and financial assistance for 1,322 women-headed households.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The UN's assistance allowed Côte d'Ivoire to operationalize the project performance monitoring platform as part of the COVID-19 response plan (https://projectperformancemonitoring.org/). UN agencies supported 1,691 women and girls aged 15 and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months and 2,313 children aged 1-17 who experienced physical punishment and/or psychological aggression by caregivers during the past months.
3.2 | Results: Output Level | Please include output level results achieved | A COVID-19 response results monitoring framework was developed (with the support of the two statistical experts that were assigned to the committee of national coordination mechanisms) to monitor the contribution of each actor (government structures, technical, and financial partners) in terms of financial and material resources invested in the fight against COVID-19, the results recorded, and the evolution of the pandemic (evolution of the number of active cases and cures, evolution of the positivity rate, etc.). 244 social welfare workers were trained on psychosocial first aid, parenting, family skills, and family therapy. 1,322 women-headed households benefitted from a financial assistance. 4,062 cases of violence, abuse, exploitation, and mistreatment were reported, including through the operationalized helpline, referred assistance, and received assistance. 104,304 parents and primary caregivers were provided with community-based mental health and psychosocial support. Two surveys were conducted: one on identifying the determinants of domestic violence and sexual abuse, and a second one on the perceptions of violence. More than 3,000 inmates from two major prisons from the greater Abidjan area were provided with hygiene kits, thanks to a joint intervention from implementing UN agencies and the Ministry of Justice. The process to procure sewing machines for women to produce masks was initiated. Implementing UN agencies supported the Ministries in charge of Labour and Social Protection, Health, Solidarity and the Fight Against Poverty, the National Health Insurance Agency (CNAS), and regional social protection and health divisions with the organization of a series of workshops to document and share good practices and lessons learnt relative to the provision of cash transfers to vulnerable populations affected by COVID-19 and their enrolment to the Universal Health Coverage (UHC). As a result of these workshops, action plans were developed with corrective actions aimed at improving the access of households and children affected by the COVID-19 pandemic to cash benefits and health services.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The COVID-19 prevention measures decreed by the Government and the lockdown of the greater Abidjan area, combined with tensions related to the presidential election, had a significant impact on the implementation of project activities with regards to the mobilization of partners. These measures hindered the completion of capacity building activities for law enforcement officers engaged in the fight against human trafficking, social welfare workers, health workers, and community workers engaged in the management or prevention of violence. The project was significantly delayed due to the failure to mobilize all of the State's resources to support the impacted agricultural sectors and delays in making these funds available to said sectors. The exhaustive lists of producers, respective zones, and productions for the periods concerned have not yet been finalized by two agricultural sectors. The finalization of the recruitment process for the audit company, however, remains dependent on the effective availability of these beneficiary lists. Regarding the sharing of information on the finalization of the lists of targeted producers, cash transfer programme for producers, and the involvement and participation of stakeholders in all project activities, an advisory committee was set up to monitor and support project activities. Movement restrictions between regions and cities due to COVID-19 delayed social service interventions in the field. The national helpline was unable to always provide timely support to victims of violence referred through calls. To overcome this bottleneck, new and improved software was provided, and the staff was trained to use it.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The implementation of teleworking during the COVID-19 pandemic by the national counterparts was constrained by their lack of technical and material capacity. The provision of appropriate ITC tools and equipment (videoconferencing, Zoom license, etc.) has had a significant positive impact on business continuity, enabling a continued collaboration between the various stakeholders and promoting the coordination of interventions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project team regularly held coordination meetings with national and international partners working in implementing or supporting the Government's COVID-19 response plan. During these discussions, the results obtained were shared with other actors. This sharing of information made it possible to mobilize USD 85,000 from other UN projects, which enabled the acquisition of COVID-19 kits for communities. Thanks to the results achieved during this project, particularly in working with street children, a new, USD 273,000 project with this group of children was developed and launched, allowing the mobilization of new resources to support street children and provide them with other sustainable alternatives.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Using their own funds, UNDP and UNICEF supported by the National Institute of Statistics (INS) and research institutes to measure the socio-economic impact of COVID-19 on the living conditions of households, children, businesses, and informal production units in Côte d'Ivoire. These studies provided valuable, real-time information and reference data for decision makers relative to the first consequences of COVID-19. This allowed to better target interventions and plan national support measures for the affected social and economic sectors.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Due to the electoral period in Cote d’Ivoire, the procurement of sewing machines to set up mask production facilities in prisons for inmates was delayed. All administrative processes were completed and the procured goods are expected to be received before the end of January 2021.

## RMF_CdI1
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] : Effective, accountable, and transparent institutions are developed at all levels.
Indicator 1.1 : Number of National Strategic Monitoring Mechanism established, functional and operational |  |  | Report
Baseline: 0
Planned Target: 1 | 1
Indicator 1.2 : Proportion of population with satisfactory recent experience with public services. | On going |  | Survey
Baseline: 0%
Planned Target: 30%
Output 1.1: A National Strategic Monitoring Mechanism for the monitoring and mitigation of the socio-economic effects of the COVID-19 pandemic is established | 1 | A result monitoring framework has been developed, with support of the 2 statistical experts assigned to the national coordination mechanisms committee, to monitor, based on the performance indicators, the progress towards the achievement of the expected results. But for insufficient funds, the projet was unable to mobilize the consultants to develop the government's crisis management and communication plan | Activity report
Indicator 1.1.1: Number of tools for project implementation monitoring and reporting.
Baseline: 0
Planned Target: 2
Indicator 1.1.2: Number of surveys and analyses to monitor and understand the evolution of the impact of the crisis and control its effects. | 2 | UNDP supported the government to carry out two (02) studies, focuses on the social determinants of the prevalence and accentuation of gender-based violence (GBV) and on the perception of the coronavirus by populations in emergency situations in Côte d'Ivoire. | Study report
Baseline: 1
Planned Target: 3
Indicator 1.1.3: Number of mappings of multidimensional poverty exacerbated by the COVID-19 pandemic produced. | 1 | Using its own funds, UNDP supported a survey carried out by the National Institute of Statistics (INS) to measure the socio-economic impact of COVID-19 on the living conditions of households, businesses and informal production units in Côte d'Ivoire. | Report
Baseline: 0
Planned Target: 3
Output 1.2: Reinforce the crisis management system of the country and strengthen the targeting system for the inclusion of marginalized groups | On going |  | Activity report
Indicator 1.2.1: Number of small rubber and palm oil producers identified and profiled, and number of lists developed and reviewed.
Baseline: 0
Planned Target: 160,000 (including at least 50% of women and young people)
Indicator 1.2.2: Number of impact assessment studies developed. | On going |  | Activity report and study report
Baseline: 0
Planned Target: 1
Output 1.3: Mechanism for monitoring the impact of the measures taken | On going |  | Audit and impact report
Indicator 1.3.1: Audit and impact assessment report on transfers to more than 180,000 rubber and palm oil producers available.
Baseline: 0
Planned Target: 1
Indicator 1.3.2: Existence of a database to guide interventions. |  |  | Report
Baseline: 0
Planned Target: 1
Outcome 2[1] : Women, girls, and boys continue to access appropriate protection services during the COVID-19 emergency. | T= 2313 / G= 1635 - B= 678 |  | SIPE, GBVIMS
Indicator 2.1: Number of children aged 1 to 17 years old who experienced physical punishment and/or psychological aggression by caregivers in the past month (SDG Indicator 16.2.1), disaggregated by sex.
Baseline: 985
Planned Target: 1,500
Indicator 2.2: Number of women and girls aged 15 years and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months, by type of violence and by age (SDG Indicator 5.2.1), disaggregated by sex. | 1691 |  | SIPE, GBVIMS
Baseline: 1,022
Planned Target: 1,500
Output 2.1: Social services are equipped to ensure the continuity of basic essential services and managed data collection. | 244 |  | Reports from MEPS and MFFE
Indicator 2.1.1: Number of social welfare workers, health workers, and community workers trained on psychosocial first aid, parenting, family skills, and family therapy.
Baseline: 75
Planned Target: 200
| 122 services. Rate of completion: 81% | Due to staff turnover and new staffs not trained on data collection tools.
Indicator 2.1.2: Number of facilities ensuring the regular publication of statistics on violence, including GBV, abuse, and exploitation during the COVID-19 pandemic. |  |  | SIPE, GBVIMS
Baseline: 0
Planned Target: 150
| 57000 | With the forms deposited in the maternity services, we were able to register all the new births.
Indicator 2.1.3: Number of boys and girls registered by the health facilities and declared by the civil registry services during the COVID-19 pandemic. |  |  | Registry of civil registry services
Baseline: 31,000
Planned Target: 56,370
Output 2.2: The capacities of protection actors and communities, men’s engagement, are strengthened to support the prevention and response to violence including GBV, abuse, exploitation and mistreatment of children related to the situation of confinement, youth and provide support to vulnerable families, identified by local governmental structures and communities. | 104304 |  | SIPE, GBVIMS
Indicator 2.2.1: Number of children, parents, and primary caregivers provided with community-based mental health and psychosocial support.
Baseline: 25,000
Planned Target: 50,000
Indicator 2.2.1.1 : Number of non-governmental organisations and reception centres hosting victims of trafficking provided with hygiene and sanitary and food protection kits | 4 |  | Activity report
Baseline: 00
Planned target: 04
Indicator 2.2.2: Number of community (women and Young) and religeous leaders sensitized on the early detection of victims of trafficking during the pandemic and on barrier measures against the spread of the Covid-19 virus | 350 |  | Activity report
Baseline: 00
Planned Target: 250
Output 2.3: The actors involved in the response to COVID 19 are able to put in place functional mechanisms for dealing with women and children who are victims of violence, abuse and exploitation, and document lessons learns and good practices. | T=4062/F=3318 and M=744 |  | SIPE, GBVIMS
Indicator 2.3.1: Number of cases of violence, abuse, exploitation, and mistreatment reported by families and community actors
Baseline: 1,022
Planned Target: 1,500
Indicator 2.3.2: Number of cases of violence, abuse, exploitation, and mistreatment reported and referred to the relevant services. | 100% | 4062 cases have been reported and referred to the relevant services. | SIPE, GBVIMS
Baseline: 75%
Planned Target: 100%
Indicator 2.3.3: Number of women-headed households and refugees who benefitted from a material and/or financial assistance. | 1322 | The reduction of the number of beneficiaries is due to the increase of the amount of household assistance decided by the Government from 36,000 FCFA to 75,000 FCFA. | Reports from MEPS and MFFE
Baseline: 600
Planned Target: 1,500
Output 2.4: Infection prevention and control (IPC) measures in prisons are integrated into/are in line with the public health response to COVID-19 in the community | 3000 : including 264 women, 719 children of which 672 boys and 47 girls |  | Report
Indicator 2.4.1: Number of prisoners who benefitted from hygiene kits, disaggregated by sex.
Baseline:0
Planned Target: 3,000
Indicator 2.4.2: Number of girls and women involved in the rehabilitation programme. |  | the prison rehabilitation programme has not yet stated due to the delay of the procurement with the elections in Côte d'Ivoire | Report
Baseline:0
Planned Target: 45

## Comm_an _CdI1
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Sessions de sensibilisation à Port-Bouët et Assouba.
En réponse à la crise de la COVID-19, l´ONUDC distribue des kits sanitaires et alimentaires aux victimes de la traite des personnes en Côte d’Ivoire.
2020-12-10 health and food kits TIPSOM Cote d'Ivoire (unodc.org)

## General Information-Intermediat
Programme Title & Project Number |  | Programme Duration |  | Programme Title & Project Number |  | Programme Duration
Programme Title: | Support to the governance of the overall national response and assistance to populations made vulnerable by the covid-19 crisis | Overall Duration (months) | 9 | Programme Title: | Support to the governance of the overall national response and assistance to populations made vulnerable by the COVID-19 crisis | Overall Duration (months) | 9
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-07-15 | Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-07-15
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2021-01-31 | MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Côte d’Ivoire | Current End date(dd.mm.yyyy) | 2021-03-31 | Country | Côte d’Ivoire | Current End date(dd.mm.yyyy) | 3/31/2021, before extention
Recepient UN Organizations |  | Implementing Partners |  | Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF (The lead Agency) UNODC UNDP FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Primature Ministre de l’Agriculture et du Développement Rural Operational Monitoring Committee "CSOCOVID-19" Direction Générale de la Protection Sociale, Ministère Emploi et Protection Sociale, Direction de la Protection de l’Enfant, Ministère Femme, Famille, Enfant Direction de l’Action Sociale, Ministère Emploi et Protection Sociale Administration Pénitentiaire Institut national de la Statistique NGOs : Cavoequiva, CIP, DDE-CI, AFJCI etc. | Organizations that have received direct funding from the MPTF Office under this programme | UNICEF (lead agency) UNODC UNDP FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Prime Minister Minister of Agriculture and Rural Development CSOCOVID-19 Operational Monitoring Committee General Directorate of Social Protection, Ministry of Employment and Social Protection Directorate of Child Protection, Ministry of Women, Families, Children Directorate of Social Action, Ministry of Employment and Social Protection Penitentiary Administration National Institute of Statistics NGOs: Cavoequiva, CIP, DDE-CI, AFJCI, etc.
Report Cleared By |  |  |  | Report Cleared By
o Name: | SERGHEI TOMA BURUIANA |  |  | o Name: | Serghei Toma BURUIANA
o Title: | Chef Politiques Sociales UNICEF |  |  | o Title: | Head of Social Policy, UNICEF
o Email address: | sburuiana@unicef.org |  |  | o Email address: | sburuiana@unicef.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY |  |  |  | The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY |  |  |  | The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate |  |  |  | As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities. |  |  |  | If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Intermediate
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The UN agencies implementing the project focused their interventions on two strategies: 1) supporting the Government with the overall coordination of the COVID-19 response; and 2) providing financial and in-kind support to the most vulnerable and affected segments of the population. Thanks to the project’s assistance, the Government of Côte d’Ivoire set up an indicator coordination and monitoring matrix, which was set at the level of the Operational Monitoring Committee of the Prime Minister's COVID-19 Response Plan (CSOCOVID-19). Two project experts contributed to the collection, centralization, and analysis of data on COVID-19, which helped better plan the response and better monitor the evolution of the pandemic in Côte d'Ivoire. The Government was supported to carry out two studies, one focused on the social determinants of the prevalence and accentuation of gender-based violence (GBV), and one on the perception of the coronavirus by populations in emergency situations in Côte d'Ivoire. These reports help all actors in planning gender-sensitive responses. Monetary transfer mechanisms for targeted small producers of palm oil and rubber trees have been put in place by the organizations of the two sectors. The lists of targeted beneficiaries are being finalized for the two sectors. The audit firm was selected. It will be responsible for verifying disbursement procedures, checking the identification, profiling, and targeting the small rubber and oil palm producers, and assessing the impact of cash transfers relative to the mitigation of the socio-economic impacts of COVID-19. The ToR for the impact study of Covid-19 on the two agricultural sectors and analysis of the crisis management in these sectors vere validated, in the preparation to launching the studies. The project supported 1,691 women and girls aged 15 and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months. It also supported 2,313 children aged 1-17 who experienced physical punishment and/or psychological aggression by caregivers during the past months. All national social services received hygiene and handwashing kits. All 224 social services received cash transfers to care for victims of violence, abuse, and exploitation. The inmates for two of Côte d’Ivoire's major prisons received hygiene kits. In addition, a training on COVID-19 prevention measures for prison workers is ongoing.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The project contributed to the reinforcement of the reponse's governance systems, and the creation of a conducive environment for the delivery of support by governmental COVID-19 funds to the most affected groups of the population. It also provided hygienic hygiene and sanitary, food protection kits to four (4) NGOs accommodating and hosting in theirs transit centers victims of trafficking in personskits and to more than 3,000 inmates, psychologic support to approximately 1,700 victims of violence and exploitation, psychological first aid training for 244 social workers, as well as parenting, family skills, and financial assistance for 1,322 women-headed households.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The UN's assistance allowed Côte d'Ivoire to operationalize the project performance monitoring platform as part of the COVID-19 response plan (https://projectperformancemonitoring.org/). UN agencies supported 1,691 women and girls aged 15 and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months and 2,313 children aged 1-17 who experienced physical punishment and/or psychological aggression by caregivers during the past months.
3.2 | Results: Output Level | Please include output level results achieved | A COVID-19 response result monitoring framework was developed (with the support of the two statistical experts assigned to the committee of national coordination mechanisms) to monitor the contribution of each actor (government structures, technical, and financial partners) in terms of financial and material resources invested in the fight against COVID-19, the results recorded, and the evolution of the pandemic (evolution of the number of active cases and cures, evolution of the positivity rate, etc.). 244 social welfare workers were trained on psychosocial first aid, parenting, family skills, and family therapy. 1,322 women-headed households benefitted from a financial assistance. 4,062 cases of violence, abuse, exploitation, and mistreatment were reported, including through the operationalized helpline, referred assistance, and received assistance. 104,304 parents and primary caregivers were provided with community-based mental health and psychosocial support. Two surveys were conducted: one on identifying the determinants of domestic violence and sexual abuse, and a second one on the perceptions of violence. More than 3,000 inmates from two major prisons from the greater Abidjan area were provided with hygiene kits, thanks to a joint intervention from implementing UN agencies and the Ministry of Justice. The process to procure sewing machines for women to produce masks was initiated. 13 social workers and community workers, including the Deputy Coordinating Director of PNSSU (National School and University Health Program) participated in an online capacity building with supervision plan on psychosocial first aid and on the Elements of Family Therapy to prevent violence, including treatment for adolescents with substance use disorders in contact with or at risk of the criminal justice system. The production of information brochures is underway (UNODC-lockdown-leaflet / 500 copies, UN-lockdown-refugees-leaflet / 500 copies, UN-Caring-for-child-in-Covid19-booklet / 500 copies, 12 sheets Healthy Parenting Tips / 500 copies) to be made available to social protection staff and community workers for parents during the COVID19 pandemic and for parents or other caregivers in crowded Food and non-food composed of sugar, rice, oil, spaguettis, tomatoes, fish, flour, milk, potatoes, kidney, peas, yam, hard soap, liquid soap, hydro gel, bleach, bucket, nose mask, paper towel, were purchased by UNODC for transit centre and NGOs hosting victims of trafficking. Four (4) structures received these support: NGO Cavoequiva, Dignite et droits des enfants -DDE-CI, LISAD and Cote d'Ivoire Prosperite. Also the operational capabilities of 33 law enforcement officers from police stations and gendarmerie brigades in the District of Abidjan, 06 NGOs involved in the protection of vulnerable persons, have been strengthened in the areas of identification and efficient care of victims of human trafficking. 350 people were sensitized during two community and victim awareness sessions in Port-Bouet (Abidjan) and Assouba (Aboisso) on early detection of victims of trafficking during the pandemic and barrier measures against the spread of Covid-19 virus. Implementing UN agencies supported the Ministries in charge of Labour and Social Protection, Health, Solidarity and the Fight Against Poverty, the National Health Insurance Agency (CNAS), and regional social protection and health divisions with the organization of a series of workshops to document and share good practices and lessons learnt relative to the provision of cash transfers to vulnerable populations affected by COVID-19 and their enrolment to the Universal Health Coverage (UHC). As a result of these workshops, action plans were developed with corrective actions aimed at improving the access of households and children affected by the COVID-19 pandemic to cash benefits and health services.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The COVID-19 prevention measures decreed by the Government and the lockdown of the greater Abidjan area, combined with tensions related to the presidential election, had a significant impact on the implementation of project activities with regards to the mobilization of partners. These measures hindered the completion of capacity building activities for law enforcement officers engaged in the fight against human trafficking, social welfare workers, health workers, and community workers engaged in the management or prevention of violence. The project was significantly delayed due to the failure to mobilize all of the State's resources to support the impacted agricultural sectors and delays in making these funds available to said sectors. The exhaustive lists of producers, respective zones, and productions for the periods concerned is still under finalization by two agricultural sectors. While the audit company was recruited, it remains dependent on the effective availability of beneficiary lists. Regarding the sharing of information on the finalization of lists of targeted producers, the cash transfer programme for producers, and the involvement and participation of stakeholders in all project activities, an advisory committee was set up to monitor and support project activities. Movement restrictions between regions and cities due to COVID-19 delayed social service interventions in the field. The national helpline was unable to always provide timely support to victims of violence referred through calls. To overcome this bottleneck, new and improved software was provided and the staff was trained to use it.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | During the COVID-19 pandemic, the national counterparts' implementation of teleworking was constrained by their lack of technical and material capacity. The provision of appropriate ICT tools and equipment (videoconferencing software, Zoom licenses, etc.) has had a significant positive impact on business continuity, enabling a continued collaboration between the various stakeholders and promoting the coordination of interventions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project team regularly held coordination meetings with national and international partners working in implementing or supporting the Government's COVID-19 response plan. During these discussions, the results obtained were shared with other actors. This sharing of information made it possible to mobilize USD 85,000 from other UN projects, which enabled the acquisition of COVID-19 kits for communities. Thanks to the results achieved during this project, particularly in working with street children, a new, USD 273,000 project with this group of children was developed and launched, allowing the mobilization of new resources to support street children and provide them with other sustainable alternatives.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Using their own funds, UNDP and UNICEF supported by the National Institute of Statistics (INS) and research institutes to measure the socio-economic impact of COVID-19 on the living conditions of households, children, businesses, and informal production units in Côte d'Ivoire. These studies provided valuable, real-time information and reference data for decision makers relative to the first consequences of COVID-19. This allowed to better target interventions and plan national support measures for the affected social and economic sectors.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNODC received COVID-19 sanitary materials and products. A handover ceremony is scheduled to be held on 12 April. The process of procuring 17 sewing machines to set up mask production facilities in prisons for inmates has been completed and the procured goods are expected to be received during the first week of April 2021.

## RBM-Intermediate
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] : Effective, accountable, and transparent institutions are developed at all levels.
Indicator 1.1 : Number of National Strategic Monitoring Mechanism established, functional and operational |  |  | Report
Baseline: 0
Planned Target: 1 | 1
Indicator 1.2 : Proportion of population with satisfactory recent experience with public services. | On going |  | Survey
Baseline: 0%
Planned Target: 30%
Output 1.1: A National Strategic Monitoring Mechanism for the monitoring and mitigation of the socio-economic effects of the COVID-19 pandemic is established | 3 | A result monitoring framework has been developped with support from the two statistical experts assigned to the national coordination mechanisms committee to monitor the progress towards the achievement of the expected results based on performance indicators. Based on this technical expertise provided, three monitoring tools have been developped: i) a national COVID-19 database (https://projectperformancemonitoring.org); ii) a monitoring matrix for development partners' contributions; and iii) a monitoring indicator matrix. | Activity report
Indicator 1.1.1: Number of tools for project implementation monitoring and reporting.
Baseline: 0
Planned Target: 2
Indicator 1.1.2: Number of surveys and analyses to monitor and understand the evolution of the impact of the crisis and control its effects. | 2 | UNDP supported the Government to carry out two studies, focuses on the social determinants of the prevalence and accentuation of gender-based violence (GBV) and on the perception of the coronavirus by populations in emergency situations in Côte d'Ivoire. UNDP analyzed 14,000 views on social media and the data helped to put in place stronger response measures, including support to the "PAVIOS" referential centre to increase access to prevention and care services for GBV victims. | Study report
Baseline: 1
Planned Target: 3
Indicator 1.1.3: Number of mappings of multidimensional poverty exacerbated by the COVID-19 pandemic produced. | 1 | Using its own funds, UNDP supported a survey carried out by the National Institute of Statistics (INS) to measure the socio-economic impact of COVID-19 on the living conditions of households, businesses, and informal production units in Côte d'Ivoire. This study became the reference document on how to target support where it is most needed. However, discussions with the World Bank and the INS allowed the continuation of studies on the socio-economic impact of COVID-19. As a result, a partnership has been developped with the World Bank to conduct periodic studies. However, these studies have not yet been scheduled. | Report
Baseline: 0
Planned Target: 3
Output 1.2: Reinforce the crisis management system of the country and strengthen the targeting system for the inclusion of marginalized groups | 137,056 rubber producers were identified in 24 rubber growing areas, including 101,143 who were rigorously certified and 35,349 in litigation who are currently being verified (plantation and production). Identification is underway at the level of oil palm producers. The provisional date for the finalization of the list of rubber and palm oil producers was set for 31 March 2021. A complaint mechanism has been put in place with FAO's support. | The delay is due to: i) non-effective mobilization of the planned resources; and ii) the long duration of the checklists. Out of 3.5 billion FCFA planned, the AIPH received only 500 million FCFA. Out of 24.980 billion FCFA planned, APROMAC received 6 billion FCFA. | Activity report
Indicator 1.2.1: Number of small rubber and palm oil producers identified and profiled, and number of lists developed and reviewed.
Baseline: 0
Planned Target: 160,000 (including at least 50% of women and young people)
Indicator 1.2.2: Number of impact assessment studies developed. | The firm responsible for this study has been selected. | The impact assessment of cash transfers can begin after the end of cash transfers. Cash transfer operations have not yet started. | Activity report and study report
Baseline: 0
Planned Target: 1
Output 1.3: Mechanism for monitoring the impact of the measures taken | The list of producers is under finalisation. The firm responsible for this audit has been selected. | Cash transfers to producers have not yet started in the two rubber and oil palm sectors. The probable date of finalization of cash transfers is set for 30 June 2021 for the palm oil sector. | Audit and impact report
Indicator 1.3.1: Audit and impact assessment report on transfers to more than 180,000 rubber and palm oil producers available.
Baseline: 0
Planned Target: 1
Indicator 1.3.2: Existence of a database to guide interventions. | The TOR for the specific socioeconomic impact study of COVID-19 on the two rubber and palm oil sectors have been drawn up. The study will start soon. | The existence of databases depends on the effectiveness of transfers. | Report
Baseline: 0
Planned Target: 1
Outcome 2[1] : Women, girls, and boys continue to access appropriate protection services during the COVID-19 emergency. | T= 2313 / G= 1635 - B= 678 |  | SIPE, GBVIMS
Indicator 2.1: Number of children aged 1 to 17 years old who experienced physical punishment and/or psychological aggression by caregivers in the past month (SDG Indicator 16.2.1), disaggregated by sex.
Baseline: 985
Planned Target: 1,500
Indicator 2.2: Number of women and girls aged 15 years and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months, by type of violence and by age (SDG Indicator 5.2.1), disaggregated by sex. | 1691 |  | SIPE, GBVIMS
Baseline: 1,022
Planned Target: 1,500
Output 2.1: Social services are equipped to ensure the continuity of basic essential services and managed data collection. | 244 |  | Reports from MEPS and MFFE
Indicator 2.1.1: Number of social welfare workers, health workers, and community workers trained on psychosocial first aid, parenting, family skills, and family therapy.
Baseline: 75
Planned Target: 200
| 122 services. Rate of completion: 81%. | There is a high staff turnover and new staffs were not trained on data collection tools. | SIPE, GBVIMS
Indicator 2.1.2: Number of facilities ensuring the regular publication of statistics on violence, including GBV, abuse, and exploitation during the COVID-19 pandemic.
Baseline: 0
Planned Target: 150
| 57000 | With the forms deposited in the maternity services, we were able to register all the new births. | Registry of civil registry services
Indicator 2.1.3: Number of boys and girls registered by the health facilities and declared by the civil registry services during the COVID-19 pandemic.
Baseline: 31,000
Planned Target: 56,370
Output 2.2: The capacities of protection actors and communities, men’s engagement, are strengthened to support the prevention and response to violence including GBV, abuse, exploitation and mistreatment of children related to the situation of confinement, youth and provide support to vulnerable families, identified by local governmental structures and communities. | 104304 |  | SIPE, GBVIMS
Indicator 2.2.1: Number of children, parents, and primary caregivers provided with community-based mental health and psychosocial support.
Baseline: 25,000
Planned Target: 50,000
Indicator 2.2.1.1 : Number of non-governmental organisations and reception centres hosting victims of trafficking provided with hygiene and sanitary and food protection kits | 4 |  | Activity report
Baseline: 00
Planned target: 04
Indicator 2.2.2: Number of community (women and Young) and religeous leaders sensitized on the early detection of victims of trafficking during the pandemic and on barrier measures against the spread of the Covid-19 virus | 350 |  | Activity report
Baseline: 00
Planned Target: 250
Output 2.3: The actors involved in the response to COVID 19 are able to put in place functional mechanisms for dealing with women and children who are victims of violence, abuse and exploitation, and document lessons learns and good practices. | T=4062/F=3318 and M=744 |  | SIPE, GBVIMS
Indicator 2.3.1: Number of cases of violence, abuse, exploitation, and mistreatment reported by families and community actors
Baseline: 1,022
Planned Target: 1,500
Indicator 2.3.2: Number of cases of violence, abuse, exploitation, and mistreatment reported and referred to the relevant services. | 100% | 4,062 cases have been reported and referred to the relevant services. | SIPE, GBVIMS
Baseline: 75%
Planned Target: 100%
Indicator 2.3.3: Number of women-headed households and refugees who benefitted from a material and/or financial assistance. | 1.322 | The reduction of the number of beneficiaries is due to the increase of the amount of household assistance decided by the Government (from FCFA 36,000 to FCFA 75,000). | Reports from MEPS and MFFE
Baseline: 600
Planned Target: 1,500
Output 2.4: Infection prevention and control (IPC) measures in prisons are integrated into/are in line with the public health response to COVID-19 in the community | 3,000, including 264 women and 719 children (672 boys and 47 girls). |  | Report
Indicator 2.4.1: Number of prisoners who benefitted from hygiene kits, disaggregated by sex.
Baseline:0
Planned Target: 3,000
Indicator 2.4.2: Number of girls and women involved in the rehabilitation programme. | 0 | The prison rehabilitation programme has not yet stated due to the delay of the procurement with the elections in Côte d'Ivoire | Report
Baseline:0
Planned Target: 45

## Communication-Intermediate
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Sessions de sensibilisation à Port-Bouët et Assouba.
En réponse à la crise de la COVID-19, l´ONUDC distribue des kits sanitaires et alimentaires aux victimes de la traite des personnes en Côte d’Ivoire.
2020-12-10 health and food kits TIPSOM Cote d'Ivoire (unodc.org)

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Support to the governance of the overall national response and assistance to populations made vulnerable by the COVID-19 crisis | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-07-15
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Côte d’Ivoire | Current End date(dd.mm.yyyy) | 2021-09-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF (lead agency) UNODC UNDP FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Prime Minister Minister of Agriculture and Rural Development CSOCOVID-19 Operational Monitoring Committee General Directorate of Social Protection, Ministry of Employment and Social Protection Directorate of Child Protection, Ministry of Women, Families, Children Directorate of Social Action, Ministry of Employment and Social Protection Penitentiary Administration National Institute of Statistics NGOs: Cavoequiva, CIP, DDE-CI, AFJCI, etc.
Report Cleared By
o Name: | Serghei Toma BURUIANA
o Title: | Head of Social Policy, UNICEF
o Email address: | sburuiana@unicef.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The UN agencies implementing the project focused their interventions on two strategies: 1) supporting the Government with the overall coordination of the COVID-19 response; and 2) providing financial and in-kind support to the most vulnerable and affected segments of the population. Thanks to the project’s assistance, the Government of Côte d’Ivoire set up an indicator coordination and monitoring matrix, which was set at the level of the Operational Monitoring Committee of the Prime Minister's COVID-19 Response Plan (CSOCOVID-19). Two project experts contributed to the collection, centralization, and analysis of data on COVID-19, which helped better plan the response and better monitor the evolution of the pandemic in Côte d'Ivoire. The Government was supported to carry out two studies, one focused on the social determinants of the prevalence and accentuation of gender-based violence (GBV), and one on the perception of the coronavirus by populations in emergency situations in Côte d'Ivoire. These reports help all actors in planning gender-sensitive responses. Cash transfer mechanisms for targeted small oil palm and rubber producers have been put in place by organizations from both sectors and lists of targeted beneficiaries have been drawn up. To monitor the progress of the project, a monitoring committee was set up by FAO. This committee includes the Prime Minister, the FAO and the heads of the implied sectors. Periodic consultations within the committee made it possible to resolve the difficulties encountered and to reorient certain activities of the project. Despite the 2 extensions of the project, the resources planned for the producers could only be released at a very low level. Under these conditions, the audit of resource transfers to producers was no longer relevant. As a result, the national stakeholders, the leaders of the sectors, the Prime Minister, the Resident Cordinator and the FAO decided to use the resources of the project for a large assessment study of the impact of COVID 19 which reached 400 producers from 3 sectors (mango, cashew and cotton), ie 1,200 producers in total and more than 550 actors (state actors, cooperatives and inter-branch organizations, local authorities, processors, exporters, input suppliers) in 13 regions of Ivory Coast. The project supported 1,691 women and girls aged 15 and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months. It also supported 2,313 children aged 1-17 who experienced physical punishment and/or psychological aggression by caregivers during the past months. All national social services received hygiene and handwashing kits. All 224 social services received cash transfers to care for victims of violence, abuse, and exploitation. The inmates for two of Côte d’Ivoire's major prisons received hygiene kits. In addition, a training on COVID-19 prevention measures for prison workers is ongoing.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The project contributed to the reinforcement of the reponse's governance systems, and the creation of a conducive environment for the delivery of support by governmental COVID-19 funds to the most affected groups of the population. It also provided hygienic hygiene and sanitary, food protection kits to four (4) NGOs accommodating and hosting in theirs transit centers victims of trafficking in personskits and to more than 3,000 inmates, psychologic support to approximately 1,700 victims of violence and exploitation, psychological first aid training for 244 social workers, as well as parenting, family skills, and financial assistance for 1,322 women-headed households. The impact study of COVID 19 on the 5 sectors (mango, cotton, cashew, rubber and oil palm) reached 1,200 producers and more than 550 actors (state actors, cooperatives and inter-branch organizations, local authorities, processors, exporters, input suppliers ) in 13 regions of Ivory Coast.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The UN's assistance allowed Côte d'Ivoire to operationalize the project performance monitoring platform as part of the COVID-19 response plan (https://projectperformancemonitoring.org/). UN agencies supported 1,691 women and girls aged 15 and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months and 2,313 children aged 1-17 who experienced physical punishment and/or psychological aggression by caregivers during the past months. The impact study of COVID 19 on the 5 sectors (mango, cotton, cashew, rubber and oil palm) reached 1,200 producers and more than 550 actors (state actors, cooperatives and inter-branch organizations, local authorities, processors, exporters, input suppliers ) in 13 regions of Ivory Coast.
3.2 | Results: Output Level | Please include output level results achieved | A COVID-19 response result monitoring framework was developed (with the support of the two statistical experts assigned to the committee of national coordination mechanisms) to monitor the contribution of each actor (government structures, technical, and financial partners) in terms of financial and material resources invested in the fight against COVID-19, the results recorded, and the evolution of the pandemic (evolution of the number of active cases and cures, evolution of the positivity rate, etc.). Cash transfer mechanisms for targeted small oil palm producers have been put in place by organizations from both sectors. Lists of targeted beneficiaries have been established and are in the process of being verified by the two sectors. FAO had already selected the audit firm responsible for verifying disbursement procedures, verifying the identification, profiling and targeting of beneficiary producers. A complaint mechanism has been put in place with FAO's support.The TOR for the impact study of Covid-19 on the two sectors and the analysis of crisis management in these sectors have been validated. All the stakeholders in the project were waiting for the transfer of resources from the state to the producers, in order to effectively launch the various studies. Ultimately, despite the 2 extensions of the project, the resources planned for the producers could only be released at a very low level. The rubber and palm oil sectors received CFAF 6 billions and CFAF 500 million respectively, which they spent mainly on the identification of producers. Under these conditions, the audit of resource transfers to producers was no longer relevant.To monitor the progress of the project, a monitoring committee was set up by FAO. This committee includes the Prime Minister, the FAO and the heads of the implied sectors. Periodic consultations within the committee made it possible to resolve the difficulties encountered and to reorient certain activities of the project. As a result, the national stakeholders, the leaders of the sectors, the Prime Minister, the RC and the FAO decided to use the resources of the project for a large assessment study of the impact of COVID 19 on 5 sectors namely hevea, oil palm, mango, cotton and cashew. This study, commissioned by the AETS-Afrique consultancy firm, is in the process of being finalized. The survey and data collection (see study scoping report and data collection note in appendix) reached 400 producers from each of 3 sectors (mango, cashew and cotton), ie 1,200 producers in total and more than 550 actors (state actors, cooperatives and inter-branch organizations, local authorities, processors, exporters, input suppliers) in 13 regions of Ivory Coast ; a national workshop to register the stakeholders of the 5 sectors is planned for next week to validate the reports. 244 social welfare workers were trained on psychosocial first aid, parenting, family skills, and family therapy. 1,322 women-headed households benefitted from a financial assistance. 4,062 cases of violence, abuse, exploitation, and mistreatment were reported, including through the operationalized helpline, referred assistance, and received assistance. 104,304 parents and primary caregivers were provided with community-based mental health and psychosocial support. Two surveys were conducted: one on identifying the determinants of domestic violence and sexual abuse, and a second one on the perceptions of violence. More than 3,000 inmates from two major prisons from the greater Abidjan area were provided with hygiene kits, thanks to a joint intervention from implementing UN agencies and the Ministry of Justice. The process to procure sewing machines for women to produce masks was initiated. 13 social workers and community workers, including the deputy director of coordination of the PNSSU (National School and University Health Program) were trained online with a supervision session, by UNODC, on psychosocial first aid and on the Elements of Family Therapy to prevent violence, including the care of adolescents with drug addiction disorders in contact with or at risk of the criminal justice system. Information brochures were produced (UNODC-lockdown-leaflet / 500 copies, UN-lockdown-refugees-leaflet / 500 copies, UN-Caring-for-child-in-Covid19-bookt / 500 copies, 12 Healthy Parenting sheets Tips / 500 copies) and made available to social protection staff and community workers for parents during the COVID19 pandemic and for parents or other caregivers in crowded environments The production of information brochures is underway (UNODC-lockdown-leaflet / 500 copies, UN-lockdown-refugees-leaflet / 500 copies, UN-Caring-for-child-in-Covid19-booklet / 500 copies, 12 sheets Healthy Parenting Tips / 500 copies) to be made available to social protection staff and community workers for parents during the COVID19 pandemic and for parents or other caregivers in crowded Food and non-food composed of sugar, rice, oil, spaguettis, tomatoes, fish, flour, milk, potatoes, kidney, peas, yam, hard soap, liquid soap, hydro gel, bleach, bucket, nose mask, paper towel, were purchased by UNODC for transit centre and NGOs hosting victims of trafficking. Four (4) structures received these support: NGO Cavoequiva, Dignite et droits des enfants -DDE-CI, LISAD and Cote d'Ivoire Prosperite. Also the operational capabilities of 33 law enforcement officers from police stations and gendarmerie brigades in the District of Abidjan, 06 NGOs involved in the protection of vulnerable persons, have been strengthened in the areas of identification and efficient care of victims of human trafficking. 350 people were sensitized during two community and victim awareness sessions in Port-Bouet (Abidjan) and Assouba (Aboisso) on early detection of victims of trafficking during the pandemic and barrier measures against the spread of Covid-19 virus. Implementing UN agencies supported the Ministries in charge of Labour and Social Protection, Health, Solidarity and the Fight Against Poverty, the National Health Insurance Agency (CNAS), and regional social protection and health divisions with the organization of a series of workshops to document and share good practices and lessons learnt relative to the provision of cash transfers to vulnerable populations affected by COVID-19 and their enrolment to the Universal Health Coverage (UHC). As a result of these workshops, action plans were developed with corrective actions aimed at improving the access of households and children affected by the COVID-19 pandemic to cash benefits and health services.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The COVID-19 prevention measures decreed by the Government and the lockdown of the greater Abidjan area, combined with tensions related to the presidential election, had a significant impact on the implementation of project activities with regards to the mobilization of partners. These measures hindered the completion of capacity building activities for law enforcement officers engaged in the fight against human trafficking, social welfare workers, health workers, and community workers engaged in the management or prevention of violence. The project was significantly delayed due to the failure to mobilize all of the State's resources to support the impacted agricultural sectors and delays in making these funds available to said sectors. The exhaustive lists of producers, respective zones and productions for the periods concerned are established and being verified by the two agricultural sectors. While the audit company has been recruited, its work depends on the effective availability of lists of beneficiaries and above all on the effective transfer of resources to the beneficiaries. Regarding the sharing of information on the finalization of lists of targeted producers, the cash transfer programme for producers, and the involvement and participation of stakeholders in all project activities, an advisory committee was set up to monitor and support project activities.Periodic consultations within the committee made it possible to resolve the difficulties encountered and to reorient certain activities of the project. As a result, the national stakeholders, the leaders of the sectors, the Prime Minister, the RC and the FAO decided to use the resources of the project for a large assessment study of the impact of COVID 19 on 5 sectors namely hevea, oil palm, mango, cotton and cashew. This study, commissioned by the AETS-Afrique consultancy firm, is in the process of being finalized. Regarding the sharing of information on the finalization of lists of targeted producers, the cash transfer programme for producers, and the involvement and participation of stakeholders in all project activities, an advisory committee was set up to monitor and support project activities. Movement restrictions between regions and cities due to COVID-19 delayed social service interventions in the field. The national helpline was unable to always provide timely support to victims of violence referred through calls. To overcome this bottleneck, new and improved software was provided and the staff was trained to use it.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | During the COVID-19 pandemic, the national counterparts' implementation of teleworking was constrained by their lack of technical and material capacity. The provision of appropriate ICT tools and equipment (videoconferencing software, Zoom licenses, etc.) has had a significant positive impact on business continuity, enabling a continued collaboration between the various stakeholders and promoting the coordination of interventions. Due to the dissatisfaction of producers who are still awaiting transfers of resources from the state, field surveys are made difficult even insecure in certain areas (oil palm and rubber especially). Faced with the refusal of response from certain producers and / or cooperatives targeted in certain areas, but dissatisfied, replacements were made but this considerably delayed the investigations.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project team regularly held coordination meetings with national and international partners working in implementing or supporting the Government's COVID-19 response plan. During these discussions, the results obtained were shared with other actors. This sharing of information made it possible to mobilize USD 85,000 from other UN projects, which enabled the acquisition of COVID-19 kits for communities. Thanks to the results achieved during this project, particularly in working with street children, a new, USD 273,000 project with this group of children was developed and launched, allowing the mobilization of new resources to support street children and provide them with other sustainable alternatives.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Using their own funds, UNDP and UNICEF supported by the National Institute of Statistics (INS) and research institutes to measure the socio-economic impact of COVID-19 on the living conditions of households, children, businesses, and informal production units in Côte d'Ivoire. These studies provided valuable, real-time information and reference data for decision makers relative to the first consequences of COVID-19. This allowed to better target interventions and plan national support measures for the affected social and economic sectors.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNODC has provided COVID-19 sanitary materials and products, including 17 sewing machines to set up mask production facilities in prisons for inmates.The penitentiary rehabilitation program has started and is underway in the detention and correction centres of Abidjan, Man and Abengourou (Côte d'Ivoire).

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] : Effective, accountable, and transparent institutions are developed at all levels.
Indicator 1.1 : Number of National Strategic Monitoring Mechanism established, functional and operational | 1 |  | Report
Baseline: 0
Planned Target: 1
Indicator 1.2 : Proportion of population with satisfactory recent experience with public services. | On going | We are still awaiting the report from the Directorate of Prison Administration (DAP), which is still slow to come back to us due to the judicial vacations. | Report DAP
Baseline: 0%
Planned Target: 30%
Output 1.1: A National Strategic Monitoring Mechanism for the monitoring and mitigation of the socio-economic effects of the COVID-19 pandemic is established
Indicator 1.1.1: Number of tools for project implementation monitoring and reporting. | 3 | A result monitoring framework has been developped with support from the two statistical experts assigned to the national coordination mechanisms committee to monitor the progress towards the achievement of the expected results based on performance indicators. Based on this technical expertise provided, three monitoring tools have been developped: i) a national COVID-19 database (https://projectperformancemonitoring.org); ii) a monitoring matrix for development partners' contributions; and iii) a monitoring indicator matrix. | Activity report
Baseline: 0
Planned Target: 2
Indicator 1.1.2: Number of surveys and analyses to monitor and understand the evolution of the impact of the crisis and control its effects. | 2 | UNDP supported the Government to carry out two studies, focuses on the social determinants of the prevalence and accentuation of gender-based violence (GBV) and on the perception of the coronavirus by populations in emergency situations in Côte d'Ivoire. UNDP analyzed 14,000 views on social media and the data helped to put in place stronger response measures, including support to the "PAVIOS" referential centre to increase access to prevention and care services for GBV victims. | Study report
Baseline: 1
Planned Target: 3
Indicator 1.1.3: Number of mappings of multidimensional poverty exacerbated by the COVID-19 pandemic produced. | 1 | Using its own funds, UNDP supported a survey carried out by the National Institute of Statistics (INS) to measure the socio-economic impact of COVID-19 on the living conditions of households, businesses, and informal production units in Côte d'Ivoire. This study became the reference document on how to target support where it is most needed. However, discussions with the World Bank and the INS allowed the continuation of studies on the socio-economic impact of COVID-19. As a result, a partnership has been developped with the World Bank to conduct periodic studies. However, these studies have not yet been scheduled. | Report
Baseline: 0
Planned Target: 3
Output 1.2: Reinforce the crisis management system of the country and strengthen the targeting system for the inclusion of marginalized groups
Indicator 1.2.1: Number of small rubber and palm oil producers identified and profiled, and number of lists developed and reviewed. | 137,056 rubber producers were identified in 24 rubber growing areas, including 101,143 who were rigorously certified and 35,349 in litigation who are currently being verified (plantation and production). Identification is underway at the level of oil palm producers. The lists of beneficiary rubber and palm oil producers were established by their riders as of March 31, 2021. A complaint mechanism has been put in place with FAO's support. | The delay is due to: i) non-effective mobilization of the planned resources; and ii) the long duration of the checklists. Out of 3.5 billion FCFA planned, the AIPH received only 500 million FCFA. Out of 24.980 billion FCFA planned, APROMAC received 6 billion FCFA. | Activity report
Baseline: 0
Planned Target: 160,000 (including at least 50% of women and young people)
Indicator 1.2.2: Number of impact assessment studies developed. | 1 | The impact assessment of cash transfers can begin after the end of cash transfers. Cash transfer operations have not yet started. Despite the 2 extensions of the project, the resources planned for the producers could only be released at a very low level. The rubber and palm oil sectors received CFAF 6 billions and CFAF 500 million respectively, which they spent mainly on the identification of producers. Under these conditions, the audit of resource transfers to producers was no longer relevant. The national stakeholders, the leaders of the sectors, the Prime Minister, the RC and the FAO decided to use the resources of the project for a large assessment study of the impact of COVID 19 on 5 sectors namely hevea, oil palm, mango, cotton and cashew. This study, commissioned by the AETS-Afrique consultancy firm, is in the process of being finalized. The survey and data collection (see study scoping report and data collection note in appendix) reached 400 producers from each of 3 sectors (mango, cashew and cotton), ie 1,200 producers in total and more than 550 actors (state actors, cooperatives and inter-branch organizations, local authorities, processors, exporters, input suppliers) in 13 regions of Ivory Coast. A national workshop is planned for next week to validate the report (4-8 October 2021). | Activity report and study report
Baseline: 0
Planned Target: 1
Output 1.3: Mechanism for monitoring the impact of the measures taken
Indicator 1.3.1: Audit and impact assessment report on transfers to more than 180,000 rubber and palm oil producers available. | 1 | The Advisory Commitee decided to carry up a assessment study of the impact of COVID 19 on 5 sectors namely hevea, oil palm, mango, cotton and cashew .The survey and data collection (see study scoping report and data collection note in appendix) reached 400 producers from each of 3 sectors (mango, cashew and cotton), ie 1,200 producers in total and more than 550 actors (state actors, cooperatives and inter-branch organizations, local authorities, processors, exporters, input suppliers) in 13 regions of Ivory Coast. | Impact reports
Baseline: 0
Planned Target: 1
Indicator 1.3.2: Existence of a database to guide interventions. | 1 | The TORs of the COVID 19 impact study on the 5 sectors, the scoping report as well as the data collection note are available.The impact study reports on the 5 sectors will be validated by the national stakeholders beginning of October. Delays in data collection are reflected in the national stakeholder workshop. | Report
Baseline: 0
Planned Target: 1
Outcome 2[1] : Women, girls, and boys continue to access appropriate protection services during the COVID-19 emergency.
Indicator 2.1: Number of children aged 1 to 17 years old who experienced physical punishment and/or psychological aggression by caregivers in the past month (SDG Indicator 16.2.1), disaggregated by sex. | T= 2313 G= 1635 & B= 678 |  | SIPE, GBVIMS
Baseline: 985
Planned Target: 1,500
Indicator 2.2: Number of women and girls aged 15 years and older who were subject to physical, sexual, or psychological violence by a current or former intimate partner over the past 12 months, by type of violence and by age (SDG Indicator 5.2.1), disaggregated by sex. | 1691 |  | SIPE, GBVIMS, MFFE
Baseline: 1,022
Planned Target: 1,500
Output 2.1: Social services are equipped to ensure the continuity of basic essential services and managed data collection. | 244 |  | Reports from MEPS and MFFE
Indicator 2.1.1: Number of social welfare workers, health workers, and community workers trained on psychosocial first aid, parenting, family skills, and family therapy.
Baseline: 75
Planned Target: 200
| 122 services. Rate of completion: 81%. | There is a high staff turnover and new staffs were not trained on data collection tools. | SIPE, GBVIMS
Indicator 2.1.2: Number of facilities ensuring the regular publication of statistics on violence, including GBV, abuse, and exploitation during the COVID-19 pandemic.
Baseline: 0
Planned Target: 150
| 57000 | With the forms deposited in the maternity services, we were able to register all the new births. | Registry of civil registry services
Indicator 2.1.3: Number of boys and girls registered by the health facilities and declared by the civil registry services during the COVID-19 pandemic.
Baseline: 31,000
Planned Target: 56,370
Output 2.2: The capacities of protection actors and communities, men’s engagement, are strengthened to support the prevention and response to violence including GBV, abuse, exploitation and mistreatment of children related to the situation of confinement, youth and provide support to vulnerable families, identified by local governmental structures and communities.
Indicator 2.2.1: Number of children, parents, and primary caregivers provided with community-based mental health and psychosocial support. | 104304 |  | SIPE, GBVIMS
Baseline: 25,000
Planned Target: 50,000
Indicator 2.2.1.1 : Number of non-governmental organisations and reception centres hosting victims of trafficking provided with hygiene and sanitary and food protection kits | 4 |  | Activity report
Baseline: 00
Planned target: 04
Indicator 2.2.2: Number of community (women and Young) and religeous leaders sensitized on the early detection of victims of trafficking during the pandemic and on barrier measures against the spread of the Covid-19 virus | 350 |  | Activity report
Baseline: 00
Planned Target: 250
Output 2.3: The actors involved in the response to COVID 19 are able to put in place functional mechanisms for dealing with women and children who are victims of violence, abuse and exploitation, and document lessons learns and good practices. | T=4062/F=3318 and M=744 |  | SIPE, GBVIMS
Indicator 2.3.1: Number of cases of violence, abuse, exploitation, and mistreatment reported by families and community actors
Baseline: 1,022
Planned Target: 1,500
Indicator 2.3.2: Number of cases of violence, abuse, exploitation, and mistreatment reported and referred to the relevant services. | 100% | 4,062 cases have been reported and referred to the relevant services. | SIPE, GBVIMS
Baseline: 75%
Planned Target: 100%
Indicator 2.3.3: Number of women-headed households and refugees who benefitted from a material and/or financial assistance. | 1.322 | The reduction of the number of beneficiaries is due to the increase of the amount of household assistance decided by the Government (from FCFA 36,000 to FCFA 75,000). | Reports from MEPS and MFFE
Baseline: 600
Planned Target: 1,500
Output 2.4: Infection prevention and control (IPC) measures in prisons are integrated into/are in line with the public health response to COVID-19 in the community | 3,000, including 264 women and 719 children (672 boys and 47 girls). |  | Report
Indicator 2.4.1: Number of prisoners who benefitted from hygiene kits, disaggregated by sex.
Baseline:0
Planned Target: 3,000
Indicator 2.4.2: Number of girls and women involved in the rehabilitation programme. | On going | The penitentiary rehabilitation program has started and is underway in the remand and correction centres of Abidjan, Man and Abengourou, in Côte d'Ivoire. | Report DAP
Baseline:0
Planned Target: 45

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Sessions de sensibilisation à Port-Bouët et Assouba.
En réponse à la crise de la COVID-19, l´ONUDC distribue des kits sanitaires et alimentaires aux victimes de la traite des personnes en Côte d’Ivoire.
2020-12-10 health and food kits TIPSOM Cote d'Ivoire (unodc.org)
Deux sessions de renforcement de capacités des agents d’application de la loi et des ONGs sur l’identification des victimes de traites et leur prise en charge , 09 au 12 mars 2021, Wafou Hotel Bietry Abidjan.
Produits d'hygiène fournis par ONUDC pour les populations carcérales
Machines à coudre fournies par ONUDC pour les atelier de rehabilitation et de production de caches-reutilisable
Désinfectants et accessoires de couture pour la production de caches-nez reutilisable dans les maisons d'arrêt et de correction