## Consolidated (E)
ANNUAL WORK PLAN 2009 UN-GOV Joint Programme on Gender Equality | [11 empty] | Period: April 2009 - December 2009
National Implementing Partners: Ministry of Labour, Invalids and Social Affairs; Ministry of Culture, Sports and Tourism and General Statistics Office
UN participating Agencies: UNIFEM, UNFPA, UNDP, ILO, UNESCO, UNIDO, IOM, FAO, UNODC, WHO, UNICEF, UNAIDs
Programme code and NIPs IDs: VNM7G31A - VNM7G31A/VNM0012; VNM7G31A/VNM0014; VNM7G31A/VNM0015
OUTCOME: JP Outcome 1 Improved skills, knowledge and practices for the implementation, monitoring, evaluation and reporting of the Law on Gender Equality and Law on Domestic Violence Prevention and Control. JP Outcome 2. Enhanced partnerships and coordination around gender equality within and outside of government JP Outcome 3 Strengthened evidence-based data and data systems for promoting gender equality.
UN Organization Specific Annual Targets | UN Organization | Key Activities/ Annual Targets | Time Frame (2009) |  |  |  | Responsible Parties (name of NIP/CIPs, other National Partners including Sub-contractor, if any) |  |  |  | Program Budget (US$)
|  |  | Q1 | Q2 | Q3 | Q4 | Component Project/NIP | National Agencies | UN Agencies | MDT-F categories | National Implementation | UN Implementation | Total | UNFPA categories and Activities in Atlas
Output 1.1 Capacity assessed of the SMAs, line ministries, National Assembly, Communist Party, mass organizations including the Vietnam Women's Union and concerned agencies at the local level to implement, monitor, evaluate and report on the two Laws. Output 1.1 Indicators: SMAs (MOLISA and MOSCT) and key stakeholders have a realistic understanding and TOR for their role and capacity for the implementation, monitoring and reporting on the laws. Clear Assessment of strengths, weaknesses and needs concerning the two laws. Annual Targets: + Enhanced the capacity of Government agencies and relevant civil society in the implementation, monitoring evaluation and reporting of the two laws.(1.1.1) + Defined government agencies the capacity levels and desired capacities to implement the two laws (1.1.1)
| UNIFEM | Activity 1.1.1 - Capacity assessments for the SMAs of the two laws, CP, NA and other concerned agencies and line ministries to implement the GEL and the DVL. |  | X | X |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM | CONTRACT | 40950 | 72450 | 113400 | ACTIVITY 07
| UNFPA | Activity 1.1.1 - Capacity assessments for the SMAs of the two laws, CP, NA and other concerned agencies and line ministries to implement the GEL and the DVL. |  | X | X |  | MOLISA | MOLISA CP, NA line ministries and concerned local agencies | UNFPA | TRAINING OF counterpart | 6000 | 8388 | 14388 | ACTIVITY 04 PERSON, OPEX, MISC
|  | SUB-TOTAL OUTPUT 1.1 | [8 empty] | 46950 | 80838 | 127788
Output 1.2 : Relevant plans of action developed for the SMAs (MOLISA & MOCST), line ministries, National Assembly, Communist Party at the central and local levels to implement, evaluate, monitor and report on the two Laws. Output 1.2 Indicators: - Availability of relevant POAs, - Availability of M&E Framework for the two laws Annual Targets: + Defined strategies of development and plans of actions to implement the two laws (1.2.1) + Multiagency collaboration mechanism developed, finalized and approved (1.2.2). + Outline of the M&E Framework for measuring the implementation of the GEL law developed (1.2.3) + Outline of the M&E Framework for measuring the implementation of the DVP law developed (1.2.3)
| UNIFEM | Activity 1.2.1 - Support to the SMAs, CP, NA, VWU and concerned agencies in selected provinces to develop relevant POAs for implementation, evaluation, monitoring and reporting on the two laws |  |  | X | X | MOLISA | MOLISA , Communist Party, NA, line ministries and concerned local agencies | UNIFEM | CONTRACT | 75600 | 47985 | 123585 | ACTIVITY 07
| UNFPA | Activity 1.2.1 - Support to the SMAs, CP, NA, VWU and concerned agencies in selected provinces to develop relevant POAs for implementation, evaluation, monitoring and reporting on the two laws |  | X | X | X | MOLISA | MOLISA, MOCST, Communist Party, National Assembly, line ministries and concerned local agencies | UNFPA | TRAINING of counterpart | 17060 | 1525 | 18585 | ACTIVITY 04
| UNFPA | Activity 1.2.2 - MOCST to develop multi-agency collaboration mechanisms for the prevention of DV. |  |  | X | X | MOCST | MOCST | UNFPA | CONTRACT | 12810 | 7185 | 19995 | ACTIVITY 08
| UNDP | Activity 1.2.3. (a): MOLISA, NA, line ministries and other duty bearers to develop and sustain M&E framework (MEF) in government system for measuring the implementation of the GEL |  | X | X | X | MOLISA | MOLISA Collaborating agencies: GSO, NA, line ministries | UNDP | CONTRACTS | 20000 | 40000 | 60000 | ACTIVITY 07
| UNDP | Activity 1.2.3 (b) - MOCST, National Assembly, line ministries and other duty bearers to develop and sustain M&E framework for measuring the implementation of the DVL |  | X | X | X | MOCST | - MOCST - Other national partners: PCSA (NA), line ministries and other related agencies | - UNDP | CONTRACT | 37000 | 40000 | 77000 | ACTIVITY 08
|  | SUB-TOTAL OUTPUT 1.2 | [8 empty] | 162470 | 136695 | 299165
Output 1.3 Technical assistance provided to improve capacity of the SMAs, line ministries, NA, CP to implement, evaluate, monitor and report on the two laws. Output 1.3 Indicators: - Availability of tools and information for gender analysis across sectors - GE and DV laws integrated into Annual Work Plans and PoAs of key line ministries and - Relevant plans of action disseminated to all institutions and levels of implementation; Annual Targets: +Training materials for DVP are reviewed, adjusted or developed (if needed) and used for training for concerned staff of relevant agencies at central and lower levels (1.3.2 and 1.3.3). + Developed skills among Women Parliamentarian Group to oversight the two laws (1.3.5) + Training organized for officers from GSO and MARD (1.3.6) + (number of) national programmes reviewed and done gender analysis for recommending how gender should be integrated (1.3.7) + Training needs assessment identified and training materials on gender mainstreaming finalized (1.3.7) + (number of) officers at different levels on gender mainstreaming trained. (1.3.7) + Research on the working conditions of women workers in industrial parks & export-processing zones conducted (1.3. 9.a) + Research on the access to employment and economic opportunities available to women and men conducted (1.3.9.b) + Research on specific working conditions of women in domestic and informal economy conducted (1.3.9.c) '+ Regulatory documents relating to law enforcement and justice sector for the implementation of the law of Domestic Violence Prevention and Control developed, finalized and approved for use (1.3.10 and 1.3.11). + Training materials on law enforcement and justice sector officers developed, finalized and used for training of these two sectors (1.3.12) + Development of training and learning materials on gender mainstreaming (GE) in education (1.3.14) + Two training workshops on GE for educational officials held. (1.3.14) + Preparation and finalization of implementation plan (1.3.15) + Consultation workshop on methodology on textbook review from gender's perspective (1.3.15) + Review textbook (1.3.15)
| UNFPA | Activity 1.3.2 (a) - Develop training materials on the GEL to make them available to the MOLISA, line ministries, CP and other duty bearers for better implementation of the law. |  | X | X | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA | CONTRACTS | 6000 | 4000 | 10000 | ACTIVITY 07
| UNFPA | Activity 1.3.2 (b) - Development of training materials on the DVL to make them available to MOCST, line ministries, CP and other duty bearers for better implementation of the law. |  | X | X | X | MOCST | - MOCST and key line ministries and agencies (Social Faculty of Institute of Labour, Invalid & Social Affairs). - Central Party Committee for Education and Popularization; PCSA will be consulted | UNFPA, UNAIDS | CONTRACT | 9400 | 4000 | 13400 | ACTIVITY 08
| UNFPA | Activity 1.3.3 (a) - Support training of staff of MOLISA, CP and branches on the GEL at central and provincial levels including key cities. |  |  |  | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA | TRAINING OF COUNTERPARTS | 20000 | 4774 | 24774 | ACTIVITY 07
| UNFPA | Activity 1.3.3 (b) - Support training of MOCST, CP and branches on the DVL in selected provinces. |  |  | X | X | MOCST | - MOCST; - Officials under line of Central Party Committee for Education and Popularization at provincial and grassroots levels - Elected deputies at provincial levels | UNFPA | TRAINING of counterparts | 46330 | 4774 | 51104 | ACTIVITY 05 Workshops, seminar, meetings
| UNICEF | Activity 1.3.4 - Develop training package and training of selected NA's Deputies and Members of Provincial People's Councils on the two Laws, and international treaties and standards relating to GE and children's rights to strengthen the capacity of Elected Officials for carrying out their law making and oversight functions. |  | X | X |  | MOLISA | NA Committee for Culture, Education, Youth and Children, Human Resource Institute/ HCM Academy | UNICEF | CONTRACT | 11250 | 2799 | 14049 | ACTIVITY 07
| UNIFEM | Activity 1.3.5 - Training and capacity assistance to NA in developing skills of the Women Parliamentarian Group to oversight of the two laws |  |  | X | X | MOLISA | MOLISA, NA , MOCST | UNIFEM | TRAINING OF counterparts | 7350 | 5568 | 12918 | ACTIVITY 07
| FAO | Activity 1.3.6 - Training of GSO and MARD staff responsible for gender and sex-disaggregated data collection and analysis |  |  |  | X | GSO | GSO, MARD, Collaborating agencies: MOLISA, MOCST | FAO | TRAINING | 0 | 14019 | 14019 | ACTIVITY 06 PERSON, OPEX, MICS
| UNFPA | Activity 1.3.6 - Training of GSO and MARD staff responsible for gender and sex-disaggregated data collection and analysis |  |  |  | X | GSO | GSO, MARD, Collaborating agencies: MOLISA, MOCST | UNFPA | TRAINING of counterpart | 8900 | 6988 | 15888 | ACTIVITY 06 PERSON, OPEX, MICS
| ILO | Activity 1.3.7 - MOLISA to mainstream gender into labour and employment policies, national programmes, including translation, adaptation and adoption of gender mainstreaming and auditing tools as related to the GEL |  | X | X | X | MOLISA | MOLISA | ILO | CONTRACTS | 23100 | 30450 | 53550 | ACTIVITY 07
| ILO | Activity 1.3.9 - Provide TA for 3 researches on working conditions of vulnerable rural women living in poverty. These researches are linked with activities 3.3.5 |  |  | X | X | MOLISA | MOLISA | ILO |  | 17850 | 23100 | 40950
| WHO | Activity 1.3.10 - MOH to develop sub-law and regulatory documents necessary for implementation of DVL and GEL |  | X | X | X | MOCST |  | - WHO, UNFPA - Sub-contractor: MOH | CONTRACT | 0 | 40000 | 40000
| UNFPA | Activity 1.3.10 - MOH to develop sub-law and regulatory documents necessary for implementation of DVL and GEL |  |  | X | X |  |  | UNFPA | CONTRACT |  | 6000 | 6000 | ACTIVITY 08 PERSON, OPEX, MISC
| UNODC | Activity 1.3.11 - MOJ and MPS to develop regulatory documents necessary for the implementation of the Law on Domestic Violence Prevention and Control |  | X | X |  | MOCST |  | - UNODC - Sub-contractors: MPS, MOJ | TRAINING of counterparts |  | 24570 | 24570
| UNODC | Activity 1.3.12 - MOJ and MPS to develop training materials on DV and to pilot these trainings for law enforcement and justice sector officers. |  | X | X | X | MOCST |  | - UNODC, - Sub-contractors: MPS, MOJ. | TRAINING of counterpart |  | 134835 | 134835 | ACTIVITY 05
| UNESCO | Activity 1.3.13 - Capacity-building of MOIC on gender mainstreaming in communication at central and provincial levels |  | X | X | X | MOLISA | MOIC | UNESCO | CONTRACTS | 10000 | 13500 | 23500 | ACTIVITY 07
| UNESCO | Activity 1.3.14: Capacity-building of MOET on gender mainstreaming in education at central and provincial levels |  | X | X | X | MOLISA | MOET | UNESCO | CONTRACT | 10000 | 12020 | 22020 | ACTIVITY 07
| UNESCO | Activity 1.3.15 - National textbook review and analysis from gender perspective, including piloting teacher-training programmes to incorporate GE issues in line with the two laws. |  | X | X | X | MOLISA | MOET | UNESCO | CONTRACT | 15000 | 42620 | 57620 | ACTIVITY 07
|  | SUB-TOTAL OUTPUT 1.3 | [8 empty] | 185180 | 374017 | 559197
Output 2.1 Networks on gender equality are strengthened and sustained through relevant government and outside of government systems, with effective linkages and information among stakeholder Output 2.1 Indicators: - Gender Partnership group and functions effectively - GEMCOMNET and GAP bring GE issues to attention of policy makers. -Gender Equality issues are fed into National Policy dialogues Annual Targets: + National Level Forum made up of representatives of the three sub-networks ( government and public organizations, agencies engaged in gender equality work, media professionals) (2.1.1) (2.1.2) + Network of DV victims set up (2.1.4) + Gencomnet bring GE issues to attention of policy makers (2.1.3).
| UNIFEM | Activity 2.1.1 - Develop and sustain semi-annual forums on GE to feed into policy dialogues and the CG meetings. |  |  | X | X | MOLISA | MOLISA, MOCST, GSO | UNIFEM | TRAINING of counterparts | 21000 | 10151 | 31151 | ACTIVITY 04
| UNIFEM | Activity 2.1.2 - Provide TA to selected NGOs of Gencomnet to expand their network and host consultation meetings on the two laws with SMAs, Government, civil society groups, NGOs and concerned agencies |  |  | X | X | MOLISA | Select NGOs from Gencomnet Network , MOLISA, MOCST, concerned agencies | UNIFEM | TRAINING of counterpart | 0 | 18900 | 18900 | ACTIVITY 04
| UNIFEM | Activity 2.1.3 - NCFAW and MOLISA to strengthen GAP |  | X | X | X | MOLISA | NCFAW & MOLISA | UNIFEM | TRAINING of counterpart | 7184 | 840 | 8024 | ACTIVITY 04
| IOM | Activity 2.1.4 - Enhance the capability of grass-roots support groups for victims of DV and advocate directly at the provincial and national level for improved policies and intervention programme |  | X | X | X | MOCST | CWD/VWU | IOM | TRAINING of counterpart | 8411 | 935 | 9346 | ACTIVITY 05 Workshops, seminar, meetings
|  | SUB-TOTAL OUTPUT 2.1 | [8 empty] | 36595 | 30826 | 67421
Output 2.2: Improved partnership between mass organizations and government agencies to promote women's economic empowerment. Output 2.2 Indicators: - Network around women entrepreneurship at both grass-roots and national levels strengthened. -Tools and reference material for women entrepreneurship promotion and economic empowerment implemented by entrepreneurs and policy makers, especially VCCI, MOLISA and VWU. Annual Targets: + Practical policy recommendation for the implementation of GE Law and revised SME Decree 90 provided, focusing on women's economic empowerment and entrepreneurship development.(2.2.1) +The policy dialogue between the business sector, represented by VCCI, and policy makers enhanced for the promotion of women entrepreneurship. (2.2.1) +Experience sharing of grass-roots good practices of women entrepreneurship development promoted at both national and provincial levels through workshops and development of methodology.(2.2.2)
| UNIDO | Activity 2.2.1 - Facilitate enhanced partnership between VCCI, government agencies, and other political and civil society actors to develop mechanisms for promoting women's entrepreneurship in line with the GEL |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO | TRAINING /CONTRACT/PERSONNEL/OTHER DIRECT COSTS | 0 | 77280 | 77280 | ACTIVITY 04
| ILO | Activity 2.2.1 - Facilitate enhanced partnership between VCCI, government agencies, and other political and civil society actors to develop mechanisms for promoting women's entrepreneurship in line with the GEL |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO | CONTRACT | 0 | 26460 | 26460 | ACTIVITY 07
| UNIDO | Activity 2.2.2. - Support women's entrepreneurship and networking at the grass-roots level and their advocacy efforts aimed at mass organizations and government agencies working on economic empowerment policies for women. |  |  |  | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO | TRAINING/PERSONNEL/OTHERDIRECT COSTS |  | 26033 | 26033
| ILO | Activity 2.2.2. Support women's entrepreneurship and networking at the grass-roots level and their advocacy efforts aimed at mass organizations and government agencies working on economic empowerment policies for women. |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO | CONTRACT | 0 | 18953 | 18953 | ACTIVITY 07
|  | SUB-TOTAL OUTPUT 2.2 | [8 empty] | 0 | 148726 | 148726
Output 2.3 Communication network on gender equality developed for mass dissemination of two laws Output 2.3 Indicators: -Communication network on GE in existence. -Increase in press coverage on the 2 laws. Annual targets: + One press conference organized (2.3.1) + Contents of two laws are regular disseminated through key mass media agencies (2.3.2) +Relevant mass-media agencies for network building identified (2.3.3) + Training courses materials reviewed for mass media staff (2.3.3)
| UNFPA | Activity 2.3.1 - Facilitate semi-annual press conferences |  | X |  | X | MOLISA | MOLISA, MOCST | UNFPA | TRAINING of counterpart | 1000 | 544 | 1544 | ACTIVITY 04
| UNFPA | Activity 2.3.2 - Facilitate the dissemination of the laws through mass media (special columns of key magazines, newspapers, national TV coverage, VOV, etc. |  | X | X | X | MOCST |  | - UNFPA. - Sub-contractors: Key mass media agencies.. | CONTRACT | 0 | 7904 | 7904 | ACTIVITY 08
| UNFPA | Activity 2.3.3 - Development of national network of media practitioners reporting on GE issues, including providing training on the content of the two laws and support for development of the Communication on the GEL |  |  | X | X | MOLISA | MOLISA and related agencies | UNFPA | CONTRACTS | 15000 | 6266 | 21266 | ACTIVITY 07
|  | SUB-TOTAL OUTPUT 2.3 | [8 empty] | 16000 | 14714 | 30714
Output 3.1. Current gender equality and sex-disaggregated indicators are reviewed and new indicators identified through research. Output 3.1 Indicators: - Increase in number and quality of gender equality and sex-disaggregated indicators. - Three indexes (GDI, GEM, GGI) calculated (3.1.1) Annual targets: + Questionnaire developed, sample defined, and interviewers trained (3.1.2)
| UNDP | 3.1.1 GSO to calculate the Gender related Development Index (GDI), the gender empowerment measure (GEM), and the World Economic Forum's Gender Gap Index - a mix of qualitative and quantitative data to enable the preparation of periodic reports on the status of men and women in Vietnam and to provide accurate gender analysis as required. |  | X | X | X | GSO | GSO | UNDP | CONTRACTS | 14000 | 30000 | 44000 | ACTIVITY 09
| WHO | 3.1.2 GSO and MOH to conduct a national survey on women's health and domestic violence. |  | X | X | X | GSO | GSO Collaborating agencies: MOH, MOCST, other concerned agencies and research institute | WHO | CONTRACTS | 93346 | 72250 | 165596 | ACTIVITY 09
|  | SUB-TOTAL OUTPUT 3.1 | [8 empty] | 107346 | 102250 | 209596
Output 3.2: Gender equality and sex-disaggregated indicators are integrated into ongoing national data collection processes and reporting. Output 3.2 Indicators: National surveys incorporate GE and sex-disaggregated indicators Annual targets : + Current surveys and concerning capacity of GSO reviewed & assesses, integrating gender issues into the labour force survey planned (3.2.1) + TA in engender national censuses and surveys on rural issues is provided to GSO (3.2.2) + Current surveys and concerning capacity of GSO reviewed & assesses; integrating gender issues into the enterprise survey planned (3.2.3) + Stakeholders' awareness of child and gender indicators improved (3.2.4)
| ILO | 3.2.1 Provide TA to engender the labor force survey |  |  | X | X | GSO | GSO Collaborating agencies: MOLISA | ILO | CONTRACTS | 5250 | 8137.5 | 13387.5 | ACTIVITY 09 PERSON, OPEX, MISC
| FAO | 3.2.2 Provide TA to engender national censuses and surveys on rural issues |  |  | X | X | GSO | GSO, Collaborating agency: MARD | FAO | CONTRACTS | 0 | 28037 | 28037 | ACTIVITY 09 PERSON, OPEX, MISC
| ILO | 3.2.3 Provide TA to engender the annual enterprise survey |  |  | X | X | GSO | GSO Collaborating agencies: VCCI | ILO | CONTRACTS | 5775 | 8925 | 14700 | ACTIVITY 09 PERSON, OPEX, MISC
| UNICEF | 3.2.4 Compile data on children and gender equality for reporting on national and international commitments, through existing national household surveys |  | X | X |  | GSO | MOLISA | UNICEF | TRAINING of counterpart | 22100 | 0 | 22100 | ACTIVITY O6 PERSON, OPEX, MISC
|  | SUB-TOTAL OUTPUT 3.2 | [8 empty] | 33125 | 45099.5 | 78224.5
Output 3.3 Data and information collected to promote national gender equality policy dialogues for marginalized groups. Output 3.3 Indicators: - Data concerning marginalized women is collected. - Policy reports/papers cite data on marginalized women. Annual targets: + Currently available data stock-taken and reviewed, and new data and information collected (3.3.1) + Research Plan developed; Existing Data collected; National and International consultants recruited (3.3.2) + Local and international consultants recruited; Research Plans developed; Data collected (3.3.3) + National and international consultants recruited. (2) Research Plan developed. (3) Data reviewed and Research Work started up (3.3.4) + Three researches conducted to identify findings for policy recommendation to develop appropriate polices for promoting gender equality for such vulnerable women groups (which is linked with activity 1.3.9) (3.3.5)
| UNDP | Activity 3.3.1 Provide TA for research and policy dialogues on ethnic minority women's access to legal services. |  | X | X | X | MOLISA | MOLISA & NCFAW Collaborating agencies: GSO | UNDP | CONTRACTS | 19000 | 15000 | 34000 | ACTIVITY 07
| IOM | Activity 3.3.2 - Assess incidence of trafficking in boys and girls to provide data to ensure adequate attention is paid to the trafficking of boys. It is used for advocacy for anti trafficking policies |  |  | X | X | GSO | Selected NGOs Collaborating agencies: GSO | IOM | CONTRACTS | 9813 | 2804 | 12617 | ACTIVITY 09 Will start in Q3/2009 and continue in 2010.
| IOM | Activity 3.3.3 - Research on remittances from migrant workers in gender perspective including a costing of remittances and pilot interventions to better inform duty-bearers charged with developing appropriate degrees and policies related to the two laws. |  | X | X | X | GSO | Selected research institute Collaborating agencies: GSO | IOM | CONTRACTS | 5140 | 2804 | 7944 | ACTIVITY 09 Will start in Q2/2009 and continue in 2010.
| IOM | Activity 3.3.4 - Research on the situation of sex workers in Vietnam and policy gaps, with a view to bring gender discrimination to attention of policy-makers in supporting the implementation of the laws. |  |  | X |  | MOLISA | MOLISA Collaborating agencies: selected NGOs | IOM | CONTRACT | 6542 | 2805 | 9347 | ACTIVITY 07
|  | SUB-TOTAL OUTPUT 3.3 | [8 empty] | 40495 | 23413 | 63908
Output 3.4: Centralized clearinghouse of gender research reports and indicators by government, donors and political and civil society groups (VWU) established (through GSO). Output 3.4 Indicators: - A centralized system for gender research reports and data available; - Annual sex-disaggregated statistics document developed and disseminated Annual targets : + Availability of CRC/CEDAW database (3.4.3)
| UNICEF | 3.4.3 Build a database on the International Convention of Children’s Rights, CEDAW and "a World appropriate for Children” using Viet info technology |  |  | X | X | GSO | GSO Collaborating agencies: MOLISA | UNICEF | CONTRACTS | 5000 |  | 5000 | ACTIVITY 09 To be continued in Y2
|  | SUB-TOTAL OUTPUT 3.4 | [8 empty] | 5000 | 0 | 5000
| UNFPA | Support for PMU (MOLISA) |  | X | X | X | MOLISA |  |  |  | 27175 | 58909 | 86084
| UNFPA | Support for CPMU (MOCST) |  | X | X | X | MOCST |  |  |  | 16330 | 23378 | 39708
| UNFPA | Support for CPMU (GSO) |  | X | X | X | GSO |  |  |  | 19045 | 29438 | 48483
|  | SUB-TOTAL FOR JP MANAGEMENT | [8 empty] | 62550 | 111725 | 174275
|  | PROGRAMME COST | [8 empty] | 695711 | 1068303.5 | 1764014.5
|  | INDIRECT SUPPORT COSTS (7%) | [8 empty] | 48699.77 | 74781.245 | 123481.015
|  | TOTAL PLANNED BUDGET | [8 empty] | 744410.77 | 1143084.745 | 1887495.515
[11 empty] | Total Programme Budget |  | Indirect Support Cost | Total Planned Budget
[11 empty] | National Implementation | UN Implementation
|  | Total for UNIFEM Implementation | [8 empty] | 0 | 155894 | 10912.58 | 166806.58
|  | Total for UNDP Implementation | [8 empty] | 0 | 125000 | 8750 | 133750
|  | Total for ILO Implementation | [8 empty] | 0 | 116026.5 | 8121.855 | 124148.355
|  | Total for UNESCO implementation | [8 empty] | 0 | 68140 | 4769.8 | 72909.8
|  | Total for UNICEF Implementation | [8 empty] | 0 | 2799 | 195.93 | 2994.93
|  | Total for UNIDO Implementation | [8 empty] | 0 | 103313 | 7231.91 | 110544.91
|  | Total for IOM Implementation | [8 empty] | 0 | 9348 | 654.36 | 10002.36
|  | Total for FAO Implementation | [8 empty] | 0 | 42056 | 2943.92 | 44999.92
|  | Total for WHO Implementation | [8 empty] | 0 | 112250 | 7857.5 | 120107.5
|  | Total for UNODC Implementation | [8 empty] | 0 | 159405 | 11158.35 | 170563.35
|  | Total for UNFPA Implementation (a) | [8 empty] | 0 | 174073 | 12185.11 | 186258.11
|  | Total for national implementation - fund received via UNFPA as MA (b) | [8 empty] | 695711 | 0 | 48699.77 | 744410.77
|  | Total fund received by UNFPA (a+b) | [8 empty] | 695711 | 174073 | 60884.88 | 930668.88
|  | GRAND TOTAL FOR 2009 | [8 empty] | 695711 | 1068304.5 | 184365.965 | 1887496.585
Signatures
| Co-Chair of the National Steering Committee | [9 empty] | Co-Chair of the National Steering Committee
| John Hendra | [9 empty] | Nguyen Thanh Hoa
| UN Resident Coordinator United Nations Viet Nam | [9 empty] | Vice Minister, Ministry of Labour, Invalids and Social Affairs
| Date______________________ | [9 empty] | Date: _______________________
Note on J19: Nguyen Thi Thuy: UNDP transfer money to MOCST only
Note on K15: Nguyen Thi Thuy: Thuy took out the 'TRAINING" as most activities are close to "CONTRACT"
Note on K41: Nguyen Thi Thuy: Thuy took out "Contract" as most activities are close to "Training, workshop & seminar"
Note on K43: Nguyen Thi Thuy: Thuy took out the 'Contract' as key activity is 'Training"
Note on K59: Nguyen Thi Thuy: WHO leaved 2 categories in Annex 3 (B) vs. AWP. But it's closed to 'Contract'
Note on L17: Chau: Not including 7%
Note on M17: Chau: Not including 7%
Note on M54: Nguyen Thi Thuy: 25,000 for entire cycle
Note on O32: Nguyen Thi Thuy: dealing with 2 law

## MOLISA (E)
ANNUAL WORK PLAN 2009 UN-GOV Joint Programme on Gender Equality | [11 empty] | Period: April 2009 - December 2009
National Implementing Partner: Ministry of Labour, Invalids and Social Affairs
UN participating Agencies: UNIFEM, UNFPA, UNDP, ILO, UNESCO, UNIDO, IOM, FAO
Programme Code and NIP's ID: VNM 7G31A/VNM0012
OUTCOME: JP Outcome 1 Improved skills, knowledge and practices for the implementation, monitoring, evaluation and reporting of the Law on Gender Equality and Law on Domestic Violence Prevention and Control. JP outcome 2. Enhanced partnerships and coordination around gender equality within and outside of government JP Outcome 3 Strengthened evidence-based data and data systems for promoting gender equality.
UN Organization Specific Annual Targets | UN Organization | Key Activities/ Annual Targets | Time Frame (2009) |  |  |  | Responsible Parties (name of NIP/CIPs, other National Partners including Sub-contractor, if any) |  |  |  | Programme Budget (US$)
|  |  | Q1 | Q2 | Q3 | Q4 | Component Project/NIP | National Agencies | UN Agencies | MDT-F categories | National Implementation | UN Implementation | Total | UNFPA categories and Activities in Atlas
Output 1.1: Capacity assessed of the SMAs, line ministries, National Assembly, Communist Party, mass organizations including the Vietnam Women's Union and concerned agencies at the local level to implement, monitor, evaluate and report on the two Laws. Output 1.1 Indicators: - SMAs (MOLISA and MOSCT) and key stakeholders have a realistic understanding and TOR for their role and capacity for the implementation, monitoring and reporting on the laws; - Clear Assessment of strengths, weaknesses and needs concerning the two laws. Annual Targets: + Enhanced the capacity of Government agencies and relevant civil society in the implementation, monitoring evaluation and reporting of the two laws.(1.1.1) + Defined government agencies the capacity levels and desired capacities to implement the two laws (1.1.1)
| UNIFEM | Activity 1.1.1 - Capacity assessments for the SMAs of the two laws, CP, NA and other concerned agencies and line ministries to implement the GEL and the DVL. |  | X | X |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM | CONTRACT | 40950 | 72450 | 113400 | ACTIVITY 07
|  | 1.1.1.1 - Develop ToR for international and national gender capacity specialist |  | X |  |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.1.1.2 - Recruitment of international and national specialists |  | X |  |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | OPEX , MISC
|  | 1.1.1.3 - Initial Meeting with all the parties involved in the Capacity Assessment - Clarify objectives and expectations |  | X |  |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.1.1.4 - Design the methodology for the Capacity Assessment - Adapt Capacity Assessment Framework to local needs - Determine how the assessment will be conducted (team, location: 6 provinces in all the country). |  | X |  |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.1.1.5 - Conduct the Capacity Assessment - Define desired capacities and capacity levels - Articulate questions to understand existing capacity asses - Asses capacity level |  | X | X |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.1.1.6 - Summarize and Interpret Results - Define capacity development strategies |  |  | X |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.1.1.7 - Produce and disseminate surveys reports. |  |  | X |  | MOLISA | MOLISA and MOCST, Communist Party, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | MISC
| UNFPA | 1.1.1.8 - Organize orientation workshop on JP on Gender with related agencies |  | X |  |  | MOLISA | MOLISA CP, NA line ministries and concerned local agencies | UNFPA | TRAINING OF COUNTERPARTS | 6000 | 8388 | 14388 | ACTIVITY 04 PERSON, OPEX, MISC
|  | 1.1.1.9 - Organize workshop to disseminate survey findings |  |  | X |  | MOLISA | MOLISA CP, NA line ministries and concerned local agencies | UNFPA | TRAINING OF COUNTERPARTS |  |  |  | PERSON, OPEX, MISC
|  | TA from UN agencies |  |  | X |  | MOLISA |  | UNFPA |  |  |  |  | PERSON, OPEX, MISC
Output 1.2 : Relevant plans of action developed for the SMAs (MOLISA & MOCST), line ministries, National Assembly, Communist Party at the central and local levels to implement, evaluate, monitor and report on the two Laws. Output 1.2 Indicators: - Availability of relevant POAs; - Availability of M&E Framework for the two laws Annual Targets: + Defined strategies of development and plans of actions to implement the two laws (1.2.1) + Outline of the M&E Framework for measuring the implementation of the GEL developed (1.2.3)
| UNIFEM | Activity 1.2.1 - Support to the SMAs, CP, NA, VWU and concerned agencies in selected provinces to develop relevant POAs for implementation, evaluation, monitoring and reporting on the two laws |  |  | X | X | MOLISA | MOLISA , Communist Party, NA, line ministries and concerned local agencies | UNIFEM | CONTRACT | 75600 | 47985 | 123585 | ACTIVITY 07
|  | 1.2.1.1 - Recruitment of the local and international consultants |  |  | X | X | MOLISA | MOLISA , CP, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON
|  | 1.2.1.2 - Working sessions with all the participants in the assessment |  |  | X |  | MOLISA | MOLISA , CP, NA, line ministries and selected provinces | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.2.1.3 - Develop Plans of action Monitoring and Evaluation of the current POA (MOSCT) |  |  |  | X | MOLISA | MOLISA , CP, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.2.1.4 - Final workshop to disseminate the strategy/plans of action |  |  | X | X | MOLISA | MOLISA , CP, NA, line ministries and selected provinces | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 1.2.1.5 - Creation a Guideline- Plans of actions and distribution |  |  |  | X | MOLISA | MOLISA , CP, NA, line ministries and concerned local agencies | UNIFEM |  |  |  |  | MISC
| UNFPA | Activity 1.2.1: |  | X | X | X | MOLISA | MOLISA, MOCST, Communist Party, National Assembly, line ministries and concerned local agencies | UNFPA | TRAINING of counterpart | 17060 | 1525 | 18585 | ACTIVITY 04
|  | 1.2.1.6 - Organize consultation workshops with key ministries and related agencies on POA (initiate to develop POA) |  | X |  |  | MOLISA | MOLISA, MOCST, Communist Party, National Assembly, line ministries and concerned local agencies | UNFPA |  |  |  |  | PERSON, OPEX, MISC
|  | 1.2.1.7 - Develop POA |  | X |  |  | MOLISA | MOLISA, MOCST, Communist Party, National Assembly, line ministries and concerned local agencies | UNFPA |  |  |  |  | PERSON, OPEX, MISC
|  | 1.2.1.8: - Organize workshop to disseminate finalized POA |  |  | X |  | MOLISA | MOLISA, MOCST, Communist Party, National Assembly, line ministries and concerned local agencies | UNFPA |  |  |  |  | PERSON, OPEX, MISC
|  | 1.2.1.9 - Support some ministries, line ministries and local agencies to develop POA |  |  |  | X | MOLISA | MOLISA, MOCST, Communist Party, National Assembly, line ministries and concerned local agencies | UNFPA |  |  |  |  | PERSON, OPEX, MISC
|  | TA from UN agencies |  |  |  |  | MOLISA
| UNDP | Activity 1.2.3. (a): MOLISA, NA, line ministries and other duty bearers to develop and sustain M&E framework (MEF) in government system for measuring the implementation of the GEL |  | X | X | X | MOLISA | MOLISA Collaborating agencies: GSO, NA, line ministries | UNDP | CONTRACTS | 20000 | 40000 | 60000 | ACTIVITY 07
|  | 1.2.3.1 - Study tour to another country where MEF exists |  | X |  |  |  | MOLISA Collaborating agencies: GSO, NA, line ministries | UNDP |  |  | 30000 | 30000 | PERSON, OPEX, MISC
|  | 1.2.3.2 - Defining needs and indicators through a consultative and participatory process with technical assistance from GSO |  | X | X |  |  | MOLISA Collaborating agencies: GSO, NA, line ministries | UNDP |  | 10000 |  | 10000 | PERSON, OPEX, MISC
|  | 1.2.3.3 - Developing the Monitoring and Evaluation framework by national and international consultants |  |  | X | X |  | MOLISA Collaborating agencies: GSO, NA, line ministries | UNDP |  | 10000 | 10000 | 20000 | PERSON, OPEX, MISC
Output 1.3 Technical assistance provided to improve capacity of the SMAs, line ministries, NA, CP to implement, evaluate, monitor and report on the two laws. Output 1.3 Indicators: Availability of tools and information for gender analysis across sectors. Annual Targets: + Developed skills among Women Parliamentarian Group to oversight the two laws (1.3.5) + (number of) xxx national programmes reviewed and done gender analysis for recommending how gender should be integrated (1.3.7) + Training needs assessment identified and training materials on gender mainstreaming finalized (1.3.7) + (number of) xxx officers at different levels on gender mainstreaming trained. (1.3.7) + Research on the working conditions of women workers in industrial parks & export-processing zones conducted (1.3. 9.a) + Research on the access to employment and economic opportunities available to women and men conducted (1.3.9.b) + Research on specific working conditions of women in domestic and informal economy conducted (1.3.9.c) + Development of training and learning materials on gender mainstreaming (GE) in education (1.3.14) + Two training workshops on GE for educational officials held. (1.3.14) + Preparation and finalization of implementation plan (1.3.15) + Consultation workshop on methodology on textbook review from gender's perspective (1.3.15) + Review textbook (1.3.15)
| UNFPA | Activity 1.3.2 (a) - Develop training materials on the GEL to make them available to the MOLISA, line ministries, CP and other duty bearers for better implementation of the law. |  | X | X | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA | CONTRACTS | 6000 | 4000 | 10000 | ACTIVITY 07
|  | 1.3.2.1 - Compile and review existing training materials |  |  | X |  | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA |  |  |  |  | PERSON
|  | 1.3.2.2 - Modify, organize and develop TOT training materials following the evaluation in order to have a standard set of training manuals which can apply to different target groups. |  |  |  | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA |  |  |  |  | PERSON, OPEX, MISC
|  | 1.3.2.3 - Pilot training and finalize training materials |  |  |  | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA |  |  |  |  | PERSON, OPEX, MISC
TA from UN agency
| UNFPA | Activity 1.3.3 (a) - Support training of staff of MOLISA, CP and branches on the GEL at central and provincial levels including key cities. |  |  |  | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA | TRAINING OF COUNTERPARTS | 20000 | 4774 | 24774 | ACTIVITY 07
|  | 1.3.3.1 - Provide Government and Party officers and branches in the provinces and key cities with training on the GEL |  |  |  | X | MOLISA | MOLISA, line ministries, Communist Party and other duty bearers | UNFPA |  |  |  |  | PERSON, OPEX, MISC
|  | TA from UN agency |  |  |  | X | MOLISA |  | UNFPA |  |  |  |  | PERSON
| UNICEF | Activity 1.3.4 - Develop training package and training of selected NA's Deputies and Members of Provincial People's Councils on the two Laws, and international treaties and standards relating to GE and children's rights to strengthen the capacity of Elected Officials for carrying out their law making and oversight functions. |  |  |  |  | MOLISA | NA Committee for Culture, Education, Youth and Children, Human Resource Institute/ HCM Academy | UNICEF | CONTRACT | 11250 | 2799 | 14049 | ACTIVITY 07
|  | 1.3.4.1 - Development of the training package on Child Rights and Gender Equality provided in the Gender Equality Law, DV Law, and international treaties and standards |  | X |  |  | MOLISA | NA Committee for Culture, Education, Youth and Children, Human Resource Institute/ HCM Academy | UNICEF |  |  |  |  | PERSON
|  | 1.3.4.2 - Training workshop to experiment the training package |  |  | X |  | MOLISA | NA Committee for Culture, Education, Youth and Children, Human Resource Institute/ HCM Academy | UNICEF |  |  |  |  | PERSON, OPEX, MISC
| UNIFEM | Activity 1.3.5 - Training and capacity assistance to NA in developing skills of the Women Parliamentarian Group to oversight of the two laws |  |  | X | X | MOLISA | MOLISA, NA , MOCST | UNIFEM | TRAINING OF counterparts | 7350 | 5568 | 12918 | ACTIVITY 07
|  | 1.3.5.1 - Recruitment of the local consultant |  |  | X | X | MOLISA | MOLISA, NA , MOCST | UNIFEM |  |  |  |  | PERSON
|  | 1.3.5.2 - Workshop- training in developing skills to oversight the two laws -Review and understanding of the two laws -Review of the implementation of the similar laws in different countries |  |  |  | X | MOLISA | MOLISA, NA , MOCST | UNIFEM |  |  |  |  | PERSON,OPEX, MISC
| ILO | Activity 1.3.7 - MOLISA to mainstream gender into labour and employment policies, national programmes, including translation, adaptation and adoption of gender mainstreaming and auditing tools as related to the GEL |  | X | X | X | MOLISA | MOLISA | ILO | CONTRACTS | 23100 | 30450 | 53550 | ACTIVITY 07
|  | 1.3.7.1 - Review and gender analysis of national programmes and recommend how gender should be integrated into national targeted programmes, labour and social legislations |  | X | X | X | MOLISA | MOLISA | ILO |  |  |  |  | PERSON
|  | 1.3.7.2 - Review and improve training materials, assess the training needs of officers, Translate and adapt gender mainstreaming and gender auditing tools |  | X | X | X | MOLISA | MOLISA | ILO |  |  |  |  | PERSON,OPEX, MISC
|  | 1.3.7.3 Train officers at different levels on gender mainstreaming |  |  | X | X | MOLISA | MOLISA | ILO |  |  |  |  | PERSON, OPEX, MISC
| ILO | Activity 1.3.9 - Provide TA for 3 researches on working conditions of vulnerable rural women living in poverty. These researches are linked with activities 3.3.5 |  |  | X | X | MOLISA | MOLISA | ILO |  | 17850 | 23100 | 40950
|  | 1.3.9.a Research on the working conditions of women workers in industrial parks and export-processing zones, focusing more specifically on their workload as workers and as parents in efforts to ensure their equal competitiveness in the labour field, with the aim of recommending policies that advocate for shared responsibilities between men, women and employers. |  |  | X | X |  | MOLISA | ILO | CONTRACT | 6300 | 7875 | 14175 | ACTIVITY 07
|  | 1.3.9.a.1 - Develop research plans |  |  | X |  |  | MOLISA | ILO |  |  |  |  | PERSON,OPEX, MISC
|  | 1.3.9.a.2 - Conduct research |  |  |  | X | [7 empty] | PERSON, OPEX, MISC
|  | 1.3.9.b Research study on the access to employment and economic opportunities available to women and men in areas where farmers experiencing land use reform. The research aims to provide policy recommendations on vocational training, employment creation including self-employment opportunities, access to credit, etc. with a special focus on women workers |  |  | X | X | MOLISA | MOLISA, MARD | ILO ,FAO | CONTRACT | 6300 | 7350 | 13650 | ACTIVITY 07
|  | 1.3.9.b.1 - Develop research plans |  |  | X | [8 empty] | PERSON, OPEX,MISC
|  | 1.3.9.b.2 - Conduct Research |  |  |  | X | [7 empty] | PERSON, OPEX, MISC
|  | 1.3.9.c Research study on the specific working conditions of women in the domestic and informal economy, linking domestic and unpaid work, access to employment, economic opportunities, and economic empowerment for women as promoted through the law. |  |  | X | X | MOLISA | MOLISA | ILO | CONTRACT | 5250 | 7875 | 13125 | ACTIVITY 07
|  | 1.3.9.c.1 - Develop research plan |  |  | X | [8 empty] | PERSON, OPEX, MISC
|  | 1.3.9.c.2 - Conduct research |  |  |  | X | [7 empty] | PERSON, OPEX, MISC
| UNESCO | Activity 1.3.13 - Capacity-building of MOIC on gender mainstreaming in communication at central and provincial levels |  | X | X | X | MOLISA | MOIC | UNESCO | CONTRACTS | 10000 | 13500 | 23500 | ACTIVITY 07
|  | 1.3.13.1 - Situation and consultation meeting with counterparts/stakeholders |  | X | X | X | MOLISA | MOIC | UNESCO |  |  |  |  | PERSON
|  | 1.3.13.2 - Development of training/ learning materials and piloting the training materials. |  | X | X | X | MOLISA | MOIC | UNESCO |  |  |  |  | PERSON, OPEX, MISC
|  | 1.3.13.3 - Conduct training workshops |  |  |  | X | MOLISA | MOIC | UNESCO |  |  |  |  | PERSON, OPEX, MISC
| UNESCO | Activity 1.3.14: Capacity-building of MOET on gender mainstreaming in education at central and provincial levels |  | X | X | X | MOLISA | MOET | UNESCO | CONTRACT | 10000 | 12020 | 22020 | ACTIVITY 07
|  | 1.3.14. 1 - Development of training and learning materials on gender mainstreaming (GE) in education. |  | X | X |  | MOLISA | MOET, MOLISA | UNESCO |  |  |  |  | PERSON
|  | 1.3.14.2 - Two training workshops on GE for educational officials held. |  |  |  | X | MOLISA | MOET, MOLISA | UNESCO |  |  |  |  | PERSON, OPEX, MISC
| UNESCO | Activity 1.3.15 - National textbook review and analysis from gender perspective, including piloting teacher-training programmes to incorporate GE issues in line with the two laws. |  | X | X | X | MOLISA | MOET | UNESCO | CONTRACT | 15000 | 42620 | 57620 | ACTIVITY 07
|  | 1.3.15.1. Preparation and finalization of implementation plan. |  | X |  |  | MOLISA | MOET | UNESCO |  |  |  |  | PERSON
|  | 1.3.15.2. Consultation workshop on methodology on textbook review from gender's perspective. |  |  |  |  | MOLISA | MOET | UNESCO |  |  |  |  | PERSON, OPEX, MISC
|  | 1.3.15.3: Review textbook |  |  | X | X | MOLISA | MOET | UNESCO |  |  |  |  | PERSON
Output 2.1 Networks on gender equality are strengthened and sustained through relevant government and outside of government systems, with effective linkages and information among stakeholder. '- Output 2.1 Indicators: - Gender Partnership group and functions effectively - GEMCOMNET bring GE issues to attention of policy makers. - Gender Equality issues are fed into National Policy dialogues Annual Target: + National Level Forum made up of representatives of the three sub-networks (government and public organizations, agencies engaged in gender equality work, media professionals) (2.1.1) (2.1.2)
| UNIFEM | Activity 2.1.1 - Develop and sustain semi-annual forums on GE to feed into policy dialogues and the CG meetings. |  |  | X | X | MOLISA | MOLISA, MOCST, GSO | UNIFEM | TRAINING of counterparts | 21000 | 10151 | 31151 | ACTIVITY 04
|  | 2.1.1.1 - Recruitment of international and national consultants |  |  | X |  | MOLISA | MOLISA, MOCST, GSO | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.1.1.2 - Organize the Workshop in Hanoi |  |  | X |  | MOLISA | MOLISA, MOCST, GSO | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.1.1.3 - Annual Workshop in Hanoi will take place |  |  | X | X | MOLISA | MOLISA, MOCST, GSO | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
| UNIFEM | Activity 2.1.2 - Provide TA to selected NGOs of Gencomnet to expand their network and host consultation meetings on the two laws with SMAs, Government, civil society groups, NGOs and concerned agencies |  |  | X | X | MOLISA | Select NGOs from Gencomnet Network , MOLISA, MOCST, concerned agencies | UNIFEM | TRAINING of counterpart | 0 | 18900 | 18900 | ACTIVITY 04
|  | 2.1.2.1 - Prepare materials for the annual forum in Hanoi |  |  | X |  | MOLISA | Select NGOs from Gencomnet Network , MOLISA, MOCST, concerned agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.1.2.2 - Preparatory workshops for the Bi- Annual Forum Mission to get information for the forum |  |  | X |  | MOLISA | Select NGOs from Gencomnet Network , MOLISA, MOCST, concerned agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.12.3 - Annual Workshop in Hanoi will take place |  |  |  | X |  | Select NGOs from Gencomnet Network , MOLISA, MOCST, concerned agencies | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.1.2.4 - Publication of the material from Annual Forum |  |  |  | X | MOLISA | Select NGOs from Gencomnet Network , MOLISA, MOCST, concerned agencies | UNIFEM |  |  |  |  | MISC
| UNIFEM | Activity 2.1.3 - NCFAW and MOLISA to strengthen GAP |  | X | X | X | MOLISA | NCFAW & MOLISA | UNIFEM | TRAINING of counterpart | 7184 | 840 | 8024 | ACTIVITY 04
|  | 2.1.3.1 - Recruitment of the local consultant |  | X |  |  | MOLISA | NCFAW & MOLISA | UNIFEM |  |  |  |  | PERSON
|  | 2.1.3.2 - Develop TOR for GAP |  |  | X |  | MOLISA | NCFAW & MOLISA | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.1.3.3 - First workshop with all them members of the GAP to agree on the ToRs and Plan of Actions for the Working Group | X |  |  |  | MOLISA | NCFAW & MOLISA | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
|  | 2.1.3.4 - Annual Meetings Working Group |  |  | X | X | MOLISA | NCFAW & MOLISA | UNIFEM |  |  |  |  | PERSON, OPEX, MISC
Output 2.2: Improved partnership between mass organizations and government agencies to promote women's economic empowerment. Output 2.2 Indicators: - Network around women entrepreneurship at both grass-roots and national levels strengthened. - Tools and reference material for women entrepreneurship promotion and economic empowerment implemented by entrepreneurs and policy makers, especially VCCI, MOLISA and VWU. Annual Targets: + Practical policy recommendation for the implementation of GE Law and revised SME Decree 90 provided, focusing on women's economic empowerment and entrepreneurship development.(2.2.1) + The policy dialogue between the business sector, represented by VCCI, and policy makers enhanced for the promotion of women entrepreneurship. (2.2.1) + Experience sharing of grass-roots good practices of women entrepreneurship development promoted at both national and provincial levels through workshops and development of methodology.(2.2.2)
| UNIDO | Activity 2.2.1 - Facilitate enhanced partnership between VCCI, government agencies, and other political and civil society actors to develop mechanisms for promoting women's entrepreneurship in line with the GEL |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO | TRAINING /CONTRACT/PERSONNEL/OTHER DIRECT COSTS | 0 | 77280 | 77280 | ACTIVITY 04
|  | 2.2.1.1 - Formulate the small working group which consists of VCCI, MOLISA, VWU and other key organizations. |  | X |  |  | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO | PERSON, OPEX, MISC |  | 7875 | 7875
|  | 2.2.1.2 - Assist the working group to draft recommendation for the implementation and promotion of GEL and the revised SME Decree No. 90 by providing need-based training courses. |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO |  |  | 26717 | 26717
|  | 2.2.1.3 - Conduct the field research to identify technical demand of women entrepreneurs and to provide discussion basis for the working group and the study tours for the working group members. |  | X | X |  | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO |  |  | 19930 | 19930
|  | 2.2.1.4 - Host workshops to discuss and disseminate the proposals for the implementation and promotion of GE Law and the revised SME Decree No. 90. |  | X |  | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO |  |  | 22759 | 22759
| ILO | Activity 2.2.1 |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO | CONTRACT | 0 | 26460 | 26460 | ACTIVITY 07
|  | 2.2.1.1 - Formulate the small working group which consists of VCCI, MOLISA, VWU and other key organizations. |  | X |  |  | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO
|  | 2.2.1.2 - Assist the working group to draft recommendation for the implementation and promotion of GE Law and the revised SME Decree No. 90 by providing need-based training courses. |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO |  |  |  |  | PERSON,OPEX, MISC
|  | 2.2.1.3 - Conduct the field research to identify technical demand of women entrepreneurs and to provide discussion basis for the working group and the study tours for the working group members. |  | X |  |  | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO |  |  |  |  | PERSON,OPEX, MISC
|  | 2.2.1.4 - Host workshops to discuss and disseminate the proposals for the implementation and promotion of GE Law and the revised SME Decree No. 90. |  |  | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO |  |  |  |  | PERSON,OPEX, MISC
| UNIDO | Activity 2.2.2. Support women's entrepreneurship and networking at the grass-roots level and their advocacy efforts aimed at mass organizations and government agencies working on economic empowerment policies for women. |  |  |  | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO | TRAINING/ PERSONNEL/ OTHERDIRECT COSTS |  | 26033 | 26033
|  | 2.2.2.1- Organize workshops to learn and disseminate grassroots good practices and institutionalize the methodology for women entrepreneurship promotion, inviting women entrepreneurs and relevant organizations from 3 different regions. |  |  |  | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO |  |  | 19207.125 | 19207.125 | PERSON, OPEX, MISC
|  | 2.2.2.2 - Make a reference book which consolidates the existing tool kits for business service providers. |  |  |  | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO |  |  | 1575 | 1575 | PERSON, OPEX, MISC
|  | 2.2.2.3 - Assist the working group to draft a follow-up action plan for post programme periods. |  |  |  | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, concerned agencies | UNIDO |  |  | 5250 | 5250 | PERSON, OPEX, MISC
| ILO | Activity 2.2.2. |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO | CONTRACT | 0 | 18953 | 18953 | ACTIVITY 07
|  | 2.2.2.1 - Organize workshops to learn and disseminate grassroots good practices and institutionalize the methodology for women entrepreneurship promotion, inviting women entrepreneurs and relevant organizations from 3 different regions. |  | X | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO |  |  |  |  | PERSON, OPEX, MISC
|  | 2.2.2.2 - Make a reference book which consolidates the existing tool kits for business service providers. |  | X | X |  | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO |  |  |  |  | PERSON, OPEX, MISC
|  | 2.2.2.3 - Assist the working group to draft a follow-up action plan for post programme periods. |  |  | X | X | MOLISA | VCCI, Collaborating agencies: VWU, MOLISA, VCA, VGCL | ILO |  |  |  |  | PERSON, OPEX, MISC
Output 2.3 Communication network on gender equality developed for mass dissemination of two laws Output 2.3 Indicators: - Communication network on GE in existence. - Increase in press coverage on the 2 laws. Annual targets: + One press conference organized (2.3.1) + Relevant mass-media agencies for network building identified + Training courses materials reviewed for mass media staff (2.3.3)
| UNFPA | Activity 2.3.1 - Facilitate semi-annual press conferences |  | X |  | X | MOLISA | MOLISA, MOCST | UNFPA | TRAINING of counterpart | 1000 | 544 | 1544 | ACTIVITY 04
|  | Activity 2.3.3 - Development of national network of media practitioners reporting on GE issues, including providing training on the content of the two laws and support for development of the Communication on the GEL |  |  | X |  | MOLISA | MOLISA and related agencies | UNFPA | CONTRACTS | 15000 | 6266 | 21266 | ACTIVITY 07
|  | 2.3.3.1 - Identify relevant mass-media agencies for network building |  |  | X |  | MOLISA |  | UNFPA |  |  |  |  | PERSON
|  | 2.3.3.2 - Review and adjust (if necessary existing training courses available for mass-media staff |  |  |  | X | MOLISA |  | UNFPA |  |  |  |  | PERSON
Output 3.3 Data and information collected to promote national gender equality policy dialogues for marginalized groups. Output 3.3 Indicators: - Data concerning marginalized women is collected. - Policy reports/papers cite data on marginalized women. Annual targets: + Currently available data stock-taken and reviewed, and new data and information collected (3.3.1) + National and international consultants recruited. (2) Research Plan developed. (3) Data reviewed and Research Work started up (3.3.4) + Three researches conducted to identify findings for policy recommendation to develop appropriate polices for promoting gender equality for such vulnerable women groups (which is linked with activity 1.3.9) (3.3.5)
| UNDP | Activity 3.3.1 Provide TA for research and policy dialogues on ethnic minority women's access to legal services. |  | X | X | X | MOLISA | MOLISA & NCFAW Collaborating agencies: GSO | UNDP | CONTRACTS | 19000 | 15000 | 34000 | ACTIVITY 07
|  | 3.3.1.1 - Stock-take, desk review and analyze currently available data |  | X | X |  |  | MOLISA /NCFAW Collaborating agencies: GSO | UNDP |  | 5000 | 15000 | 20000 | PERSON, OPEX, MISC
|  | 3.3.1.2 - Collect some new data and information |  |  | X | X |  | MOLISA /NCFAW Collaborating agencies: GSO | UNDP |  | 9000 | 0 | 9000 | PERSON, OPEX, MISC
|  | 3.3.1.3 - Produce a policy research paper based on analysis |  |  |  | X |  | MOLISA /NCFAW Collaborating agencies: GSO | UNDP |  | 5000 | 0 | 5000 | PERSON, OPEX, MISC
| IOM | Activity 3.3.4 - Research on the situation of sex workers in Vietnam and policy gaps, with a view to bring gender discrimination to attention of policy-makers in supporting the implementation of the laws. |  |  | X |  | MOLISA | MOLISA Collaborating agencies: selected NGOs | IOM | CONTRACT | 6542 | 2805 | 9347 | ACTIVITY 07
|  | 3.3.4.1 - Recruitment of national and international consultants |  |  | X |  | MOLISA | MOLISA Collaborating agencies: selected NGOs | IOM |  |  |  |  | PERSON, OPEX, MISC
|  | 3.3.4.2 - Develop a research plan |  |  |  | X | MOLISA | MOLISA Collaborating agencies: selected NGOs | IOM |  |  |  |  | PERSON, OPEX, MISC
|  | 3.3.4.3 Review existing data |  |  |  | X | MOLISA | MOLISA Collaborating agencies: selected NGOs | IOM |  |  |  |  | PERSON, OPEX, MISC
|  | Support for PMU | [8 empty] | 27175 | 58909 | 86084
| UNFPA | Support Annual JP Progress Review Meetings and other JP activities to be organized by the PMU |  |  |  |  | MOLISA | MOLISA | UNFPA | TRAINING of counterpart | 4000 | 13890 | 17890 | TRAINING X1 Workshops, seminar, meetings
| (i) | Support salary for PMU and monitoring
|  | Support salary for 2 full-time staff (01 Program Coordinator 01 and 01 Assistant cum interpreter, 01 Accountant) for management of the JP at PMU |  | X | X | X | MOLISA | MOLISA | UNFPA | PERSONNEL - Salary for PMU staff | 17325 | 0 | 17325 | ACTIVITY 02
|  | Salary for JP Gender specialist (L contract) |  | X | X | X | MOLISA | MOLISA | UNFPA | PERSONNEL | 0 | 39682 | 39682 | ACTIVITY 02
|  | JP Monitoring by NIPs |  | X | X | X | MOCST | MOLISA | UNFPA | PERSONNEL -Monitoring by NIP | 2000 | 0 | 2000 | ACTIVITY 05
| (ii) | JP Monitoring by UN Agency (UNFPA) |  | X | X | X | MOCST |  | UNFPA | PERSONNEL -Monitoring | 0 | 1000 | 1000 | ACTIVITY 03
| (iii) | Support expendable equipment, materials, rental of other equipment. |  | X | X | X | MOCST | MOCST | UNFPA | SUPPLIES, commodities, equipment and transport | 2000 | 1140 | 3140 | ACTIVITY 01
| (iv) | Other Direct Costs |  |  |  |  | MOLISA | MOLISA | UNFPA | OTHER DIRECT COSTS | 1850 | 3197 | 5047 | ACTIVITY 10
|  | (+) Support for translation |  | X | X | X
|  | (+) Support for bank charge, telephone charge, audit fees, exchange losses. |  | X | X | X
(+) Support for audit fees
|  | PROGRAMME COST | ` | [7 empty] | 377061 | 571320 | 948381
|  | INDIRECT SUPPORT COSTS (7%) | [8 empty] | 26394.27 | 39992.4 | 66386.67
|  | TOTAL PLANNED BUDGET | [8 empty] | 403455.27 | 611312.4 | 1014767.67
[11 empty] | Total Programme Budget |  | Indirect Support Cost | Total Planned Budget
[11 empty] | National Implementation | UN Implementation
|  | Total for UNFEM Implementation | [9 empty] | 155894 | 10912.58 | 166806.58
|  | Total for UNDP Implementation | [9 empty] | 55000 | 3850 | 58850
|  | Total for ILO Implementation | [9 empty] | 98963 | 6927.41 | 105890.41
|  | Total for UNESCO implementation | [9 empty] | 68140 | 4769.8 | 72909.8
|  | Total for UNICEF Implementation | [9 empty] | 2799 | 195.93 | 2994.93
|  | Total for UNIDO Implementation | [9 empty] | 103313 | 7231.91 | 110544.91
|  | Total for IOM Implementation | [9 empty] | 2805 | 196.35 | 3001.35
|  | Total for UNFPA Implementation (a) | [9 empty] | 84406 | 5908.42 | 90314.42
|  | Total for national implementation - fund received via UNFPA as MA (b) | [8 empty] | 377061 |  | 26394.27 | 403455.27
|  | Total fund received by UNFPA (a+b) | [8 empty] | 377061 | 84406 | 32302.69 | 493769.69
|  | Grand Total | [8 empty] | 377061 | 571320 | 66386.67 | 1014767.67
[13 empty] | 165076.03 | 2523305.03
Signatures
| UNFPA as Managing Agent | [9 empty] | Ministry of Labour, Invalids and Social Affairs
| Bruce Campbell | [9 empty] | Nguyễn Thanh Hoà
| UNFPA Representative in Viet Nam | [9 empty] | Vice Minister, Ministry of Labour, Invalids and Social Affairs
| Date______________________ | [9 empty] | Date: _______________________
Note on K23: Nguyen Thi Thuy: Thuy took out the 'TRAINING" as most activities are close to "CONTRACT"
Note on K89: Nguyen Thi Thuy: Thuy took out the 'Contract' as key activity is 'Training"
Note on K95: Nguyen Thi Thuy: UNIDO wanted to keep all categories as the activities are DEX
Note on O95: Nguyen Thi Thuy: I put them all in 'Activity 04" of category 'training' as most of them are closed to it

## MOCST (E)
ANNUAL WORK PLAN 2009 for UN-GOV Joint Programme on Gender Equality | [11 empty] | Period: April 2009 - December 2009
National Implementing Partner: Ministry of Culture, Sports and Tourism
UN participating Agencies: IOM, UNAIDS, UNDP, UNFPA, UNODC, WHO.
Programme Code and NIP's IDs: VNM7G31A/VNM0014
OUTCOME: JP Outcome 1: Improved skills, knowledge and practices for the implementation, monitoring, evaluation and reporting of the Law on Gender Equality and Law on Domestic Violence Prevention and Control.
JP Outcome 2: Enhanced partnerships and coordination around gender equality within and outside of government.
UN Organization Specific Annual Targets | UN Organization | Activities | Time Frame |  |  |  | Implementing Partners (name of NIP/CIPs, other National Partners including Sub-contractor, if any) |  |  | Programme Budget (US$)
|  |  | Q1 | Q2 | Q3 | Q4 | Component Project/NIP | National Agencies | UN Agencies | MDT-F Categories | National Implementation | UN Implementation | Total | UNFPA categories and Activity ID in Atlas
JP Output: 1.2: Relevant plans of action are developed for the SMAs, line ministries, Commission of Social issues-NA, Central Party Committee for Education and Popularization at the central and local levels to implement, evaluate, monitor and report on the two laws Output 1.2 Indicators: - Availability of relevant plans of action and - Availability of M&E Framework for the two laws. Annual targets: + Multiagency collaboration mechanism developed, finalized and approved (1.2.2). + Outline of the M&E Framework for measuring the implementation of the DVP law developed (1.2.3).
| UNFPA | Activity 1.2.2 - Ministry of Culture, Sports and Tourism to develop multi-agency collaboration mechanisms for the prevention of DV. |  |  |  |  | MOCST | MOCST | UNFPA | CONTRACT | 12810 | 7185 | 19995 | ACTIVITY 08
|  | 1.2.2.1 - Develop a multi-agency mechanism for the prevention of DV |  |  | X | X |  |  |  |  | 7200 | 3700 | 10900 | PERSON, OPEX, MISC
|  | 1.2.2.2 - Hold workshops to consult with key ministries on the multi-agency mechanism |  |  | X | X |  |  |  |  | 5610 | 3485 | 9095 | PERSON, OPEX, MISC
| UNDP | Activity 1.2.3 (b) - MOCST, National Assembly, line ministries and other duty bearers to develop and sustain M&E framework for measuring the implementation of the DVL |  |  |  |  | MOCST | - MOCST - Other national partners: PCSA (NA), line ministries and other related agencies | - UNDP | CONTRACT | 37000 | 40000 | 77000 | ACTIVITY 08
|  | 1.2.3.1 - Study tour to another country where M&E framework exists |  | X | [6 empty] | 0 | 30000 | 30000 | PERSON
|  | 1.2.3.2 - Defining needs and indicators through a consultative and participatory process with TA from GSO. |  | X | X | [5 empty] | 10000 | 0 | 10000 | PERSON, OPEX, MISC
|  | 1.2.3.3 - Developing the M&E framework by national and international consultants. |  |  | X | X |  |  |  |  | 7000 | 10000 | 17000 | PERSON, OPEX, MISC
|  | 1.2.3.6 - Develop a website on DV in the website of MOCST. |  | X | [6 empty] | 20000 | 0 | 20000 | PERSON, OPEX, MISC
JP Output 1.3: Technical assistance provided to improve capacity of the SMAs, line ministries, Commission for Social issues of NA, into implement, evaluate, monitor and report on the two laws. Output 1.3 Indicators: - Availability of tools and information for gender analysis across sectors - GE and DV laws integrated into Annual Work Plans and PoAs of key line ministries and - Relevant plans of action disseminated to all institutions and levels of implementation; Annual targets: + Training materials for DVP are reviewed, adjusted or developed (if needed) and used for training for concerned staff of relevant agencies at central and lower levels (1.3.2 and 1.3.3).
+ Regulatory documents relating to law enforcement and justice sector for the implementation of the law of Domestic Violence Prevention and Control developed, finalized and approved for use (1.3.10 and 1.3.11). + Training materials on law enforcement and justice sector officers developed, finalized and used for training of these two sectors (1.3.12)
| UNFPA | Activity 1.3.2 (b) - Development of training materials on the DVL to make them available to MOCST, line ministries, CP and other duty bearers for better implementation of the law. |  |  |  |  | MOCST | - MOCST and key line ministries and agencies (Social Faculty of Institute of Labour, Invalid & Social Affairs). - Central Party Committee for Education and Popularization; PCSA will be consulted | UNFPA, UNAIDS | CONTRACT | 9400 | 4000 | 13400 | ACTIVITY 08
|  | 1.3.2.1 - Review and compile existing training materials |  | X | [6 empty] | 3400 | 2609 | 6009 | PERSON
|  | 1.3.2.2 - Modify, compile, develop TOT training materials following the assessment in order to have a standard set of training manuals which can apply to different target groups. |  |  | X | X |  |  |  |  | 6000 | 1391 | 7391 | PERSON, OPEX, MISC
| UNFPA | Activity 1.3.3 (b) - Support training of MOCST, CP and branches on the DVL in selected provinces. |  |  |  |  | MOCST | - MOCST; - Officials under line of Central Party Committee for Education and Popularization at provincial and grassroots levels - Elected deputies at provincial levels | UNFPA | TRAINING of counterparts | 46330 | 4774 | 51104 | ACTIVITY 05 Workshops, seminar, meetings
|  | 1.3.3.1 Provide Government and Party officers and branches in the provinces and key cities with training on the DVL |  |  | X | X |  |  |  |  | 46330 | 2774 | 49104 | PERSON, OPEX, MISC
|  | 1.3.3.2 Support for supportive supervision and monitoring the training courses. |  |  |  | X |  |  | UNFPA | PERSONNEL -Monitoring |  | 2000 | 2000 | ACTIVITY 03 PERSON
| WHO | Activity 1.3.10 - MOH to develop sub-law and regulatory documents necessary for implementation of DVL and GEL |  |  |  |  | MOCST |  | - WHO, UNFPA - Sub-contractor: MOH | CONTRACT | 0 | 46000 | 46000
|  | 1.3.10.1 - Employ national and international consultants to assist with activities |  | X | X | X |  |  | WHO |  |  | 11500 | 11500 | PERSON
|  | 1.3.10.2 - Visit to local projects in Vietnam that are run by UNFPA and NGOs to understand the intervention and collaboration models used |  | X | X |  |  |  | WHO |  |  | 10500 | 10500 | PERSON,OPEX, MISC
|  | 1.3.10.3 - Several consultation workshop in Ha Noi, Central, South Vietnam |  |  | X | X |  |  | WHO |  |  | 18000 | 18000 | PERSON,OPEX, MISC
|  | 1.3.10.4. Produce and Disseminate necessary regulatory documents (such as guidelines on screening, counseling, reporting, providing urgency shelter, and other requirements) |  |  |  | X |  |  | WHO |  |  |  | 0
| UNFPA | 1.3.10.5 - TA support MOH to develop regulatory document including organize consultative workshops. (UNFPA) |  |  | X | X |  |  | UNFPA | CONTRACT |  | 6000 | 6000 | ACTIVITY 08 PERSON, OPEX, MISC
| UNODC | Activity 1.3.11 - MOJ and MPS to develop regulatory documents necessary for the implementation of the Law on Domestic Violence Prevention and Control |  |  |  |  | MOCST |  | - UNODC - Sub-contractors: MPS, MOJ | TRAINING of counterparts | 0 | 24570 | 24570
|  | 1.3.11.1 - Study tour for key officers of these two ministries (combined with activity 1.3.12). |  | X | X | [7 empty] | 0 | PERSON
|  | 1.3.11.2 - A workshop to identify areas which should be included in the regulatory documents |  | X | [6 empty] | 0 | 2000 | 2000 | PERSON, OPEX, MICS
|  | 1.3.11.3 - Two rounds of consultative meetings, one for each law enforcement and justice sector |  | X | X | [5 empty] | 0 | 12500 | 12500 | PERSON, OPEX, MICS
|  | 1.3.11.4 - A cross-sectoral 2-day consultation workshop to ensure that health, law enforcement and justice sectors synergize their efforts. |  | X | X | [6 empty] | 10070 | 10070 | PERSON, OPEX, MICS
| UNODC | Activity 1.3.12 - MOJ and MPS to develop training materials on DV and to pilot these trainings for law enforcement and justice sector officers. |  |  |  |  | MOCST |  | - UNODC, - Sub-contractors: MPS, MOJ. | TRAINING of counterpart | 0 | 134835 | 134835 | ACTIVITY 05
|  | 1.3.12.1 - A national consultant and international law enforcement and justice sector experts on DV are recruited to Develop specific training materials for both sectors on DV prevention. |  | X | X | [6 empty] | 101250 | 101250 | PERSON
|  | 1.3.12.2 - TOT training (for relevant staff in Can Tho, Da Nang, Ha Noi and Thai Nguyen provinces) followed by further trainings |  |  | X | X | [5 empty] | 33585 | 33585 | PERSON, OPEX, MISC
JP Output: 2.1: Networks on GE are strengthened and sustained through relevant Government and outside Government systems, with effective linkages and information among stakeholders. Output 2.1 Indicators: Gender Equality issues are fed into National Policy dialogues. Annual targets: + Network of DV victims set up (2.1.4) + Gencomnet bring GE issues to attention of policy makers.
| IOM | Activity 2.1.4 - Enhance the capability of grass-roots support groups for victims of DV and advocate directly at the provincial and national level for improved policies and intervention programme |  |  |  |  | MOCST | CIP: CWD/VWU. | IOM | TRAINING of counterpart | 8411 | 935 | 9346 | ACTIVITY 05 Workshops, seminar, meetings
|  | 2.1.4.1 - Develop the network of DV victims |  | X | X | X | [7 empty] | PERSON, OPEX, MISC
|  | 2.1.4.2 - Hold workshops on Gender and Life Skills |  | X | X | X | [7 empty] | PERSON, OPEX, MISC
|  | 2.1.4.3 - Host conferences and seminars to support victims and identify particular cases to support policy mobilization |  |  |  | X | [7 empty] | PERSON, OPEX, MISC
Output 2.3: Communication network on gender equality developed for mass dissemination of two laws. Output 2.3 Indicators: - Communication network on gender equality in existence and - Increase in press coverage on the 2 laws. Annual targets: + Contents of two laws are regular disseminated through key mass media agencies (2.3.2)
| UNFPA | Activity 2.3.2 - Facilitate the dissemination of the laws through mass media (special columns of key magazines, newspapers, national TV coverage, VOV, etc. |  |  |  |  | MOCST |  | - UNFPA. - Sub-contracts: Key mass media agencies.. | CONTRACT | 0 | 7904 | 7904 | ACTIVITY 08
|  | 2.3.2.1 - Integrate content of the two laws into special columns of key magazines and newspapers, TV coverage and radio broadcasting programmes for public dissemination. |  | X | X | X |  |  |  |  | 0 | 7904 | 7904 | PERSON, OPEX, MISC
| UNFPA | Support for PMU/CPMU | [8 empty] | 16330 | 23378 | 39708
| (i) | Support Annual JP Progress Review Meetings and other JP activities to be organized by the PMU/CPMU |  |  |  |  | MOCST | MOCST | UNFPA | TRAINING of counterpart | 1205 | 3710 |  | - TRAINING X1 - ACTIVITY 05 Workshops, seminar, meetings, monitoring by NIP
| (ii) | Support salary for PMU/CPMU and monitoring
|  | Support salary for 2 full-time staff (01 Component Project Manager and 01 Accountant cum Secretary) for management of the JP Component Project, CPMU and Gender Specialist. |  | X | X | X | MOCST | MOCST | UNFPA | PERSONNEL - Salary for CPMU staff | 12825 | 17296 | 30121 | ACTIVITY 02
|  | JP Monitoring by NIPs |  | X | X | X | MOCST | MOCST |  | PERSONNEL -Monitoring by NIP | 1000 |  | 1000 | ACTIVITY 05, monitoring by NIP
| (iii) | JP Monitoring by UN Agency (UNFPA) |  | X | X | X | MOCST |  | UNFPA | PERSONNEL -Monitoring | 0 | 1000 | 1000 | ACTIVITY 03
| (iv) | Support expendable equipment, materials, rental of other equipment. |  | X | X | X | MOCST | MOCST | UNFPA | SUPPLIES, commodities, equipment and transport | 720 | 360 | 1080 | ACTIVITY 01
| (v) | Other Direct Costs |  |  |  |  | MOCST | MOCST | UNFPA | OTHER DIRECT COSTS | 580 | 1012 | 1592 | ACTIVITY 10
|  | (i) Support for translation |  | X | X | X | [6 empty] | 0
|  | (ii) Support for bank charge, telephone charge, audit fees, exchange losses. |  | X | X | X
(iii) Support for audit fees
|  | PROGRAMME COST | [8 empty] | 130281 | 293581 | 423862
|  | INDIRECT SUPPORT COSTS (7%) | [8 empty] | 9119.67 | 20550.67 | 29670.34 | ICFOR UNFPA
|  | TOTAL PLANNED BUDGET | [8 empty] | 139400.67 | 314131.67 | 453532.34
[11 empty] | Total Programme Budget |  | Indirect Support Cost | Total Planned Budget
[11 empty] | National Implementation | UN Implementation
|  | Total for UNDP Implementation | [9 empty] | 40000 | 2800 | 42800
|  | Total for WHO Implementation | [9 empty] | 40000 | 2800 | 42800
|  | Total for UNODC Implementation | [9 empty] | 159405 | 11158.35 | 170563.35
|  | Total for IOM Implementation | [9 empty] | 935 | 65.45 | 1000.45
|  | Total for UNFPA Implementation (a) | [9 empty] | 53241 | 3726.87 | 56967.87
|  | Total for national implementation - fund received via UNFPA as MA (b) | [8 empty] | 130281 |  | 9119.67 | 139400.67
|  | Total fund received by UNFPA (a+b) | [8 empty] | 130281 | 53241 | 12846.54 | 196368.54
|  | Grand Total | [8 empty] | 130281 | 293581 | 29670.34 | 453532.34
[13 empty] | 72187.22 | 1103433.22
Signatures
| UNFPA as Managing Agent | [9 empty] | Ministry of Culture, Sport and Tourism
| Bruce Campbell | [9 empty] | Huynh Vinh Ai
| UNFPA Representative in Viet Nam | [9 empty] | Vice Minister of Ministry of Culture, Sport and Tourism
| Date______________________ | [9 empty] | Date: _______________________
Note on K7: Chau: Not including Indirect Support Costs (7%)
Note on L11: Chau: Not including 7%
Note on M11: Chau: Not including 7%
Note on M47: Nguyen Thi Thuy: 25,000 for entire cycle
Note on N11: Chau: Not including 7%
Note on N12: Chau: Not including 7%
Note on N13: Chau: Not including 7%
Note on O27: Nguyen Thi Thuy: dealing with 2 law

## GSO (E)
ANNUAL WORK PLAN 2009 UN-GOV Joint Programme on Gender Equality | [13 empty] | Period: April 2009 - December 2009
Implementing Partner: General Statistic Office
UN participating Agencies: UNDP, IOM, UNFPA, WHO, ILO, FAO, UNICEF
Programme Code and NIP's IDs: VNM7G31A/VNM0015
OUTCOME: JP Outcome 1: Improved skills, knowledge and practices for the implementation, monitoring, evaluation and reporting of the Law on Gender Equality and Law on Domestic Violence.
JP Outcome 3: Strengthen evidence-based and data systems for promoting gender equality
UN Organization Specific Annual Targets | UN Organization | Activities | Time Frame |  |  |  | Implementing Partners (name of NIP/CIPs, other National Partners including Sub-contractor, if any) |  |  | Programme Budget (US$)
|  |  | Q1 | Q2 | Q3 | Q4 | Component Project/NIP | National Agencies | UN Agencies | MDT-F Categories | National Implementation | UN Implementation | Total | UNFPA categories and Activity ID in Atlas
OUTPUTS AND OUTPUT INDICATORS: Output 1.3: Technical assistance provided to improve capacity of the SMAs, line ministries, National Assembly, Communist Party (+VWU) into implement, evaluate, monitor and report on the two laws. Output 1.3 Indicators: - Availability of tools and information for gender analysis across sectors - GE and DV laws integrated into Annual Work Plans and PoAs of key line ministries and - Relevant plans of action disseminated to all institutions and levels of implementation; Annual targets : + Training organized for officers from GSO and MARD (1.3.6)
| FAO | Activity 1.3.6 - Training of GSO and MARD staff responsible for gender and sex-disaggregated data collection and analysis |  |  |  | X | GSO | GSO, MARD, Collaborating agencies: MOLISA, MOCST | FAO | TRAINING | 0 | 14019 | 14019 | ACTIVITY 06 PERSON, OPEX, MICS
| UNFPA | Activity 1.3.6 |  |  |  | X | GSO | GSO, MARD, Collaborating agencies: MOLISA, MOCST | UNFPA | TRAINING of counterpart | 8900 | 6988 | 15888 | ACTIVITY 06 PERSON, OPEX, MICS
Output: 3.1: Current gender equality and sex-disaggregated indicators are reviewed and new indicators identified through research. Output 3.1 Indicators: Increase in number and quality of GE and sex-disaggregated indicators Annual targets : + Three indexes (GDI, GEM, GGI) calculated (3.1.1) + Questionnaire developed, sample defined, and interviewers trained (3.1.2)
| UNDP | Activity 3.1.1 - GSO to calculate the Gender related Development Index (GDI), the gender empowerment measure (GEM), and the World Economic Forum's Gender Gap Index - a mix of qualitative and quantitative data to enable the preparation of periodic reports on the status of men and women in Vietnam and to provide accurate gender analysis as required. |  | X | X | X | GSO |  | UNDP | CONTRACTS | 14000 | 30000 | 44000 | ACTIVITY 09
|  | 3.1.1.1 - A study tour to UNDP and GSO in Malaysia where gender gap index was calculated in 2006 |  | X | X | [6 empty] | 30000 | 30000 | PERSON, OPEX, MISC
|  | 3.1.1.2 - Technical assistance to GSO to collect and calculate data for all three indexes |  | X | X | [5 empty] | 7000 |  | 7000 | PERSON, OPEX, MISC
|  | 3.1.1.3 - Developing and printing guidelines on calculation of three indexes and collection of required data (including a consultative workshop) |  |  | X | X |  |  |  |  | 7000 |  | 7000 | MISC
|  | 3.1.1.4 Dissemination of publications and information of indexes through a national workshop |  |  |  |  | GSO | [5 empty] | 0 | To be implemented in Q1, Y2
| WHO | Activity 3.1.2 - GSO and MOH to conduct a national survey on women's health and domestic violence. |  | X | X | X | GSO | GSO Collaborating agencies: MOH, MOCST, other concerned agencies and research institute | WHO | CONTRACTS | 93346 | 72250 | 165596 | ACTIVITY 09
|  | 3.1.2.1 Recruit local and international consultants to support implementation of sub activities |  | X | X | X | GSO | GSO, MOH |  |  |  |  | 0 | PERSON, OPEX
|  | 3.1.2.2 Develop questionnaire and sample (including consultation, pilot testing, printing) |  |  | X | X | GSO | GSO, MOH |  |  |  |  | 0 | PERSON, OPEX, MISC
|  | 3.1.2.3 Organize training for interviewers and supervisors |  |  |  | X | GSO | GSO, MOH |  |  |  |  | 0 | PERSON, OPEX, MISC
Output 3.2: Gender equality and sex-disaggregated indicators are integrated into ongoing national data collection processes and reporting. Output 3.2 Indicators: National surveys incorporate GE and sex-disaggregated indicators Annual targets : + Current surveys and concerning capacity of GSO reviewed & assesses, integrating gender issues into the labor force survey planned (3.2.1) + TA in engender national censuses and surveys on rural issues is provided to GSO (3.2.2) + Current surveys and concerning capacity of GSO reviewed & assesses; integrating gender issues into the enterprise survey planned (3.2.3) + Stakeholders' awareness of child and gender indicators improved (3.2.4)
| ILO | Activity 3.2.1 - Provide TA to engender the labor force survey |  |  | x | x | GSO | GSO Collaborating agencies: MOLISA | ILO | CONTRACTS | 5250 | 8138.5 | 13388.5 | ACTIVITY 09 PERSON, OPEX, MISC
| FAO | Activity 3.2.2 - Provide TA to engender national censuses and surveys on rural issues |  |  | x | x | GSO | GSO, Collaborating agency: MARD | FAO | CONTRACTS | 0 | 28037 | 28037 | ACTIVITY 09 PERSON, OPEX, MISC
| ILO | Activity 3.2.3 - Provide TA to engender the annual enterprise survey |  |  | x | x | GSO | GSO Collaborating agencies: VCCI | ILO | CONTRACTS | 5775 | 8925 | 14700 | ACTIVITY 09 PERSON, OPEX, MISC
| UNICEF | Activity 3.2.4 - Compile data on children and gender equality for reporting on national and international commitments, through existing national household surveys |  | x | x |  | GSO | MOLISA | UNICEF | TRAINING of counterpart | 22100 | 0 | 22100 | ACTIVITY O6 PERSON, OPEX, MISC
Output 3.3: Data and information collected to promote national gender equality policy dialogues for marginalized groups. Output 3.3 Indicators: - Gender Equality data concerning marginalized women is collected; - Policy reports/papers cite data on marginalized women Annual targets : + Research Plan developed; Existing Data collected; National and International consultants recruited (3.3.2) + Local and international consultants recruited; Research Plans developed; Data collected (3.3.3)
| IOM | Activity 3.3.2 - Assess incidence of trafficking in boys and girls to provide data to ensure adequate attention is paid to the trafficking of boys. It is used for advocacy for anti trafficking policies |  |  | x | x | GSO | Selected NGOs Collaborating agencies: GSO | IOM | CONTRACTS | 9813 | 2804 | 12617 | ACTIVITY 09 Will start in Q3/2009 and continue in 2010.
|  | 3.3.2.1 Organize a consultative workshop to develop a research plan |  |  | x |  | GSO | [5 empty] | 0 | PERSON, OPEX, MISC
|  | 3.3.2.2 Review existing data |  |  |  | x | GSO | [5 empty] | 0 | PERSON, OPEX, MISC
|  | 3.3.2.3 Recruitment of national and international consultants |  |  |  | x | GSO | [5 empty] | 0 | PERSON
| IOM | Activity 3.3.3 - Research on remittances from migrant workers in gender perspective including a costing of remittances and pilot interventions to better inform duty-bearers charged with developing appropriate degrees and policies related to the two laws |  | x | x | x | GSO | Selected research institute Collaborating agencies: GSO | IOM | CONTRACTS | 5140 | 2804 | 7944 | ACTIVITY 09 Will start in Q2/2009 and continue in 2010.
|  | 3.3.3.1 Recruit local and international consultants |  | x |  |  | GSO | [5 empty] | 0 | PERSON
|  | 3.3.3.2 Build research plans |  |  | x |  | GSO | [5 empty] | 0 | PERSON, OPEX, MISC
|  | 3.3.3.3 Make research, analyze results and prepare research reports |  |  |  | x | GSO | [5 empty] | 0 | PERSON, OPEX, MISC
Output 3.4: Centralized clearinghouse of gender research reports and indicators by government, donors and political and civil society groups (VWU) established (through GSO). Output 3.4 Indicators: - A centralized system for gender research reports and data available; - Annual sex-disaggregated statistics document developed and disseminated Annual targets : + Availability of CRC/CEDAW database (3.4.3)
| UNICEF | Activity 3.4.3 - Build a database on the International Convention of Children’s Rights, CEDAW and "a World appropriate for Children” using Viet info technology |  |  | x | x | GSO | GSO Collaborating agencies: MOLISA | UNICEF | CONTRACTS | 5000 | 0 | 5000 | ACTIVITY 09 To be continued in Y2
|  | 3.4.3.1 Support GSO to develop CRC/CEDAW database using VI technology (including on-the-job data admin training for core staff of GSO and MOLISA) |  |  | x | x | GSO |  |  |  | 5000 |  | 5000 | PERSON, OPEX, MISC
| UNFPA | Support for CPMU | [8 empty] | 19045 | 29438 | 48483
| (i) | Support Annual JP Progress Review Meetings and other JP activities to be organized by the CPMU |  |  |  |  | GSO | GSO | UNFPA | TRAINING of counterpart | 3400 | 2517 | 5917 | - TRAINING X1
| (ii) | Support salary for CPMU and monitoring | [9 empty] | 0 | 0
|  | Support salary for 2 full-time staff (01 Component Project Manager and 01 assistant cum Accountant) for management of CPMU |  |  | X | X | GSO | GSO | UNFPA | PERSONNEL - Salary for CPMU staff | 12825 | 24022 | 36847 | ACTIVITY 02
|  | JP Monitoring by NIPs |  | X | X | X | GSO | GSO | UNFPA | PERSONNEL -Monitoring by NIP | 1000 | 0 | 1000 | ACTIVITY 02
| (iii) | JP Monitoring by UN Agency (UNFPA) |  | X | X | X | GSO | GSO | UNFPA | PERSONNEL -Monitoring | 0 | 1000 | 1000 | ACTIVITY 03
| (iv) | Support expendable equipment, materials, rental of other equipment. |  | X | X | X | GSO | GSO | UNFPA | SUPPLIES, commodities, equipment and transport | 1000 | 500 | 1500 | ACTIVITY 01
| (v) | Other Direct Costs |  |  |  |  | GSO | GSO | UNFPA | OTHER DIRECT COSTS | 820 | 1399 | 2219 | ACTIVITY 10
|  | (i) Support for translation |  | X | X | X | [6 empty] | 0
|  | (ii) Support for bank charge, telephone charge, audit fees, exchange losses. |  | X | X | X | [6 empty] | 0
|  | (iii) Support for audit fees | [10 empty] | 0
|  | PROGRAMME COST | [8 empty] | 188369 | 203403.5 | 391772.5 |  | 391772.5
|  | INDIRECT SUPPORT COSTS (7%) | [8 empty] | 13185.83 | 14238.245 | 27424.075 | ICFORUNFPA
|  | TOTAL PLANNED BUDGET | [8 empty] | 201554.83 | 217641.745 | 419196.575
[11 empty] | Total Programme Budget |  | Indirect Support Cost | Total Planned Budget
[11 empty] | National Implementation | UN Implementation
|  | Total for UNDP Implementation | [9 empty] | 30000 | 2100 | 32100
|  | Total for IOM Implementation | [9 empty] | 5608 | 392.56 | 6000.56
|  | Total for WHO Implementation | [9 empty] | 72250 | 5057.5 | 77307.5
|  | Total for ILO Implementation | [9 empty] | 17063.5 | 1194.445 | 18257.945
|  | Total for FA0 Implementation | [9 empty] | 42056 | 2943.92 | 44999.92
|  | Total for UNICEF Implementation | [9 empty] | 0 | 0 | 0
|  | Total for UNFPA Implementation | [9 empty] | 36426 | 2549.82 | 38975.82
|  | Total for national implementation - fund received via UNFPA as MA (b) | [8 empty] | 188369 |  | 13185.83 | 201554.83
|  | Total fund received by UNFPA (a+b) | [8 empty] | 188369 | 36426 | 15735.65 | 240530.65
|  | Grand Total | [8 empty] | 188369 | 203403.5 | 27424.075 | 419196.575
[13 empty] | 70583.8 | 1078923.8
Signatures
| UNFPA as Managing Agent | [9 empty] | Ministry of Planning and Investment
General Statistics Office
| Bruce Campbell | [9 empty] | Do Thuc
| UNFPA Representative in Viet Nam | [9 empty] | General Deputy -Director of General Statistical Office
| Date______________________ | [9 empty] | Date______________________
Note on K8: Chau: Not including Indirect Support Costs (7%)
Note on K20: Nguyen Thi Thuy: WHO leaved 2 categories in Annex 3 (B) vs. AWP. But it's closed to 'Contract'