## UNDP FAO WP
Annex A: WORK PLAN
For MDGF1713-E-11a-AFG “Strengthened Approach for the Integration of Sustainable Environmental Management in Afghanistan”
Period: 1st Year 2009
Annual targets | Activities | TIME FRAME |  |  |  | UN AGENCY | RESPON-SIBLE PARTY | PLANNED BUDGET
1st year
|  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Amount
JP Output 1.1: National environmental concerns reflected in the ANDS and selected sectoral plans, and institutional capacity strengthened to operationalise them.
Annual targets: | Activity 1.1.1 |  |  |  |  | UNDP | NEPA | MDG-F | Training of counterparts | 6000
| i. Desk review of existing references; | [7 empty] | Contracts | 10000
UNDP: Environmental mainstreaming guideline drafted; NABDP infrastructure operational guideline revised; NEPA capacity assessment initiated | ii. Technical consultation with NEPA, UNEP and other partners, including finalization of the list of relevant line ministries (to be selected from the CEC members) and departments; | [7 empty] | Personnel | 143077.9935
| iii. Identify focal points within the target ministries / departments; | [7 empty] | Supplies, commodities, equipment and transport | 24115
FAO: Training needs identified and training initiated, the range land monitoring tools designed | iv. Organise consultation workshops with the identified ministry participants towards a needs assessment; | [7 empty] | Travel | 2229
| v. Draft an environmental mainstreaming guideline/user friend tool for usage by ministries in their programme work | [7 empty] | Miscellaneous | 4340
[9 empty] | F&A* | 14283.1608
| Activity 1.1.2: |  |  |  |  | UNDP | MRRD | MDG-F | Training of counterparts | 8000
| i. Share the draft environmental mainstreaming guideline with MRRD, and prepare guideline piloting schedule within NABDP; | [7 empty] | Personnel | 52103.1678
| ii. Incorporate environmental guideline into the NABDP operational (PCM) guideline on infrastructure projects | [7 empty] | Supplies, commodities, equipment and transport | 24115
[9 empty] | Travel | 2229
[9 empty] | Miscellaneous | 3160
[9 empty] | F&A | 6744.6255
| Activity 1.1.3: |  |  |  |  | UNDP | NEPA | MDG-F | Training of counterparts | 4000
| i. Review past capacity assessment of NEPA, if any, and on-going external support provided to NEPA (in addition to UNEP support) to identify capacity needs; | [7 empty] | Contracts | 5000
| ii. Conduct capacity assessment which includes self-assessment by NEPA staff and departments, sensitization workshops, review of division ToRs in light of the ANDS Environment Strategy; | [7 empty] | Travel | 8969
[9 empty] | Personnel | 39317.5166
[9 empty] | Supplies, commodities, equipment and transport | 24115
[9 empty] | Miscellaneous | 3200
[9 empty] | F&A | 6367.8561
| Activity 1.1.4: |  |  |  |  | FAO | MoAIL | MDG-F | Training of counterparts | 10000
| i. Review current annual planning process related to Rangeland Management and identify the gaps and options for improvement; | [7 empty] | Personnel | 14168
| ii. Train the MoAIL’s Range Land Department in planning implementing, and monitoring range land management activities based on (i); | [7 empty] | Supplies, commodities, equipment and transport | 0
[9 empty] | Travel | 0
[9 empty] | Miscellaneous | 0
[9 empty] | F&A | 1819
| Activity 1.1.5: |  |  |  |  | FAO | MoAIL | MDG-F | Travel | 17200
| i. Establish together with Range Land Department a central monitoring database to document (legal documentation, maps, management plans) participatory range land management initiatives and to monitor the improvement (or degradation) of range land condition in areas under community management. | [7 empty] | Personnel | 54568
[9 empty] | Supplies, commodities, equipment and transport | 88850
[9 empty] | Miscellaneous | 6764
[9 empty] | F&A | 12599
597334.3202
JP Output 1.2: Environmental concerns are fully reflected in provincial and district development plans.
Annual targets: | Activity 1.2.1: |  |  |  |  | UNDP | NEPA | MDG-F | Contracts | 20000
| i. Design and agree on the content of environmental awareness materials and media programmes in consultation with the programme partners (NEPA, UNEP, MoAIL, FAO, MRRD) | [7 empty] | Personnel | 43743.3189
UNDP: Environmental awareness materials designed; target communities for awareness building identified and capacity assessed, formulation of environmental sub-committees initiated under CDC/DDA; MRRD community empowerment guideline revised and target community selection criteria developed | [8 empty] | Supplies, commodities, equipment and transport | 24115
[9 empty] | Travel | 2229
FAO: Nil | [8 empty] | Miscellaneous | 3200
[9 empty] | F&A | 7021.6262
| Activity 1.2.2: |  |  |  |  | UNDP | MRRD | MDG-F | Training of counterparts | 12000
| i. In consultation with FAO and UNEP, identify target communities for general environmental awareness training in the same districts/provinces identified as above; | [7 empty] | Personnel | 56528.9701
| ii. Undertake a quick needs assessment of capacities and environmental status in the target communities; | [7 empty] | Supplies, commodities, equipment and transport | 24115
| iii. Establish environment sub-committees under existing DDAs, CDCs or shuras (where possible separate women groups for more women-oriented awareness) | [7 empty] | Travel | 2229
[9 empty] | Miscellaneous | 2500
[9 empty] | F&A | 7329.1483
| Activity 1.2.3: |  |  |  |  | UNDP | MRRD | MDG-F | Training of counterparts | 16000
| i. Review MRRD/NABDP operational guideline on community empowerment to reflect environmental concepts; | [7 empty] | Contracts | 5000
| ii. Develop prioritization criteria checklist for selecting target provinces/districts for environmental mainstreaming; | [7 empty] | Personnel | 46693.8538
[9 empty] | Supplies, commodities, equipment and transport | 24115
[9 empty] | Travel | 2229
[9 empty] | Miscellaneous | 2800
[9 empty] | F&A | 7288.8707
309137.7879
JP Output 2.1: Communities are able to develop and implement projects for sustainable use of natural resources and livelihoods
Annual targets: | Activity 2.1.1: (No activity planned for Year 1) |  |  |  |  | UNDP | MRRD | MDG-F
| Activity 2.1.2 |  |  |  |  | FAO | MoAIL | MDG-F | Travel | 6600
UNDP:Nil | i. Conduct RRA focusing on NR (range land and water) utilization in all accessible districts (3 provinces) | [7 empty] | Personnel | 19368
| ii. Select target communities based on RRA results and NRM priorities identified during local planning processes (CDC, district and provincial levels), in consultation with UNDP/MRRD and UNEP | [7 empty] | Supplies, commodities, equipment and transport | 0
FAO: RRA/PRA conducted and target communities selected.Formulation of the rangeland management plan initiated in at least one provice. Livelihood improvement plans developed and implementation of relevant proejcts initiated in at least one province. | [8 empty] | Miscellaneous | 1932
[9 empty] | F&A | 2100
| Activity 2.1.3: |  |  |  |  | FAO | MoAIL | MDG-F | Travel | 10400
| i. Conduct PRA covering Range Land utilization and user rights, resource condition and livelihoods support systems in selected target communities (in preparation of range land management and integrated livelihoods improvement activities. | [7 empty] | Personnel | 55068
| ii. Finalise the indicators to monitor and evaluate the NRM activities. | [7 empty] | Supplies, commodities, equipment and transport | 47900
| iii. Based on the PRA exercise, set initial baseline data for future evaluation | [7 empty] | Miscellaneous | 2882
[9 empty] | F&A | 8750
| Activity 2.1.4: |  |  |  |  | FAO | MoAIL | MDG-F | Training of counterparts | 15000
| i. Facilitate the establishment of local Range Land Management Committees (to be termed as “Community Range Land Associations” under the draft Range Land Law, which may be established within CDCs); | [7 empty] | Travel | 10400
| ii. Develop of range land management plans including resource mapping, protection, regulations, conflict resolution mechanisms, range land improvement measures and participatory monitoring systems | [7 empty] | Personnel | 64404
[9 empty] | Supplies, commodities, equipment and transport | 70850
[9 empty] | Miscellaneous | 6714
[9 empty] | F&A | 12598
| Activity 2.1.5: (No activities in Year 1) |  |  |  |  | FAO | MoAIL | MDG-F
| Activity 2.1.6: |  |  |  |  | FAO | MoAIL | MDG-F | Training of counterparts | 15000
| i. Review the existing livelihood options within the communities; | [7 empty] | Personnel | 27368
| ii. In collaboration with MRRD/UNDP, identify areas of intervention focusing on environmental and social sustainability; | [7 empty] | Supplies, commodities, equipment and transport | 7350
| iii. In collaboration with MRRD/UNDP, plan integrated livelihoods improvement activities through community based approaches | [7 empty] | Travel | 3600
[9 empty] | Miscellaneous | 2482
[9 empty] | F&A | 4200
| Activity 2.1.7: |  |  |  |  | FAO | MoAIL | MDG-F | Contracts | 50000
| i. In collaboration with MRRD/UNDP, implement integrated livelihoods improvement plans in support of range land management activities | [7 empty] | Personnel | 58736
[9 empty] | Supplies, commodities, equipment and transport | 42350
[9 empty] | Travel | 3600
[9 empty] | Miscellaneous | 3382
[9 empty] | F&A | 11898
| Activity 2.1.8:(not planned in Year 1) |  |  |  |  | FAO | MoAIL | MDG-F
564932
JP Output 2.2: Institutional knowledge management improved in relation with community based field interventions
Annual targets: | Activity 2.2.1: |  |  |  |  | UNDP | MRRD | MDG-F | Training of counterparts | 4000
| i. Desk review of existing CBNRM training manuals and references; | [7 empty] | Personnel | 60135.1794
UNDP: Desk review of existing CBNRM manuals and references conducted; technical consultation with FAO, UNEP and other partners conducted | ii. Conduct technical consultation with FAO, UNEP and other partners who have carried out CBNRM in the country; | [7 empty] | Supplies, commodities, equipment and transport | 24115
[9 empty] | Travel | 2229
FAO: Workshop & training planned and initiated. | [8 empty] | Miscellaneous | 3200
[9 empty] | F&A | 7051.121
| Activity 2.2.2: |  |  |  |  | FAO | MoAIL | MDG-F | Training of counterparts | 8000
| Training on Participatory Rural Appraisal, Participatory Monitoring and CBNRM (initial technical training needed for the implementation of range land management activities by government, non-government and community partners | [7 empty] | Personnel | 0
[9 empty] | Supplies, commodities, equipment and transport | 12350
[9 empty] | Travel | 3600
[9 empty] | Miscellaneous | 2182
[9 empty] | F&A | 1967
| Activity 2.2.3: |  |  |  |  | FAO | MoAIL | MDG-F | Training of counterparts | 4000
| In country study tours for field level government, non-government and community partners directly involved in range land management activities. | [7 empty] | Personnel | 0
[9 empty] | Supplies, commodities, equipment and transport | 3850
[9 empty] | Travel | 3600
[9 empty] | Miscellaneous | 2482
[9 empty] | F&A | 1049
143810.3004
Total Planned Budget | [9 empty] | 1615214.4086
* F&A is 7% agency overhead calculated with “off-the-top” method – [programmable amount ÷ 93 x7] | [10 empty] | Sum of US$ Amount | UN Agencies |  | Grand Total
[12 empty] | FAO | UNDP
[11 empty] | Personnel | 293680 | 441600 | 735280
[11 empty] | Contracts | 50000 | 40000 | 90000
[11 empty] | Training of counterparts | 52000 | 50000 | 102000
[11 empty] | Supplies, commodities, equipment and transport | 273500 | 168805 | 442305
[11 empty] | Travel | 59000 | 22343 | 81343
[11 empty] | Miscellaneous | 28820 | 22400 | 51220
[11 empty] | F&A | 56980 | 56086.4086 | 113066.4086
[11 empty] | Total costs | 813980 | 801234.4086 | 1615214.4086