## Drft 6 Month (Jun-Nov 09) WP
SAISEM Project Joint (FAO-UNDP-UNEP) June - Nov. 2009 Work plan
Project Document Outputs | ProDoc Activities | Priority Activities | Timeline | HOW | Remarks (Programme, Budget, etc.) | UNEP Advisory Role
JP Output 1.1: National environmental concerns reflected in the ANDS and selected sectoral plans, and institutional capacity strengthened to operationalize them | Activity 1.1.1 (UNDP)
| i. Desk review of existing references | Review guidelines and policy frameworks regarding environment management. | July-Aug. |  |  | Baseline Situation Report produced
| ii. Technical consultation with NEPA, UNEP, and other partners, including finalization of the list of relevant ministries and depts. |  | Completed | round table participatory discussions | Completed | Check outcomes with UNEP (Tek Gurung) and Ecodit
| iii. Identify focal points within the target ministries/departments |  | Completed |  | Completed | Check outcomes with UNEP (Tek Gurung) and Ecodit
| iv. Organize consultation workshops with the identified ministry participants with the objective of completing a needs assessment; | Organize one training workshop (3-5 days) for NEPA officials (50) to address training needs identified in the capacity and training needs assessment | Aug. | selection of participants with NEPA, drawing a training module, developing training modules, and organizing and conducting w/shop
|  | Organize one consultative workshop for identified line ministry focal points (30) for the purpose of completing needs assessment | Aug.
| v. Draft an environmental mainstreaming guideline/user friendly tool for usage by ministries in their programme work | Joint project staff will draft guidelines in consultation with NEPA, MRRD, and MoAIL | Oct.-Nov. |  |  | UNEP can review (Tek Gurung)
|  | Conduct one consultative workshop involving NEPA, MRRD, MoAIL, and other relevant line Ministries and departments to discuss the proposed guidelines. | Oct.-Nov.
Activity 1.1.2 (UNDP)
| i. Share the draft environmental mainstreaming guidelines with MRRD, and prepare guidelines piloting schedule within NABDP | Joint project team will share the guidelines mentioned above [See Activity 1.1.1.(v)] | Oct.-Nov. | share hard and soft copies and request for in-put
|  | Conduct four meetings with NABDP/Community Empowerment Unit, and Rural Energy Unit regarding the development of mechanisms schedule | Oct.-Nov. | meetings and w/shop settings with presentations, discussions, and participants feedbacks | 100 per meeting for 4 meetings
|  | Translate the guidelines into Pashto and Dari | Nov. |  | 500 pgs/$14
| ii. Incorporate environmental guidelines into the NABDP operational (PCM) guideline on infrastructure projects | Convene two meetings with NABDP to initiate the process of incorporation of environmental guidelines into the project cycle management (PCM) | Sept. - Oct. | developing concepts, suggestions, deskwork as well as meetings | 300/meeting
|  | Development of revised environmental guidelines for infrastructure projects | Nov.
Activity 1.1.3 (UNDP)
| i. Review past capacity assessment of NEPA, and on-going external support provided to NEPA (in addition to UNEP support) to identify capacity needs |  | June - July |  | Process initiated in Jan.; Nat. Training Coor. needs to meet with NEPA program division chiefs and other organizations (offering training) to update | Project staff reviewed draft Training Plan and SWOT Analysis developed Mar. - April
Activity 1.1.4 (FAO)
| (i) Review current annual planning process related to rangeland management and identify the gaps and options for improvement; | No work planned in the time frame under consideration (work will be conducted during winter months)
| (ii) Train the MoAIL's rangeland department in planning, implementing and monitoring rangeland activities based on (i) | No work planned in the time frame under consideration (work will be conducted during winter months) |  |  | Conduct training for MoAIL staff | Work with SALEH project, synergies with training given already by ICIMOD
Activity 1.1.5 (FAO)
| i. Establish together with the Rangeland Department a central monitoring database (legal documentation, maps, management plans) to document participatory rangeland management initiatives and to monitor the improvement (or degradation) of rangeland condition in areas under community management | Contact all organizations registered with MAIL for rangeland-related work to request project documentation as described in the activity. Transfer all documentation to PDF documents and create Excel database | Completed by July 15 |  | (Communication Cost)
JP Output 1.2: Environmental concerns are fully reflected in provincial and district development plans. | Activity 1.2.1 (UNDP)
| i. Design and agree on the content of environmental awareness materials and media programmes in consultation with the programme partners (NEPA, UNEP, MoAIL, FAO, MRRD); | Organize two consultation meetings for designing environmental awareness materials |  |  | Development of Communication Strategy, Consideration of CC (Climate Change) | Avoid overlap with what UNEP has done already
|  | Design media programmes and sign contracts with relevant media companies |  |  | 2 documentaries (5000 ea) 4 radio programmes (500 ea) and 1 TV Special(3000)/month | Join forces with UNEP EE component and do a joint activity
|  | Publish one full-page monthly environment article in national printed media (Newspapers, Magazines, etc.) |  |  | 2000 per full page | Coordinate with UNEP (Soudeh Jamshidian)
|  | Support NEPA to commemorate important national and international environmental days (e.g., WED, Mountains Day) |  |  | 10000 per day | Requires close coordination with UNEP and FAO. Also liaise with UNAMA RCO media relation officer
Activity 1.2.2 (UNDP - FAO)
| i. In consultation with UNEP, identify target communities for general environmental awareness training in the same districts/provinces identified; |  | Aug-Sep | concepts, training modules, discussions | 50 ppl US$100/person for 3 days | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). Ernie Wijangco is the UNEP focal point.
|  | Prioritized and selected the targeted provinces and districts | July |  |  | The selection criteria will be discussed and agreed by all
| ii. Undertake a quick needs assessment of capacities and environmental status in the target communities; | Visit potential implementation partners and conclude the selection of prospective project areas by the end of July 09 (UNDP). Systematic community assessment will be conducted in the community selection and mobilization process to be initiated in July (FAO). | June - July | organizing field missions and visiting communities in conjunction with MRRD/NABDP structures and personnel in the provinces |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan).
| iii. Establishment of environment sub-committees under existing DDAs, CDCs or shuras (where possible separate women groups for more women-oriented awareness) | Environmental sub-committees (within DDAs and CDCs) established in consultation with MRRD and NABDP (UNDP). Review of best suitable community mobilization mechanism will be conducted specific to each cooperating community (FAO). | July- Nov. |  | Request NABDP support for convening DDAs meetings; Request NSP support for convening CDC meetings. | Look at draft rangeland law and forest law
Activity 1.2.3 (UNDP)
| i. Review MRRD/NABDP operational guidelines on community empowerment to reflect environmental concepts; | Organize meetings with MRRD/NABDP to review Operational Guidelines. | Sept. | through meetings with partners to understand what is available
|  | Consultative meetings and planning workshops with MRRD/NABDP for the integration of environmental concepts into the Operational Guidelines | Oct. | meetings and w/shop settings with presentations, discussions, and participants feedbacks |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan).
| ii. Develop prioritization criteria checklist for selecting target provinces/districts for environmental mainstreaming; | The process of selecting the project areas will be completed by July (refer to Activity 1.2.2) | July |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan).
JP Output 2.1: Communities are able to develop and implement projects for sustainable use of natural resources and livelihoods (to include rural energy systems). | Activity 2.1.1 (No Activities for Y1)
Activity 2.1.2 (FAO)
| (i) Conduct RRA focusing on NR (rangeland and water) utilization in all accessible districts (three provinces) | This activity overlaps with 1.2.2 (ii) and (iii). A systematic community selection and mobilization process is required to identify communities with adequate cooperation potential. This process must encompass all relevant aspects: natural resources, social structure, wealth distribution, community attitude towards communal action, relationships within the community and with neighboring communities | July-Nov. |  | Travel cost and meetings with different communities of the three provinces
| (ii) Select target communities based on RRA results and NRM priorities identified during local planning processes (CDC, district and provincial levels), in consultation with UNDP/MRRD and UNEP | see above | July-Nov. |  | Travel cost and meetings with CDCs and line ministries | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan).
Activity 2.1.3 (FAO)
| (i) Conduct PRA covering rangeland utilization and user rights, resource condition and livelihoods support systems in selected target communities in preparation of rangeland and integrated livelihoods improvement activities. | This activity overlaps with 1.2.2 (ii) and (iii). A systematic community selection and mobilization process is required to identify communities with adequate cooperation potential. This process must encompass all relevant aspects: natural resources, social structure, wealth distribution, community attitude towards communal action, relationships within the community and with neighboring communities | July-Nov. |  | Conducting workshops for PRA and land user rights and woodlots and fodder crop Demo-plots establishment | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan).
| (ii) Finalize the indicators to monitor and evaluate the NRM activities | see above | July-Nov.
| (iii) Based on the PRA exercise, set initial baseline data for future evaluation | see above | July-Nov.
Activity 2.1.4 (FAO)
| (i) Facilitate the establishment of local rangeland management committees (to be termed 'Community Rangeland Associations") under the draft rangeland law, which may be established within CDCs | To be conducted during the community selection and mobilization process | July-Nov. |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). Ensure that national policy and legislative framework is complied with
| (ii) Development of rangeland management plans including resource mapping, protection, regulations, conflict resolution mechanisms, rangeland improvement measures and participatory monitoring systems | Initiated in the community selection and mobilization process. Process will have to be continued in Y 2 | July-Nov. |  | Three missions to three provinces /Conduct workshops | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). Ensure that national policy and legislative framework is complied with
Activity 2.1.5 (FAO) (No Activities for Y1)
(i) Support local communities implementation of the rangeland management plan prepared above
(ii) Conduct Community Based Participatory M&E to evaluate the intervention
Activity 2.1.6 (FAO)
| (i) Review the existing livelihood options within the communities | see above | July-Nov.
| (ii) In collaboration with MRRD/UNDP, identify areas of intervention focusing on environmental and social sustainability | see above | July-Nov. |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan)
| (iii) In collaboration with MRRD/UNDP, plan integrated livelihoods improvement activities through community based approaches | see above | July-Nov. |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan)
Activity 2.1.7 (FAO)
| (i) In collaboration with MRRD/UNDP, implement integrated livelihoods improvement plans in support of range land management activities | No activities planned for Y 1
| (ii) In collaboration with MRRD/UNDP, conduct participatory M&E of the livelihood improvement activities implemented in | No activities planned for Y 1
Activity 2.1.8 (FAO)
| (i) Identify potential irrigation/water harvesting structures based on PRA for intervention | Initiated in the community selection and mobilization process
| (ii) Select the appropriate projects based on technical need and local priorities | Initiated in the community selection and mobilization process
| (iii) Finalize detail design and cost estimate after technical and social survey | No activities planned for Y 1
| (iv) Implement construction through community mobilization | No activities planned for Y 1
JP Output 2.2: Institutional knowledge management improved in relation with community based field interventions | Activity 2.2.1 (UNDP)
| i. Desk review of existing CBNRM training manuals and references | Undertake desk review of existing CBNRM training manuals and references; | Nov |  |  | Coordinate with UNEP (Ernie Wijangco).
| ii. Conduct technical consultation with FAO, UNEP and other partners who have carried out CBNRM in the country; | Meetings with FAO, UNEP and other partners |  |  |  | Coordinate with UNEP (Ernie Wijangco).
|  | Based on the reviews conducted develop and as needed update existing CBNRM training manuals |  |  | Meeting, Translation, Publications, Distribution | Link to SALEH
Activity 2.2.2 (FAO)
| Training on participatory rural appraisal, participatory monitoring and CBNRM (initial technical training needed for the implementation of rangeland activities by government, non-government and community partners | Identifying and including MAIL personnel in field team for community selection and mobilization - training on the job | July-Oct. |  |  | Can be done in collaboration with UNEP under its CBNRM programme.
Activity 2.2.3 (FAO)
| In country study tours for field level government, non-government and community partners directly involved in rangeland management activities | No activities planned for Y 1 |  |  |  | Link to SALEH, NGO programs

## Drft 6 Month (Jun-Nov 09)-B
SAISEM Project Joint (FAO-UNDP-UNEP) June - Nov. 2009 Work plan
Project Document Outputs | ProDoc Activities | Priority Activities | Timeline | HOW | Remarks (Programme, Budget, etc.) | UNEP Advisory Role | Budget Projections (USD)
JP Output 1.1: National environmental concerns reflected in the ANDS and selected sectoral plans, and institutional capacity strengthened to operationalize them | Activity 1.1.1 (UNDP)
| i. Desk review of existing references | Review guidelines and policy frameworks regarding environment management. | July-Aug. |  |  | Baseline Situation Report produced | 2000
| ii. Technical consultation with NEPA, UNEP, and other partners, including finalization of the list of relevant ministries and depts. |  | Completed | round table participatory discussions | Completed | Check outcomes with UNEP (Tek Gurung) and Ecodit | 0
| iii. Identify focal points within the target ministries/departments |  | Completed |  | Completed | Check outcomes with UNEP (Tek Gurung) and Ecodit | 0
| iv. Organize consultation workshops with the identified ministry participants with the objective of completing a needs assessment; | Organize one training workshop (3-5 days) for NEPA officials (50) to address training needs identified in the capacity and training needs assessment | Aug. | selection of participants with NEPA, drawing a training module, developing training modules, and organizing and conducting w/shop |  |  | 20500
|  | Organize one consultative workshop for identified line ministry focal points (30) for the purpose of completing needs assessment | Aug. |  |  |  | 3000
| v. Draft an environmental mainstreaming guideline/user friendly tool for usage by ministries in their programme work | Joint project staff will draft guidelines in consultation with NEPA, MRRD, and MoAIL | Oct.-Nov. |  |  | UNEP can review (Tek Gurung)
|  | Conduct one consultative workshop involving NEPA, MRRD, MoAIL, and other relevant line Ministries and departments to discuss the proposed guidelines. | Oct.-Nov. |  |  |  | 2000
Activity 1.1.2 (UNDP)
| i. Share the draft environmental mainstreaming guidelines with MRRD, and prepare guidelines piloting schedule within NABDP | Joint project team will share the guidelines mentioned above [See Activity 1.1.1.(v)] | Oct.-Nov. | share hard and soft copies and request for in-put |  |  | 1000
|  | Conduct four meetings with NABDP/Community Empowerment Unit, and Rural Energy Unit regarding the development of mechanisms schedule | Oct.-Nov. | meetings and w/shop settings with presentations, discussions, and participants feedbacks | 100 per meeting for 4 meetings |  | 400
|  | Translate the guidelines into Pashto and Dari | Nov. |  | 500 pgs/$14 |  | 7000
| ii. Incorporate environmental guidelines into the NABDP operational (PCM) guideline on infrastructure projects | Convene two meetings with NABDP to initiate the process of incorporation of environmental guidelines into the project cycle management (PCM) | Sept. - Oct. | developing concepts, suggestions, deskwork as well as meetings | 300/meeting |  | 600
|  | Development of revised environmental guidelines for infrastructure projects | Nov. |  |  |  | 2000
Activity 1.1.3 (UNDP)
| i. Review past capacity assessment of NEPA, and on-going external support provided to NEPA (in addition to UNEP support) to identify capacity needs |  | June - July |  | Process initiated in Jan.; Nat. Training Coor. needs to meet with NEPA program division chiefs and other organizations (offering training) to update | Project staff reviewed draft Training Plan and SWOT Analysis developed Mar. - April
Activity 1.1.4 (FAO)
| (i) Review current annual planning process related to rangeland management and identify the gaps and options for improvement; | No work planned in the time frame under consideration (work will be conducted during winter months)
| (ii) Train the MoAIL's rangeland department in planning, implementing and monitoring rangeland activities based on (i) | No work planned in the time frame under consideration (work will be conducted during winter months) |  |  | Conduct training for MoAIL staff | Work with SALEH project, synergies with training given already by ICIMOD | 10000
Activity 1.1.5 (FAO)
| i. Establish together with the Rangeland Department a central monitoring database (legal documentation, maps, management plans) to document participatory rangeland management initiatives and to monitor the improvement (or degradation) of rangeland condition in areas under community management | Contact all organizations registered with MAIL for rangeland-related work to request project documentation as described in the activity. Transfer all documentation to PDF documents and create Excel database | Completed by July 15 |  | (Communication Cost) |  | 500
JP Output 1.2: Environmental concerns are fully reflected in provincial and district development plans. | Activity 1.2.1 (UNDP)
| i. Design and agree on the content of environmental awareness materials and media programmes in consultation with the programme partners (NEPA, UNEP, MoAIL, FAO, MRRD); | Organize two consultation meetings for designing environmental awareness materials |  |  | Development of Communication Strategy, Consideration of CC (Climate Change) | Avoid overlap with what UNEP has done already | 2000
|  | Design media programmes and sign contracts with relevant media companies |  |  | 2 documentaries (5000 ea) 4 radio programmes (500 ea) and 1 TV Special(3000)/month | Join forces with UNEP EE component and do a joint activity | 40000
|  | Publish one full-page monthly environment article in national printed media (Newspapers, Magazines, etc.) |  |  | 2000 per full page | Coordinate with UNEP (Soudeh Jamshidian) | 12000
|  | Support NEPA to commemorate important national and international environmental days (e.g., WED, Mountains Day) |  |  | 10000 per day | Requires close coordination with UNEP and FAO. Also liaise with UNAMA RCO media relation officer | 20000
Activity 1.2.2 (UNDP - FAO)
| i. In consultation with UNEP, identify target communities for general environmental awareness training in the same districts/provinces identified; |  | Aug-Sep | concepts, training modules, discussions | 50 ppl US$100/person for 3 days | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). Ernie Wijangco is the UNEP focal point. | 15000
|  | Prioritized and selected the targeted provinces and districts | July |  |  | The selection criteria will be discussed and agreed by all | 0
| ii. Undertake a quick needs assessment of capacities and environmental status in the target communities; | Visit potential implementation partners and conclude the selection of prospective project areas by the end of July 09 (UNDP). Systematic community assessment will be conducted in the community selection and mobilization process to be initiated in July (FAO). | June - July | organizing field missions and visiting communities in conjunction with MRRD/NABDP structures and personnel in the provinces |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). | 12400
| iii. Establishment of environment sub-committees under existing DDAs, CDCs or shuras (where possible separate women groups for more women-oriented awareness) | Environmental sub-committees (within DDAs and CDCs) established in consultation with MRRD and NABDP (UNDP). Review of best suitable community mobilization mechanism will be conducted specific to each cooperating community (FAO). | July- Nov. |  | Request NABDP support for convening DDAs meetings; Request NSP support for convening CDC meetings. | Look at draft rangeland law and forest law | 10000
Activity 1.2.3 (UNDP)
| i. Review MRRD/NABDP operational guidelines on community empowerment to reflect environmental concepts; | Organize meetings with MRRD/NABDP to review Operational Guidelines. | Sept. | through meetings with partners to understand what is available |  |  | 2000
|  | Consultative meetings and planning workshops with MRRD/NABDP for the integration of environmental concepts into the Operational Guidelines | Oct. | meetings and w/shop settings with presentations, discussions, and participants feedbacks |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). | 1000
| ii. Develop prioritization criteria checklist for selecting target provinces/districts for environmental mainstreaming; | The process of selecting the project areas will be completed by July (refer to Activity 1.2.2) | July |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). | 0
JP Output 2.1: Communities are able to develop and implement projects for sustainable use of natural resources and livelihoods (to include rural energy systems). | Activity 2.1.1 (No Activities for Y1)
Activity 2.1.2 (FAO)
| (i) Conduct RRA focusing on NR (rangeland and water) utilization in all accessible districts (three provinces) | This activity overlaps with 1.2.2 (ii) and (iii). A systematic community selection and mobilization process is required to identify communities with adequate cooperation potential. This process must encompass all relevant aspects: natural resources, social structure, wealth distribution, community attitude towards communal action, relationships within the community and with neighboring communities | July-Nov. |  | Travel cost and meetings with different communities of the three provinces |  | 24000
| (ii) Select target communities based on RRA results and NRM priorities identified during local planning processes (CDC, district and provincial levels), in consultation with UNDP/MRRD and UNEP | see above | July-Nov. |  | Travel cost and meetings with CDCs and line ministries | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). | 10000
Activity 2.1.3 (FAO)
| (i) Conduct PRA covering rangeland utilization and user rights, resource condition and livelihoods support systems in selected target communities in preparation of rangeland and integrated livelihoods improvement activities. | This activity overlaps with 1.2.2 (ii) and (iii). A systematic community selection and mobilization process is required to identify communities with adequate cooperation potential. This process must encompass all relevant aspects: natural resources, social structure, wealth distribution, community attitude towards communal action, relationships within the community and with neighboring communities | July-Nov. |  | Conducting workshops for PRA and land user rights and woodlots and fodder crop Demo-plots establishment | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). | 52000
| (ii) Finalize the indicators to monitor and evaluate the NRM activities | see above | July-Nov.
| (iii) Based on the PRA exercise, set initial baseline data for future evaluation | see above | July-Nov.
Activity 2.1.4 (FAO)
| (i) Facilitate the establishment of local rangeland management committees (to be termed 'Community Rangeland Associations") under the draft rangeland law, which may be established within CDCs | To be conducted during the community selection and mobilization process | July-Nov. |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). Ensure that national policy and legislative framework is complied with | 16000
| (ii) Development of rangeland management plans including resource mapping, protection, regulations, conflict resolution mechanisms, rangeland improvement measures and participatory monitoring systems | Initiated in the community selection and mobilization process. Process will have to be continued in Y 2 | July-Nov. |  | Three missions to three provinces /Conduct workshops | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan). Ensure that national policy and legislative framework is complied with | 24000
Activity 2.1.5 (FAO) (No Activities for Y1)
(i) Support local communities implementation of the rangeland management plan prepared above
(ii) Conduct Community Based Participatory M&E to evaluate the intervention
Activity 2.1.6 (FAO)
| (i) Review the existing livelihood options within the communities | see above | July-Nov.
| (ii) In collaboration with MRRD/UNDP, identify areas of intervention focusing on environmental and social sustainability | see above | July-Nov. |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan)
| (iii) In collaboration with MRRD/UNDP, plan integrated livelihoods improvement activities through community based approaches | see above | July-Nov. |  |  | Link to UNEP CBNRM project areas (Bamiyan, Herat, Badakshan)
Activity 2.1.7 (FAO)
| (i) In collaboration with MRRD/UNDP, implement integrated livelihoods improvement plans in support of range land management activities | No activities planned for Y 1
| (ii) In collaboration with MRRD/UNDP, conduct participatory M&E of the livelihood improvement activities implemented in | No activities planned for Y 1
Activity 2.1.8 (FAO)
| (i) Identify potential irrigation/water harvesting structures based on PRA for intervention | Initiated in the community selection and mobilization process
| (ii) Select the appropriate projects based on technical need and local priorities | Initiated in the community selection and mobilization process
| (iii) Finalize detail design and cost estimate after technical and social survey | No activities planned for Y 1
| (iv) Implement construction through community mobilization | No activities planned for Y 1
JP Output 2.2: Institutional knowledge management improved in relation with community based field interventions | Activity 2.2.1 (UNDP)
| i. Desk review of existing CBNRM training manuals and references | Undertake desk review of existing CBNRM training manuals and references; | Nov |  |  | Coordinate with UNEP (Ernie Wijangco). | 2000
| ii. Conduct technical consultation with FAO, UNEP and other partners who have carried out CBNRM in the country; | Meetings with FAO, UNEP and other partners |  |  |  | Coordinate with UNEP (Ernie Wijangco). | 500
|  | Based on the reviews conducted develop and as needed update existing CBNRM training manuals |  |  | Meeting, Translation, Publications, Distribution | Link to SALEH | 5000
Activity 2.2.2 (FAO)
| Training on participatory rural appraisal, participatory monitoring and CBNRM (initial technical training needed for the implementation of rangeland activities by government, non-government and community partners | Identifying and including MAIL personnel in field team for community selection and mobilization - training on the job | July-Oct. |  |  | Can be done in collaboration with UNEP under its CBNRM programme. | 28000
Activity 2.2.3 (FAO)
| In country study tours for field level government, non-government and community partners directly involved in rangeland management activities | No activities planned for Y 1 |  |  |  | Link to SALEH, NGO programs
324900
[6 empty] | UNDP Budget | 123000
[6 empty] | FAO Budget | 164500
[6 empty] | UNDP & FAO Budget | 37400
[6 empty] | Total Budget | 324900
Summary of Project Financial Status- UNDP
| UNDP Operational Costs Year 1 | Budget | Remark |  | 241200
| staff salaries | 241200 | US$40,200/month |  | 80000
| Vehicles (2 land cruiser) | 80000 |  |  | 12000
| Monthly Operational Cost | 12000 | 2000/month |  | 5000
| Equipment and Furniture | 5000 |  |  | 15000
| Vehicle Maintenance and Running | 15000 |  |  | 50000
| Misc. | 50000
| Total | 403200
| Total Project Budget-UNDP | 765409
| Operational + Activity Budget | 440600
| GMS Cost (7%) | 30842
| Total Expected Expenditures | 471442
Summary of Project Financial Status - FAO
|  |  |  | Prior Years |  |  | Current Year 2009 Up To:2009-13 |  |  | Cumulative Up To 2009-13 |  |  | Future Years | [8 empty] | Project Total
|  |  |  | 2008 |  |  | 2009 |  |  | CUMULATIVE |  |  | 2010 |  |  | 2011 |  |  | 2013 |  |  | TOTAL
|  |  |  | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance
| Funds Received |  |  |  | -813705 | 813705 |  |  |  |  | -813705 | 813705 | [10 empty] | -813705 | 813705
|  | 3001 Contributions Received In Advance (Parent) |  |  | -813705 | 813705 |  |  |  |  | -813705 | 813705 | [10 empty] | -813705 | 813705
| Expenditure |  |  | 186880.52 | 186880.52 | 0 | 777806 | 199140.51 | 578665.49 | 964686.52 | 386021.03 | 578665.49 | 883828 | 0 | 883828 | 84581 | 0 | 84581 | 567097.48 | 0 | 567097.48 | 2500193 | 386021.03 | 2114171.97
|  | 5011 Salaries Professional (Parent) |  | 0 | 0 | 0 | 192000 | 173289.06 | 18710.94 | 192000 | 173289.06 | 18710.94 | 332000 | 0 | 332000 | 32000 | 0 | 32000 | 96000 | 0 | 96000 | 652000 | 173289.06 | 478710.94
|  | 5013 Consultants (Parent) |  | 0 | 0 | 0 | 155760 | 10416 | 145344 | 155760 | 10416 | 145344 | 176360 | 0 | 176360 | 23160 | 0 | 23160 | 96200 | 0 | 96200 | 451480 | 10416 | 441064
|  | 5014 Contracts (Parent) |  | 0 | 0 | 0 | 140000 | 201 | 139799 | 140000 | 201 | 139799 | 125000 | 0 | 125000 |  |  |  | 125000 | 0 | 125000 | 390000 | 201 | 389799
|  | 5020 Locally Contracted Labour (Parent) | [5 empty] | 5 | -5 |  | 5 | -5 | [10 empty] | 5 | -5
|  | 5021 Travel (Parent) |  | 0 | 0 | 0 | 65600 | 0 | 65600 | 65600 | 0 | 65600 | 58100 | 0 | 58100 | 7000 | 0 | 7000 | 49000 | 0 | 49000 | 179700 | 0 | 179700
|  | 5023 Training (Parent) |  | 0 | 0 | 0 | 61000 | 4 | 60996 | 61000 | 4 | 60996 | 38000 | 0 | 38000 | 3500 | 0 | 3500 | 47000 | 0 | 47000 | 149500 | 4 | 149496
|  | 5024 Expendable Procurement (Parent) |  | 1020 | 1020 | 0 | 15000 | 3587 | 11413 | 16020 | 4607 | 11413 | 15000 | 0 | 15000 | 2000 | 0 | 2000 | 26980 | 0 | 26980 | 60000 | 4607 | 55393
|  | 5025 Non Expendable Procurement (Parent) |  | 172752 | 172752 | 0 | 0 | 0 | 0 | 172752 | 172752 | 0 | [6 empty] | 15748 | 0 | 15748 | 188500 | 172752 | 15748
|  | 5027 Technical Support Services (Parent) |  | 0 | 0 | 0 | 10500 | 0 | 10500 | 10500 | 0 | 10500 | [6 empty] | 10500 | 0 | 10500 | 21000 | 0 | 21000
|  | 5028 General Operating Expenses (Parent) |  | 882.69 | 882.69 | 0 | 83500 | 10366.13 | 73133.87 | 84382.69 | 11248.82 | 73133.87 | 77500 | 0 | 77500 | 11000 | 0 | 11000 | 60117.31 | 0 | 60117.31 | 233000 | 11248.82 | 221751.18
|  | 5029 Support Costs (Parent) |  | 12225.83 | 12225.83 | 0 | 54446 | 1272.32 | 53173.68 | 66671.83 | 13498.15 | 53173.68 | 61868 | 0 | 61868 | 5921 | 0 | 5921 | 40552.17 | 0 | 40552.17 | 175013 | 13498.15 | 161514.85
|  | Total Expenditure |  | 186880.52 | 186880.52 | 0 | 777806 | 199140.51 | 578665.49 | 964686.52 | 386021.03 | 578665.49 | 883828 | 0 | 883828 | 84581 | 0 | 84581 | 567097.48 | 0 | 567097.48 | 2500193 | 386021.03 | 2114171.97
| Balance |  |  |  | -626824.48 |  |  | 199140.51 |  |  | -427683.97 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -427683.97