China Youth, Employment and Migration Annual Work Plan Color-coded

Green = done, light yellow = ongoing, and red = not started

| Annual targets | Activities | TIME FRAME YEAR 1 | UN AGENCY | RESPON-SIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Amount |

| JP Output 1.1: National migration policy informed by stronger national knowledge base and knowledge sharing |
| --- |
| Stakeholders agreed on the platform for the migration information, and its format and objectives | 1.1.1 (RF 1.1.1) Review existing information and identify gaps and needs of national/provincial stakeholders to identify information gaps | * | * |  |  | ILO | CASS | MDG-F | Contracts | 15,000 |
|  |  |  |  |  |  | UNFPA | NBS / CASS |  | Contracts | 15,000 |
|  | 1.1.2 (RF1.1.2) Technical meeting on establishing a platform for migration information |  |  | * |  | ILO | CASS | MDG-F | Training | 5,000 |
|  |  |  |  | * |  | UNFPA | CASS | MDG-F | Training | 10,000 |
|  | 1.1.3 (RF1.1.2) Compilation of required information with standardized data definitions |  |  | * | * | ILO | CASS | MDG-F | Personnel | 6,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 40,000 |
|  |  |  |  |  |  |  |  |  | Equipment | 1,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  |  |  |  |  |  |  |  |  | MISC | 3,000 |
|  | 1.1.4 (RF1.1.2) Collection and analysis of additional data on youth, migration and employment |  |  | * | * | UNFPA | NBS / NPFPC | MDG-F | Contracts | 15,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 12,000 |
|  |  |  |  |  |  |  |  |  | Training | 10,000 |
|  |  |  |  |  |  |  |  |  | Equipment | 6,000 |
|  | 1.1.5 (RF1.1.4) Mapping of migration trends especially on domestic workers; policy review of existing institutional services, protection mechanisms and programme initiatives in China. | * | * | * | * | UNIFEM | ACWF/ Center for Women Law studies and legal services | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Travel | 3,000 |

| JP Output 1.2: Policy advocated and awareness raised and capacity built between and amongst government, civil society and young people at national and local levels. |
| --- |
| Existing policies and mechanism for the registration of migrants including children of migrants assessed in selected sending and receiving areas | 1.2.1 (RF1.2.1) Undertake a policy review of existing local and national policies on registration of migrant focusing on registration of migrant and left behind children | * | * |  |  | UNICEF | NWCCW MPS | MDG-F | Training | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts |  |
|  | 1.2.2 (RF1.2.1) Conduct field assessment in selected areas on existing local and national mechanism of registration of migrants, especially migrant and left behind children | * | * |  |  | UNICEF | NWCCW MPS | MDG-F | Training | 6,000 |
|  |  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  |  | Travel |  |
|  | 1.2.3 (RF1.2.1) Draft report with recommendation and plan for the development of a bilateral coordinated registration mechanism |  |  | * |  | UNICEF | NWCCW MPS | MDG-F | Contracts | 2,000 |
| A dialogue mechanism and social/legal support network developed for migrants and young people in rural areas | 1.2.4 (RF1.2.2) Develop and test counseling mechanism for returned migrants and pre-departure youth in selected sites, through cooperation with village administrators, specialized institutes, enterprises to provide a better mental preparation for their urban life | * | * |  |  | UNESCO | DRC CASS | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training | 15,000 |
|  | 1.2.5 (RF1.2.3) Organize Regular Inter-ministerial Forums to facilitate situation-and-policy-oriented dialogue and cooperation between and among government, civil society organizations, young migrant representatives and other related individuals |  |  | * |  | UNESCO | DRC CASS | MDG-F | Training | 30,000 |
|  |  |  |  |  |  |  |  |  | Travel | 10,000 |
| Advocacy and awareness raising to promote social inclusion of migrant workers and to protect their rights in risk sectors | 1.2.6 (RF1.2.5) Produce a guideline for creation of social/legal support network for migrants in risk sectors |  |  | * | * | UNESCO | DRC CASS | MDG-F | Contracts | 18,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 16,000 |
| Key findings on barriers of migrants to urban society, issues and challenges of governance for social inclusion, to be prepared for awareness campaigns | 1.2.7 (RF1.2.6) Plan and prepare participatory tools, instruments and guidelines |  | * |  |  | UNDP | MCA | MDG-F | Personnel | 2,500 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
|  |  |  |  |  |  |  |  |  | Training | 500 |
|  | 1.2.8 (RF1.2.6) Conduct participatory rapid assessment on community governance concerning social and institutional barriers in field in selected sites |  | * | * |  | UNDP | MCA | MDG-F | Contracts | 22,000 |
|  | 1.2.9 (RF1.2.6) Report preparation and documentation on key findings |  |  | * |  | UNDP | MCA | MDG-F | Contracts | 5,000 |
|  | 1.2.10 (RF1.2.6) Present findings and challenges at various venues for feedback to design awareness campaign programs |  |  |  | * | UNDP | MCA | MDG-F | Trainings | 3,000 |
|  | 1.2.11 (RF1.2.6) Design contents, tools and programs of campaigns and provide training programs to key stakeholders for awareness campaigns |  |  | * | * | UNDP | MCA | MDG-F | Printing | 1,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 7,500 |
| UNIFEM Advocacy and gender awareness raised to promote social inclusion of domestic workers along with the need for legislative reform and protection for young female domestic workers. | 1.2.12 (RF1.2.9) Prepare promotional materials for advocacy activities (booklets and or pamphlets) as well as training toolkits | * |  |  |  | UNIFEM | ACWF and MOHRSS | MDG-F | Contracts | 8,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
|  | 1.2.13 (RF1.2.9) Design advocacy and training programs on issues related to contracting practices for domestic workers, gender based discrimination etc. | * |  |  |  | UNIFEM | ACWF and MOHRSS | MDG-F | Contracts | 8,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
|  | 1.2.14 (RF1.2.10) Organize training workshops for policy makers and administrators from labor and social security departments, and relevant civil society partners on issues and concerns of women domestic workers, including on laws and policies related to domestic workers, social protection, gender based discrimination etc. | * | * | * |  | UNIFEM | ACWF and MOHRSS | MDG-F | Personnel | 3,000 |
|  |  |  |  |  |  |  |  |  | Training | 13,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
|  | 1.2.15 (RF1.2.11) Organize consultations with recruiting agencies, and relevant civil society partners in recruitment and contracts, including ethical code of conduct. | * | * | * |  | UNIFEM | ACWF and MOHRSS | MDG-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Training | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |

| JP Output 1.3 Policy implementation strengthened through piloting of models and the participation of migrants in policy dialogue. |
| --- |
| Participatory consultations to better understand migration trends, institutional mechanism to protect young migrants | 1.3.1 (RF1.3.1) Prepare interview protocols for consultations with young migrants on regulatory framework and implementation process in areas of household registration, household welfare record system, community administrative services, scope and standardization of community services, and level of participation in urban society |  | * |  |  | UNDP | NDRC | MDG-F | Personnel | 8,000 |
|  |  |  |  |  |  |  |  |  | Travel | 4,000 |
|  | 1.3.2 (RF1.3.1) Hire suitable partners and experts to conduct the consultations with young migrants and their families |  | * |  |  | UNDP | NDRC | MDG-F | Contracts | 26,000 |
|  |  |  |  |  |  |  |  |  | Training | 2,000 |
|  | 1.3.3 (RF1.3.2) Present findings at workshops with participation of young migrant representatives to formulate recommendations for regulatory and institutional improvement and on performance measurement system to strengthen community social inclusion for migrants |  |  | * |  | UNDP | NDRC | MDG-F | Training | 20,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 3,000 |
| Community demonstrative mechanism designed and capacity built for CSOs and social workers’ delivery of social inclusion programs | 1.3.4 (RF1.3.3) Identify and contract technical institution to design demonstrative mechanism and model of CSO delivering community-based social inclusion programs |  | * | * |  | UNDP | MCA | MDG-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  | 1.3.5 (RF1.3.3) Develop guidelines and MOUs for open tenders to CSOs and their service delivery |  |  | * |  | UNDP | MCA | MDG-F | Contracts | 13,000 |
|  | 1.3.6 (RF1.3.3) Design a capacity building framework, plan and conduct training programs to related government agencies and potential partnering CSOs as well as social workers |  |  |  | * | UNDP | MCA | MDG-F | Contracts | 8,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 3,000 |
|  | 1.3.7 (RF1.3.5)Conduct monitoring, mid-term assessment, consultative meetings and produce M&E reports |  |  |  | * | UNDP | MCA | MDG-F | Personnel | 2,500 |
|  |  |  |  |  |  |  |  |  | Travel | 1,000 |
| Platform developed for sharing the knowledge and experiences to protect rights of domestic workers especially domestic workers by national labor laws. | 1.3.8 (RF1.3.6) Initiate policy dialogues involve CSOs and female migrant workers with government to address gender concerns particularly the needs of domestic workers, including recruitment/contract practices, procedures, and protection measures | * | * |  |  | UNIFEM | ACWF / Center for Women Law Studies and Legal Services | MDG-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Training | 6,000 |
|  |  |  |  |  |  |  |  |  | travel | 2,000 |
| A set of guidelines for employment services and MOUs between sending and receiving areas, and a piloting strategy developed | 1.3.9 (RF1.3.7) Conduct study and identify good practices of employment services and the different types of bilateral agreements (and other linkages between sending and receiving areas) being used to promote safe and orderly migration | * |  |  |  | ILO | MOHRSS | MDG-F | Contracts | 15,000 |
|  | 1.3.10 (RF1.3.8) Develop a set of guidelines for employment services and MOUs between local governments, and with and between vocational training institutions and enterprises |  | * |  |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  | 1.3.11 (RF1.3.9) Design Behavioral Change Communication (BCC) campaign on the value of formal migration channels |  | * |  |  | ILO | MOHRSS | MDG-F | Contract | 10,000 |
|  | 1.3.12 (RF1.3.8 & 1.3.9) Bring stakeholders together to discuss guidelines, good practices, BCC campaign and piloting strategy |  |  | * |  | ILO | MOHRSS | MDG-F | Training | 15,000 |
|  | 1.3.13 (RF1.3.8 & 1.3.9) Print materials and start to carry out BCC campaign activities |  |  | * | * | ILO | MOHRSS | MDG-F | Contracts | 15,000 |

| JP Output 2.1 Access to non-formal education for migrants to prevent premature entry into the labor force improved. |
| --- |
| Flexible courses developed and pilot-tested for out-of-school children and over-aged children | 2.1.1 (RF2.1.1) Conduct a base-line survey and analyze the situation of out-of-school children and over-aged children | * |  |  |  | UNICEF | CAST | MDG-F | Contracts | 28,000 |
|  |  |  |  |  |  |  |  |  | Travel | 10,000 |
|  | 2.1.2 (RF2.1.2) Hold consultative meetings with stakeholders on the needs of out-of-school children and over-aged children to disseminate the results of the baseline survey and to decide on three access channels for non-formal education |  | * |  |  | UNICEF | CAST | MDG-F | Training | 20,000 |
|  | 2.1.3 (RF2.1.3) Develop flexible courses for out-of-school children and over-age children |  | * | * | * | UNICEF | CAST | MDG-F | Contract | 60,000 |
|  |  |  |  |  |  |  |  |  | Travel | 15,000 |
| Volunteer tutoring/mentoring programme designed for in-school migrant youth | 2.1.4 (RF2.1.7) Conduct base-line survey and analyze the situation of in school migrant youth and availability of university volunteers | * |  |  |  | UNDP | UNV/CYVA | MDG-F | Contracts | 6,000 |
|  |  |  |  |  |  |  |  |  | Travel | 4,000 |
|  | 2.1.5 (RF2.1.8) Determine project management roles; select informal migrant schools and participating universities; design pilot intervention | * | * |  |  | UNDP | UNV/CYVA | MDG-F | Contracts | 14,750 |
|  |  |  |  |  |  |  |  |  | Travel | 10,000 |
|  | 2.1.6 (RF2.1.9) Draft volunteer handbook and implement volunteer training |  | * | * |  | UNDP | UNV/CYVA | MDG-F | Training | 8,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 7,000 |
|  | 2.1.7 (RF2.1.10) Implement, monitor and assess suitability of volunteer programme and undertake course corrections |  |  |  | * | UNDP | UNV/CYVA | MDG-F | Transport | 10,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 10,000 |

| JP Output 2.2 Access to vocational training for migrants and young people in rural areas improved to prevent premature entry to the labor force and increase self-employment opportunities. |
| --- |
| Training needs of young people in the rural areas and young migrant workers in urban areas identified and specific training tools developed for them. | 2.2.1 (RF2.2.1) Review of TVET policies and programmes of the education sector | * |  |  |  | UNESCO | CNIER | MDG-F | Contracts | 15,000 |
|  | 2.2.2 (RF2.2.2) Review of curriculum of regular junior secondary schools and secondary TVET schools in sending places | * |  |  |  | UNESCO | CNIER | MDG-F | Contracts | 15,000 |
|  |  |  |  |  |  |  |  |  | Travel | 4,000 |
|  | 2.2.3 (RF2.2.3) Assess the educational and skill profiling as well as employability of young graduates of the schools mentioned in 2.2.2 |  | * |  |  | UNESCO | CNIER | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 25,000 |
|  |  | * | * |  |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
|  |  |  |  |  |  |  |  |  | Training | 8,000 |
|  | 2.2.4 (RF2.2.4) Identify knowledge and skills needed to upgrade young graduates’ employability and develop recommendations on policy and curriculum |  | * |  |  | UNESCO | CNIER | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  | 2.2.5 (RF2.2.5) Develop apprenticeship programme, work study schemes and occupational guidance and counseling programme |  |  | * | * | ILO | MOHRSS | MDG-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  | 2.2.6 (RF2.2.6) Test pre-employment training programmes in sending places |  |  |  | * | ILO | MOHRSS | MDG-F | Contracts | 20,000 |
|  | 2.2.7 (RF2.2.7) Conduct a study to evaluate skills and employability of young people/migrants and analyse their training needs. | * | * |  |  | ILO | MOHRSS | MDG-F | Contracts | 25,000 |
|  | 2.2.8 (RF2.2.7) Skills and employability evaluation workshop |  |  | * |  | ILO | MOHRSS | MDG-F | Travel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training | 10,000 |
|  | 2.2.9 (RF 2.2.8) Conduct study to define key sectors for absorbing young people/migrants as employees and as potential entrepreneurs | * | * |  |  | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  | 2.2.10 (RF 2.2.8) Present findings at workshops with participation of youth and migrant representatives for feedback to design sector specific skills training |  |  | * |  | ILO | UNIDO |  | Training | 10,000 |
|  | 2.2.11 (RF 2.2.9) Conduct study to evaluate labour demand and skills requirements of transnational companies and other private sector entities in order to tailor training for young people/migrants | * | * |  |  | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  | 2.2.12 (RF 2.2.9) Present findings at workshops with participation of youth and migrant representatives for feedback to design appropriate technical training |  |  | * |  | ILO | UNIDO/MOHRSS | MDG-F | Training | 10,000 |
|  | 2.2.13 (RF2.2.10) Develop skills up-grading training for young migrants in receiving places |  |  |  |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  | 2.2.14 (RF 2.2.10) Develop skills up-grading training for young migrants in receiving places |  |  |  | * | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  | 2.2.15 (RF2.2.12) Adapt SYB training for rural youth | * | * |  |  | ILO | MOHRSS | MDG-F | Personnel | 15,000 |
|  |  |  |  |  |  |  |  |  | Travel | 3,000 |
|  |  |  |  |  |  |  |  |  | Equipment | 2,000 |
|  | 2.2.16 (RF 2.2.12) Develop technical business start up training for rural youth |  |  |  | * | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 6,000 |
|  |  |  |  |  |  |  |  |  | Travel | 4,000 |
|  | 2.2.17 (RF2.2.13) Pilot test of SYB for rural youth |  |  | * | * | ILO | MOHRSS | MDG-F | Contracts | 20,000 |
|  | 2.2.18 (RF 2.2.13) Pilot test technical business start up training for rural youth |  |  |  | * | ILO | UNIDO/MOHRSS | MDG-F | Contract | 2,500 |
|  |  |  |  |  |  |  |  |  | Travel | 2,500 |
|  | 2.2.19 (RF 2.2.14) Train youth associations in sending places to develop business opportunities |  |  | * |  | ILO | ACYF | MDG-F | Training | 10,000 |
|  |  |  |  |  | * | ILO | UNIDO/ACYF | MDG-F | Training | 10,000 |

| JP Output 2.3 Safe migration information and training for young people strengthened. |
| --- |
| Common and comprehensive Life Skills Training Package developed for different delivery channels based on the needs of migrants | 2.3.1 (RF2.3.1) Bring together expert team (including young migrants and partners from health, labor, gender, and education fields) to evaluate needs of young migrants and the existing safe migration/life-skills training materials | * |  |  |  | UNFPA | CFPA | MDG-F | Contract | UNIFEM 5,000 |
|  |  |  |  |  |  |  |  |  | Contract | UNFPA 5,000 |
|  | 2.3.2 (RF2.3.1) Hold workshop with national partners to validate the Life Skills Training Programme and the piloting strategy | * |  |  |  | WHO | CFPA/MOH | MDG-F | Training | WHO 15,000 UNFPA 5,000 |
|  | 2.3.3 (RF2.3.2) Set up link with pilot sites counterparts, liaison and planning strategies |  | * | * | * | UNICEF | ACWF | MDG-F | Travel | 5,000 |
|  | 2.3.4 (RF2.3.3) Develop Life Skills Training Programme and implementation strategy for schools in pilot sites |  | * | * |  | UNICEF | ACWF | MDG-F | Contracts | 10,000 |
|  | 2.3.5 (RF2.3.4) Produce and Print Life Skills Training Package |  |  | * |  | UNICEF | ACWF | MDG-F | Contracts | 40,000 |
|  | 2.3.6 (RF2.3.3) Carry out pilot test of Life Skills package |  |  |  | * | UNICEF | ACWF | MDG-F | Training | 10,000 |
|  | 2.3.7 (RF2.3.7) Life skill training in pilot schools monitored, evaluated and results/lessons learned and documented |  | * | * | * | UNICEF | ACWF | MDG-F | Travel | 5,000 |
|  | 2.3.8 (RF2.3.8) Fine-tune Life Skills Training Programme for vocational training institutions in pilot sites |  | * | * |  | ILO | MOHRSS | MDG-F | Contracts | 5,000 |
|  | 2.3.9 (RF2.3.8) Print Life Skills Training Package for vocational training institutions in pilot sites |  |  | * |  | ILO | MOHRSS | MDG-F | Contracts | 15,000 |
|  | 2.3.10 (RF2.3.9) Carry out local training on delivering Life Skills package to trainers in vocational training institutions in pilot sites |  |  | * | * | ILO | MOHRSS | MDG-F | Training | 15,000 |
|  | 2.3.11 (RF2.3.10) Fine-tune Life Skills Training Programme for workplaces in pilot sites |  | * | * |  | ILO | CEC/ACFTU | MDG-F | Contract | 5,000 |
|  | 2.3.12 (RF2.3.10) Print Life Skills Training Package for workplaces in pilot sites |  |  | * |  | ILO | CEC/ACFTU | MDG-F | Contracts | 10,000 |
|  | 2.3.13 (RF2.3.11) Carry out local training on delivering Life Skills package to trainers in workplaces in pilot sites |  |  | * | * | ILO | CEC/ACFTU | MDG-F | Training | 15,000 |
|  | 2.3.14 (RF2.3.12) Develop Life Skills Training modules for community centers in pilot sites |  |  | * |  | UNESCO | CAEA/CNIER | MDG-F | Contracts | 41,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Travel | 1,000 |
|  |  |  |  |  |  |  |  |  | Misc. | 3,190 |
|  | 2.3.15 (RF2.3.15) Develop Life Skills Training modules for peer-education in pilot sites |  |  | * |  | UNFPA | CFPA | MDG-F | Contracts | 5,000 |
|  | 2.3.16 (RF2.3.15) Print Life Skills Training modules for peer-education in pilot sites |  |  |  | * | UNFPA | CFPA | MDG-F | Contracts | 13,000 |

| JP Output 3.1 Registration of migrant children promoted to enhance their protection and access to social services. |
| --- |
| Standard operation procedure for the registration and referral of migrant children developed and implemented in existing pilot receiving cities with a large inflow of migrants | 3.1.1 (RF3.1.1) Conduct assessment of current practices for registration and referral of migrant children to basic social services in several pilot sites which already have registration of migrant children in place | * | * |  |  | UNICEF | NWCCW MPS | MDG-F | Training | 25,000 |
|  |  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  |  | Contracts |  |
|  | 3.1.2 (RF3.1.1) Develop standard operating procedures for the registration and referral of migrant children |  |  | * | * | UNICEF | NWCCW MPS | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Travel |  |
|  | 3.1.3 (RF3.1.2) Develop a TOT training package on the implementation of the standard operating procedures |  |  |  | * | UNICEF | NWCCW MPS | MDG-F | Contracts | 30,000 |
|  |  |  |  |  |  |  |  |  | Training |  |
|  |  |  |  |  |  |  |  |  | Contracts |  |
| A bilaterally coordinated mechanism of registration of migrant/left behind children between sending and receiving areas developed and piloted for replication and policy formulation at local and national levels | 3.1.4 (RF3.1.6) Pilot in two provinces (Jiangsu and Guangdong) a “one-card” registration mechanism developed bilaterally between sending and receiving areas for migrant and left behind children | * | * |  |  | UNICEF | NWCCW MPS | MDG-F | Training | 20,000 |
|  |  |  |  |  |  |  |  |  | Contracts |  |
|  | 3.1.5 (RF3.1.7) Develop or up grade the computer software for registration of migrant and left behind children in selected pilot sites |  | * | * |  | UNICEF | NWCCW MPS | MDG-F | Contracts | 24,000 |
|  |  |  |  |  |  |  |  |  | Travel |  |

| JP Output 3.2 Community centers enhanced in providing comprehensive, gender responsive learning opportunities, information and referral services. |
| --- |
| Community centers enhanced in providing comprehensive gender responsive learning opportunities, information and referral service | 3.2.1 (RF3.2.1) Conduct expert review of existing community centers and identify the roles and responsibilities of community learning centers | * | * |  |  | UNESCO | CAEA ACWF | MDG-F | Contracts | UNESCO 5,000 UNICEF 2,000 |
|  |  |  |  |  |  |  |  |  | Travel | UNESCO 5,000 |
|  | 3.2.2 (RF3.2.2) Build up network with local communities, training providers, service providers, employers, local governments, community organizations, labor unions, etc. |  |  | * | * | UNESCO | CAEA ACWF | MDG-F | Training | UNESCO 4,000 UNICEF 4,000 |
|  |  |  |  |  |  |  |  |  | Misc. | UNESCO 1,000 |
|  | 3.2.3 (RF3.2.3) Establish relations with local partners and draw up strategic plan to improve young people’s access to job information, labor rights protection, training opportunities, etc. | * |  |  |  | ILO | MOHRSS | MDG-F | Training | 10,000 |
|  | 3.2.4 (RF3.2.3) Carry out specific needs-based activities linking the community centers with the labor bureau, public and private employment agencies, vocational training centers, and workers’ and employers’ organizations |  | * | * | * | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  | 3.2.5 (RF3.2.5) Prepare SOP for effective functioning of the community center and identify potential sites based on certain criteria |  |  | * | * | UNESCO | CAEA ACWF | MDG-F | Contracts | UNESCO 10,000 UNICEF 3,000 |
|  | 3.2.6 (RF3.2.9) Monitor the implementation and document lessons learned |  | * | * | * | UNICEF | ACWF | MDG-F | Travel | UNICEF 3,000 |

| JP Output 3.3 Access to basic health information and care for migrants and left-behind youth improved. |
| --- |
| Design and testing of health promotion model to promote use of appropriate health services by migrant youth. | 3.3.1 (RF3.3.1) Expert team review of existing services and care available for young migrants conducted by UN agencies and partners (international best practice review and workshop). | * |  |  |  | WHO | MOH | MDG-F | Contracts | 18,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 32,000 |
|  | 3.3.2 (RF3.3.2) City level multi-stakeholder meetings (WF, education, FP, education etc.) |  | * | * |  | WHO | MOH | MDG-F | Contracts | 30,000 |
|  | 3.3.3 (RF3.3.3) Community advocacy workshop for policy makers and programme managers on the rights and needs or health education and services for migrant youth (one workshop pr. city) |  | * | * |  | UNFPA | MOH | MDG-F | Contracts | 39,000 |
|  |  |  |  |  |  |  |  |  | Travel | 6,000 |
|  | 3.3.4 (RF3.3.4) Baseline and endline surveys/data mining using quantitative and qualitative methods conducted. | * | * |  |  | UNFPA | MOH | MDG-F | Contracts | 30,000 |
|  | 3.3.5 (RF3.3.5) Local PoA |  |  | * |  | WHO | MOH | MDG-F | Contracts | 40,000 |
|  | 3.3.6 (RF3.3.6) Social marketing for promotion of health education, condoms and health services |  |  | * | * | UNFPA | MOH | MDG-F | Contracts | 20,000 |
|  | 3.3.7 (RF3.3.13) Monitoring and evaluation |  |  |  | * | WHO | MOH | MDG-F | Travel | 7,000 |
|  |  |  |  |  |  |  |  |  | Training | 14,000 |

| JP Output 3.4 Implementation and enforcement of existing legislation for migrant workers strengthened and safe migration ensured. |
| --- |
| Capacity building materials developed to support the implementation and enforcement of relevant labor legislation, and capacity enhanced among young female migrants in risk sectors | 3.4.1 (RF3.4.1) Develop training materials for labor authorities | * |  |  |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  | 3.4.2 (RF3.4.1) Hold consultation workshop to validate the training materials and develop training strategy |  | * | * |  | ILO | MOHRSS | MDG-F | Training | 20,000 |
|  | 3.4.3 (RF3.4.2) Conduct training for labor authorities in pilot sites |  |  | * |  | ILO | MOHRSS | MDG-F | Training | 40,000 |
|  | 3.4.4 (RF3.4.3) Propose a code of conduct approach based on a review of national and international good practices on how employers’ and workers’ organizations can support the implementation of the law | * | * |  |  | ILO | ACFTU, CEC | MDG-F | Contracts | 7,500 |
|  | 3.4.5 (RF3.4.3) Hold tripartite consultation workshop to validate the code of conduct approach |  |  | * |  | ILO | ACFTU, CEC | MDG-F | Training | 12,500 |
|  | 3.4.6 (RF3.4.4) Conduct training on code of conduct for employers’ and workers’ organizations in pilot sites |  |  |  | * | ILO | ACFTU, CEC | MDG-F | Training | 10,000 |
|  | 3.4.7 (RF3.4.5) Conduct review of contracts, wages (including piece-rate) and working time in the garment and footwear manufacturing sector | * | * |  |  | ILO | MOHRSS, ACFTU, CEC | MDG-F | Contracts | 10,000 |
|  | 3.4.8 (RF3.4.5) Hold policy consultation seminar with tripartite constituents on the findings of the study and international experience |  |  | * |  | ILO | MOHRSS, ACFTU, CEC | MDG-F | Training | 20,000 |
|  | 3.4.9 (RF3.4.8) Conduct studies on female migrants working in low-end service industry |  | * | * |  | UNESCO | CASS, Tsinghua University | MDG-F | Contract | 15,000 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  | 3.4.10 (RF3.4.9) Roundtable to discuss outcomes of the assessment and design appropriate awareness raising and support interventions |  |  |  | * | UNESCO | CASS, Tsinghua University | MDG-F | Training | 25,000 |
|  | 3.4.11 (RF3.4.12) Review of the Chinese labor laws and advocate for strengthening of law from a gender equality and rights based perspective and/or removal of discriminatory articles within the law for the protection of rights of domestic workers |  | * | * | * | UNIFEM | ACWF, MOHRSS | MDG-F | Contracts | 8,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
|  | 3.4.12 (RF3.4.13) Map existing services, gaps to services, and barriers to accessing support and services |  | * | * | * | UNIFEM | MOHRSS, ACWF | MDG-F | Contracts | 8,000 |
|  |  |  |  |  |  |  |  |  | Travel | 2,000 |
| Monitoring and Evaluation * (ILO) | 19,200 |
| Monitoring and Evaluation (UNDP) | 4,500 |
| Monitoring and Evaluation (UNESCO) | 3,000 |
| Monitoring and Evaluation (UNIFEM) | 6,000 |
| Project preparation/formulation (Funds administered by UNDP) | 20,000 |
| UN Programme Coordinator (Funds to be administered by UNDP on behalf of UNRCO) | 72,000 |
| National Programme Coordinator and assistant (to be administered by UNDP) | 52,000 |
| PMO budget (to be administered by UNDP) | 25,000 |
| Total Planned Budget without management fee | 2,177,640 |
| Management Fee for MDG-F (7%) | 152,435 |