This Workplan is based on the assumption that (as per recommendation of the Programme Management Committee) the starting date of the YEM will be duly revised to reflect the reality of the implementation cycle

Q1: Jan-Mar 09	                                     Q3: Jul-Aug 09                                 GREEN: completed			RED: not yet started

Q2: Apr-Jun 09                                     Q4: Sep-Dec 09                                 YELLOW : ongoing

| ANNUAL TARGETS | ACTIVITIES | TIME FRAME | UN AGENCY | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Amount |
| Output 1.1 The capacity of policy makers to address the nexus between informal employment and migration of young people enhanced Target : 15 statistical indicators developed and used 1 analysis of the links between informal employment and migration conducted 20 staff of line ministries, INSTAT, NES and NSDI Coordination Unit produce and/or use data on youth employment, informal employment and migration 1 plan of action to tackle the informal economy developed | 1.1.1 Adapt the ILO school-to-work survey methodology to collect data on informal employment and migration of young people |  |  |  |  | ILO | INSTAT | MDG-F | Chief technical adviser Local staff Local consultants Translation/interpretation Equipment Miscellaneous AMS (7%) Total | 27.300 3.465 8.136 1.455 2.300 7.280 3.496 53.432 |
|  | 1.1.2 Run survey on informal employment and migration of young people |  |  |  |  | IOM | INSTAT | MDG-F | Administration of questionnaire and data tabulation (contracts survey) Survey data analysis (contracts) AMS (7%) Total | 20.000 10.000 2.100 32.100 |
|  | 1.1.3 Analyze the links between informal employment and migration of youth |  |  |  |  | ILO | MOLSAEO | MDG-F | Chief technical adviser Local staff Translation/interpretation AMS (7%) Total | 27.300 3.465 1.455 2.255 34.475 |
|  | 1.1.4 Conduct staff development programme for 20 participants on the use and production of statistical indicators on youth employment, informal employment and migration |  |  |  |  | ILO | MOLSAEO | MDG-F | Chief technical adviser Local staff Local consultants Translation/interpretation Training AMS (7%) Total | 27.300 3.465 2.910 1.455 10.000 3.159 48.289 |
|  | 1.1.5 Provision of policy advice on necessary reforms to tackle the informal economy |  |  |  |  | UNDP | Council of Ministers | MDG-F | Local consultants International consultants Contracts AMS (7%) Total | 7.000 8.000 15.000 2.100 32.100 |
| 1.2. Migration, employment creation and youth policies of the NSDI aligned with labour market strategies and operationalized through Youth Employment National Action Plan (NAP) – Target 1 inter-institutional committee established 1 NAP on youth employment with specific priorities and outcomes, designed and targets included in NSDI | 1.2.1 Establish inter-institutional group to review strategies on employment, youth and migration and conduct capacity building programme |  |  |  |  | ILO | MOLSAEO | MDG-F | Chief technical adviser Training Translation/interpretation Miscellaneous AMS (7%) Total | 27.300 50.000 1.455 1.089 5.589 85.433 |
|  | 1.2.2. Align national employment, youth development and migration policies with youth employment objectives |  |  |  |  | ILO | MOLSAEO | MDG-F | Chief technical adviser International consultants Local staff Local consultants Translation/interpretation Training Miscellaneous AMS (7%) Total | 27.300 12.000 3.465 6.000 1.455 30.000 1.280 5.705 87.205 |
|  | 1.2.3 Develop and implement NAP with specific priorities, outcomes, results, and human and financial resources |  |  |  |  | ILO | MOLSAEO | MDG-F | International consultants Local staff Local consultants Translation/interpretation Training and fellowship Mission ILO experts Miscellaneous AMS (7%) Total | 12.000 3.465 2.500 1.455 60.000 2.200 1.020 5.785 88.425 |
| 1.3 Public-private partnerships (PPPs) for youth employment established and contributing to the implementation of the priorities of the NAP Target 1 framework for PPPs developed and used One third of the signatories of the GC are contributing to the implementation of the NAP priorities | 1.3.1 Build capacity of labour market institutions to design a framework for the development and management of PPPs on youth employment through CSR. |  |  |  |  | ILO | MOLSAEO | MDG-F | Chief technical adviser International consultants Local consultants Translation/interpretation Training Miscellaneous AMS (7%) Total | 27.300 6.000 2.500 1.000 15.000 1.740 3.748 57.288 |
|  | 1.3.2 Build a portfolio of youth employment project to mobilize private sector’s human and financial resources and give visibility to CSR approaches through role-model enterprises that successfully participated in PPPs for youth employment. |  |  |  |  | UNDP | Employers’ Organization | MDG-F | Local staff Sub-contracts Training AMS (7%) Total | 15.000 45.000 10.000 4.900 74.900 |
| 2.1. Youth employment coordination mechanism established in the regions of Kukes and Shkodra and responsible for managing the Employment Fund (EF) Target 2 regional coordination mechanisms established 1 Employment Fund established | 2.1.1 Assess capacity of local stakeholders (municipalities, employment offices, the social partners, labour inspectorate, youth organizations and the private sector) to address youth employment and manage the EF |  |  |  |  | UNICEF | MCTYS | MDG-F | Contracts Equipment Internal travel Miscellaneous AMS (7%) Total | 11.500 2.000 1.000 500 1.050 16.050 |
|  | 2.1.2 Establish Employment Fund to be managed by the regional coordination mechanism and financing youth employment interventions |  |  |  |  | ILO | NES | MDG-F | Local staff Local consultants Training Internal travel AMS (7%) Total | 3.465 2.000 45.000 7.440 4.053 61.958 |
| 2.2. Labour market programmes targeting youth at risk of migration implemented through the EF in the regions of Kukes and Shkodra Target 1 skills survey conducted in the two regions 60 Counsellors of the NES trained on tailored counselling and guidance 1,200 young workers in the informal economy counselled 150 disadvantaged youth trained in demand-driven competency-based training 15 informal young workers moved to the informal economy | 2.2.1 Skills survey to identify emerging occupations in the two regions |  |  |  |  | IOM | Regional coordination mechanism | MDG-F | Administration of questionnaire and data tabulation (contracts-skills survey) Survey data analysis (contracts) AMS (7%) Total | 15.000 5.000 1.400 21.400 |
|  | 2.2.2 Strengthen the capacity of NES to provide career guidance |  |  |  |  | UNICEF | NES local branches | MDG-F | Local staff Contracts Training staff NES Supplies Equipment Miscellaneous AMS (7%) Total | 6.000 23.000 10.000 20.000 20.000 1.000 5.600 85.600 |
|  | 2.2.3 Conduct livelihood and employability skills training (ABCS model) for young informal workers (linked to activities 2.2.4 and 2.2.5) |  |  |  |  | UNICEF | NES local branches | MDG-F | Local staff Livelihood and employability skills training (ABCS model) Supplies Equipment Miscellaneous AMS (7%) Total | 4.000 53.141 5.000 5.000 1.000 4.770 72.911 |
|  | 2.2.4 Conduct employment-oriented training programmes in emerging occupations (e.g. ICT and eco-tourism) that are linked to work experience. (linked to activities 2.2.3 and 2.2.5) |  |  |  |  | UNDP | NES local branches | MDG-F | International consultants Local staff Sub-contracts Employment oriented training programmes Supplies Miscellaneous AMS (7%) Total | 20.000 45.000 10.000 105.000 5.000 5.000 13.300 203.300 |
|  | 2.2.5 Develop a line of services to assist enterprises to improve productivity and move to the formal economy (linked to activities 2.2.3 and 2.2.4) |  |  |  |  | ILO | Social partners | MDG-F | Chief technical adviser Service to enterprises (contracts) Miscellaneous AMS (7%) Total | 27.300 25.000 640 3.706 56.646 |
| 2.3. Youth awareness raised on employment and safe migration Target 3,500 information packages on regular migration and risks of irregular migration and trafficking published 10 counsellors of the NES trained on provision of information on regular migration and risks of irregular migration and trafficking -3,500 information material packages on educational choices, employment opportunities and rights at work published 12 outreach activities in schools, NES offices and communities conducted | 2.3.1 Develop and disseminate information packages targeting youth on regular migration and risks of irregular migration and trafficking |  |  |  |  | IOM | MCTYS | MDG-F | Local staff International consultants Local consultants Training packages for NES (contracts) Awareness raising materials on migration/risk (contracts) Interpretation services (contracts) Training Equipment Supplies Miscellaneous AMS (7%) Total | 30.000 12.000 24.000 4.000 20.000 2.000 4.000 1.400 5.640 840 7.272 111.152 |
|  | 2.3.2 Develop information material on educational choices, employment opportunities and rights at work to be disseminated through outreach activities (in schools, NES offices and communities) |  |  |  |  | UNICEF | MCTYS | MDG-F | Contracts Supplies Equipment Miscellaneous AMS (7%) Total | 14.500 5.000 10.000 500 2.100 32.100 |
| 3.1. Increased number of Albanian young graduates returning home after studies abroad Target 1 survey mapping young Albanians studying abroad conducted 3 incentive packages provided to qualified Albanians abroad for their return | 3.1.1. Design a portfolio of profiles of Albanian students abroad and disseminate it among public administration, academia and the private sector |  |  |  |  | UNDP | MFA | MDG-F | Map of Albanian students abroad and development of a profile portfolio (sub-contracts) AMS (7%) Total | 20.000 1.400 21,400 |
|  | 3.1.2. Provide a package of incentives to qualified Albanians abroad to return and to work in the public administration, academia and the private sector |  |  |  |  | UNDP | MFA | MDG-F | Local staff Package of incentives to attract qualified Albanians abroad (sub-contracts) Equipment Internal travel AMS (7%) Total | 15,530 109,417 22,463 1,600 10.431 159.441 |

| Subtotal without management fee | 1,360,378 |
| --- | --- |
| Management fee for MDG-Fund (7%) + advance for JDP formulation | 95,227 |
| TOTAL JOINT PROGRAMME – First instalment | 1,435,605 |
| Delivery target by 6th November 2009 | ILO | IOM | UNDP | UNICEF | 1,004,923 |
|  | > 401,205 | > 115,256 | > 343,799 | > 144,663 |  |
| Delivery to date (11th June 2009) | 65,660 (12%) | 37,943 (23%) | … (5%) | 34,000 (18%) |  |