# United Nations Development Group Iraq Trust Fund

# Project #:C5-07

# Date and Quarter Updated: Q1 2008

# Operationally Closed

| Participating UN Organisation: UNEP | Cluster: Agriculture, Food Security, Natural Resources and Environment |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Environment |

# Programme/Project Number:

| Title | C5-07 Strengthening Environmental Governance in Iraq through Environmental Assessment and Capacity Building |
| --- | --- |
| Location | Iraq |
| Project Cost | USD 4,700,000 |
| Duration | 38 months |
| Approval Date (SC) | 8 July 04 | Starting Date | July 04 | Completion Date | September 07 |
| Project Description | Capacity building in the Ministry of Environment to improve environmental governance |

# Development Goal and Immediate Objectives

Development Goal “To support the sustainable development of Iraq by strengthening government capacity for environmental management and for addressing immediate environmental threats to human health and livelihoods Immediate Objectives “to provide training, equipment, technical assistance and supervision to selected staff of the Iraqi environmental administration in order that baseline information can be produced to support the identification of environmental problems, priorities, policies and projects.”

# Outputs, Key activities and Procurement

| Outputs | Policy Training for upto 200 Staff Technical Training upto 50 staff Environmental Assessment Equipment Database |
| --- | --- |
| Activities | Training, field assessment, establishment of library, information cetner and laboratory |
| Procurement (major items) | Laboratory Equipment Library items Information Center items |

# Part Two: Situation as of 31 December 2007

| Funds Committed | 4,700,000 | % of approved | 100 % |
| --- | --- | --- | --- |
| Funds Disbursed | 4,700,000 | % of approved | 100 % |
| Forecast final date | Project is now complete | Delay (months) |  |

# Quantitative achievements against objectives and results

| Capacity building for site assessment | Capacity has been built, 5 sites assessed | % of planned | 100 % |
| --- | --- | --- | --- |
| Training of staff on various policy and technical issues | Training completed | % of planned | 100% |
| Infrastructure upgrade in library, information and laboratory | All equipment provided | % of planned | 100 % |

# Qualitative achievements against objectives and results

The project was completed and delivered against very difficult logistical constraints due to the security