- United Nations Development Group Iraq Trust Fund

- Project #: A5 - 16

- Date and Quarter Updated: 15 July 2009 (April-June 2009)

| Participating UN Organisation: FAO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Agriculture (MoA) |  |

| Title | Rehabilitation and Development of the National Seed Industry in Iraq |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Nationwide coverage for the strategy and technical assistance. Seed policy and legislation. Physical rehabilitation in North, Centre and South. Training overseas and in the country |  |  |  |  |
| Project Cost | USD 5 383 460 |  |  |  |  |
| Duration | 41 months |  |  |  |  |
| Approval Date (SC) | 20/4/2006 | Starting Date | 18/05/2006 | Completion Date | 30/09/2009 |
| Project Description | Formulation of a national seed policy; revision and updating of existing seed legislation; improvement of coordination and oversight arrangements; rehabilitation of damaged seed production infrastructure in government research centres and the State Board for Seed Testing and Certification; training of selected personnel in key seed industry disciplines. |  |  |  |  |

- Development Goal and Immediate Objectives

The development goal of the project is to improve food security and nutrition in Iraq. This will be achieved through the immediate objectives of rehabilitation and improvement of the national seed programme, which will promote the availability and use of high quality seeds of adapted varieties to farmers and provide the foundation of a sustainable seed industry.

| - Outputs, Key activities and Procurement |  |
| --- | --- |
| Outputs | - A national seed policy formulated, existing seed legislation reviewed and recommendations provided for its further improvement; - A functional seed programme coordination and oversight body, the National Seed Council put in place; existing database for seed quality control operations improved and strengthened; transportation and communication system in SBSTC for field inspection, seed processing plants and other seed quality control operations improved with procurement of essential equipment; - Essential buildings for seed testing laboratories constructed. Adapted varieties characterized and breeder seeds produced in the research stations; variety maintenance techniques and procedures for the targeted crops developed; foundation seed production undertaken for wheat, barley, maize and rice using breeder seeds from the research stations; - Exposure of 2 senior Iraqi staff and 30 scientists to the latest international technologies and development in improving national seed industry. In-service training of 115 Iraqi technical staff in different areas of seed technology |
| Activities | - Organize a national seed workshop followed by a national seed policy forum and draft a national seed policy; prepare full TOR, structure and mandate of a National Seed Council; undertake review of existing seed legislation; - Undertake laboratory building construction works; as well as install equipment and machines in seed laboratories and research stations; - Seeds production and quality control: assist research stations in the production of breeder seeds; assist in production of foundation seed production in the centres; develop required techniques and procedures for variety maintenance; Capacity building: arrange study tour overseas for 2 senior staff; organize fellowships abroad on seed technology of targeted crops for 30 participants; conduct in-service training on variety maintenance, variety development and evaluation, seed production and marketing system, and seed quality control; organize in-service training for 115 technical personnel in area of seed technology including use and management of improved database. |
| Procurement (major items) | Agricultural equipment, green houses, seed processing plant, and seed testing equipment. |

| Funds Committed | USD 648 207 | % of approved | 12% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 3 670 264 | % of approved | 68% |
| Forecast final date | 30/09/2009 | Delay (months) |  |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 106 | 70% |
| Women | 15 | 10% |
| Children | n.a. |  |
| IDPs | n.a. |  |
| Others | n.a. |  |
| Indirect beneficiaries |  |  |
| Employment generation (men/women) |  |  |

| - Quantitative achievements against objectives and results |  |  |  |
| --- | --- | --- | --- |
| Formulation of National Seed Policy document | National Seed Policy document formulated after organizing a national seed policy forum, was adopted by the Government of Iraq | % of planned | 100% |
| Seed Legislative Review Meeting | Seed legislative review meeting participated by seed industry stakeholders was organized which resulted in the drafting of Iraq Seed Law | % of planned | 100% |
| Mobile seed processing plants installation | Eight units of mobile seed processing plants to be used for processing foundation class seeds were installed and fully operated | % of planned | 100% |
| Procurement of farm machinery, seed testing equipment and laboratory commodities | Procurement of platform balance and germination paper undertaken. | % of planned | 100% |
| Greenhouse construction | Four units of greenhouses were delivered | % of planned | 100% |
| Seed quality control labs construction | The construction of seed testing laboratories being undertaken. | % of planned | 75% |
| Procurement of rice seed lab | . The bid evaluation of additional seed laboratory testing equipment undertaken and sent for MoA endorsement. | % of planned | 85% |
| International Training of Trainers (ToT) programme | Training on variety verification and genetically-modified organism detection completed | % of planned | 100% |
| Seed technology in-service training | In-service training course on varietal development and evaluation organized for 30 technical personnel belonging to SBSTC, SBAR of the MoA | % of planned | 100% |

- Qualitative achievements against objectives and results

Iraq National Seed Policy document formulated following organization of Seed Policy Forum participated by seed industry stakeholders was adopted by the Government of Iraq as blueprint for the growth of the national seed industry. The policy document clearly outlines the regulatory functions of the government and its role in support to the private sector for greater involvement in the seed industry. In line with the Policy, a draft of the Iraq Seed Law has been prepared as result of the seed legislative review meeting through a consultative process participated by legal experts and Iraqi seed industry stakeholders. The Government has provided comments and further fine-tuning of the fundamental seed law of the country of is being undertaken through a final legislative review meeting with stakeholders in the next reporting period. Through participation in the in-service training course on varietal development and evaluation by thirty technical personnel of the State Board for Agricultural Research (SBAR), State Board of Seed Testing and Certification (SBSTC), of the Ministry of Agriculture included women staff, the trainees acquired new skills which were transferred to them by the resource persons trained in overseas training programme (training of trainers programme). The enhanced capacity building of the local staff will contribute positively in the sustainability of the seed programme. . The procurement of farm equipment will be useful in Iraqi scientists’ efforts to breeders’ seed production. Laboratory equipment and supplied commodities are used in seed testing procedures to determine the quality attributes. The aim of supplying these equipments is to avail the farmers of high quality seeds to result improved crops production and productivity. The utilization of the climate-controlled greenhouses will facilitate the Iraqi scientists for varietal evaluation and screening all the year round. The rice seed testing equipments are to be used by SBAR. The construction of laboratory buildings which is in full swing will further strengthen MoA’s capacity for crop improvement and seed quality control.

- Main implementation constrains & challenges (2-3 sentences)

General implementation and monitoring aspects are affected due to the prevailing situation in Iraq. The general peace, law and order problem in Iraq creates problem for any expatriate staff to visit. Even local staffs have problems visiting concerned offices, research centres and farms. Consequently information flow from the field to Amman has been slow This definitely affects the implementation of this remote-controlled project implementation. As expected, progress may be slow and output not as set in the work plan. However, it should catch up once peace and stability returns to Iraq. Other than this there are no other problems.