# United Nations Development Group Iraq Trust Fund

# Project Summary Sheet

# Project #: A5 - 18

# Date and Quarter Updated: June 2009

| Participating UN Organisation: FAO | Sector: A – Agriculture and Food Security |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Water Resources (MoWR) |

# Programme/Project Number: A5-18 (OSRO/IRQ/702/UDG)

| Title | Rehabilitation and Maintenance of Traditional Irrigation Schemes in Resettled Areas |
| --- | --- |
| Location | Iraq Erbil, Dohuk and Sulaimaniyah Governorates |
| Project Cost | US$ 3,598,077 |
| Duration | 1 Year |
| Approval Date (SC) | April 2007 | Starting Date | 01/07/2007 | Completion Date | 31/12/2009 |
| Project Description | The project’s goal is to address the need of food security within resettled or to be resettled rural areas by rehabilitating and improving existing irrigation infrastructure and by strengthening institutional capacity for maintenance of rehabilitated infrastructure. Continued investment in projects targeted at rural areas will also create temporary employment opportunities and will attract workers and IDPs to the beneficiary villages of these projects away from cities. |

# Development Goal and Immediate Objectives

Development Goal: The project intends to improve the existing infrastructure through the rehabilitation and improvements in conveyance and delivery of irrigation water to the farmers’ fields. The development goal of the project is to enhance agricultural production and food security, and increase incomes of resettled or to be resettled smallholders. This shall create a conducive environment for them to remain in their localities and may encourage some of those who migrated to urban centres to return to their original settlements for farming Immediate Objectives: 1. Increase agricultural productivity; 2. Improve farmers’ livelihoods; 3. Create an institutional understanding and capacity and provide the means for a sustainable operation and maintenance of the rehabilitated infrastructure, involving both the beneficiaries and the government institutions.

# Outputs, Key activities and Procurement

| Outputs | Outputs related to objective1: 1.1 Extension workers and key farmers are aware of the significant potential for reducing conveyance and on-farm water losses during irrigation. 1.2 Farmers (male and female), and other community members trained in effective irrigation water management and efficient irrigation water use. 1.3 Availability of natural resources such as land and water is increased by more efficient use. Outputs related to objective2: 2.1 Increased agricultural and livestock production due to increased water availability. 2.2 Short-term employment opportunities created by the infrastructure rehabilitation component. Outputs related to Objective 3: 3.1 Local communities play an active and decisive role in the identification of rehabilitation measures; 3.2 A prioritised programme prepared for repair and rehabilitation of irrigation infrastructure based on previous needs assessments; 3.3 A number of essential infrastructure items repaired and put again into operation. It is estimated that 50 Km of secondary and tertiary canals can be rehabilitated / cleaned while some 1,900 ha of gravity irrigation schemes can be put back into production; 3.4 Conditions created for these irrigation infrastructures to be properly managed and maintained by the users-beneficiaries through the establishment of Water Users Associations supported by the concerned local institutions of the Ministries of Agriculture and Water Resources. |
| --- | --- |
| Activities | Activities of the outputs 1.1-1.3: 1.1.1 Identification of 46 irrigation schemes and 103 spring sources for rehabilitation and cleaning in collaboration with Ministry of Agriculture (MoA) and Ministry of Water Resource (MoWR). 1.1.2 Rehabilitation and cleaning of 46 irrigation schemes and 103 spring sources in order to bring back into production 1,900 ha under gravity irrigation. Activities of the output 2.1 - 2.2 : 2.1.1 Paid labour amounting to 200,000 days of labour is provided, through rehabilitation and cleaning works from activity 1.1.1 Activities of the output 3.1 – 3.4: 3.1.1 Recruit International project personnel 3.1.2 Establish contacts and operational links with relevant central technical institutions 3.1.3 Identify and recruit local consultants set up project office for WRISU, procure and install office equipment. 3.1.4 On the basis of previous assessments, propose and obtain endorsement of priority list for intervention, prepare project inception report and work-plan 3.1.5 Detailed damage assessment of irrigation infrastructure, preparation of proposals for repair / rehabilitation / replacement of irrigation infrastructure. 3.1.6 Establish Water Users Associations (WUAs) to ensure full involvement in rehabilitation work and subsequent maintenance thus ensuring sustainability 3.2.1 Appraise the planned proposals and measures together with the WUAs and key members of local communities 3.2.3 Prepare designs, work contracts, estimated, detailed equipment lists, budget requirements for different schemes, in order of priority 3.3.1 Contract out work to national institutions, NGOs and private contractors 3.3.2 Co-ordinate and supervise work implementation 3.3.3 Monitor and report project implementation progress. 3.3.4 Postponing the work from End of November 2008 until end of February 2009.(because sedimentation from the raining and temperature degree). 3.3.5 Contract out work to national institutions. 3.3.6 Co-ordinate and supervise work implementation. 3.3.7 Monitor and report project implementation progress. 3.3.8 Time extension for the project until 31 December 2009. 3.3.9 Hand over certificates to 11 Villages in in Soran District (Pirdashar, Gojar, Khanaqa, Razhokarian, Warte, Sole Warte, Barozhi Warte, Zeway Warte, Dargala, Badilian and Kareta ) 3.3.10 Hand over certificates to 11 Villages for 10 villages in Shaqlawa Area (Sheikh Mamodian, Allwa, Bawian, Darband, Dore, Hujran, Kani Sorik, Kore, Qalasinj and Razga Dwin) |
| Procurement (major items) | N/A |

# Situation as of end May 2009

| Funds Committed | US $ 1438062 | % of approved | 40 % |
| --- | --- | --- | --- |
| Funds Disbursed | US $ 1564051 | % of approved | 43 % |
| Forecast final date | 31/12/2009 | Delay (months) | 18 |

# Quantitative achievements against objectives and results

| Pre-feasibility study had been completed and the priority list also prepared | % of planned | 100 % |
| --- | --- | --- |
| The contract for the detailed survey to generate the tender documents and BOQ has been awarded and currently under operation. | % of planned | 100 % |
| The draft proposal for tendering the work for rehabilitation and maintenances of 120 micro irrigation schemes, has been prepared by Avesta Company (Erbil) and sent to Rome for technical clearance. After the clearance is received, a tender for the work will be let, then the rehabilitation and maintenance of the designated irrigation schemes will be conducted by local contractors divided into districts ( Shaqlawa, Choman, Mergasor and Soran). | % of planned | 100 % |
| Complete the rehabilitation and maintenance of the designated irrigation schemes as per the contract. | % of planned | 80 % |
| Local training for MoWR/ KRG staff and farmers for the three governorates of Dohuk, Erbil and Sulimanyah is being arranged and took place on November 2008 for Erbil and on February 2009 for Sulimanyah in Iraq and for Dohuk on June 2009 . | % of planned | 100% |
| WUA training in country | % of planned | 20% |
| Extension of the project to be in Sulaymaniah and Dohuk | % of planned | 0% |

# Qualitative achievements against objectives and results

The project is being implemented in line with the approved project document, as revised at the beginning of November 2007 in a Project Implementation Meeting between MoWR/KRG and FAO. The implementation of this irrigation rehabilitation project in Northern Iraq has taken longer than expected due to the number of sites (120) distributed over 4 large districts. It was logistically complicated to affect the feasibility study and the detailed survey in the time estimated. The tendering for the main contract has been completed and the contracts awarded, plus the Supervising Engineers have been engaged to commence the work. The implementation of the main contract for the project has commenced and required at least nine months not included Postponing the work from End of November 2008 until end of February 2009 (because Concrete works didn't be allowed for the said period as the temperature degree for the project area was below the zero- degree and as the cleaning of canals for the time- being will be useless due to the coming sedimentation from the raining and flooding) therefore an extension is required up to 31 December 2009. Training for MoWR/ KRG staff and farmers was arranged and took place in Iraq- Erbil governorate by University of Salahaddin– College of Engineering from the three governorates of Erbil (November 2008), Sulimanyah (February 2009) and the last for Dohuk (June 2009)