- United Nations Development Group Iraq Trust Fund

- Project Summary Sheet

- Project #: A5 - 20

- Date and Quarter Updated: 20 June 2008

| Participating UN Organisation: FAO - UNIDO | Sector: Agriculture and Food Security |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Planning and Ministry of Agriculture |  |

- Programme/Project Number: A5-20 (OSRO/IRQ/603/UDG)

| Title | Job Creation through Cottage and Micro-industries Promotion in Al-Qadessia |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Location | Al Qadissiya Governorate (Diwaniya) |  |  |  |  |
| Project Cost | USD 6,171,891 |  |  |  |  |
| Duration | 18 months |  |  |  |  |
| Approval Date (SC) | 28/01/2007 | Start Date | March, 2007 | Completion Date | 30 July 2008 |
| Project Description | This project addresses the socio-economics priorities of the Diwaniya Governorate with a focus on community empowerment and the promotion of income-generating activities/job creation. More specifically, the project aims at increasing the capability of rural and urban communities in the region to engage in viable non-farming enterprises, reducing their dependency on relief aid and helping them to move towards sustainable livelihood. Planned interventions include: - Providing targeted communities with the capacity to plan and manage their development activities and restoring a functional base for economic growth and social peace. - Improving the livelihood of approximately 4,500 households living in the project area through strengthening of their productive capacities in post-harvest and other income-generating activities. - Enabling a large number of youth to gain basic knowledge in productive skills through practical experiences and activity-based learning. Particular emphasis will be placed on providing the youth and IDP’s with marketable skills effectively meeting the labour demand requirement such as for the construction/rehabilitation, manufacturing or support services. |  |  |  |  |

- Development Goal and Immediate Objectives

Development Goal:

Improve the socio-economic conditions of the population in the project area through community empowerment and rehabilitation of the livelihoods and productive capacities in the al-Qadissiya Governorate (Diwaniya).

Key Immediate Objective/s:

- Provide targeted communities with the capacity to plan and manage their development activities and restoring a functional base for economic growth and social peace. 2. Improve the livelihood of approximately 4,500 people (50% women) living in the project area through strengthening of their productive capacities in post-harvest and other income-generating activities. 3. Enable large number of youth and women who have been deprived by the conflict to gain basic knowledge in productive skills through practical experiences and activity-based learning.

- Outputs, Key activities and Procurement

| Outputs | - Enhanced capacities at the community level in support of socio-economic growth and peaceful coexistence (MDG 1, 3). - Sources of income and employment for men and women creating an environment for productive employment through training and provision of tools for individuals and organized production groups (associations) (MDG 1, 3 and 5). - A minimum of 1,000 people (50% female) are provided with marketable skills to enable them to obtain jobs and/or start-up an economic activity to sustain livelihoods for themselves and their families (MDG 1, 3). |
| --- | --- |
| Activities |  |
| Procurement (major items) | Training equipment and Beneficiaries tools |

- Situation As of June 2008/ Food Sector

| Funds Committed | 342 000 | % of approved | 12 |
| --- | --- | --- | --- |
| Funds Disbursed | 357 995 | % of approved | 13 |
| Forecast final date |  | Delay (months) |  |

- Quantitative achievements against objectives and results

| Procurement of equipment Plant and machinery | Under procurement/delivery | % of planned | 40 |
| --- | --- | --- | --- |
| Rehabilitation and renovation and equipping VTC |  | % of planned | 90 |
| Training of Trainers |  | % of planned | 5 |
| Training of Beneficiaries |  | % of planned | 0 |
| Distribution of equipment to beneficiaries and associations |  | % of planned | 0 |
|  |  | % of planned | % |

- Qualitative achievements against objectives and results

Rehabilitation of VTC