- United Nations Development Group Iraq Trust Fund

- Project #: A5-20

- Date and Quarter Updated: 07 July 2009 (Quarter 2)

| Participating UN Organisation: UNIDO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: | Ministry of Agriculture Ministry of Labour and Social Affairs Ministry of Planning and Development Cooperation |

| Title: | Job Creation Through Micro Industries Promotion in Al-Qadissiyah, Iraq |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Al-Qadissiyah Governorate |  |  |  |  |
| Project Cost | $5,871,891 |  |  |  |  |
| Duration | 18 months |  |  |  |  |
| Approval Date (SC) | 28 Jan 2007 | Starting Date | 30 Jan 2007 | Completion Date | 31 December 2009 |
| Project Description | This project addresses the socio-economic priorities of the Dewaniyah Governorate with a focus on community empowerment and the promotion of income-generating activities/job creation. The project has been designed to increase the capability of marginalized and poor communities to engage in viable non-farming agro-enterprises, thus reducing their dependency on a variety of relief aid packages and strengthening the sustainable livelihoods recovery process. |  |  |  |  |

Development Goal and Immediate Objectives

Development Goal

To improve the socio-economic conditions of the population in the project area through community empowerment and rehabilitation of the livelihoods and productive capacities in Al-Qadissiyah.

Key Immediate Objectives:

- Provide targeted communities with the capacity to plan and manage their development activities and restoring a functional base for economic growth and social peace.

- Improve the livelihood of approximately 4,500 households living in the project area through strengthening of their productive capacities in post-harvest and other income-generating activities.

- Enable large number of youth who have been deprived by conflict to gain basic knowledge of productive skills through practical experiences and activity-based learning.

- Outputs, Key activities and Procurement

- Outputs

- 1.1 Enhanced capacities at the community level in support of socio-economic growth and peaceful coexistence.

- 2.1 Sources of income and employment for men and women in targeted communities are improved through increased quality and diversity of sustainable livelihoods activities benefiting 4,500 households.

- 3.1 A minimum of 1,000 youth (50% female) are provided with marketable skills to enable them to obtain jobs and/or start-up an economic activity to sustain livelihoods for themselves and their families.

- Key Activities

- Assessing the needs of project beneficiaries (using selected participatory appraisal tools), identifying viable productive income generation activities and appropriate technologies.

- Selecting project sites with the collaboration of all stakeholders, based on the distribution of vulnerable groups in both urban and rural areas and the availability of raw materials and markets.

- Finalising selection and identification of beneficiaries based on the criteria agreed upon by all stakeholders: local governments, women’s associations, directorates of counterpart ministries, village elders and Project Steering Committee members.

- Rehabilitation of the Dewaniyah Vocational Training Centre.

- Training of Trainers in selected technical and entrepreneurship training areas.

- Procurement and installation/transfer of training workshop equipment for the Dewaniyah Vocational Training Centre, project beneficiary ‘toolkits’, and productivity enhancing technologies in Production Groups and other project support micro industries.

- Training of beneficiaries in technical, vocational, entrepreneurial skills areas so as to assist them in starting their own business or to increase employment opportunities.

- Mentoring of project beneficiaries and the activities of Production Groups.

Procurement Non-Food: The Project Management Unit (PMU) has completed the acquisition, transfer, and installation of all project procured training equipment. The completion of this activity has allowed the newly renovated Dewaniyah Vocational Training Centre (DVTC) to begin technical and vocational skills upgrading and training to project beneficiaries. Technical areas that the DVTC is currently providing non-food training in include: agro/auto-mechanics, metalworking, welding, carpentry, spinning and weaving, mobile phone repair, and sewing/tailoring. The project has also procured equipment for allocation to a number of Production Groups (PG) to be established in the governorate. In addition, the PMU will also provide start up capital, in terms of technology ‘toolkits’, to project beneficiaries so as to assist in the promotion of self-employment opportunities and/or the development of micro enterprises. Food: To support food related post-harvest processing activities, the project has procured, installed and commissioned a variety of food related training technologies/equipment/resources to upgrade the knowledge and skills of project targeted beneficiaries. Similarly to the non-food component of the project, the PMU has located the training equipment at the DVTC and is currently providing training in a number of fields including beekeeping, fruit/vegetable processing, bread and pastry, dairy products, sesame/tahini processing, etc. To assist in the revitalization of post-harvest capacity and productivity in the governorate, the project is resourcing a number of PGs. To accomplish this, productivity enhancing equipment will be transferred to various PGs working in the fruit and vegetable, beekeeping, bread and pastries, and olive processing sectors. Finally, project targeted beneficiaries are receiving training relevant agro-processing toolkits to enable them to start up their own small enterprises or raise household level productivity at the end of their training courses. Project funds allocated towards the procurement of equipment and toolkits is budgeted at approximately 2,700,000 USD. Project procured institutional strengthening and capacity-building equipment transfers accounts for approximately 46% of the total project budget.

| Funds Committed | $4,678,145 | % of approved | 80% |
| --- | --- | --- | --- |
| Funds Disbursed | $3,245,262 | % of approved | 55% |
| Forecast final date | 31 December 2009 | Delay (months) | 18 Months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 500 | 45% |
| Women | 500 | 30% |
| Youth (youth 18-25) | 1000 (50% Women) | 45% |
| IDPs | TBD |  |
| Others | NA |  |
| Indirect beneficiaries | 2500 |  |
| Employment generation (men/women) | 2000 | 25% |

- Quantitative achievements against objectives and results

| - Provide targeted communities with the capacity to plan and manage their development activities and restoring a functional base for economic growth and social peace. | % of planned | 90 |
| --- | --- | --- |
| - Improve the livelihood of approximately 4,500 households living in the project area through strengthening of their productive capacities in post-harvest and other income-generating activities. | % of planned | 40 |
| - Enable large number of youth who have been deprived by conflict to gain basic knowledge of productive skills through practical experiences and activity-based learning. | % of planned | 40 |

- Qualitative achievements against objectives and results

The design, development, and implementation of project sensitization workshops, with core project stakeholder groups, have been completed. The project has confirmed the needs of project beneficiary groupings through the preparation of a comprehensive needs assessment report that was conducted in collaboration with COSIT from the Ministry of Planning.

The selection of project sites and the ‘mapping’ of beneficiary groups, project extension services, project supported training sites, and other agro-infrastructure is largely completed. Our mapping and tracking ‘platform’ has been designed to be easily updateable and will be regularly revised as the project moves through the project cycle.

The identification and promotion of locally relevant and appropriate agro-economic technologies has been completed. The completion of this activity was facilitated through a demand driven and market based assessment of raw materials, support services, distribution nodes, and market access points conducted in project targeted areas.

The preparation of the technical specification for project procured equipment has been finalized and procurement activities have been completed by both UNIDO and FAO. The project has completed its inventory reporting on project-purchased equipment and tools that will be distributed to the DVTC, project beneficiaries, and project established PGs. Training related equipment has been installed and commissioned in the newly renovated DVTC and formal agreements and conditions of use documents have been finalized to structure technology transfers between the PMU, GoI Line Ministries, and other end-user groups.

- All training of trainers (TOT) sessions have been completed for various technical and vocational skills upgrading of ministerial counterpart staff.  These staff will be attached to the project’s food and non-food vocational training and skills upgrading centre. The project has trained 48 TOT in a variety of technical, enterprise development, and management thematic areas.  Furthermore, the project has completed its training of 13 Community Development Leaders and is actively working with this group to promote and monitor development activities in project targeted districts in the governorate. The PMU is currently working with GoI focal points to identify and nominate candidates that will become business mentors and coaches to the various micro enterprises and Production Groups to be established by the project.

The Training of Beneficiaries (ToB) component of the project has started with the training of project targeted beneficiaries in a number of food-related and post harvest areas. Currently the project is training or has trained over 700 project beneficiaries in a large number of non-food type technical and vocational skills areas. The PMU is closely monitoring the Project Steering Committee endorsed ToB training action plan. This plan has been prepared to facilitate the timely unfolding of training sessions.

The project has completed the rehabilitation works at the DCTV and the placement of trainers from various project participating ministries has been agreed to. The PMU is organized the First Receiving Committee ceremony and final arrangements are being made to organize an official handover ceremony. The Ceremony will provide an important opportunity to showcase the involvement of key stakeholders from the Governors Office, the provincial council, the GoI counterpart ministries, and project linked community development leaders.

The project has made linking Producer Groups (PG) with various agro-related financial facilities an essential project activity. Using the established MISP methodology, the PMU has hired a National Consultant to help identify and select the most suitable productive facilities and workshops to participate in the PG component of the project. Once these PGs have been established, they will be linked with the most economical funding mechanism in the project area. At that time, the PMU will begin the process of tracking changes in the operations of PGs and the agro-enterprise sector.

- Main implementation constrains & challenges

- The fragile security situation hampers free movement of international and national project staff and consultants, posing some difficulties to the effective implementation of project activities. - Effective targeting of women remains a challenge for project managers. The project is working in a more traditional part of the country and securing women to be enrolled in training programmes, travel (escorted and non-escorted), decision-making bodies, and other aspects of the project have been difficult and challenging. - Limited cooperation and assistance by the project national counterparts have been encountered during the last 6 months of project activity implementation. Lack of collaboration.

Photos

Dewaniyah VTC Entrance					     Machine Tools Training Area

Food Processing Training Area				     Dewaniyah VTC Site Plan