- United Nations Development Group Iraq Trust Fund

- Project #: A5-20

- Date and Quarter Updated: 15 October 2008 (Quarter 3)

| Participating UN Organisation: UNIDO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: | Ministry of Agriculture Ministry of Labour and Social Affairs Ministry of Planning and Development Cooperation |

| Title: | Job Creation Through Micro Industries Promotion in Al Qadessia, Iraq |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Diwaniyah |  |  |  |  |
| Project Cost | $5,871,891 |  |  |  |  |
| Duration | 18 months |  |  |  |  |
| Approval Date (SC) | 28 Jan 2007 | Starting Date | 5 Feb 2007 | Completion Date | 31 March 2009 |
| Project Description | This project addresses the socio-economic priorities of the Dewaniyah Governorate with a focus on community empowerment and the promotion of income-generating activities/job creation. The project has been designed to increase the capability of marginalized and poor communities to engage in viable non-farming agro-enterprises, thus reducing their dependency on a variety of relief aid packages and strengthening the sustainable livelihoods recovery process. |  |  |  |  |

Development Goal and Immediate Objectives

Development Objective

To improve the socio-economic conditions of the population in the project area through community empowerment and rehabilitation of the livelihoods and productive capacities in Al-Qadissiyah.

Key Immediate Objectives

- Provide targeted communities with the capacity to plan and manage their development activities and restoring a functional base for economic growth and social peace.

- Improve the livelihood of approximately 4,500 households living in the project area through strengthening of their productive capacities in post-harvest and other income-generating activities.

- Enable large number of youth who have been deprived by conflict to gain basic knowledge of productive skills through practical experiences and activity-based learning.

- Outputs, Key activities and Procurement

- Outputs

- 1.1 Enhanced capacities at the community level in support of socio-economic growth and peaceful coexistence.

- 2.1 Sources of income and employment for men and women in targeted communities are improved through increased quality and diversity of sustainable livelihoods activities benefiting 4,500 households.

- 3.1 A minimum of 1,000 youth (50% female) are provided with marketable skills to enable them to obtain jobs and/or start-up an economic activity to sustain livelihoods for themselves and their families.

- Key Activities

- Assessing the needs of project beneficiaries (using selected participatory appraisal tools), identifying viable productive income generation activities and appropriate technologies.

- Selecting project sites with the collaboration of all stakeholders, based on the distribution of vulnerable groups in both urban and rural areas and the availability of raw materials and markets.

- Finalising selection and identification of beneficiaries based on the criteria agreed upon by all stakeholders: local governments, women’s associations, directorates of counterpart ministries, village elders and Project Steering Committee members.

- Rehabilitation of vocational training centres.

- Training of trainers in the selected technologies and entrepreneurship.

- Procurement of pilot plants and workshop equipment for the training centre, project beneficiaries, model cottage and micro-industries; and installation of these equipments.

- Training of beneficiaries in entrepreneurial skills and technology to start their own business or to increase employment opportunities.

- Mentoring the beneficiaries through their businesses.

Procurement

Non-Food: The project has purchased training equipment for industrial schools and vocational training providers in mechanics, metal working, welding, carpentry, leatherworking, and sewing/tailoring. In addition, project procured equipment has also been allocated for the establishment of a number of Production Groups in agro and auto repair, welding and fabrication, machine workshops, carpet weaving, tailoring, and carpentry/joinery. The project has also procured beneficiary toolkits for its various vocational training course participants.

Food: To support food related post-harvest processing activities the project has procured training equipment to upgrade the knowledge and skills that project targeted beneficiaries have in food related technologies. Like in the non-food component of the course, the project is transferring, installing, and commissioning this equipment in a number of training providers throughout the two governorates. In addition, the project is resourcing a number of Production Groups in food technologies. These include, fruit and vegetable, beekeeping, bread and pastries, and olive processing. Finally, project targeted beneficiaries will receive toolkits to enable them to start up their own small enterprises or raise household level productivity.

Project funds allocated towards the procurement of equipment and toolkits is budgeted at approximately 2,700,000 USD. Project procured institutional strengthening and capacity-building equipment transfers accounts for approximately 46% of the total project budget.

| Funds Committed | 3,007,809 | % of approved | 51.22 |
| --- | --- | --- | --- |
| Funds Disbursed | 1,761,328 | % of approved | 30 |
| Forecast final date | March 2009 | Delay (months) | 6 Months |

- Quantitative achievements against objectives and results

| - Provide targeted communities with the capacity to plan and manage their development activities and restoring a functional base for economic growth and social peace. | % of planned | 80 |
| --- | --- | --- |
| - Improve the livelihood of approximately 4,500 households living in the project area through strengthening of their productive capacities in post-harvest and other income-generating activities. | % of planned | 25 |
| - Enable large number of youth who have been deprived by conflict to gain basic knowledge of productive skills through practical experiences and activity-based learning. | % of planned | 25 |

- Qualitative achievements against objectives and results

The design, development, and implementation of project sensitization workshops, with core project stakeholder groups, has been completed. The project has confirmed the needs of project beneficiary groupings through the preparation of a comprehensive needs assessment report that was conducted in collaboration with COSIT. This ‘demand-side’ assessment has been used to guide the targeting and selection of project beneficiaries and linking them to appropriate training sessions based upon the economic profile of their communities.

The selection of project sites and the ‘mapping’ of beneficiary groups, project extension services, project supported training sites, and other agro-infrastructure has begun and this will be updated as the project moves through the project cycle.

The identification and promotion of locally relevant and appropriate agro-economic technologies has been completed which has been anchored by a market based assessment of raw materials, quality of agro-industrial support services, reliability of the product and service distribution network , and availability and access to key market channels/points. This comprehensive survey covers the entire governorate and provides the Project Management Unit (PMU) with sub-district level planning data to effectively target various project beneficiary groups involved in the project.

The preparation of the technical specification for project procured equipment has completed. Procurement activities have been completed by both UNIDO and FAO and currently the project is the process of finalizing the archival and inventory reporting of project procured equipment and tools, the installation and commissioning of training equipment at the newly completed Dewaniyah Vocational Training Centre (based on a formal agreement between the PMU, GoI Line Ministries, and end-users), or formalizing the receipt of equipment and other project goods currently under shipment/transport to the project area.

- The Phase One Training of Trainers (ToT) training sessions have been completed for skills upgrading of ministerial counterpart staff that will be attached to the project’s food and non-food vocational training and skills upgrading centre. Over 80 percent of Phase Two ToT training sessions have been completed. This phase of training has seen the most highly qualified ToTs being sent outside the country for more advanced and specialized training in a variety of vocational, technical, and enterprise development and management type training streams. These trainers will be the core cadre of trainers that will be utilized for the training of project beneficiaries and Production Group leaders.

The project has made a dedicated effort to conduct a technical assessment of vocational and technical training institutes and centres and decisions relating to the resourcing of these facilities has been made in conjunction with the PMU, Ministerial Representatives, and other Project Steering Committee members. The identification of these alternate training facilities is part of the PMU risk management back-up strategy.

Training of Beneficiaries has recently started and once training equipment has been formally commissioned at the newly established Dewaniyah Vocational Training Centre and as soon as the ToTs have received their final instructional skills training upgrading aimed at improving training outcomes for marginalized and vulnerable project beneficiary groupings.

The newly completed Dewaniyah Vocational Training Centre is currently being commissioned and short production and training related ‘run-throughs’ are being organized prior to the core training streams being conducted. During this period, project staff are working to ensure that training production runs are optimized and that the facility is ready to accept its trainee intake. These efforts will help to build the capacity of Centre staff to administer technical and vocational skills upgrading programmes in the governorate and are an important sustainability enhancing mechanism for the Project Management Unit.

The project has made linking Producer Groups with various agro-related financial facilities an important project activity. Currently, project staff are organizing for delivery of a enterprise-level survey of key agro-industrial assets in the project area. The survey will allow the PMU to identify and establish a number of dynamic Production Groups (PG) and link them with the most economical funding mechanism and business development service provider in the project area. Once established, the PMU will begin the process of tracking changes in the operations, employment levels, and revenue streams of PGs and other agro-industrial resources engaged by the project.