# United Nations Development Group Iraq Trust Fund

# Project #:A7-04

# Date and Quarter Updated: 2nd quarter – 30 June 2008

| Participating UN Organisation: UNDP | Sector: Protection – Mine Action |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Environment |

| Title | Mine Action Capacity Development/Local NGO I |
| --- | --- |
| Geographic Location | Basra, Az Zubair |
| Project Cost | US$ 3,195,797 |
| Duration | 27 months |
| Approval Date (SC) | 28/09/2006 | Starting Date | 28/9/2006 | Completion Date | 31/12/2008 |
| Project Description | Continued strengthening of the established National Mine Action Organisation in Southern Iraq by providing on the job training for clearance teams and providing management training for the national staff. |

# Development Goal and Immediate Objectives

| Support the sustainable development of Iraq and remove threats to human security and livelihood by increasing the capacity of the National Mine Action Authority (NMAA), and the Regional Mine Action Centre in Southern Iraq, through the creation and strengthening of a sustainable national Iraqi human and institutional capacity in the form of a national NGO capable of undertaking Explosive Ordnance Disposal (EOD) and related Mine Action activities. Strategic Framework Programme Outcome 2004-2007: “A National Mine Action Authority capable of managing the mine action functions of government in all of Iraq”. |  |
| --- | --- |

# Outputs, Key activities and Procurement

| Outputs | National NGO able to manage and provide clearance services, explosive ordnance disposal capacity strengthened and able to operate independent of international supervision. Staff of the national Mine Action organization able to raise funds, plan and manage its activities properly to ensure sustainability of its operations. 1.3. Explosive Remnants of War (ERW) obstacles cleared and land made available for further reconstruction- and/or livelihood activities. |
| --- | --- |
| Activities | 1.1.1. On the job training provided by the international contractor through supervision, mentoring and monitoring of all EOD teams, giving them the ability to carry out EOD operations independent of international supervision and in accordance with the International Mine Action Standards (IMAS). 1.2.1. Develop the management and institutional systems and structure of the local NGO through improving the organisational structure and workflow, and introducing clearly defined responsibility and accountability frames. 1.2.2 Support the management team of the local national NGO to acquire sound operations/implementation and planning abilities, and to consequently develop quality assurance systems. 1.2.3. Support the management team through continuous guidance and training to master management, planning, NGO administration, and fund raising skills for ensuring long term sustainability of the National NGO. 1.3.1. The 10 EOD teams continue to clear Explosive Remnants of War (ERW) during on the job training. |
| Procurement (major items) | NA |

| Funds Committed | US$ 2,825,734.96 | % of approved | 88.4% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 2,818,138.03 | % of approved | 88.1% |
| Forecast final date | 31 December 2008 | Delay | 15 months |

# Quantitative achievements against objectives and results

| National NGO able to manage and provide clearance services and to operate independent of international supervision | Target: 10 qualified Iraqi EOD teams successfully conducting EOD activities independent of international supervision in accordance with IMAS Achievement: 10 EOD teams operational | % of planned | 100% |
| --- | --- | --- | --- |
| Explosive Remnants of War (ERW) obstacles cleared and land made available for reconstruction and livelihoods activities | Target: Minimum 6 km² of high impact contaminated land made available for reconstruction efforts and/or productive agricultural activities in southern Iraq Achievement: 30.03 km2 land cleared from Oct 06 to Sept 07 (during the period which DDG/RDO funded from this project) | % of planned | 500% |

# Qualitative achievements against objectives and results

Output 1.1 National NGO able to manage and provide clearance services and to operate independent of international supervision – The national NGO officially registered in May 2007 and managed by nationals. For strategic long-term planning, organizational development, asset management, donor relations, it still requires international monitoring partner’s support. Output 1.2 Staff of NGO able to raise funds, plan and manage its activities: The national NGO management (including Operations Manager) is able to prepare and manage daily activities and monthly plans. It is now able to handle funding directly given by UNDP; however, staff skill to raise funds directly from other donors still needs to be developed.