CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of 30 of June 2008

| Participating UN or Non-UN Organization: | ILO |  | UNCAPAHI Objective(s) covered: |  | Objective 2: sustaining livelihoods Objective 3: human health Objective 4: coordination of national, regional and international stakeholders Objective 5: public information |  |
| --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | OSH Centre, Department of Manpower and Transmigration, Asosiasi Pengusaha Indonesia (Indonesian Employers Association), Konfederasi Serikat Pekerja Seluruh Indonesia (Confederation of All Indonesia Workers Union), Konfederasi Serikat Buruh Sejahtera Indonesia (Confederation of Indonesia Welfare Workers Union), Konfederasi Serikat Pekerja Indonesia (Confederation of Indonesia Workers Union), Muhammadiyah, local and informal leaders of communities |  |  |  |  |  |
| Programme Number: | CFIA-A7 |  |  |  |  |  |
| Programme Title: | Avian Influenza and the Work Place in Indonesia |  |  |  |  |  |
| Total Approved Programme Budget: | US$ 250,000 |  |  |  |  |  |
| Location: | Jakarta |  |  |  |  |  |
| MC Approval Date: | 20 February 2008 |  |  |  |  |  |
| Programme Duration: | 12 months | Starting Date: | 1 April 2008 | Completion Date: |  | 31 Mar 2009 |
| Funds Committed: | US$ 25,740.94 |  |  | Percentage of Approved: |  | 10.3% |
| Funds Disbursed: | US$ 5,965.10 |  |  | Percentage of Approved: |  | 2.4% |
| Expected Programme Duration: | 12 | Forecast Final Date: | 30 June 2009 | Delay (Months): |  | 3 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Establish a project office and assigning staff | National Project Coordinator and Admin/Finance Assistance were recruited and project’s office was set up. | 100% |
| Research for mapping informal sector | These project activities start on July 2008, hence the timeline for these activities will be adjusted accordingly. | 0% |
| Reviewing existing training materials |  | 0% |
| Collecting OSH good practices |  | 0% |
| Qualitative achievements against outcomes and results: |  |  |
| The disbursed funds indicated above were used to cover preparatory activities in relation to the project approval and implementation. Project office was established, as National Project Coordinator and Administrative Finance assistance were recruited as full-time project staff. |  |  |

The term “programme” is used for projects, programmes and joint programmes.