CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of June 2009

| Participating UN or Non-UN Organization: | International Organization for Migration IOM) |  | UNCAPAHI Objective(s) covered: |  | Objective 5: Public Information and Communication for behavior change |  |
| --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | International Organization for Migration (IOM), UN partners, Relevant national and state authorities, NGOs, CBOs. |  |  |  |  |  |
| Programme Number: | CFIA A-9 |  |  |  |  |  |
| Programme Title: | Social Mobilization of Migrant Poultry Workers, Traders and Transporters in Nigeria |  |  |  |  |  |
| Total Approved Programme Budget: | $ 312,690 |  |  |  |  |  |
| Location: | Nigeria |  |  |  |  |  |
| MC Approval Date: | 20 February, 2008 |  |  |  |  |  |
| Programme Duration: | 12 months | Starting Date: | 1 April 2008 | Completion Date: |  | 31 March 2009 |
| Funds Committed: | $ 312,690 |  |  | Percentage of Approved: |  | 100% |
| Funds Disbursed: | $ 220,826* |  |  | Percentage of Approved: |  | 71% |
| Expected Programme Duration: | 18 months | Forecast Final Date: | 30 Sept. 2009 | Delay (Months): |  | 6 |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Baseline data on avian influenza and pandemic preparedness among migrant poultry workers, traders and transporters | The final report of the KAPB survey has been completed. | 100% |
| Inclusion of migrants and mobile population needs in national pandemic preparedness plans | - IOM Nigeria continues to work in coordination with the Nigerian government and the UN partners to raise awareness of the Influenza A (H1N1) outbreaks and pandemic preparedness. - IOM promotes the inclusion of migrants into national communication strategies. IOM is an active member of the communication sub-group of the AHI Technical Working Group (TWG) that includes the government, the UN and other partners. The communication group has developed a communication strategy, guidelines, information alert, a general protocol, and messages for different audiences. | 80% |
| Evaluation of the project in four target State | An external consultant has been hired to evaluate the project. | 25% |
| Qualitative achievements against outcomes and results: |  |  |
| IOM through the AHI Technical Working Group and the Public Enlightenment Committee has provided support to the government for the development of behavior change communication strategies that include migrants and mobile populations. |  |  |

The term “programme” is used for projects, programmes and joint programmes.

* Recent activities conducted in June have not been charged to this project code at the time of preparing this report